## MAIN
Republic of the Philippines PROVINCIAL GOVERNMENT OF PALAWAN Office of the Provincial Engineer Capitol Complex, Puerto Princesa City, Palawan
Physical Accomplishment Report
FY 2024 Fourth Quarterly Report
NO. | PROVINCIAL GOVERNMENT OF PALAWAN PROJECT NAME | PROJECT ID | PPDO CATEGORY | PROJECT DESCRIPTION | LOCATION | MUNICIPALITY | IMPLEMENTING OFFICE | YEAR | SOURCE OF FUND | PROJECT COST | CONTRACT COST | C.D | NTP DATE | NO. OF EXTENSION | TARGET COMPLETION DATE | REVISED COMPLETION DATE | DATE COMPLETED | AS OF DECEMBER 2024 | TOTAL COST INCURED TO DATE | MODE OF PROCUREMENT | GENERAL REMARKS | PROJECT CONTRACTOR | TIN NUMBER | REASON
1 | Concreting of So. Tagbarasan Bgy. Sagpangan FMR |  | Transportation Facilities | Construction 2 barrel RCBC = 2 units - PCCP L=740m - w=5m - T=0.2m (Station 0+000 to 0+250, Sta. 3+300 - 3+830 | Bgy. Sagpangan | Aborlan | PEO | 2014 | Department of Agriculture | 7700000 |  | 150 | [5 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
2 | Concreting of Sto. Tomas FMR, Sto. Tomas-Maningning-New Rizal, Dumarao | TF 416 DA FMR 15-104 | Transportation Facilities |  | Bgy. Dumarao | Roxas | PEO | 2014 | Department of Agriculture | 7700000 | 7486991.48 | 150 | 2015-07-14 |  | 2015-12-11 |  |  |  |  | By contract | For Termination | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Legal Endorsement
3 | Concreting of Marcilla Road (intermittent Section) |  | Transportation Facilities |  |  | Coron | PEO | 2014 | Department of Agriculture | 5000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
4 | Concreting of Kaybulusan-Decala Rd. w/ 2 Barrel Box Culvert, Bgy. Caruray | TF 416 DILG PCF 2014-16-001 | Transportation Facilities | PCCP L=1020m - W=5.00m - T=0.20m - Shoulder: 1.50m bothsides - 2 barrel box culvert = 6.00m x 5.00m | Bgy. Caruray | San Vicente | PEO | 2014 | Performance Challenge Fund | 7000000 | 6980434.55 | 140 | 2016-10-23 |  | 2017-03-12 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
5 | Rehabilitation of Sandoval Water System, Bgy. Sandoval & Minara |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Sandoval & Minara | Roxas | PEO | 2014 | 20% Development Fund | 4300000 | [7 empty] | 100% |  | By Admin | Completed | By Admin
6 | Improvement of Pamantolon Water System, Bgy. Pamantolon & Poblacion |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Pamantolon & Poblacion | Taytay | PEO | 2014 | 20% Development Fund | 6600000 | [7 empty] | 100% |  | By Admin | Completed | By Admin
7 | Improvement of Puntabaja Water System , Puntabaja |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Punta Baja, Rizal | Rizal | PEO | 2014 | 20% Development Fund | 4800000 | [7 empty] | 100% |  | By Admin | Completed | By Admin
8 | Concreting of Junction National Highway- Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2014 | 20% Development Fund | 3026800 | 2967671.01 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
9 | Concreting of Junction National Highway - Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2014 | 20% Development Fund | 3007873.46 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
10 | Construction of 4CL Building, PSU Rizal |  | Educational Facilities | 4 Classroom School Building | PSU Rizal | Rizal | PEO | 2014 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
807 |  |  | Educational Facilities |  | PSU Rizal | Rizal |  |  | 20% Development Fund | [10 empty] | By contract
Formulas:
TARGET COMPLETION DATE = [NTP DATE]+[C.D]