## MAIN
NO | PROJECT NAME | PROJECT ID | CATEGORY | SUB CATEGORY | PROJECT DESCRIPTION | LOCATION | MUNICIPALITY | IMPLEMENTING OFFICE | YEAR | SOURCE OF FUND | PROJECT COST | CONTRACT COST | C.D | NTP DATE | NO. OF EXTENSION | TARGET COMPLETION DATE | REVISED COMPLETION DATE | DATE COMPLETED | AS OF DECEMBER 2024 | TOTAL COST INCURED TO DATE | MODE OF PROCUREMENT | GENERAL REMARKS | PROJECT CONTRACTOR | TIN NUMBER | REASON
1 | Concreting of So. Tagbarasan Bgy. Sagpangan FMR | NULL | Transportation Facilities | ROAD | Construction 2 barrel RCBC = 2 units - PCCP L=740m - w=5m - T=0.2m (Station 0+000 to 0+250, Sta. 3+300 - 3+830 | Bgy. Sagpangan | Aborlan | PEO | 2014 | Department of Agriculture | 7700000 | NULL | 150 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
2 | Concreting of Sto. Tomas FMR, Sto. Tomas-Maningning-New Rizal, Dumarao | TF 416 DA FMR 15-104 | Transportation Facilities | ROAD | NULL | Bgy. Dumarao | Roxas | PEO | 2014 | Department of Agriculture | 7700000 | 7486991.48 | 150 | 2015-07-14 | NULL | 2015-12-11 | NULL | NULL | NULL | NULL | By contract | For Termination | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Legal Endorsement
3 | Concreting of Marcilla Road (intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | NULL | Coron | PEO | 2014 | Department of Agriculture | 5000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
4 | Concreting of Kaybulusan-Decala Rd. w/ 2 Barrel Box Culvert, Bgy. Caruray | TF 416 DILG PCF 2014-16-001 | Transportation Facilities | ROAD | PCCP L=1020m - W=5.00m - T=0.20m - Shoulder: 1.50m bothsides - 2 barrel box culvert = 6.00m x 5.00m | Bgy. Caruray | San Vicente | PEO | 2014 | Performance Challenge Fund | 7000000 | 6980434.55 | 140 | 2016-10-23 | NULL | 2017-03-12 | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
5 | Rehabilitation of Sandoval Water System, Bgy. Sandoval & Minara | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Bgy. Sandoval & Minara | Roxas | PEO | 2014 | 20% Development Fund | 4300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By Admin | Completed | By Admin | NULL | NULL
6 | Improvement of Pamantolon Water System, Bgy. Pamantolon & Poblacion | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Bgy. Pamantolon & Poblacion | Taytay | PEO | 2014 | 20% Development Fund | 6600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By Admin | Completed | By Admin | NULL | NULL
7 | Improvement of Puntabaja Water System , Puntabaja | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Punta Baja, Rizal | Rizal | PEO | 2014 | 20% Development Fund | 4800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By Admin | Completed | By Admin | NULL | NULL
8 | Concreting of Junction National Highway- Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2014 | 20% Development Fund | 3026800 | 2967671.01 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
9 | Concreting of Junction National Highway - Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2014 | 20% Development Fund | 3007873.46 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
10 | Construction of 4CL Building, PSU Rizal | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | PSU Rizal | Rizal | PEO | 2014 | 20% Development Fund | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
11 | Construction of 2CL Building, Nangalao National High School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Nangalao National High School | Linapacan | PEO | 2014 | 20% Development Fund | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
12 | Construction of 2CL Building, Tarumpitao Point Elementary School, Punta Baja | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Punta Baja, Rizal | Rizal | PEO | 2014 | 20% Development Fund | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
13 | Road Repair in Cagayancillo | NULL | Transportation Facilities | ROAD | NULL | NULL | Cagayancillo | PEO | 2014 | 20% Development Fund | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
14 | Road Concreting in Agutaya | NULL | Transportation Facilities | ROAD | NULL | Municipality of Agutaya | Agutaya | PEO | 2014 | 20% Development Fund | 1000000 | 965836.63 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
15 | Magsaysay/Cuyo Circumferential Road Concreting | NULL | Transportation Facilities | ROAD | NULL | NULL | Magsaysay | PEO | 2014 | 20% Development Fund | 2000000 | 1975820.87 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
16 | Road Concreting Binudac | NULL | Transportation Facilities | ROAD | NULL | NULL | Culion | PEO | 2014 | 20% Development Fund | 1000000 | 965292.13 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
17 | Construction of Wooden Bridge, Bgy. Sto. Niño | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Sto. Niño, San Vicente | San Vicente | PEO | 2014 | 20% Development Fund | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
18 | Construction of Detour & Rehabilitation of Tumarbong Bridge | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Roxas | PEO | 2014 | 20% Development Fund | 668747.78 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
19 | Redecking of Caruray Bridge | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Caruray, San Vicente | San Vicente | PEO | 2014 | 20% Development Fund | 70000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
20 | Repair of Ilian Hanging Bridge | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Ilian, Dumara, | Dumaran | PEO | 2014 | 20% Development Fund | 254200 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
21 | Construction of 1CL Building, Nangalao Pre-School | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Classroom School Building | Bgy. Nangalao | Linapacan | PEO | 2014 | 20% Development Fund | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
22 | Dr. Jose Rizal District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2014 | DOH-Trust Fund | 49000000 | 48997422.62 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
23 | Coron District Hospital Rehabilitation/Improvement of Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2014 | DOH-Trust Fund | 4000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
24 | Construction of NPPH Additional Facility (Isolation Building) |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion | Taytay | PEO | 2014 | DOH-Trust Fund | 3000000 | 2997801.43 | 165 | 2017-11-20 |  | 2018-05-04 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
25 | Improvement of Northern Palawan Provincial Hospital (Construction of Motorpool/COOP Store/Storage)Phae I |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion | Taytay | PEO | 2014 | DOH-Trust Fund | 2000000 | 1995919.14 | 90 | 2017-11-20 |  | 2018-02-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
26 | Expansion of Barangay Health Station Batang-batang |  | Medical Facilities | BHS |  | Bgy. Batang-batang | Narra | PEO | 2014 | DOH - HFEP | 666666.66 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
27 | Expansion of Barangay Health Station Caguisan |  | Medical Facilities | BHS |  | Bgy. Caguisan | Narra | PEO | 2014 | DOH - HFEP | 666666.66 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
28 | Expansion of Barangay Health Station Elvita |  | Medical Facilities | BHS |  | Bgy. Elvita | Narra | PEO | 2014 | DOH - HFEP | 666666.66 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
29 | Expansion of Barangay Health Station Bemonc ,Calumpang |  | Medical Facilities | BHS |  | Bgy. Calumpang | Quezon | PEO | 2014 | DOH - HFEP | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
30 | Expansion of Barangay Health Station Bemonc,Isugod |  | Medical Facilities | BHS |  | Bgy. Isugod | Quezon | PEO | 2014 | DOH - HFEP | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
31 | Expansion of Barangay Health Station Bemonc,Panitian |  | Medical Facilities | BHS |  | Bgy. Panitian | Quezon | PEO | 2014 | DOH - HFEP | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
32 | Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  |  | Aborlan | PEO | 2014 | DOH - HFEP | 31384000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
33 | Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municapal Hospital | Narra | PEO | 2014 | DOH - HFEP | 10000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
34 | Quezon Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | QuezonMedicare Hospital | Quezon | PEO | 2014 | Trust Fund - DOH | 8000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
35 | Coron District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  |  | Coron | PEO | 2014 | DOH - HFEP | 49000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
36 | Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo, Palawan | Cuyo | PEO | 2014 | DOH - HFEP |  | 26362962.68 | 380 | 2016-11-03 |  | 2017-11-18 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
37 | Roxas Medical Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2014 | DOH - HFEP | 12300000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
38 | Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2014 | Trust Fund -DOH | 10999080 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
39 | Site Development, Road Concreting and Construction of NHA Yolanda Housing Units | B2 TF 416 NHA CONST OF NHA YOLANDA HOUSING UNIT 17-250 | Other Facilities | OTHER FACILITIES | NULL | Bgy. Binudac, Bgy. Galoc, Bgy. Baldat | Culion | PEO | 2014 | NHA Fund | 194700000 | 194699088.21 | 360 | 2018-09-05 | NULL | 2019-08-31 | 2023-01-21 | NULL | 100% | NULL | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814 | NULL
40 | Concreting of Barangay Road of Sitio Sader, Bgy. Bantulan | ROAD 300-15-08-12075 | Transportation Facilities | ROAD | NULL | Sitio Sader, Bgy. Bantulan, Taytay | Taytay | PEO | 2015 | 20% Development Fund | 1000000 | 987653.71 | 60 | 2015-10-12 | NULL | 2015-12-11 | NULL | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
41 | Construction of Mauringen Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Mauringen | Araceli | PEO | 2015 | 20% Development Fund and DOH | 500000 | 500000 | [8 empty] | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
42 | Construction of Banbanan Barangay Health Station | TF 416 DOH -15-118 | Medical Facilities | BHS | 6.50m (w) x 9.00 m (l) Single Storey Building complete with CR and Electrical | Bgy. Banbanan | Taytay | PEO | 2015 | TF - DOH HFEP 2014 | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
43 | Construction of Calawag Barangay Health Station | TF 416 DOH -15-117 | Medical Facilities | BHS | 6.50m (w) x 9.00 m (l) Single Storey Building complete with CR and Electrical | Bgy. Calawag | Taytay | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
44 | Construction of 4 units Multi-purpose Bldg. in Gaudencio Abordo Mem. NHS, Agutaya, Palawan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Gaudencio Abordo Memorial National High School | Agutaya | PEO | 2015 | 20% Development Fund | 2540000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Validation | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | For Validation: Cancelled
45 | Construction of Multi-Purpose Bldg. in So. Kadulan, Panalingaan, Rizal | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | So. Kadulan, Panalingaan, Rizal | Rizal | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
46 | Construction of Multi-Purpose Cumahos Elementary School, Panalingaan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Panalingaan | Rizal | PEO | 2015 | 20% Development Fund | 2140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
47 | Construction of Multi-Purpose Bldg., Calawag National High School | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Calawag, Taytay, Palawan | Taytay | PEO | 2015 | 20% Development Fund | 1605000 | 1553062.08 | 100 | 2015-11-17 | NULL | 2016-02-25 | NULL | NULL | NULL | NULL | By contract | For Validation | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Validation: Cancelled
48 | Construction of Bebeledan Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Bebeledan | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
49 | Construction of Bucana Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Bucana | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
50 | Construction of Mabini Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Mabini | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
51 | Construction of Teneguiban Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Teneguiban | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
52 | Construction of Villa Paz Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Paz | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
53 | Construction of Jolo Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Jolo | Roxas | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
54 | Construction of Tumarbong Barangay Health Station |  | Medical Facilities | BHS |  | Bgy. Tumarbong | Roxas | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
55 | Construction of Caramay Barangay Health Station | TF 416 DOH -15 - 121 | Medical Facilities | BHS |  | Bgy. Caramay | Roxas | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
56 | Construction of Multi-purpose Bldg. Agutaya Phase 3 | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Municipality of Agutaya | Agutaya | PEO | 2015 | 20% Development Fund | 2000000 | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
57 | Construction of Motorpool | NULL | Other Facilities | OTHER FACILITIES | NULL | NULL | Rizal | PEO | 2015 | 20% Development Fund | 6900000 | 6637160.49 | 130 | 2016-09-16 | NULL | 2017-01-24 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
58 | Construction of Motorpool Brooke's Point | NULL | Other Facilities | OTHER FACILITIES | NULL | Bgy. Pangobilian, Brooke's Point | Brooke's Point | PEO | 2015 | 20% Development Fund | 6900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Jas Trading and Construction | NULL | NULL
59 | Construction of Motorpool Phase II, Irawan | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 5000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
60 | Concreting of Road of Roxas Medicare Hospital | ROAD 300-15-09-13154 | Transportation Facilities | ROAD | NULL | Barangay III, Roxas, Palawan | Roxas | PEO | 2015 | 20% Development Fund | 500000 | 497887.18 | 30 | 2016-02-04 | NULL | 2016-03-05 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
61 | Concreting of Road Towards Elnido Medicare Hospital | NULL | Transportation Facilities | ROAD | NULL | Elnido Medicare Hospital | El Nido | PEO | 2015 | 20% Development Fund | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
62 | Concreting of Road towards Rizal Municipal/PGP Motorpool | NULL | Transportation Facilities | ROAD | NULL | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2015 | 20% Development Fund | 5000000 | 3501330.96 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
63 | Concreting of Roads towards PGP Motorpool, Irawan | NULL | Transportation Facilities | ROAD | NULL | Bgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 2000000 | 1910798.55 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
64 | Concreting of Circumferential Road, Magsaysay - Cuyo | NULL | Transportation Facilities | ROAD | NULL | NULL | Magsaysay | PEO | 2015 | 20% Development Fund | 3500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
65 | Concreting of Cagayancillo Circumferential Road | ROAD 300-15-05-07193 | Transportation Facilities | ROAD | PCCP L=885m - W=2m - T=0.15m : Shoulder=1.00m bothsides - One (1) Lane PCCP | Cagayancillo, Palawan | Cagayancillo | PEO | 2015 | 20% Development Fund | 2000000 | 1975497.2 | 60 | 2015-11-16 | NULL | 2016-01-15 | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
66 | Concreting of Suba - Pawa 2.5m with 2nd Lane, Cuyo | NULL | Transportation Facilities | ROAD | NULL | Cuyo | Cuyo | PEO | 2015 | 20% Development Fund | 2000000 | 1965054.26 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
67 | Concreting of Zabanal Road, San Vicente | NULL | Transportation Facilities | ROAD | NULL | NULL | San Vicente | PEO | 2015 | 20% Development Fund | 5000000 | 4995752.1 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
68 | Concreting of Road Bgy. Liminangcong, Taytay | NULL | Transportation Facilities | ROAD | NULL | NULL | Taytay | PEO | 2015 | 20% Development Fund | 3500000 | 3234305.76 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
69 | Concreting of Road of Bgy. Aramaywan, Narra | NULL | Transportation Facilities | ROAD | NULL | Bgy. Aramaywan | Narra | PEO | 2015 | 20% Development Fund | 1500000 | 1480746.01 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
70 | Concreting of Dumaran Road, Dumaran | NULL | Transportation Facilities | ROAD | NULL | Dumaran | Dumaran | PEO | 2015 | 20% Development Fund | 2000000 | 1908041.04 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
71 | Concreting of Bgy. Road, Minara, Roxas | NULL | Transportation Facilities | ROAD | NULL | Bgy. Minara | Roxas | PEO | 2015 | 20% Development Fund | 640000 | 633860.25 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
72 | Concreting of Bgy. Road, Bgy. Calawag, Taytay | NULL | Transportation Facilities | ROAD | NULL | Bgy. Calawag, Taytay | Taytay | PEO | 2015 | 20% Development Fund | 2424000 | 2360130.36 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
73 | Construction of Detour Road w/ Spillway, Taradungan,Roxas | NULL | Transportation Facilities | ROAD | NULL | Bgy. Taradungan | Roxas | PEO | 2015 | 20% Development Fund | 8000000 | 7861836.42 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
74 | Construction of Multipurpose Bldg., Underground ES, Alfonso XIII, Quezon | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. XIII | Quezon | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
75 | Construction of Multipurpose Bldg., Tarumpitao ES, Rizal | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Tarumpitao ES, Rizal | Rizal | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
76 | Construction of Multipurpose Bldg., Aplaya ES, Aborlan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Aplaya ES, Aborlan | Aborlan | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
77 | Construction of Multipurpose Bldg., Aramaywan II ES, Aramaywan, Narra | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Aramaywan | Narra | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
78 | Const. of Bahay Kubo w/ Fencing in PJMD, Bancao2 PPC | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Bancao | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 338000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
79 | Const. of KILN in PJMD Annex Bldg., Banca-bancao, PPC | NULL | Other Facilities | PGP FACILITIES | NULL | Banca-bancao, PPC | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
80 | Const. of PEPO Bunkhouse Quarters, Irawan | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Irawan | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Jas Trading and Construction | NULL | NULL
81 | Rehabilitation of Narra Gymnasium | NULL | Other Facilities | OTHER FACILITIES | NULL | Bgy. Narra | Narra | PEO | 2015 | 20% Development Fund | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
82 | Const. of Perimeter Fence of SPPH, Brooke's Point |  | Medical Facilities | MEDICAL FACILITIES |  | SPPH, Brooke's Point | Brooke's Point | PEO | 2015 | 20% Development Fund | 1500000 | [7 empty] | 100% |  | By contract | Completed | Jas Trading and Construction
83 | Const. of Perimeter Fence of Roxas Medicare Hospital | ROAD 300-15-08-12073 | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2015 | 20% Development Fund | 1600000 | 1434227.27 | 75 | 2016-02-01 |  | 2016-04-16 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
84 | Const. of Seawall Protection, Bgy. Rizal, Roxas | NULL | Ports and Airports | PORTS | NULL | Bgy. Rizal, Roxas | Roxas | PEO | 2015 | 20% Development Fund | 1800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
85 | Improvement of Agutaya Sea Port, Agutaya, Palawan | NULL | Ports and Airports | PORTS | NULL | Municipality of Agutaya | Agutaya | PEO | 2015 | 20% Development Fund | 988000 | 987358.13 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
86 | Const. of Boat Landing in New Guinlo, Taytay | NULL | Ports and Airports | PORTS | NULL | New Guinlo | Taytay | PEO | 2015 | 20% Development Fund | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
87 | Const. of Boat Landing in Old Guinlo, Taytay | NULL | Ports and Airports | PORTS | NULL | Old Guinlo | Taytay | PEO | 2015 | 20% Development Fund | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
88 | Construction of Water System Project Phase I, Bantulan | B2 ROADS 300-15-05-06875 | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Bgy. Bantulan | Taytay | PEO | 2015 | 20% Development Fund | 8900000 | NULL | NULL | 2017-01-04 | NULL | 2017-01-04 | NULL | NULL | 100% | NULL | By contract | Completed | Atlanta Construction Company Inc. | NULL | NULL
89 | Construction of Barangay Health Station, Bagong Bayan |  | Medical Facilities | BHS |  | Bagong Bayan, El Nido | El Nido | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
90 | San Vicente Barangay Health Station, Caruray |  | Medical Facilities | BHS |  | Caruray, San Vicente | San Vicente | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
91 | San Vicente Barangay Health Station, Alimanguan |  | Medical Facilities | BHS |  | Alimanguan, San Vicente | San Vicente | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
92 | Sofronio Española Rural Health Unit |  | Medical Facilities | RHU |  |  | Sofronio Española | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
93 | Samareñana Barangay Health Station |  | Medical Facilities | BHS |  |  | Brooke's Point | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
94 | Magbabadil Barangay Health Station |  | Medical Facilities | BHS |  |  | Aborlan | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
95 | Narra Rural Health Unit |  | Medical Facilities | RHU |  |  | Narra | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
96 | Construction of Barangay Health Station, Bgy. Mendoza, Roxas | B2 BFIP 300-16-10-14515-14516 (Construction of Barangay Health Station at Bgy. Nicanor Zabala and Bgy. Mendoza, Roxas, Palawan) | Medical Facilities | BHS |  | Bgy. Mendoza, Roxas | Roxas | PEO | 2015 | 20% Development Fund | 1000000 | 992639.37 | 150 | 2017-01-16 |  | 2017-06-15 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
97 | Construction of Barangay Health Station ,Bgy Nicanor Zabala,Roxas | B2 BFIP 300-16-10-14515-14516 (Construction of Barangay Health Station at Bgy. Nicanor Zabala and Bgy. Mendoza, Roxas, Palawan) | Medical Facilities | BHS |  | Bgy. Nicanor Zabala,Roxas | Roxas | PEO | 2015 | 20% Development Fund | 1000000 | 992639.37 | 150 | 2017-01-16 |  | 2017-06-15 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
98 | Construction of Barangay Hall in Bato-Bato, Narra | NULL | Other Facilities | OTHER FACILITIES | NULL | Bato-Bato, Narra | Narra | PEO | 2015 | 20% Development Fund | 1800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
99 | Construction of 4 units Multi-Purpose Bldg in Mendoza NHS, Mendoza, Roxas | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Mendoza, Roxas | Roxas | PEO | 2015 | 20% Development Fund | 2140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
100 | Construction of 2 units Multi-Purpose Building in Mabini ES, Aborlan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Mabini ES, Aborlan | Aborlan | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
101 | Construction of 2 units Multi-Purpose Building in Labangan ES, Bgy. Bunog, Rizal | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Labangan Elementary School, Bgy. Bunog, Rizal | Rizal | PEO | 2015 | 20% Development Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
102 | Rehabilitation of Saraza Bridge ( Tagbalogo-Saraza Road) Brooke's Point | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Brooke's | Brooke's Point | PEO | 2015 | 20% Development Fund | 880000 | 852413.86 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
103 | Repair of Inalyawan Bailey Bridge (Cataban - Limininangcong Rd. ) | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Taytay | PEO | 2015 | 20% Development Fund | 250000 | 249269.92 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
104 | Installation of 1 line - 24" RCPC with concrete headwall ( Bagong Sikat Line 8 Rd. ), Narra | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Narra | PEO | 2015 | 20% Development Fund | 50000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
105 | Installation of 1 line - 36" RCCP with concrete headwall ( Sumbiling-Canipaan Rd. ) | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Bataraza | PEO | 2015 | 20% Development Fund | 80000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
106 | Installation of 3 lines - 36" RCCP serve as detour for Impatian Bridge ( Paglaum - Itangil Rd. ), Dumaran | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Dumaran | PEO | 2015 | 20% Development Fund | 120000 | 112443.4 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
107 | Installation of 1 line (22pcs) - 36" RCCP with concrete headwall ( Plaridel-Apis-Cabigaan Rd. ), Aborlan | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Aborlan | PEO | 2015 | 20% Development Fund | 130000 | 128595.94 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
108 | Installation of 6 lines - 24" RCCP with concrete headwall ( Itangil-Magsaysay-Culasian Rd. ), Dumaran | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Dumaran | PEO | 2015 | 20% Development Fund | 199168 | 188097.09 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
109 | Concreting of Taritien, Narra - Farm to Market Road | NULL | Transportation Facilities | ROAD | NULL | Narra | Narra | PEO | 2015 | 20% Development Fund | 6470000 | 6412611.41 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
110 | Construction of RCDG, Kaybulusan Bridge, Purok Masigla, Magara, Roxas | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Magara | Roxas | PEO | 2015 | Locally Funded | 4150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
111 | Construction of RCDG, Malebeb Bridge, Purok Masigla, Magara, Roxas | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Magara | Roxas | PEO | 2015 | Locally Funded | 3420000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
112 | Concreting of Barangay Road, Magara | NULL | Transportation Facilities | ROAD | NULL | NULL | Roxas | PEO | 2015 | Locally Funded | 1000000 | 987317.01 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
113 | Repair of Footbridge in Bgy. Silanga | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Silanga | Taytay | PEO | 2015 | Locally Funded | 600000 | 600000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | NULL | NULL | NULL
114 | Concreting of Road from 570th to Main Gate of WESCOM (Golf Course Side) | NULL | Transportation Facilities | ROAD | NULL | NULL | Puerto Princesa City | PEO | 2015 | Locally Funded | 1900000 | 1900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
115 | Construction of 2CL Sch. Building in Manamoc ES, Manamoc | ROAD 300-15-08-11724 | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Bgy. Manamoc | Cuyo | PEO | 2015 | Locally Funded | 1270000 | 1226903.21 | 70 | 2015-10-23 | NULL | 2016-01-01 | NULL | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
116 | Rehabilitation and Improvement of Capitol Building and Facilities | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 7288773 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
117 | Improvement of Boat Landing in Banbanan | NULL | Ports and Airports | PORTS | NULL | Bgy. Banbanan | Taytay | PEO | 2015 | Locally Funded | 150000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | EM Paule Construction and Trading | NULL | NULL
118 | Construction of Fence of PNP Headquarters - Provincial Police Office in Tiniguiban | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Tiniguiban | Puerto Princesa City | PEO | 2015 | Locally Funded | 490000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
119 | Construction of 2 CL School building in Libertad ES Elementary School | SB1 300-15-12-20595 | Educational Facilities | SCHOOL FACILITIES | 2 CL - No. of Storey: 1 storey: Floor area: 18.0mx7.0m: Hallway: 18.0m x 1.2m: Type of Truss: Steel Truss | Libertad ES Elementary School | Taytay | PEO | 2015 | Special Education Fund | 1070000 | 1064474.36 | 70 | 2016-03-11 | NULL | 2016-05-20 | NULL | NULL | NULL | NULL | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
120 | Construction of 2CL School Building in Agutayan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Agutayan Elementary School | Balabac | PEO | 2015 | Special Education Fund | 1270000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
121 | Construction of 2CL School Building in Antipuluan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Antipuluan Elementary School | Narra | PEO | 2015 | Special Education Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
122 | Construction of 2CL School Building in Cabuluan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Cabuluan Elementary School | Narra | PEO | 2015 | Special Education Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
123 | Construction of 4CL School Building in Tagpait Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | Tagpait Elementary School | Aborlan | PEO | 2015 | Special Education Fund | 2140000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
124 | Construction of 3CL School Building in Pinaglabanan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Pinaglabanan Elementary School | Quezon | PEO | 2015 | Special Education Fund | 1605000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
125 | Construction of 2CL School Building in Pinuwasan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Pinuwasan Elementary School | Bataraza | PEO | 2015 | Special Education Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
126 | Construction of 2CL School Building in Rafael R. Estiandan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Rafael R. Estiandan Elementary School | Brooke's Point | PEO | 2015 | Special Education Fund | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
127 | Construction of 3CL School Building in Mainit Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Mainit Elementary School | Brooke's Point | PEO | 2015 | Special Education Fund | 1605000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
128 | Construction of 4CL School Building in Linapacan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | Linapacan Elementary School | Linapacan | PEO | 2015 | Special Education Fund | 2540000 | 2359957.11 | 200 | 2016-01-05 | NULL | 2016-07-23 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
129 | Construction of 2 Classroom School Building in Balala Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Bgy. Balala | Culion | PEO | 2015 | Locally Funded | 1070000 | 1070000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
130 | Construction of Evacuation Center/Multi-Purpose Bldg., Cagayancillo, Palawan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | NULL | Cagayancillo | PEO | 2015 | Locally Funded | 2738000 | 2738000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | EM Paule Construction and Trading | NULL | NULL
131 | Construction of Agutaya Multi-purpose | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Municipality of Agutaya | Agutaya | PEO | 2015 | Trust Fund- Cong. Alvarez | 2970000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | On going | NULL | NULL | NULL
132 | Construction of Roxas Multi-Purpose Building | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | NULL | Roxas | PEO | 2015 | Trust Fund- Cong. Alvarez | 4950000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | NULL | NULL | NULL
133 | Construction of Pre-fabrication Office Building of Western Command Camp, Tiniguiban, PPC | NULL | Other Facilities | PGP FACILITIES | NULL | Tiniguiban, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 400000 | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | NULL | NULL | NULL
134 | Construction of PSWD Building, Puerto Princesa City | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 3000000 | 3000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | NULL | NULL | NULL
135 | Construction of Material Recovery Facilities Building |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municapal Hospital | Narra | PEO | 2015 | DBP Loan | 600000 | 586100.28 | [6 empty] | 100% |  | By contract | Completed
136 | Construction of Dietary & Linen Building |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municapal Hospital | Narra | PEO | 2015 | DBP Loan | 2490085.72 | [7 empty] | 100% |  | By contract | Completed
137 | Construction of Isolation Building |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municapal Hospital | Narra | PEO | 2015 | DBP Loan | 2402013.62 | [7 empty] | 100% |  | By contract | Completed
138 | Upgrading of Itangil Bailey Bridge to RCDG Bridge | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Itangil | Dumaran | PEO | 2015 | PCF 2015 (DILG) | 7000000 | 6987806.15 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
139 | Construction of Dietary & Linen Building |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2015 | DBP Loan | 2500000 | [7 empty] | 100% |  | By contract | Completed
140 | Construction of Doctor's Quarter |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2015 | DBP Loan | 4500000 | [7 empty] | 100% |  | By contract | Completed
141 | Construction of Roxas Medicare Hospital (Main Building) Phaase II |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2015 | DOH | 6300000 | [7 empty] | 100% |  | By contract | Completed
142 | Construction of 3CL School Building in Mangsee Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy. Mangsee | Balabac | PEO | 2015 | Special Education Fund | 1905000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
143 | Construction of 3CL School Building Paliisan Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy. Paliisan | Balabac | PEO | 2015 | Special Education Fund | 1905000 | NULL | NULL | 2018-01-10 | NULL | 2018-01-10 | NULL | NULL | NULL | NULL | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
144 | Construction of Palawan People Technology Vocational University, Bgy. Plaridel | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | Bgy. Plaridel | Aborlan | PEO | 2015 | Locally Funded | 17762000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
145 | Rehabilitation and Improvement of Gov. Office and mini conference room and Facilities | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 1367300 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | NULL | NULL | NULL
146 | Rehabilitation and Improvement of centenial pavillion and stage | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 733500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | NULL | NULL | NULL
147 | Rehabilitation and Improvement of Gov. Conference Room and Facilities | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 648574 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | NULL | NULL | NULL
148 | Rehabilitation and Improvement of the 2nd Floor left wing , Capitol Bldg. | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 2061970 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | NULL | NULL | NULL
149 | Construction of Slaking & Storage Facilities |  | Medical Facilities | MEDICAL FACILITIES |  |  | Quezon | PEO | 2015 | Locally Funded | 199900 | [7 empty] | 100% |  | By contract | Completed
150 | Renovation/Improvement of PNP Academic & Transient Bldg., Tiniguiban | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Tiniguiban | Puerto Princesa City | PEO | 2015 | Locally Funded | 3620351 | 3620351 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | NULL | NULL | NULL
151 | Construction of Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Pangobilian, Brooke's Point, Palawan | Brooke's Point | PEO | 2015 | DBP Loan | 44410000 | [7 empty] | 100% |  | By contract | Completed
152 | Construction of Dietary & Linen Building |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 2490085.71 | [7 empty] | 100% |  | By contract | Completed
153 | Construction of Isolation Building |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 2402013.62 | [7 empty] | 100% |  | By contract | Completed
154 | Construction of Doctor's Quarter |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 4405153.15 | [7 empty] | 100% |  | By contract | Completed
155 | Construction of Material Recovery Facilities Building |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 586100.28 | [7 empty] | 100% |  | By contract | Completed
156 | Construction of Mortuary Building |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 778374.63 | [7 empty] | 100% |  | By contract | Completed
157 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 1507888.49 | [7 empty] | 100% |  | By contract | Completed
158 | Construction of Circular Elevated Water Tank |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 480869.63 | [7 empty] | 100% |  | By contract | Completed
159 | Upgrading of Villa Constancia Bailey Bridge to RCDG | ROAD 300-16-06-05893 | Transportation Facilities | BRIDGES | NULL | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 7320000 | 7169578.6 | 210 | 2016-03-11 | NULL | 2016-10-07 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
160 | Upgrading of Ariman-an Bailey Bridge to RCDG | ROAD 300-16-06-05891 | Transportation Facilities | BRIDGES | NULL | Bgy. Talog | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4553792.92 | 120 | 2016-11-18 | NULL | 2017-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
161 | Upgrading of Impatian Bailey Bridge I to RCDG | ROAD 300-16-06-05894 | Transportation Facilities | BRIDGES | NULL | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4606459.03 | 120 | 2016-11-18 | NULL | 2017-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
162 | Upgrading of Impatian Bailey Bridge II to RCDG | ROAD 300-16-06-07511 | Transportation Facilities | BRIDGES | NULL | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 6000000 | 5910060.61 | 120 | 2016-09-19 | NULL | 2017-01-17 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
163 | Upgrading of Tagumpay Bailey Bridge III to RCDG | ROAD 300-16-06-05890 | Transportation Facilities | BRIDGES | NULL | Bgy. Sta. Maria | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4710678.74 | 120 | 2016-11-18 | NULL | 2017-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
164 | Upgrading of Sta. Maria Bailey Bridge 1 to RCDG (Length = 12.70lm) | B2 BFIP 300-16-11-15237 | Transportation Facilities | BRIDGES | NULL | Bgy. Sta. Maria | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4721144.63 | 120 | 2017-03-07 | NULL | 2017-07-05 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
165 | Upgrading of Caruray Bailey Bridge to RCDG (Length = 15.24 lm) | NULL | Transportation Facilities | BRIDGES | NULL | NULL | San Vicente | PEO | 2016 | 20% Development Fund | 6000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Validation | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
166 | Construction of Barangay Health Station in Sitio Lamud, Bgy. Luac | B2 BFIP 300-16-1-16176-166177 | Medical Facilities | BHS |  | Bgy. Luac | Culion | PEO | 2016 | 20% Development Fund | 1500000 | 1491336 | 150 | 2017-03-08 |  | 2017-08-05 |  | 2022-11-05 | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
167 | Construction of Multi-purpose Building in Bgy. Poblacion | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Poblacion | El Nido | PEO | 2016 | 20% Development Fund | 2500000 | 2497989.47 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
168 | Repair of VEP Powerhouse | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bisucay | Cuyo | PEO | 2016 | 20% Development Fund-Savings | 409504.09 | 407517.25 | 30 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
169 | Concreting of Malapandeg - Rancho Road (Intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | NULL | Rizal | PEO | 2016 | 20% Development Fund | 2800000 | 2793289.78 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
170 | Concreting of Critical Sections of Highway Junction - Taradungan Road | B2 BFIP 300-16-11-15239 | Transportation Facilities | ROAD | NULL | Tumarbong and Taradungan, Roxas, Palawam | Roxas | PEO | 2016 | 20% Development Fund | 7047308.25 | 6949230.94 | 150 | 2017-08-11 | NULL | 2018-01-08 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
171 | Concreting of Highway Junction of New Guinlo Road (Intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | Bgy. New Guinlo | Taytay | PEO | 2016 | 20% Development Fund | 1880000 | 1876807.01 | 120 | 2017-03-08 | NULL | 2017-07-06 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
172 | Construction of Transformer Platform in Rizal Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2016 | 20% Development Fund | 227000 | 226313.49 | [6 empty] | 100% |  | By contract | Completed
173 | Rehabilitation of Hanging Bridge of San Juan | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. San Juan | Aborlan | PEO | 2016 | 20% Development Fund | 745000 | 743271.86 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
174 | Construction of RC Slide Slope Protection and Approach PCCP for Antonino RCBC | B2 BFIP 300-16-11-15240 | Other Infrastructure | SLOPE PROTECTION | NULL | Brgy. Antonino, Roxas, Palawan | Roxas | PEO | 2016 | 20% Development Fund | 1300000 | 1239259.58 | 40 | 2017-03-07 | NULL | 2017-04-16 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
175 | Concreting of Road network inside Aborlan Medicare Hospital Facilities | NULL | Transportation Facilities | ROAD | NULL | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 2500000 | 2487509.99 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
176 | Concreting of Zabanal Road Phase 2 | NULL | Transportation Facilities | ROAD | NULL | NULL | San Vicente | PEO | 2016 | 20% Development Fund | 5000000 | 4967139.44 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
177 | Construction of 4 barrels Reinforced Concrete Box Culvert in PSU Road (Ht. 4m) | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Bataraza | PEO | 2016 | 20% Development Fund | 3670000 | 3612204.01 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
178 | Construction of Multi-Purpose Pavement, Barangay Mendoza | B2 BFIP 300-16-11-16175 | Other Facilities | MULITI-PURPOSE | NULL | Bgy. Mendoza | Roxas | PEO | 2016 | 20% Development Fund | 664514.67 | 664196.41 | 15 | 2017-02-24 | NULL | 2017-03-11 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
179 | Construction of Multi-Purpose Bldg. in Alfonso XIII | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Alfonso XIII | Quezon | PEO | 2016 | 20% Development Fund | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
180 | Construction of Multi-Purpose Bldg. in Punta Baja | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Punta Baja | Rizal | PEO | 2016 | 20% Development Fund | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
181 | Construction of Multi-Purpose Bldg. in Pangobilian | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Pangobilian | Brooke's Point | PEO | 2016 | 20% Development Fund | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
182 | Construction of Perimeter Fence of Aborlan Medicare Hospital Phase 2 |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 650000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
183 | Construction of Transformer Platform in Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
184 | Construction of Transformer Platform in Roxas Medicare Hospital | B2 BFIP 300-16-11-15228 | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | 20% Development Fund | 227000 | 226313.49 | 27 | 2017-03-17 |  | 2017-04-13 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
185 | Construction of Transformer Platform in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
186 | Upgrading of Little Caramay Bailey Bridge to RCDG (Length= 19.00lm) | NULL | Transportation Facilities | BRIDGES | NULL | San Vicente | San Vicente | PEO | 2016 | 20% Development Fund | 7400000 | 7363650.94 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
187 | Rehabilitation of Sagpangan - Pandacan Spillway | NULL | Other Infrastructure | OTHER FACILITIES | NULL | NULL | Aborlan | PEO | 2016 | 20% Development Fund | 3000000 | 2919485.77 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
188 | Rehabilitation of Ipilan Spillway w/ riprap on riverbank | NULL | Other Infrastructure | OTHER FACILITIES | NULL | NULL | Brooke's Point | PEO | 2016 | 20% Development Fund | 2500000 | 2425815.59 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
189 | Ipilan Slope Protection | NULL | Other Infrastructure | SLOPE PROTECTION | NULL | NULL | Brooke's Point | PEO | 2016 | 20% Development Fund | 1900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
190 | Concreting of Panitian - Abokayan Road | NULL | Transportation Facilities | ROAD | NULL | Bgy. Abokayan | Sofronio Española | PEO | 2016 | 20% Development Fund | 1500000 | 1439993.06 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
191 | Construction of Kalupisan Spillway, Punta Baja | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Punta | Rizal | PEO | 2016 | 20% Development Fund | 1620000 | 1487895.23 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
192 | Construction of 1 Barrell RCBC - Antonino Road | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Antonino | Roxas | PEO | 2016 | 20% Development Fund | 854012 | 850719.43 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
193 | Concreting of Bgy. Road, Minara (110m x 2.5m x 0.20m) | NULL | Transportation Facilities | ROAD | (110m x 2.5m x 0.20m) | Bgy. Minara | Roxas | PEO | 2016 | 20% Development Fund | 400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
194 | Construction of 4 Barrels Reinforced Concrete Box Culvert, Pamantolon | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Pamantolon | Taytay | PEO | 2016 | 20% Development Fund | 3670000 | 3666585.05 | 120 | 2016-11-09 | NULL | 2017-03-09 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
195 | Construction of 4 Barrel Box Culvert, Dumarao | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Dumarao | Roxas | PEO | 2016 | 20% Development Fund | 2330000 | 2319095.71 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
196 | Construction of San Nicolas Spillway | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Nicolas, Coron | Coron | PEO | 2016 | 20% Development Fund | 3300000 | 3262614.04 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
197 | Construction of Motorpool | NULL | Other Facilities | OTHER FACILITIES | NULL | NULL | Rizal | PEO | 2016 | 20% Development Fund | 6900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
198 | Construction of Perimeter Fence of Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 3144388 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
199 | Construction of Perimeter Fence of Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2016 | 20% Development Fund | 3100000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
200 | Construction of Pamantolon Dist. Pipeline (going to Pob.) | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | NULL | Taytay | PEO | 2016 | 20% Development Fund | 18355612 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
201 | Concreting of Road Network Inside Southern Palawan Provincial Hospital Facilities with Gate |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 3500000 | 3490500.14 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
202 | Concreting of Road Network Inside Roxas Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2500000 | 2497858.36 | 120 | 2018-02-14 |  | 2018-06-14 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
203 | Concreting of Road Network inside Narra Municipal Hospital | B2 SB6 PEO17-300-18-03-01951 | Medical Facilities | MEDICAL FACILITIES | (a) PCCP 360M (4M & 5M Width) - (b) 45m (L) x 6m(W) (C) 14LN.M | Narra Municipal Hospital | Narra | PEO | 2016 | SB No. 6 - Debt Servicing Under 20% DF (2014-2015-2016) | 3500000 | 3483428.65 | 60 | 2018-05-25 |  | 2018-07-24 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
204 | Concreting of Road Network Coron District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2000000 | 1996206.34 | [6 empty] | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
205 | Construction of Cuyo Medicare Hospital Perimeter Fence with Gate Phase I, Cuyo, Palawan | B2 SB6 PEO 300-17-11-20076 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2016 | Supplemental Budget No. 6 | 2500000 | 2497556.65 | 120 | 2018-02-14 |  | 2018-06-14 |  |  |  |  | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
206 | Installation of Conversion of Single phase to Three Phase Line going to Roxas Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 148826.09 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
207 | Installation of Extension 3 Phase Line going to Rizal District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Rizal District Hospital | Rizal | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 904034.98 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
208 | Upgrading/Construction of RCDG Cabigaan Bridge 2 | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Aborlan | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 8000000 | 7848266.35 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
209 | Concreting of Road, Brgy Poblacion II | NULL | Transportation Facilities | ROAD | NULL | Brgy Poblacion II | Balabac | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 300000 | 299280.19 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
210 | Completion of Multipurpose Hall for Bgy Poblacion II | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Brgy Poblacion II | Balabac | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
211 | Construction of TB DOTS for SPPH |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 1242063.76 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
212 | Comstruction of Perimeter Fence in Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2500000 | [7 empty] | 100% |  | By contract | Completed
213 | Construction of Lamayo Processing Center Phase I, Sitio Yakal, New Guinlo, Taytay, Palawan | NULL | Other Facilities | AGRICULTURAL FACILITIES | NULL | Sitio Yakal, New Guinlo | Taytay | PEO | 2016 | Locally Funded | 3000000 | NULL | NULL | 2016-12-12 | NULL | 2016-12-12 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
214 | Construction of 30m reinforced Spillway, Bgy. Candawaga | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Candawaga | Rizal | PEO | 2016 | Performance Challenge Fund | 2837038.87 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
215 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I) Busuanga |  | Medical Facilities | RHU |  | Bgy. Salvacion | Busuanga | PEO | 2016 | Trust Fund - DOH | 21800000 | 20927555.05 | 300 | 2018-09-21 |  | 2019-07-18 | 2023-12-09 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
216 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Sofronio Española |  | Medical Facilities | RHU |  | Sofronio Española | Sofronio Española | PEO | 2016 | Trust Fund - DOH | 19940000 | 19925093.35 | 210 | 2018-09-21 |  | 2019-04-19 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
217 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Bgy. Aporawan Phase 1 |  | Medical Facilities | RHU |  | Bgy. Aporawan | Aborlan | PEO | 2016 | Trust Fund - DOH | 11940000 | 11917517.14 | 300 | 2018-08-10 |  | 2019-06-06 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
218 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Bgy. Panalingaan Phase 1 |  | Medical Facilities | RHU |  | Bgy. Panalingaan | Rizal | PEO | 2016 | Trust Fund - DOH | 11940000 | 11916499.76 | 300 | 2018-08-10 |  | 2019-06-06 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
219 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Linapacan |  | Medical Facilities | RHU |  | Linapacan | Linapacan | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-11-26 |  | 2019-09-22 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
220 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Agutaya |  | Medical Facilities | RHU |  | Municipality of Agutaya | Agutaya | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-12-13 | 2 | 2019-10-09 | For approval | 2023-11-23 | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
221 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Magsaysay |  | Medical Facilities | RHU |  | Magsaysay | Magsaysay | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-12-13 |  | 2019-10-09 | 2020-12-15 |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
222 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Cagayancillo |  | Medical Facilities | RHU |  | Cagayancillo | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2019-11-28 |  | 2020-09-23 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
223 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Pancol |  | Medical Facilities | RHU |  | Bgy. Pancol | Taytay | PEO | 2016 | Trust Fund - DOH | 11940000 | 11915174.28 | 300 | 2018-11-15 |  | 2019-09-11 |  |  | 100% |  | By contract | Completed | High Riser Construction & Trading | TIN 928-603-901
224 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Northeast Taytay |  | Medical Facilities | RHU |  | Northeast Taytay | Taytay | PEO | 2016 | Trust Fund - DOH | 11940000 | 11915174.28 | 300 | 2018-11-15 |  | 2019-09-11 |  |  | 100% |  | By contract | Completed | High Riser Construction & Trading | TIN 928-603-901
225 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Bgy. Mangsee |  | Medical Facilities | RHU |  | Bgy. Mangsee | Balabac | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-12-13 |  | 2019-10-09 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
226 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I) Bgy. Bancalaan |  | Medical Facilities | RHU |  | Bgy. Bancalaan | Balabac | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933384.21 | 300 | 2018-12-14 |  | 2019-10-10 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
227 | Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2016 | Trust Fund - DOH | 49750000 | 49743376.32 | 364 | 2017-03-13 |  | 2018-03-12 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
228 | Construction of 4CL School Building in Magkalip ES, Bgy. Taburi | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | Bgy. Taburi | Rizal | PEO | 2016 | Roads and Bridges Dev. Program-TF (2016) | 3000000 | 2991423.66 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
229 | Construction of Perimeter Fence of Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  |  | Narra | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2949649.54 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
230 | Casian Village Electrifcation Project | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Casian | Taytay | PEO | 2016 | Energy Development Program | 5329561.03 | 5327093.43 | 210 | 2017-05-22 | NULL | 2017-12-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
231 | Procurement of Construction Materials for the Rehabilitation of Small Division DAM Rancho I | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | Bgy. Rancho | Rizal | PEO | 2016 | DILG - BUB / LGSF | 328925.25 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | RAK Trading Construction & Supply | NULL | NULL
232 | Procurement of Construction Materials for the Construction of Irrigation Canal | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | Malaca-laca Kampong Ulay, Rizal | Rizal | PEO | 2016 | DILG - BUB / LGSF | 425032.06 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | RAK Trading Construction & Supply | NULL | NULL
233 | Construction of 2 Barrel RCBC, So. Singcab, Bgy Punang | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy Punang | Sofronio Española | PEO | 2016 | Performance Challenge Fund | 1162644.4 | 1125555.37 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
234 | Construction of 30 m reinforced Spillway,Sitio Maruso, Bgy. Candawaga | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Candawaga | Rizal | PEO | 2016 | Performance Challenge Fund | 2837038.87 | 2833978.07 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
235 | Concreting of Araceli- Dumaran Road "A" (Intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | Araceli | Araceli | PEO | 2016 | DILG -Kalasada Program | 55624667 | 40462906.79 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
236 | Concreting of Araceli- Dumaran Road "B" | NULL | Transportation Facilities | ROAD | NULL | Araceli | Araceli | PEO | 2016 | DILG -Kalasada Program | 40495136.54 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
237 | Concreting of Latungay- Sta. Terisita Road (Intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | NULL | Dumaran | PEO | 2016 | DILG -Kalasada Program | 42397934.4 | 42358978.67 | 270 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
238 | Construction of Malambunga Spillway, Punta Baja | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Punta Baja | Rizal | PEO | 2016 | 20% Development Fund | 2250000 | 2057472.07 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
239 | Construction of Slope Protection within the Roxas Medicare Hospital Area | B2 BFIP 300-16-11-15614 | Other Infrastructure | SLOPE PROTECTION | NULL | Roxas Medicare Hospital | Roxas | PEO | 2016 | 20% Development Fund | 2000000 | 1994845.1 | 90 | 2017-03-22 | NULL | 2017-06-20 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
240 | Construction of Transformer Platform in Coron District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
241 | Construction of Transformer Platform in Coron District Hospital | B2 BFIP 300-16-11-15232 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2016 | 20% Development Fund | 227000 | 226313.49 | 27 | 2017-03-03 |  | 2017-03-30 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
242 | Construction of Transformer Platform in Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | QuezonMedicare Hospital | Quezon | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
243 | Construction of Transformer Platform in Narra Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Medicare Hospital | Narra | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
244 | Construction of Perimeter Fence of Roxas Medicare Hospital Phase 2 |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | 20% Development Fund | 1726000 | [7 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
245 | Construction of Multi-purpose Building, Type II, in Sitio Balen | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Balen | Rizal | PEO | 2016 | 20% Development Fund | 950000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
246 | Construction of Multi-purpose Building, Type II, in Bgy. Salvacion | B2 BFIP 16 300-17-02-01581 | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Salvacion | Roxas | PEO | 2016 | 20% Development Fund | 950000 | 937594.76 | 120 | 2018-01-10 | NULL | 2018-05-10 | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
247 | Construction of Multi-purpose Building in Bgy. Pulot Center | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Pulot | Sofronio Española | PEO | 2016 | 20% Development Fund | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
248 | Construction of 4 Barrels Reinforced Concrete Box Culvert in Sta. 11+900, Alacalian | NULL | Other Infrastructure | DRAINAGE | Sta. 11+900, Alacalian (Ht. 4m) | Bgy. Alacalian | Taytay | PEO | 2016 | 20% Development Fund | 3670000 | 3612204.01 | 170 | 2017-03-17 | NULL | 2017-09-03 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
249 | Construction of Multi-purpose Building in Bgy. VI, Poblacion | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. VI, Poblacion | Balabac | PEO | 2016 | 20% Development Fund | 2500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
250 | Construction of Multi-Purpose Building Type I | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | NULL | Balabac | PEO | 2016 | 20% Development Fund | 2497986.48 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
251 | Rehabilitation of Bagumbayan- Latungay Road with Spillway | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgry. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 4200000 | 4159238.05 | 120 | 2017-03-07 | NULL | 2017-07-05 | 2017-05-07 | NULL | NULL | NULL | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
252 | Upgrading of Itangil Bridge 1 to RCDG | NULL | Transportation Facilities | ROAD | NULL | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 6000000 | 5995492.35 | 180 | 2016-12-20 | NULL | 2017-06-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
253 | Upgrading of Layok Bridge Timber Bridge to RCDG (Bgy. Itangil) | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 6237588.54 | 6228973.74 | 185 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
254 | Upgrading of Lamoro Ibajay Bailey Bridge I to RCDG | NULL | Transportation Facilities | BRIDGES | NULL | NULL | El Nido | PEO | 2016 | 20% Development Fund | 7100000 | 6892703.22 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
255 | Upgrading of Tumarbong Bailey Bridge to RCDG | B2 BFIP 300-16-12-17193 | Transportation Facilities | BRIDGES | (Length = 18.90 lm) | Tumarbong, Roxas, Palawan | Roxas | PEO | 2016 | 20% Development Fund | 7320000 | 7015047.47 | 210 | 2017-10-13 | NULL | 2018-05-11 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
256 | Upgrading of Abokayan Bailey Bridge to RCDG | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Sofronio Española | PEO | 2016 | 20% Development Fund | 10600000 | 10572619.91 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
257 | Construction of Multi-purpose Pavement, Sitio Bubusawin, Aporawan | NULL | Other Facilities | MULITI-PURPOSE | NULL | Sitio Bubusawin, Aporawan | Aborlan | PEO | 2016 | 20% Development Fund | 486000 | 484062.83 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
258 | Upgrading of Tulduan Bridge I to RCDG | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Tulduan | Taytay | PEO | 2016 | 20% Development Fund | 4800000 | 4381276.38 | NULL | 2016-11-18 | NULL | 2016-11-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
259 | Upgrading of Cataban Bailey Bridge I to RCDG | ROAD 300-16-06-05887 | Transportation Facilities | BRIDGES | NULL | Bgy. Cataban | Taytay | PEO | 2016 | 20% Development Fund | 6000000 | 5995492.35 | 180 | 2016-09-19 | NULL | 2017-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
260 | Upgrading of Caniqui Bridge I to RCDG | ROAD 300-16-06-05889 | Transportation Facilities | BRIDGES | NULL | Bgy. Caniqui | Taytay | PEO | 2016 | 20% Development Fund | 6000000 | 5995492.35 | 180 | 2016-09-19 | NULL | 2017-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
261 | Upgrading of Inalwayan Bailey Bridge to RCDG | B2 BFIP 300-16-11-15234 | Transportation Facilities | BRIDGES | NULL | Bgy. Liminangcong | Taytay | PEO | 2016 | 20% Development Fund | 6237588.54 | 6228194 | 180 | 2017-03-07 | NULL | 2017-09-03 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
262 | Construction of Barangay Health Station in Bgy. Binudac |  | Medical Facilities | BHS |  | Bgy. Binudac | Culion | PEO | 2016 | 20% Development Fund | 1500000 | 1491336 | 150 | 2017-03-08 |  | 2017-08-05 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
263 | Construction of Barangay Health Station, Tagpait |  | Medical Facilities | BHS |  | Bgy. Tagpait | Aborlan | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
264 | Construction of Barangay Health Station, Madoldolon | Cluster: Construction of BHS (Bgy. Madoldolon - Bgy. Osmeña - Bgy. Balogo, Araceli, Palawan)B2 TF 416 DOH HFEP 17-021/022/024 (N-17-01) - Madoldolon (TF 416 DOH HFEP 17-021) | Medical Facilities | BHS | Dimension: 8.95m x 11.075m - Area: 99.12 sq.m | Bgy. Madoldolon | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1998979.25 | 120 | 2017-08-14 |  | 2017-12-12 |  |  | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
265 | Construction of Barangay Health Station, Osmeña | Cluster: Construction of BHS (Bgy. Madoldolon - Bgy. Osmeña - Bgy. Balogo, Araceli, Palawan)B2 TF 416 DOH HFEP 17-021/022/024 (N-17-01) - Osmeña (TF 416 DOH HFEP 17-022) | Medical Facilities | BHS | Dimension: 8.95m x 11.075m - Area: 99.12 sq.m | Bgy. Osmeña | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
266 | Construction of Barangay Health Station, Balogo | Cluster: Construction of BHS (Bgy. Madoldolon - Bgy. Osmeña - Bgy. Balogo, Araceli, Palawan)B2 TF 416 DOH HFEP 17-021/022/024 (N-17-01) - Balogo (TF 416 DOH HFEP 17-024) | Medical Facilities | BHS | Dimension: 8.95m x 11.075m - Area: 99.12 sq.m | Bgy.Balogo | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1988907.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  |  |  | By contract | Terminated | Lea & Sons Trading & Construction | TIN 134-897-002
267 | Construction of Barangay Health Station, Sto. Niño |  | Medical Facilities | BHS |  | Bgy. Sto. Niño | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1958925.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
268 | Construction of Barangay Health Station, San Jose De Oro | B2 TF 416 DOH HFEP 17-023-025-026-(N-17-02) | Medical Facilities | BHS |  | Bgy.San Jose De Oro | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989081.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  |  |  | By contract | Terminated | Lea & Sons Trading & Construction | TIN 134-897-002
269 | Construction of Barangay Health Station, Taloto | B2 TF 416 DOH HFEP 17-023-025-026 (N-17-02) | Medical Facilities | BHS |  | Bgy. Taloto | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1988979.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  |  |  | By contract | Terminated | Lea & Sons Trading & Construction | TIN 134-897-002
270 | Construction of Barangay Health Station, Panitian, Bgy. Catagumpan |  | Medical Facilities | BHS |  | Sitio Panitian, Bgy. Catagumpan | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 240 | [5 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
271 | Construction of Barangay Health Station, Kambang Tuli, Melville | B2 TF 416-DOH HFEP 17-027-028-029 | Medical Facilities | BHS |  | Kambang Tuli, Bgry. Melville | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  |  |  | By contract | Order of Termination | Rhodamay Construction and Supply | 322-759-45
272 | Construction of Barangay Health Station, Catagupan Centro |  | Medical Facilities | BHS |  | Bgy. Catagupan Centro | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
273 | Construction of Barangay Health Station, Sitio Caguisan Bgy. Salang | B2 TF 416 DOH HFEP 17-030/031/032 (S-17-03) | Medical Facilities | BHS |  | Sitio Caguisan Bgy. Salang | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  |  |  | By contract | Order of Termination | Rhodamay Construction and Supply | 322-759-45
274 | Construction of Barangay Health Station, Maria Hangin | B2 TF 416 DOH HFEP 17-030-031-032 (S-17-03) | Medical Facilities | BHS |  | Bgy. Maria Hangin | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  |  |  | By contract | Order of Termination | Rhodamay Construction and Supply | 322-759-45
275 | Construction of Barangay Health Station, Sebaring |  | Medical Facilities | BHS |  | Bgy. Sebaring | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.65 | 240 | 2017-09-18 |  | 2018-05-16 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
276 | Construction of Barangay Health Station, Puring |  | Medical Facilities | BHS |  | Bgy. Puring | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
277 | Construction of Barangay Health Station, Igang-igang |  | Medical Facilities | BHS |  | Bgy. Igang | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
278 | Construction of Barangay Health Station, Iwahig/Mampyu |  | Medical Facilities | BHS |  | Bgy.Iwahig | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
279 | Construction of Barangay Health Station, Tabud |  | Medical Facilities | BHS |  | Bgy. Tabud | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
280 | Construction of Barangay Health Station, Tagnato |  | Medical Facilities | BHS |  | Bgy. Tagnato | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
281 | Construction of Barangay Health Station, Taratak |  | Medical Facilities | BHS |  | Bgy. Taratak | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
282 | Construction of Barangay Health Station, Tagolango | TF 416-DOH HFEP 17-038-039-040-041- (S-17-015) | Medical Facilities | BHS |  | Bgy. Tagolango | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989328.03 | 300 | 2017-11-13 |  | 2018-09-09 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
283 | Construction of Barangay Health Station, Salogon |  | Medical Facilities | BHS |  | Bgy. Salogon | Brooke's Point | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
284 | Construction of Barangay Health Station, Bgy. Panlaitan | TF 416-DOH HFEP 17-033-034 | Medical Facilities | BHS |  | Bgy. Panlaitan | Busuanga | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989490.72 | 180 | 2017-12-29 |  | 2018-06-27 |  |  |  |  | By contract | Order of Termination | JFR Construction
285 | Construction of Barangay Health Station, Bgy. Quezon |  | Medical Facilities | BHS |  | Bgy. Quezon | Busuanga | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | JFR Construction
286 | Construction of Barangay Health Station, Santa Cruz |  | Medical Facilities | BHS |  | Bgy.Santa Cruz | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 300 | 2017-06-01 |  | 2018-03-28 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
287 | Construction of Barangay Health Station, Nusa | B2 TF 416 DOH HFEP 17-059-060-061-062 (N-17-04) | Medical Facilities | BHS |  | Bgy. Nusa | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 300 | 2017-06-01 |  | 2018-03-28 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
288 | Construction of Barangay Health Station, Talaga | B2 TF 416 DOH HFEP 17-059/060//061/062/(N-17-04) | Medical Facilities | BHS |  | Bgy. Talaga | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 300 | 2017-06-01 |  | 2018-03-28 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
289 | Construction of Barangay Health Station, Wahig |  | Medical Facilities | BHS |  | Bgy. Wahig | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
290 | Construction of Barangay Health Station, Bgy. Turda | B2 TF 416 DOH HFEP 17-057-058 (N-17-05) | Medical Facilities | BHS | Area: 99.12 sq.m | Bgy. Turda | Coron | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2018-02-05 |  | 2018-06-05 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
291 | Construction of Barangay Health Station, Bgy. Tagumpay | B2 TF 416 DOH HFEP 17-057-058 (N-17-05) | Medical Facilities | BHS | Area: 99.12 sq.m | Bgy. Tagumpay | Coron | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2018-02-05 |  | 2018-06-05 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
292 | Construction of Barangay Health Station, Bgy. Halsey | B2 TF 416 DOH HFEP 17-044-045 (N-17-06) | Medical Facilities | BHS |  | Bgy. Halsey | Culion | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-13 |  | 2017-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
293 | Construction of Barangay Health Station, So. Tampil, Bgy. Osmeña | B2 TF 416 DOH HFEP 17-044-045 (N-17-06) | Medical Facilities | BHS |  | So. Tampil, Bgy. Osmeña | Culion | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-13 |  | 2017-12-10 |  |  |  |  | By contract | Notice to Terminate | E.V Villaos Trading and Construction Supply | TIN 134-897-002
294 | Construction of Barangay Health Station, Bgy. Caburian | B2 TF 416-DOH-HFEP 17-015-017 (N-17-07) | Medical Facilities | BHS |  | Bgy. Caburian | Cuyo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1990000 | 180 | 2018-03-05 |  | 2018-09-01 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Unreasonable price increase
295 | Construction of Barangay Health Station, So Malunlon, Bgy. Tanatanaen | TF 416-DOH HFEP 17-046-047 (N-17-08) | Medical Facilities | BHS |  | So Malunlon, Bgy. Tanatanaen | Dumaran | PEO | 2016 | Trust Fund - DOH | 1990000 | 3978738.42 | 180 | 2017-06-13 |  | 2017-12-10 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Insifficient budget
296 | Construction of Barangay Health Station, So. Nagtalula, Bgy. Catep | TF 416-DOH HFEP 17-046-047 (N-17-08) | Medical Facilities | BHS |  | So. Nagtalula, Bgy. Catep | Dumaran | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 180 | 2017-06-13 |  | 2017-12-10 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Insifficient budget
297 | Construction of Barangay Health Station, Manlag | TF 416-DOH HFEP 17-048-049 (N-17-09) | Medical Facilities | BHS |  | Bgy. Manlag, El Nido | El Nido | PEO | 2016 | Trust Fund - DOH | 1990000 | 1978738.42 |  | 2017-06-13 |  | 2017-06-13 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
298 | Construction of Barangay Health Station, Poblacion, Upper Quirino |  | Medical Facilities | BHS |  | Poblacion, Upper Quirino | Narra | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
299 | Construction of Barangay Health Station, Sowangan |  | Medical Facilities | BHS |  | Bgy. Sowangan | Quezon | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
300 | Construction of Barangay Health Station, Cocoro | B2 TF 416 DOH-HFEP 17-015-017 (N-17-07) | Medical Facilities | BHS |  | Bgy. Cocoro | Magsaysay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1990000 | 180 | 2018-03-05 |  | 2018-09-01 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Unreasonable price increase
301 | Construction of Barangay Health Station, Barangonan |  | Medical Facilities | BHS |  | Bgy. Barangonan | Linapacan | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-09 |  | 2017-12-06 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
302 | Construction of Barangay Health Station, Maroyogroyog | B2 TF 416 DOH HFEP 17-042-043 (N-17-10) | Medical Facilities | BHS |  | Bgy. Maroyogroyog | Linapacan | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-09 |  | 2017-12-06 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Design not suitable to actual site condition
303 | Construction of Barangay Health Station, So. Ogis, Ransang |  | Medical Facilities | BHS |  | So. Ogis, Ransang | Rizal | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
304 | Construction of Barangay Health Station, Malotoc, Ransang |  | Medical Facilities | BHS |  | Malotoc, Ransang | Rizal | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
305 | Construction of Barangay Health Station, Green Island |  | Medical Facilities | BHS |  | Bgy. Green Island | Roxas | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
306 | Construction of Barangay Health Station, Caruray |  | Medical Facilities | BHS |  | Bgy. Caruray | San Vicente | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
307 | Construction of Barangay Health Station, Port Barton |  | Medical Facilities | BHS |  | Port Barton | San Vicente | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
308 | Construction of Barangay Health Station, Abo-abo |  | Medical Facilities | BHS |  | Bgy. Abo-abo | Sofronio Española | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
309 | Construction of Barangay Health Station, Bgy. Old Guinlo | B2 TF 416-DOH HFEP 17-050-054-056 (N-17-12) | Medical Facilities | BHS |  | Bgy. Old Guinlo | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 120 | 2018-01-02 |  | 2018-05-02 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
310 | Construction of Barangay Health Station, Baras | B2 TF 416-DOH HFEP 17-050-054-056 (N-17-12) | Medical Facilities | BHS | Building: 8.95m x 11.075m | Bgy. Baras | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 120 | 2018-01-02 |  | 2018-05-02 |  |  |  |  | By contract | Terminated
311 | Construction of Barangay Health Station, Tumbod | B2 TF 416-DOH HFEP 17-050-054-056 (N-17-12) | Medical Facilities | BHS | Building: 8.95m x 11.075m | Bgy. Tumbod | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 120 | 2018-01-02 |  | 2018-05-02 |  |  |  |  | By contract | Terminated
312 | Construction of Barangay Health Station, Biton | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | BHS | Building: 8.95m x 11.075m | Bgy. Biton | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  |  |  | By contract | Issued Notice to Terminate | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Design not suitable to actual site condition
313 | Construction of Barangay Health Station, Libertad | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | BHS | Building: 8.95m x 11.075m | Bgy. Libertad | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  | 100% |  | By contract | Completed
314 | Construction of Barangay Health Station, Meytegued | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | BHS | Building: 8.95m x 11.075m | Bgy. Meytegued | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  |  |  | By contract | Issued Notice to Terminate |  |  | Design not suitable to actual site condition
315 | Construction of Barangay Health Station, Poblacion | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | BHS | Building: 8.95m x 11.075m | Bgy. Poblacion | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  | 100% |  | By contract | Completed
316 | Construction of San Vicente District Hospital | B2 TF 416 DOH HFEP 16-506 | Medical Facilities | MEDICAL FACILITIES | Building: 60.0m x 60.0m single storey | San Vicente District Hospital | San Vicente | PEO | 2016 | Trust Fund - DOH | 49750000 | 49743028.84 | 364 | 2017-05-15 |  | 2018-05-14 |  |  | 100% |  | By contract | Completed | MGB Construction and Trading
317 | Construction of Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2016 | Trust Fund - DOH | 49750000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
318 | Construction of El NidoCommunity Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El NidoCommunity Hospital | El Nido | PEO | 2016 | Trust Fund - DOH | 49750000 | 49743710.84 |  | 2017-05-16 |  | 2017-05-16 |  |  | 100% |  | By contract | Completed | MGB Construction and Trading
319 | Construction of Bgy. Buluang Rescue Center | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Buluang | Busuanga | PEO | 2016 | Trust Fund - DOH | 2487500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | JFR Construction | NULL | NULL
320 | Construction of Bgy. Cheey Rescue Center | NULL | other Infrastructure | OTHER FACILITIES | NULL | Bgy. Cheey | Busuanga | PEO | 2016 | Trust Fund - DOH | 2487500 | 2485845.67 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | JFR Construction | NULL | NULL
321 | Construction of Guadalupe Rescue Center | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Guadalupe | Coron | PEO | 2016 | Trust Fund - DOH | 2487500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | JFR Construction | NULL | NULL
322 | Construction of San Fernando Rescue Center | NULL | Other Infrastructure | OTHER FACILITIES | NULL | El Nido | El Nido | PEO | 2016 | Trust Fund - DOH | 2487500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
323 | Repair of KILN of Provincial Jail | NULL | Other Facilities | PGP FACILITIES | NULL | NULL | Puerto Princesa City | PEO | 2016 | Locally Funded | 75916 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
324 | Expansion of Southern Palawan Technical Vocational School | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | Southern Palawan Technical Vocational School | Aborlan | PEO | 2016 | Locally Funded | 35000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
325 | Construction of Northern Palawan Technical Vocational School (Phase I) | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | Northern Palawan Technical Vocational School | Taytay | PEO | 2016 | Locally Funded | 8254313.19 | 8250949.51 | NULL | 2021-02-05 | NULL | 2021-02-05 | NULL | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
326 | Construction of PNP Crime Laboratory (Provincial Police Office) | NULL | Other Facilities | PGP FACILITIES | NULL | NULL | Puerto Princesa City | PEO | 2016 | Locally Funded | 3363671.8 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | UGM Construction | TIN 102-967-201 | NULL
327 | Extension of 3 Phase line going to Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  |  | Aborlan | PEO | 2016 | Energy Development Program | 473929.12 |  | 121 | 2021-01-14 |  | 2021-05-15 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
328 | Installation of Cables, Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | Energy Development Program | 1865000 | [7 empty] | 100% |  | By contract | Completed
329 | Purchase of 75 KVA Transformer and Accessories for 2 Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | Energy Development Program | 1762368.5 | [7 empty] | 100% |  | By contract | Completed
330 | Concreting of Cataban- Liminangcong Rd. (Intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | NULL | Taytay | PEO | 2017 | 20% Development Fund | 8888869.31 | 8837664.39 | NULL | 2018-10-11 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
331 | Concreting of Circumferential Road Phase II | NULL | Transportation Facilities | ROAD | NULL | NULL | Cagayancillo | PEO | 2017 | 20% Development Fund | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
332 | Concreting of Circumferential Road | NULL | Transportation Facilities | ROAD | NULL | Linapacan | Linapacan | PEO | 2017 | 20% Development Fund | 1500000 | 1488875.51 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
333 | Concreting of Aramaywan Road (Extention), Bgy. Aramaywan | NULL | Transportation Facilities | ROAD | NULL | Bgy. Aramaywan | Narra | PEO | 2017 | 20% Development Fund | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
334 | Construction of 3 Barrel RCBC, So. Nala, Sta Teresita | NULL | Other Infrastructure | DRAINAGE | NULL | So. Nala, Bgy. Sta Teresita | Dumaran | PEO | 2017 | 20% Development Fund | 1900000 | 1843310.04 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
335 | Construction of Alimoto Bridge RC Slope Protection, Sta. Teresita | B2 ROADS 300-17-07-11954 | Other Infrastructure | SLOPE PROTECTION | NULL | Bgy. Sta Teresita | Dumaran | PEO | 2017 | 20% Development Fund | 600000 | 598468.53 | 30 | 2018-01-10 | NULL | 2018-02-09 | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
336 | Construction of Three (3) Barrel Reinforced Concrete Box Culvert with Detour Road (Re-bid) | B2 Roads 300-17-06-08439 | Other Infrastructure | DRAINAGE | NULL | Pamantolon - Pulariquen Road (Tagale Bridge), Taytay, Palawan | Taytay | PEO | 2017 | 20% Development Fund | 2000000 | 1996350.53 | 210 | 2017-10-24 | NULL | 2018-05-22 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
337 | Construction of Barake 4 Barrel RCBC, Bgy. Barake | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Aborlan | PEO | 2017 | 20% Development Fund | 3670000 | 3465963.05 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
338 | Construction of Jose Rizal Spillway (Box Type), Bgy. Jose Rizal | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Jose Rizal | Aborlan | PEO | 2017 | 20% Development Fund | 1344000 | 1308041 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
339 | Construction of Tub-tub 3 Barrel RCBC w/ Slope Protection | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Brooke's Point | PEO | 2017 | 20% Development Fund | 1900000 | 1838690.15 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
340 | Construction of Amas 2 Barrel RCBC w/ Slope Protection | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Brooke's Point | PEO | 2017 | 20% Development Fund | 1300000 | 1195111.75 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
341 | Construction of Calvit Creek 3 Barrel RCBC w/ Slope Protection, Bunog | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Bunog | Rizal | PEO | 2017 | 20% Development Fund | 1900000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
342 | Construction of Kalampinay BB (Lamoro Bridge II) to RCDG (Superstructure), Bgy. Pasadeña | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Pasadeña | El Nido | PEO | 2017 | 20% Development Fund | 8000000 | 7969852.98 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
343 | Upgrading of Sta. Maria Bailey Bridge II to RCDG, Sta. Maria | B2 ROADS 300-17-06-08436 | Transportation Facilities | BRIDGES | NULL | Bgy. Sta. Maria | Dumaran | PEO | 2017 | 20% Development Fund | 8000000 | 7691148.95 | 210 | 2016-09-19 | NULL | 2017-04-17 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
344 | Upgrading of Taradungan Bridge to RCDG, Bgy. Taradungan | B2 ROADS 300-17-06-08446 | Transportation Facilities | BRIDGES | NULL | Bgy. Taradungan | Roxas | PEO | 2017 | 20% Development Fund | 5500000 | 5489999.65 | 210 | 2017-10-13 | NULL | 2018-05-11 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
345 | Upgrading of Iraan Bridge to RCDG, Bgy. Magara | B2 ROADS 300-17-06-08445 | Transportation Facilities | BRIDGES | NULL | Bgy. Magara | Roxas | PEO | 2017 | 20% Development Fund | 8000000 | 7879325.37 | 135 | 2017-11-06 | NULL | 2018-03-21 | NULL | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
346 | Upgrading of Maharlika Bridge I to RCDG, Bgy. Magara | B2 ROADS 300-17-06-08447 | Transportation Facilities | BRIDGES | NULL | Bgy. Magara | Roxas | PEO | 2017 | 20% Development Fund | 5500000 | 5412281.88 | 120 | 2017-11-06 | NULL | 2018-03-06 | NULL | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
347 | Upgrading of Burirao Timber Bridge to RCDG (Superstructure), Bgy. Burirao | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Burirao | Narra | PEO | 2017 | 20% Development Fund | 6000000 | 5969311.36 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
348 | Upgrading of Barak-barakan Bridge to RCDG w/ Slope Protection | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Bataraza | PEO | 2017 | 20% Development Fund | 9600000 | 9595724.71 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
349 | Installation of RCCP and Const. of RCBC, Capayas - Salimbanog - Lamyang Road | B2 ROADS 300-17-08-12582 | Other Infrastructure | DRAINAGE | NULL | Bgy. Capayas | Dumaran | PEO | 2017 | 20% Development Fund | 10000000 | 9729175.83 | 120 | 2018-02-28 | NULL | 2018-06-28 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
350 | Installation of RCCP and Const. of RCBC, Cauban - Banbanan - Minapla Road | B2 ROADS 300-17-12-22014 | Other Infrastructure | DRAINAGE | NULL | Banbanan - Minapla Road | Taytay | PEO | 2017 | 20% Development Fund | 15344253 | 14700000.58 | NULL | 2018-03-21 | NULL | 2018-03-21 | NULL | NULL | 100% | NULL | By contract | Completed | LB Leoncio Trading and Construction | TIN 181-143-624 | NULL
351 | Concreting of Barangay Road Galoc | B2 ROADS 300-17-06-08450 | Transportation Facilities | ROAD | NULL | Bgy. Galoc | Culion | PEO | 2017 | 20% Development Fund | 1550000 | 1549444.93 | 76 | 2018-01-01 | NULL | 2018-03-18 | NULL | NULL | NULL | NULL | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
352 | Concreting of Agutaya Circumferential Road | NULL | Transportation Facilities | ROAD | NULL | Municipality of Agutaya | Agutaya | PEO | 2017 | 20% Development Fund | 2000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | TIN 944-093-894-001 | NULL
353 | Construction of 1 Barrel RCBC, Latungay-Bagumbayan Road | B2 ROADS 300-17-06-08442 | Other Infrastructure | DRAINAGE | NULL | Dumaran | Dumaran | PEO | 2017 | 20% Development Fund | 800000 | 783919.14 | 120 | 2017-09-06 | NULL | 2018-01-04 | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
354 | Concreting of Cataban-Liminangcong Road,(intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | NULL | Taytay | PEO | 2017 | 20% Development Fund | 8888869.31 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
355 | Upagrading of Pag-asa Bridge I to RCDG, So. Pag-asa, Little Caramay | NULL | Transportation Facilities | BRIDGES | NULL | NULL | San Vicente | PEO | 2017 | 20% Development Fund | 7000000 | 6982887.32 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
356 | Cleaning of Solid Rocks & Boulders along Runway of Airstrip | NULL | Ports and Airports | AIRPORTS | NULL | NULL | Cagayancillo | PEO | 2017 | 20% Development Fund | 1800000 | 1798538.91 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
357 | Upgrading of Labog Bridge to RCDG w/ Slope Protection, Bgy. Labog | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Labog | Sofronio Española | PEO | 2017 | 20% Development Fund | 8250000 | 8224810.78 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
358 | Rehabilitation/repair of Multi-Purpose Hall | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | NULL | Narra | PEO | 2017 | 20% Development Fund | 1100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Rhodamay Construction and Supply | 322-759-45 | NULL
359 | Construction of Local Access Road | NULL | Transportation Facilities | ROAD | NULL | Panaga, Rizal, Palawan | Rizal | PEO | 2017 | DILG - BUB/LGSF | 998442.34 | 998442.35 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
360 | Concreting of Balala- Malaking Patag Road | B2 TF 416 DILG CMGP 17-128 | Transportation Facilities | ROAD | NULL | Culion, Palawan | Culion | PEO | 2017 | Kalsada | 169562217 | 169320307.53 | 279 | 2017-10-10 | NULL | 2018-07-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
361 | Concreting of Calasaguen Feeder Road | NULL | Transportation Facilities | ROAD | NULL | NULL | Brooke's Point | PEO | 2017 | Kalsada | 62339864 | 54393934.43 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Keilana Resources and DF Corporation | NULL | NULL
362 | Concreting of Magbabadil-Cabigaan Road | B2 TF 416 DILG CMGP 17-125 | Transportation Facilities | ROAD | NULL | Aborlan, Palawan | Aborlan | PEO | 2017 | Kalsada | 116980113 | 105281882.25 | 250 | 2018-01-31 | NULL | 2018-10-08 | NULL | NULL | 100% | NULL | By contract | Completed | Werr Corporation International | NULL | NULL
363 | Concreting of Sandoval Feeder Road | B2 TF 416 DILG CMGP 17-122 | Transportation Facilities | ROAD | NULL | Narra, Palawan | Narra | PEO | 2017 | Kalsada | 58155240 | 56916633.65 | 125 | 2017-12-19 | NULL | 2018-04-23 | NULL | NULL | 100% | NULL | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547 | NULL
364 | Concreting of Ipilan-Linao Road | NULL | Transportation Facilities | ROAD | NULL | NULL | Brooke's Point | PEO | 2017 | Kalsada | 80757611 | 79131323.98 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547 | NULL
365 | Concreting of Paglaum-Itangil Road | B2 TF 416 DILG CMGP 17-127 | Transportation Facilities | ROAD | NULL | Taytay & Dumaran, Palawan | Taytay | PEO | 2017 | Kalsada | 152478300 | 152323850.62 | 170 | 2017-10-10 | NULL | 2018-03-29 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
366 | Concreting of Tumarbong- Ilian Road (Intermittent Section) | B2 TF 416 DILG CMGP 17-126 | Transportation Facilities | ROAD | NULL | Roxas, Palawan | Roxas | PEO | 2017 | Kalsada | 218855506 | 218593654.41 | 236 | 2017-10-10 | NULL | 2018-06-03 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
367 | Concreting of Lungsod-Igabas-Emilod Road "A" | B2 TF 416 DILG CMGP 17-124 | Transportation Facilities | ROAD | NULL | Cuyo, Palawan | Cuyo | PEO | 2017 | Kalsada | 19731548 | 19704566.23 | 72 | 2017-10-10 | NULL | 2017-12-21 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
368 | Construction of ALS Learning Center | B2 SEF 300-17-10-17290 | Educational Facilities | SCHOOL FACILITIES | Area: 36.00 sq.m | Balabac, Palawan | Balabac | PEO | 2017 | Special Education Fund | 650000 | 649077.52 | 90 | 2018-01-10 | NULL | 2018-04-10 | NULL | NULL | NULL | NULL | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
369 | Construction of ALS Learning Center | B2 SEF 300-17-10-17292 | Educational Facilities | SCHOOL FACILITIES | Area: 36.00 sq.m | Rizal, Palawan | Rizal | PEO | 2017 | Special Education Fund | 650000 | 624851.11 | 90 | 2018-01-10 | NULL | 2018-04-10 | NULL | NULL | NULL | NULL | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
370 | Construction of ALS Learning Center | B2 SEF 300-17-10-19823 | Educational Facilities | SCHOOL FACILITIES | Area: 36.00 sq.m | Taytay, Palawan | Taytay | PEO | 2017 | Special Education Fund | 650000 | 649077.51 | 90 | 2018-03-02 | NULL | 2018-05-31 | NULL | NULL | NULL | NULL | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
371 | Construction of ALS Learning Center | B2 SEF 300-17-10-17291 | Educational Facilities | SCHOOL FACILITIES | Area: 36.00 sq.m | Roxas, Palawan | Roxas | PEO | 2017 | Special Education Fund | 650000 | 649077.52 | 90 | 2018-01-10 | NULL | 2018-04-10 | NULL | NULL | NULL | NULL | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
372 | Equipping of Rural Health Unit |  | Medical Facilities | RHU |  |  | Araceli | PEO | 2017 | BUB/LGSF | 1200000 | [7 empty] | 100% |  | By contract | Completed
373 | Construction of Barangay Health Station with Birthing Facilities | B2 TF 416-DILG BUB 2016 | Medical Facilities | BHS |  | Bgy. Galoc, Culion, Palawan | Culion | PEO | 2017 | BUB/LGSF | 1525000 | 1523784.67 | [8 empty] | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
374 | Equipping of Rural Health Unit |  | Medical Facilities | RHU |  |  | Culion | PEO | 2017 | BUB/LGSF | 1200000 | [9 empty] | By contract | Subject for Reversion
375 | Rehabilitation of Barangay Health Station, Bgy. Poblacion |  | Medical Facilities | BHS |  | Bgy. Poblacion | Araceli | PEO | 2017 | BUB/LGSF | 500000 | 483664.2 |  | 2017-08-15 |  | 2017-08-15 |  |  | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
376 | Expansion of Rural Health Unit |  | Medical Facilities | RHU |  | Linapacan | Linapacan | PEO | 2017 | BUB/LGSF | 800000 | [9 empty] | By contract | Reverted | Reinastar Trading and Construction | TIN 944-093-894-001
377 | Construction of Faculty Rooms | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | NULL | Araceli | PEO | 2017 | BUB/LGSF | 1200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002 | NULL
378 | Construction of School Library | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | NULL | Araceli | PEO | 2017 | BUB/LGSF | 1200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002 | NULL
379 | Construction of School Fence | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | NULL | Araceli | PEO | 2016 | 2017-DILG - BUB/LGSF | 500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For reversion | Lea & Sons Trading & Construction | TIN 134-897-002 | NULL
380 | Flood Control Program | NULL | Other Infrastructure | DRAINAGE | NULL | NULL | Linapacan | PEO | 2017 | DILG - BUB / LGSF | 3500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Reverted | Agency to Agency Agreement | NULL | NULL
381 | Provision of Potable Water System | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | Linapacan | PEO | 2017 | 2016-DILG - BUB / LGSF | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Reverted | Agency to Agency Agreement | NULL | NULL
382 | Constuction of Irrigation Canal | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | NULL | Rizal | PEO | 2017 | 2016-DILG - BUB / LGSF | 925000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | Agency to Agency Agreement | NULL | NULL
383 | Construction of Small Water Impounding Projects | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | Rizal | PEO | 2017 | 2016-DILG - BUB / LGSF | 1000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | Agency to Agency Agreement | NULL | NULL
384 | Establishment of Shallow Tube Well | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | NULL | Rizal | PEO | 2017 | DILG - BUB / LGSF | 625000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | Agency to Agency Agreement | NULL | NULL
385 | Installation of Water Supply to Elementary Schools | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | Rizal | PEO | 2017 | DILG - BUB / LGSF | 825000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | Agency to Agency Agreement | NULL | NULL
386 | Small Diversion Dam | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | NULL | Rizal | PEO | 2017 | DILG - BUB / LGSF | 800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | Agency to Agency Agreement | NULL | NULL
387 | Procurement of Construction Materials for the Construction of Irrigation Canal | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | NULL | Rizal | PEO | 2017 | DILG - BUB / LGSF | 359359.33 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | Subject for Reversion | RAK Trading Construction & Supply | NULL | NULL
388 | Procurement of Construction Materials for the Construction of Irrigation Canal | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | Bgy Poblacion | Araceli | PEO | 2017 | DILG - BUB / LGSF | 3235000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002 | NULL
389 | Concreting of Local Core Road | B2 TF 416 DILG DSWD DBM BUB 17-096 | Transportation Facilities | ROAD | NULL | Brgy. Poblacion, Dumaran , Palawan | Dumaran | PEO | 2017 | DILG - BUB / LGSF | 5000000 | 4995034.9 | 130 | 2017-12-11 | NULL | 2018-04-20 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
390 | Construction of School Library, Dumaran National High School | B2 TF 416 DILG DSWD DBM BUB 17-095 | Educational Facilities | SCHOOL FACILITIES | 1 Unit Kindergarten Classroom | Dumaran National High School | Dumaran | PEO | 2017 | DILG - BUB/LGSF | 1200000 | 1197687.63 | 90 | 2017-10-19 | NULL | 2018-01-17 | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
391 | Construction of 1 unit Kindergarten Classroom at Lamane ES, Quezon North District | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Unit Kindergarten Classroom | Lamane ES, Quezon North District | Quezon | PEO | 2017 | Special Education Fund | 916665 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
392 | Construction of 1 unit Kindergarten Classroom at Tara ES, Camanga Annex, Coron Inland | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Unit Kindergarten Classroom: Area: 63.00 sq.m | Tara ES, Camanga Annex, Coron Inland | Coron | PEO | 2017 | Special Education Fund | 1000000 | 997425.93 | 120 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Validation | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
393 | Construction of 1 Unit of Kindergarten Classroom at Pamantolon ES | B2 SEF 300-17-10-16649 | Educational Facilities | SCHOOL FACILITIES | 1 Unit Kindergarten Classroom | Kindergarten Classroom. ES | Taytay | PEO | 2017 | Special Education Fund | 916665 | 916237.39 | 120 | 2018-01-10 | NULL | 2018-05-10 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
394 | Construction of 1 unit Kindergarten Classroom at Culandanum | B2 SEF 300-17-10-16648 | Educational Facilities | SCHOOL FACILITIES | 1 Unit Kindergarten Classroom | Culandanum Elementary School, Aborlan, Palawan | Aborlan | PEO | 2017 | Special Education Fund | 916665 | NULL | NULL | 2017-11-17 | NULL | 2017-11-17 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
395 | Construction of (3) Classroom of School Building Tara National Highschool | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Tara, Coron, Palawan | Coron | PEO | 2017 | Special Education Fund | 2400000 | NULL | 120 | 2018-03-09 | NULL | 2018-07-07 | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
396 | Construction of 3 Classroom School Building in Camanga Elementary School, Bgy Tara | B2 SEF 300-17-12-22106 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Camanga Elementary School | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2397041.4 | 120 | 2018-03-12 | NULL | 2018-07-10 | NULL | NULL | NULL | NULL | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
397 | Construction of 3 Classroom School Building in Sagrada Elementary School, Bgy Sagdrada | B2 SEF 300-17-12-2109 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy Sagrada | Busuanga | PEO | 2017 | Special Education Fund | 2250000 | NULL | NULL | 2018-03-12 | NULL | 2018-03-12 | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
398 | Construction of 3 Classroom School Building in Calauit Elementary School, Bgy Calauit | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy Calauit | Busuanga | PEO | 2017 | Special Education Fund | 2250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
399 | Construction of 3 Classroom School Building in San Nicolas National High School, Bgy. San Nicolas | B2 SEF 300-17-12-22107 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | San Nicolas National High School, Bgy. San Nicolas | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2244986.66 | 120 | 2018-03-12 | NULL | 2018-07-10 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
400 | Construction of 3 Classroom School Building in Capayas Elementary School, Bgy. VI | B2 SEF 300-17-12-22105 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy. VI, Coron, Palawan | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2245060.42 | 120 | 2018-03-12 | NULL | 2018-07-10 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
401 | Construction of 4 Classroom School Building in Carlos M. Virrey National High School, Bgy. Saraza | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | Bgy. Saraza | Brooke's Point | PEO | 2017 | Special Education Fund | 3000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
402 | Construction of 2 Classroom School Building in Balen-balen Elementary School, Bgy. Ransang | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Bgy. Ransang | Rizal | PEO | 2017 | Special Education Fund | 1480721 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
403 | Construction of 4 CL Sch. Bldg. at Aramaywan ES, Bgy. Aramaywan | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | Bgy. Aramaywan | Quezon | PEO | 2017 | Special Education Fund | 3000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
404 | Construction of 4 CL Sch. Bldg. at Marcelo Batuy NHS, Bgy. San Juan | NULL | Educational Facilities | SCHOOL FACILITIES | 4 Classroom School Building | Bgy. San Juan | Aborlan | PEO | 2017 | Special Education Fund | 3000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
405 | Construction of Multi-Purpose Building Type II, Sitio Ogis, Rizal, Palawan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Ogis | Rizal | PEO | 2017 | NULL | 950000 | 948416.55 | NULL | 2017-10-06 | NULL | 2017-10-06 | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
406 | Upgrading of Villa Constancia Bailey Bridge to RCDG | ROAD 300-16-06-05893 | Transportation Facilities | BRIDGES | NULL | Villa Constancia | Dumaran | PEO | 2017 | NULL | 7320000 | 7306468.95 | 210 | 2017-03-07 | NULL | 2017-10-03 | NULL | NULL | 100% | NULL | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | NULL
407 | Construction of Road Network inside Quezon Medicare Hospital Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 5389000 | 5359489.63 | 120 | 2019-06-28 |  | 2019-10-26 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
408 | Const. of Bahay Tuluyan in Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | 20% Development Fund | 1800000 | [7 empty] | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
409 | Supply and Installation of 75 KVA Transformer and accessories in Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 1215433.49 | [7 empty] | 100% |  | By contract | Completed
410 | Const. of Multi Purpose Building in Narra, Palawan | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Narra Sports Complex | Narra | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3350000 | 3334388.82 | NULL | 2019-05-30 | NULL | 2019-05-30 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
411 | Upgrading of Tagumpay Bailey Bridge I to RCDG So. Tagumpay, Sta. Maria Dumaran | B2 SB6 PEO18 300-19-03-01980 | Transportation Facilities | BRIDGES | NULL | Bgy. Sta. Maria | Dumaran | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 6620000 | 6280557.81 | 200 | 2019-06-28 | NULL | 2020-01-14 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
412 | Upgrading of Tagumpay Bailey Bridge II to RCDG So. Tagumpay, Sta. Maria Dumaran | B2 SB6 PEO18 300-19-03-01529 | Transportation Facilities | BRIDGES | NULL | Bgy. Sta. Maria | Dumaran | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 5300000 | 4982200.66 | 140 | 2019-06-25 | NULL | 2019-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
413 | Construction of Distribution System, Paly, Taytay | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Paly | Taytay | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 2984566.51 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
414 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 1900000 | 1853317.92 |  | 2019-10-08 |  | 2019-10-08 |  |  | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
415 | Construction. of Material Recovery Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 900000 | [7 empty] | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
416 | Construction of Mortuary Building |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 950000 | [7 empty] | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
417 | Construction of Elevated Water Tank 300 CU.M Deepwell and Water Treatment Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 6592920 | 6631000 | [6 empty] | 100% |  | By contract | Completed | Hardrock Platinum Development Corporation | TIN 008-625-254
418 | Construction of Dietary/Linen Building |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3283679.49 | 3283265.52 | 230 | 2019-04-21 |  | 2019-12-07 |  |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
419 | Construction of Isolation Building |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3455339.91 | 3454681.86 |  | 2019-04-21 |  | 2019-04-21 |  |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
420 | Construction of Sewage Treatment Plant (Phase I) Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3600000 | 3491607.31 |  | 2019-09-09 |  | 2019-09-09 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
421 | Construction of Airstrip Perimeter Fence | NULL | Ports and Airports | AIRPORTS | NULL | NULL | Rizal | PEO | 2018 | Locally Funded | 6996542.93 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
422 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 6613021.87 | 6279648.16 |  | 2018-08-15 |  | 2018-08-15 |  | 2020-11-03 | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
423 | Construction of Bahay Tuluyan in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 1800000 | 1794564.82 | 60 | 2021-08-24 |  | 2021-10-23 |  |  | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
424 | Construction of Three (3) - Storey Medical & Ward Building with Roof Deck for Helipad - Phase I in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 16943558 | 16935788.61 | [6 empty] | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
425 | Construction of Perimeter Fence Phase 2 in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 1055000 | [7 empty] | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
426 | Construction of Doctor's Quarter in Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 5389000 | 5386970.89 |  | 2018-08-10 |  | 2018-08-10 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
427 | Construction of Motorpool/Powerhouse in Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 1700000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
428 | Construction of Mortuary Building in Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 810000 | 768396.54 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
429 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 6613021 | 6398568.58 | 90 | 2018-09-26 |  | 2018-12-25 | 2019-07-02 |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
430 | Supply & Installation of 3 Transformers/Accessories/Panel Board/ Main Cable in Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 2566217 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
431 | Construction of Isolation Building in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 2900000 | 2837760.6 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
432 | Construction of Material Recovery Facilities Building in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 650000 | 646401.78 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
433 | Construction of Motorpool/Powerhouse in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 1700000 | 1667428.99 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
434 | Concreting of Road inside Hospital Facilities in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES | (a) PCCP: 497m (4m and 5m width) (b) Veh gate: 6m (w) x 2m (h) x 2 sets (C) Ped gate: 1.8(w) x 2m (h) (d) 6" PVC: 60 ln.m | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 3500000 | 3496381.73 | 60 | [5 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
435 | Construction of Perimeter Fence Phase 2 in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 2713000 | 2710750.96 | [8 empty] | By contract | Terminated | Maryknoll Builders and Supply | TIN 105-802-318
436 | Supply & Installation of 3 Transformers/Accessories/Panel Board/ Main Cable in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Dr Jose Rizal Hospital | Rizal | PEO | 2018 | 20% Development Fund | 2101217 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
437 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Dr Jose Rizal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 6613021 | 6263177.93 |  | 2018-11-16 |  | 2018-11-16 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
438 | Construction of Powerhouse Building in Roxas District Hospital | B2 PEO 300-18-05-07645 | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2018 | 20% Development Fund | 1700000 | 1693565.82 | 90 | 2018-08-09 |  | 2018-11-07 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
439 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Roxas District Hospital | B2 PEO 300-18-05-07644 | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2018 | 20% Development Fund |  | 6398568.58 | 90 | 2018-09-25 |  | 2018-12-24 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
440 | Purchase of 3 Transformer/Accessories/Panel Board/ Main Cable in Roxas District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas District Hospital | Roxas | PEO | 2018 | 20% Development Fund | 2566217 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
441 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Banbanan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Banbanan | Taytay | PEO | 2018 | Philippines Veterans Bank Loan | 3052155.48 | 3052127.77 | 150 | 2018-10-03 | NULL | 2019-03-02 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
442 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bato | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bato | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2018-10-03 | NULL | 2019-03-02 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
443 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Beton (Island) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Beton (Island) | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
444 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Busy Bees | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Busy Bees | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3760391.23 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
445 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calawag | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Calawag | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3241540.44 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
446 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Cataban | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Cataban | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3241540.43 | NULL | 2020-10-16 | NULL | 2020-10-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
447 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Depla (Island) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Depla (Island) | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3502266.88 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
448 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Liminangcong (Roofing Only) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Liminangcong | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 1997639.38 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | For Termination | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
449 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Guinlo | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. New Guinlo | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
450 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Old Guinlo | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Old Guinlo | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
451 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pamantolon | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Pamantolon | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
452 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pancol | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Pancol | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | NULL | 2019-11-12 | NULL | 2019-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
453 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Paly Island | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Paly Island | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
454 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pularaquen(Canique) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Pularaquen(Canique) | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
455 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sandoval | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Sandoval | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3760391.23 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
456 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Silanga | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Silanga | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
457 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Libertad | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Libertad | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
458 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Minapla | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Minapla | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
459 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Talog | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Talog | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
460 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Maroyogroyog | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Maroyogroyog | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
461 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Culaylayan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. New Culaylayan | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
462 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Nicolas | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Nicolas | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
463 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calibangbangan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Calibangbangan | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5028459.53 | 150 | 2019-12-26 | NULL | 2020-05-24 | NULL | NULL | NULL | NULL | By contract | For Termination | Kudz Trading and Construction | TIN 188-527-256 | NULL
464 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Decabaitot | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Decabaitot | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5028459.53 | 150 | 2019-12-26 | NULL | 2020-05-24 | NULL | NULL | NULL | NULL | By contract | For Termination | Kudz Trading and Construction | TIN 188-527-256 | NULL
465 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sta. Cruz | B2 SB1 PEO 300-19-03-02426 | Other Infrastructure | COVERED COURT | NULL | Bgy. Sta. Cruz | Cagayancillo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5173349.53 | 150 | 2019-07-30 | NULL | 2019-12-27 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
466 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lipot South (Pob.) | B2 SB1 PEO 300-19-03-02428 | Other Infrastructure | COVERED COURT | NULL | Bgy. Lipot South (Pob.) | Cagayancillo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5173349.53 | 150 | 2019-07-30 | NULL | 2019-12-27 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
467 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Talaga | B2 SB1 PEO 300-19-03-02427 | Other Infrastructure | COVERED COURT | NULL | Bgy. Talaga | Cagayancillo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5173349.53 | 150 | 2019-07-30 | NULL | 2019-12-27 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
468 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Dumarao | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Dumarao | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
469 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Antonino | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Antonino | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3052486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
470 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bagong Bayan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Bagong Bayan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053507.61 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
471 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Caramay | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Caramay | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
472 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Iraan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Iraan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
473 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Jolo | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Jolo | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
474 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malcampo | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Malcampo | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
475 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Barbacan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. New Barbacan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
476 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Cuyo | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. New Cuyo | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
477 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Barangay I (Poblacion) | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Barangay I (Poblacion) | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
478 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Rizal | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Rizal | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
479 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Salvacion | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Salvacion | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
480 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Isidro | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. San Isidro | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
481 | Construction of Covered Court/ Evacuation Center Phase 2 Bgy. San Jose | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. San Jose | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
482 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Miguel | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. San Miguel | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3054898.58 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
483 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Nicholas | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. San Nicholas | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
484 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sandoval, Roxas | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Sandoval, Roxas | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
485 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tagumpay | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Tagumpay | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3054898.58 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
486 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Taradungan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Taradungan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
487 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tinitian | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Tinitian | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
488 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Nicanor Zabala | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Nicanor Zabala | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3054898.58 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
489 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Mendoza | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Mendoza | Roxas | PEO | 2018 | NA | 3053507.61 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
490 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Minara | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. Minara | Roxas | PEO | 2018 | NA | 3053507.61 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
491 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. III (Poblacion) | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure | COVERED COURT | NULL | Bgy. III (Poblacion) | Roxas | PEO | 2018 | NA | 3053507.61 | 3053486.67 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
492 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Iraray | B2 PEO Covered Court/evacuation Center Phase I Package 2 | Other Infrastructure | COVERED COURT | NULL | Bgy. Iraray | Sofronio Española | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3684653.76 | 3682930.15 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
493 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Labog | B2 PEO Covered Court/evacuation Center Phase I Package 2 | Other Infrastructure | COVERED COURT | NULL | Bgy. Labog | Sofronio Española | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.55 | 2974211.29 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
494 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Panitian | B2 PEO Covered Court/evacuation Center Phase I Package 2 | Other Infrastructure | COVERED COURT | NULL | Bgy. Panitian | Sofronio Española | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2974211.29 | 2974211.29 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
495 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Balogo | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Balogo | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4220052.28 | 4219451.21 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
496 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Dagman | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Dagman | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Termination
497 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Dalayawon | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Dalayawon | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3576544.12 | 3572790.65 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Termination
498 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lumacad | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Lumacad | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3393834.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
499 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Madoldolon (Expand 14.4x27.20) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Madoldolon | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
500 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Mauringuen (15.8x29.20) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Mauringuen | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
501 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Osmeña (Expand 15.15x31) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Osmeña | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | NULL | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | 2022-11-13 | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
502 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Jose De Oro | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Jose De Oro | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
503 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Santo Niño | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Santo Niño | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
504 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Taloto | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Taloto | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
505 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tudela (Calandagan) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tudela (Calandagan) | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
506 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bacao | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bacao | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4220052.28 | 4219451.21 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
507 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calasag | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Calasag | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4220052.28 | 4219451.21 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | 2022-11-13 | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
508 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Capayas | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Capayas | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756944.8 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
509 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Catep | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Catep | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3498581.69 | 3498086.07 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
510 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Culasian | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Culasian | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3048664.58 | 3048972.25 | NULL | 2019-11-12 | NULL | 2019-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
511 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Danleg | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Danleg | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3048664.58 | 3048972.24 | NULL | 2019-11-12 | NULL | 2019-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
512 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Ilian | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Ilian | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756943.58 | NULL | 2020-01-19 | NULL | 2020-01-19 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
513 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Juan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Juan | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3498581.69 | 3498086.07 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
514 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Santo Thomas | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Santo Thomas | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3498581.69 | 3498086.07 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
515 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tanatanaen | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tanatanaen | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756943.58 | NULL | 2019-05-03 | NULL | 2019-05-03 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
516 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tanatanaen | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Santa Maria | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756943.58 | NULL | 2019-05-03 | NULL | 2019-05-03 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
517 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Magsaysay | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Magsaysay | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2019 | 3756697.97 | 3756944.8 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
518 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Banuang Daan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Banuang Daan | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
519 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bintuan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bintuan | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
520 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Borac | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Borac | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
521 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Buenavista | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Buenavista | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
522 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bulalacao | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bulalacao | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
523 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Decabobo | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Decabobo | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
524 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Decalachao | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Decalachao | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
525 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Guadalupe | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Guadalupe | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
526 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malawig | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Malawig | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | 2022-07-07 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
527 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Marcilla | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Marcilla | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | 2022-07-16 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
528 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. I (Poblacion) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. I (Poblacion) | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
529 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. IV (Poblacion) | B2 PEO Covered Court/Evacuation Center Phase I-Package 4 | Other Infrastructure | COVERED COURT | Court: 30(m) L x 118m (W) | Bgy. IV (Poblacion) | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654 | NULL
530 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. V (Poblacion), Coron | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. V (Poblacion), Coron | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | Subject for LD | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
531 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Jose | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Jose | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 130 | 2020-06-01 | NULL | 2020-10-09 | 2022-07-14 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
532 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Nicholas, Coron | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Nicholas, Coron | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
533 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tagumpay, Coron | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tagumpay, Coron | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | 2022-08-31 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
534 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tara | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tara | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-03-09 | NULL | 2019-08-06 | 2019-09-21 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
535 | Construction of 4CL School Building in Tagpait Elementary School | NULL | Other Infrastructure | OTHER FACILITIES | 4 Classroom School Building | NULL | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
536 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Barangay VI (Poblacion) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Barangay VI (Poblacion) | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 | NULL | 2019-03-08 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
537 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bogtong | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bogtong | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
538 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Buluang | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Buluang | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
539 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Cheey | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Cheey | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
540 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Concepcion | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Concepcion | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | 2022-07-23 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
541 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Maglalambay (Island) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Maglalambay (Island) | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | Subject for LD | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
542 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Busuanga (Poblacion) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. New Busuanga (Poblacion) | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | 2022-08-03 | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
543 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Old Busuanga | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Old Busuanga | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
544 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Panlaitan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Panlaitan | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | NULL | NULL | By contract | Cancelled | BCT Trading and Construction | TIN 102-698-654 | NULL
545 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Quezon | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Quezon | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654 | NULL
546 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sagrada | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Sagrada | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | 2022-07-24 | NULL | NULL | NULL | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654 | NULL
547 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Isidro,Busuanga | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Isidro,Busuanga | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | 2022-08-26 | NULL | NULL | NULL | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654 | NULL
548 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Rafael | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Rafael | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
549 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Santo Niño, Busuanga | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Santo Niño, Busuanga | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223995.52 | 3400068.54 | 150 | 2019-10-09 | NULL | 2020-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
550 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Balading | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Brgy. Balading, Cuyo, Palawan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
551 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bangcal (Poblacion) | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Bangcal (Poblacion), Cuyo, Palawan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
552 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Cagigsing (Poblacion) | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Cagigsing (Poblacion) | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
553 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Caburian | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Caburian | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 | NULL | 2019-06-16 | Subject for LD | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
554 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Caponayan | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Caponayan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Project price escalation
555 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Catadman (Poblacion) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Catadman | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | Subject for LD | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
556 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lagaoriao (Poblacion) | B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Lagaoriao | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Not moving
557 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lubid | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Lubid | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Not yet started
558 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lungsod (Poblacion) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Lungsod (Poblacion) | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
559 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pawa | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Pawa | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
560 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Carlos | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Carlos | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | 2023-05-01 | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
561 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tocadan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tocadan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
562 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Alcoba | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Alcoba | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
563 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Balaguen | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Balaguen | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
564 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Canipo | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure | COVERED COURT | NULL | Bgy. Canipo | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Not moving
565 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Danawan (Poblacion) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Danawan (Poblacion) | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
566 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Emilod | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Emilod | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
567 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Igabas | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Igabas | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
568 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lacaren | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Lacaren | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
569 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Los Angeles | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Los Angeles | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
570 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lucbuan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Lucbuan | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
571 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Rizal, Magsaysay | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Rizal, Magsaysay | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
572 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bagong Bayan, Magsaysay | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bagong Bayan, Magsaysay | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
573 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Buena Suerte Poblacion | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Buena Suerte Poblacion | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | NULL | NULL | By contract | Cancelled | BCT Trading and Construction | TIN 102-698-654 | NULL
574 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Barotuan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Barotuan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | NULL | 2020-06-01 | NULL | 2020-06-01 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
575 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bebeladan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bebeladan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
576 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Corong-corong Poblacion | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Corong-corong Poblacion | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
577 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Mabini | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Mabini | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
578 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Manlag | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Manlag | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
579 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Masagana Poblacion | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Masagana Poblacion | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
580 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Ibajay | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. New Ibajay | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3760806.92 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
581 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sibaltan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Sibaltan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3760806.92 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
582 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Fernando | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Fernando | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
583 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Villa Paz | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Villa Paz | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
584 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Teneguiban | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Teneguiban | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 | NULL | 2018-10-10 | NULL | 2018-10-10 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
585 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bucana | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Bucana | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 | NULL | 2018-10-10 | NULL | 2018-10-10 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
586 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Aberawan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Aberawan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | NULL | 2018-10-10 | NULL | 2018-10-10 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
587 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Gogognan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Gogognan | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3682655.34 | 3683332.62 | 150 | 2019-08-06 | NULL | 2020-01-03 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
588 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Iraan, Aborlan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Iraan, Aborlan | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3682655.34 | 3683332.62 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
589 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Magbabadil | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Magbabadil | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3683332.62 | 3683332.62 | 150 | 2018-10-19 | NULL | 2019-03-18 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
590 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Juan (pavement only) | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. San Juan | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 651557.84 | 650251.85 | NULL | 2018-10-19 | NULL | 2018-10-19 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
591 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Binudac | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Binudac | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
592 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Galoc | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Galoc | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
593 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Luac | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Luac | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
594 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malaking Patag | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Malaking Patag | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
595 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Burabod | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Burabod | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
596 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Halsey | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Halsey | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | 2022-03-20 | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
597 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Baldat | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure | COVERED COURT | NULL | Bgy. Baldat | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
598 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Aramaywan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Aramaywan | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2973942.37 | 2972186.71 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
599 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calumpang | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Calumpang | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.37 | 2973942.37 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
600 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Isugod | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Isugod | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3684653.76 | 3681975.76 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
601 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Quinlogan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Quinlogan | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.37 | 2973942.37 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
602 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Maasin | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Maasin | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
603 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sowangan | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Sowangan | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.37 | 2973942.37 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
604 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tabon | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tabon | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
605 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calatagbak | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Calatagbak | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
606 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malatgao | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Malatgao | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
607 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tagusao | Covered Courts | Other Infrastructure | COVERED COURT | NULL | Bgy. Tagusao | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 | NULL | 2019-12-14 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
608 | Construction and Repair of Covered Court Evacuation Center Phase 1 | NULL | Other Infrastructure | COVERED COURT | NULL | Bgy. Bancal | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 | NULL | 2019-06-16 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
609 | Repair and Upgrading of Mangsee Village Electrification Project | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Mangsee | Balabac | PEO | 2018 | Trust Fund - (OCD FUNDS) | 3960878.13 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
610 | Construction of One School Building Melville Elementary School | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Classroom School Building | Bgy. Melville | Balabac | PEO | 2018 | Trust Fund - (OCD FUNDS) | 1372825.3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
611 | Construction of One School Building Melville National High School | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Classroom School Building | Bgy. Melville | Balabac | PEO | 2018 | Trust Fund - (OCD FUNDS) | 1372826.3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
612 | Construction of Balabac District Hospital Building Phase I |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2018 | DOH-Trust Fund | 7900000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
613 | Construction of Dietary /Linen Building (NPPH) |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2018 | DOH-Trust Fund | 1776000 | 1760796.53 | 160 | 2019-01-07 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ian and Jayson Construction | TIN 182-291-537
614 | Construction of Doctors/Nurses Quarter | B2 TF DUE TO NGAS 18-129 | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2018 | DOH-Trust Fund | 5550000 | 5381624.42 | 160 | 2019-01-07 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ian and Jayson Construction | TIN 182-291-537
615 | Construction of Three (3) Storey Medical Ward Building with Roof Deck for Helipad Phase 2 |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | DOH-Trust Fund | 8058600 | 8056808.23 |  | 2019-12-13 |  | 2019-12-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
616 | Construction of Mini-Port Phase I | B2 TF DUE TO NGAS 18-174 | Ports and Airports | PORTS | NULL | Bgry. Mangsee, Balabac, Palawan | Balabac | PEO | 2018 | Trust Fund - DOTr | NULL | 9844495.6 | 240 | 2019-03-15 | NULL | 2019-11-10 | NULL | NULL | NULL | NULL | By contract | Terminated | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
617 | Construction of Sheltered Port Phase I Bgy. Pag-asa, Municipality of Kalayaan, Palawan | B2 TF DOTR BGY. PAG-ASA SHELTERED PORT DEVELOPMENT PROJECT 18-042 | Ports and Airports | PORTS | NULL | Bgy. Pag-asa, Municipality of Kalayaan, Palawan | Kalayaan | PEO | 2018 | Trust Fund - DOTr | 450000000 | 416709467.72 | 510 | 2018-06-24 | NULL | 2019-11-16 | NULL | NULL | 100% | NULL | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
618 | Construction of 3 Classroom School Building in Ipilan National High School, Bgy Ipilan | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy Ipilan | Brooke's Point | PEO | 2018 | Special Education Fund | 2250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
619 | Construction of 2 Classroom School Building in Mendoza Elemenatry School, Bgy. Mendoza | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Bgy. Mendoza | Roxas | PEO | 2018 | Special Education Fund | 1500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
620 | Construction of 2 Classroom School Building at Narra ES, Bgy. Minara | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Bgy. Minara | Roxas | PEO | 2018 | Special Education Fund | 1500000 | 1493726.07 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
621 | Construction of 2 Classroom School Building in Burrirao National High School, Bgy. Burirao | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Bgy. Burirao | Narra | PEO | 2018 | Special Education Fund | 1500000 | 1492714.09 | 70 | 2018-09-26 | NULL | 2018-12-05 | 2018-12-26 | NULL | 100% | NULL | By contract | Completed | Nale Construction | NULL | NULL
622 | Construction of 2 Classroom School Building in Tobo Elementary School, Bgy Punta Baja | NULL | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | NULL | Rizal | PEO | 2018 | Special Education Fund | 1500000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
623 | Construction of 3 classroom School Building in Balingasag Elem. School, Bgy. Culasian | NULL | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy. Culasian | Taytay | PEO | 2018 | Special Education Fund | 2250000 | 2245934.03 | NULL | 2018-09-12 | NULL | 2018-09-12 | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
624 | Construction 3-Classroom School Building, Bantulan Elementary School | B2 SEF 300-18-02-01124 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bantulan Elementary School | Taytay | PEO | 2018 | Special Education Fund | 2250000 | 2248739.33 | 100 | 2018-08-23 | NULL | 2018-12-01 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
625 | Construction 2-Classroom School Building Amoguez Elementary School | B2 SEF 300-18-02-01122 | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building | Amoguez Elementary School | Taytay | PEO | 2018 | Special Education Fund | 1500000 | 1496106.73 | 70 | 2018-08-23 | NULL | 2018-11-01 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
626 | Concreting of Cataban-Liminangcong Road | B2 TF CMGP 2018 18-11 | Transportation Facilities | ROAD | NULL | Municipality of Taytay, Palawan | Taytay | PEO | 2018 | Kalsada | 77853114 | 77745024.91 | 334 | 2018-10-10 | NULL | 2019-09-09 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
627 | Concreting of Highway Junction Tumarbong Road | B2 TF CMGP 2018 18-075 | Transportation Facilities | ROAD | NULL | Roxas, Palawan | Roxas | PEO | 2018 | Kalsada | 31151057 | 29923726.45 | 189 | 2018-08-14 | NULL | 2019-02-19 | NULL | NULL | 100% | NULL | By contract | Completed | Seven Digit Construction and Supplies | TIN 183-661-696 | NULL
628 | Concreting of Latungay-Sta Teresita Road, Ph 2 | NULL | Transportation Facilities | ROAD | NULL | NULL | Dumaran | PEO | 2018 | Kalsada | 40134637 | 38889231.12 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Seven Digit Construction and Supplies | TIN 183-661-696 | NULL
629 | Concreting of Araceli Road A Ph 2 | NULL | Transportation Facilities | ROAD | NULL | Araceli | Araceli | PEO | 2018 | Kalsada | 40882842 | 40065185.03 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Premium Megastructures Inc. | NULL | NULL
630 | Concreting of Lungsod-Igabas-Emilod Road (A) Ph 2 | B2 TF CMGP 2018 18-074 | Transportation Facilities | ROAD | NULL | Bgy. Lungsod Igabas, Cuyo, Palawan | Cuyo | PEO | 2018 | Kalsada | 15034559 | 14733866.49 | 92 | 2018-10-09 | NULL | 2019-01-09 | 2019-12-31 | NULL | 100% | NULL | By contract | Completed | Octagon Concrete Solution | TIN 901-128-486 | NULL
631 | Concreting of Lungsod-Balaguen Road B | NULL | Transportation Facilities | ROAD | NULL | Bgy. Lungsod Igabas, Cuyo, Palawan | Magsaysay | PEO | 2018 | Kalsada | 15317722 | 15011366.36 | 113 | 2018-10-09 | NULL | 2019-01-30 | NULL | NULL | 100% | NULL | By contract | Completed | Octagon Concrete Solution | TIN 901-128-486 | NULL
632 | Concreting of Magbabadil-Barake Road | NULL | Transportation Facilities | ROAD | NULL | NULL | Aborlan | PEO | 2018 | Kalsada | 25171607 | 25004567.72 | 130 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Werr Corporation International | NULL | NULL
633 | Concreting of Taritien Road | B2 TF CMGP 2018 18-078 | Transportation Facilities | ROAD | NULL | Narra | Narra | PEO | 2018 | Kalsada | 24798543 | 20732610.22 | 170 | 2018-09-24 | NULL | 2019-03-13 | NULL | NULL | 100% | NULL | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547 | NULL
634 | Elnido Water System Project Phase 1 | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | El Nido | PEO | 2018 | NULL | 46294665.62 | 46294665.62 | NULL | 2018-02-19 | NULL | 2018-02-19 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
635 | Concreting of Cataban-Liminangcong Road (Intermittent Section) | NULL | Transportation Facilities | ROAD | NULL | NULL | Taytay | PEO | 2018 | NULL | 8900000 | 8840406.05 | NULL | 2018-10-10 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
636 | Construction of IP Village, Bunog | NULL | Other Facilities | OTHER FACILITIES | NULL | Bgy. Bunog, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 2998634.31 | 2998634.31 | 180 | 2020-01-31 | NULL | 2020-07-29 | NULL | NULL | 100% | NULL | By contract | Completed | RAK Trading Construction & Supply | NULL | NULL
637 | Construction of Mortuary Building in Dr. Rizal District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1135000 | 1129873.53 | 60 | 2019-12-16 |  | 2020-02-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
638 | Construction of Distribution System of Bancalaan 1 Village Electrifiction Project | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Bancalaan I | Balabac | PEO | 2019 | 20% Development Fund | 12613597.66 | 11041248.36 | NULL | 2020-01-23 | NULL | 2020-01-23 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
639 | Installation of Communication System/Security Monitoring Devices (PBX, INTERCOM, CCTV) |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1090000 | [7 empty] | 100% |  | By contract | Completed | Western Fortune
640 | Construction of Sewage Treatment Plant in Dr. Jose Rizal District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 3200000 | 3124809.97 | 60 | 2019-07-30 |  | 2019-09-28 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
641 | Construction of Sewage Treatment Plant | B2 SB1 PEO 300-19-03-02430 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3200000 | 3194884.2 | 60 | 2019-08-19 |  | 2019-10-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
642 | Construction of Dietary/Linen Building | B2 SB1 PEO 300-19-03-02442 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3416000 | 3395201.94 | 90 | 2019-06-28 |  | 2019-09-26 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
643 | Construction of Isolation Building | B2 SB1 PEO 300-19-03-02441 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3740000 | 3719074.68 | 120 | 2019-06-28 |  | 2019-10-26 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
644 | Construction of Motorpool/Powerhouse Building | B2 SB1 PEO 300-19-03-02505 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 2029000 | 2007506.45 | 150 | 2019-06-28 |  | 2019-11-25 | Subject for LD |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
645 | Construction of Material Recovery Facilities | B2 SB1 PEO 300-10-03-02440 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 1073000 | 1054041.98 | 30 | 2019-06-28 |  | 2019-07-28 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
646 | Construction of Perimeter Fence Phase 1 | B2 SB1 PEO 300-19--06-08777 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3500000 | 3498790.87 | 120 | 2019-08-15 |  | 2019-12-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
647 | Construction of Doctors/Nurses Quarter, Coron District Hospital | B2 SB1 PEO 300-119-03-02419 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 5555000 | 5553227.08 | 150 | 2019-08-15 |  | 2020-01-12 |  |  |  |  | By contract | Order of Termination | Johnstar Trading and Construction Supply | TIN 912-843-647 | Inacceible site
648 | Rehabilitation/Improvement of Facilities at Coron District Hospital | B2 TF 416 DPWH DOH HFEP 17-154 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2017 | Trust Fund | 4000000 | 3999494.93 | 180 | 2017-10-27 |  | 2018-04-25 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
649 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities | B2 SB1 PEO 300-19-06-13183 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 7300000 | 7276730 | 90 | 2019-10-21 |  | 2020-01-19 |  |  |  |  | By contract | For Termination | Hardrock Platinum Development Corporation | TIN 008-625-254
650 | Construction of Mortuary Building | B2 SB1 PEO 300-19-03-02439 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 1135000 | 1113507.62 | 60 | 2019-06-28 |  | 2019-08-27 | Subject for LD |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
651 | Improvement of Hospital Landscaping and Fcilities | B2 SB1 PEO19-300-20-08-09854 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 2790554.75 | 2781729.24 | 120 | 2020-10-07 |  | 2021-02-04 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
652 | Supply and Installation of Airconditioning Unit |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 3980442 | [7 empty] | 100% |  | By contract | Completed | Nand Trading
653 | Construction of Doctors/Nurses' Quarter, Araceli/Dumaran District Hospital | B2 SB1 PEO 300-19-03-024 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2019 | 20% Development Fund | 5800000 | 5553227.08 | 150 | 2019-10-15 |  | 2020-03-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
654 | Concreting of San Vicente District Hospital Road Network and Access Road |  | Medical Facilities | MEDICAL FACILITIES | (a) PCCP (Road Network)=97.35m(l) x 5m(w) x 0.20m(l) - 356m(l) x 4m(w) x 0.20m(t) (b) PCCP (Access Road)=0.560 km x 5m(w) x 0.20m (t) - 1m shoulder both side - STA. 0+000 to STA. 0+560 | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 10500000 | 9540335.41 | 120 | 2019-10-22 |  | 2020-02-19 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
655 | Construction of Sewage Treatment Plant, San Vicente District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 3200000 | 3068141.82 |  | 2019-07-31 |  | 2019-07-31 |  |  | 100% |  | By contract | Completed | IKM Builders & Construction Supply
656 | Construction of Bahay Tuluyan |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1800000 | 1797986.31 | 90 | 2019-08-15 |  | 2019-11-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
657 | Distribution System of Concepcion Village Elctrification Project | B2 SB4 PEO 300-19-11-21287 | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Concepcion | Agutaya | PEO | 2019 | Supplemental Budget No. 4 | 8210705.55 | 8195898.89 | 105 | 2020-01-23 | NULL | 2020-05-07 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
658 | Construction of Road Network Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 6500000 | 6486107.1 |  | 2020-01-31 |  | 2020-01-31 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
659 | Construction of Dietary/Linen Building in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 3412192.76 | 3412192.76 | 180 | 2020-02-14 |  | 2020-08-12 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
660 | Construction of Motorpool/Powerhouse Building in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 2026258.99 | 2000565.43 | 90 | 2020-02-24 |  | 2020-05-24 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
661 | Construction of Perimeter Fence in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 1669993.6 | 1669576.86 | 120 | 2020-01-20 |  | 2020-05-19 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
662 | Construction of Multipurpose Building Type II, Mangsee Elementary School | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Mangsee Elementary School | Balabac | PEO | 2019 | 20% Development Fund | 3598655.44 | 3598655.44 | 150 | 2020-02-05 | NULL | 2020-07-04 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
663 | Construction of Multipurpose Building Type II, Paliisan Elementary School | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Paliisan Elementary School | Balabac | PEO | 2019 | 20% Development Fund | 3598655.44 | 3598655.44 | 150 | 2020-02-05 | NULL | 2020-07-04 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
664 | Construction of 3rd Floor OPD Building, Coron District Hospital | B2 SB4 PEO 300-19-11-21279 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 5346192.81 | 5346051.19 | 120 | 2020-02-20 |  | 2020-06-19 | Subject for LD |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
665 | Construction of Distribution System of Bancalaan 2 Village Electrifiction Project | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Bancalaan | Balabac | PEO | 2019 | 20% Development Fund | 11162045.48 | 11162045.48 | 120 | 2020-01-23 | NULL | 2020-05-22 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
666 | Evacuation/ Covered Court in Cabunlawan, Linapacan | SB 1 300-15-12-20589-20590 | Other Infrastructure | COVERED COURT | NULL | Cabunlawan, Linapacan | Linapacan | PEO | 2019 | 20% Development Fund | 5185509 | NULL | 150 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
667 | Construction of Transformer Platform in Bataraza District Hospital and Extension of 3 Phase Line from Highway to Transformer |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 1259946 | 1256727.22 | 60 | 2020-05-22 |  | 2020-07-21 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
668 | Construction of Three (3) Barrel RCBC, Kalawiton, Bgy. Canipaan | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Canipaan | Rizal | PEO | 2019 | 20% Development Fund | 2851835 | 2849356.57 | 180 | 2019-07-11 | NULL | 2020-01-07 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
669 | Upgrading of Kaybulusan Bailey Bridge to RCDG, Purok Masigla, Bgy. Magara | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Magara | Roxas | PEO | 2019 | 20% Development Fund | 7315000 | 7275366.56 | NULL | 2019-08-22 | NULL | 2019-08-22 | NULL | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
670 | Upgrading of Malebeb Bailey Bridge to RCDG, Magara-Caruray Road, | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Roxas | PEO | 2019 | 20% Development Fund | 4920000 | 4918994.3 | 177 | 2019-05-17 | NULL | 2019-11-10 | NULL | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
671 | Upgrading of Salban Bailey Bridge to RCDG, Dumaran | B2 SB4 PEO 300-19-11-21273 | Transportation Facilities | BRIDGES | NULL | Bgy. Danleg | Dumaran | PEO | 2019 | 20% Development Fund | 6045200 | 5514577.04 | 180 | 2020-01-21 | NULL | 2020-07-19 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
672 | Upgrading of Ibalod Bailey Bridge to RCDG Sta. Maria, Dumaran | NULL | Transportation Facilities | BRIDGES | NULL | Brgy. Ilian, Dumaran | Dumaran | PEO | 2019 | 20% Development Fund | 8125000 | 7970837.68 | 181 | 2020-02-13 | NULL | 2020-08-12 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
673 | Upgrading of Ibalod Bailey Bridge to RCDG Bgy. Ilian, Dumaran | NULL | Transportation Facilities | BRIDGES | NULL | NULL | Dumaran | PEO | 2019 | 20% Development Fund | 7970837.68 | 7970837.68 | NULL | 2020-02-12 | NULL | 2020-02-12 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
674 | Upgrading of Kinabuyukan Bailey Bridge to RCDG Phase I | NULL | Transportation Facilities | BRIDGES | NULL | Brgy. Caruray, San Vicente, Palawan | San Vicente | PEO | 2019 | 20% Development Fund | 7445000 | 6578371.87 | 182 | 2019-11-28 | NULL | 2020-05-28 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
675 | Distribution System of Tara Village Elctrification Project | BS SB4 PEO 300-19-11-21290 | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgry. Tara, Coron, Palawan | Coron | PEO | 2019 | 20% Development Fund | 9798841.16 | 9780949.66 | NULL | 2020-01-23 | NULL | 2020-01-23 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
676 | Upgrading of Kinabuyukan Bailey Bridge to RCDG, Phase II | NULL | Transportation Facilities | BRIDGES | NULL | NULL | San Vicente | PEO | 2019 | 20% Development Fund | 1783556.74 | 1708065.39 | NULL | 2020-02-11 | NULL | 2020-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
677 | Construction of BHS Tumarbong, Roxas | BS SB4 PEO 300-19-11-21281 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Tumarbong | Roxas | PEO | 2019 | Supplemental Budget No. 4 | 1500000 | 1498705.81 | 120 | 2020-01-20 |  | 2020-05-19 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
678 | Construction of BHS Caramay, Roxas |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Caramay | Roxas | PEO | 2019 | 20% Development Fund | 1500000 | 1498705.81 | 120 | 2020-01-20 |  | 2020-05-19 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
679 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities | MEDICAL FACILITIES | Modern Tropical Garden | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 2790554.75 | 2784585.91 | 120 | 2020-03-06 |  | 2020-07-04 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
680 | Upgrading of Caponayan Barangay Road, Bgy. Caponayan, Cuyo, Palawan | B2 SB1 PEO 300-19-03-02425 | Transportation Facilities | ROAD | Roads: PCCP: 1.180km x 1.8m (w) x 0.15m(t) - 0.92 km x 1.8m (w) x 0.15m (t) - Limits: Sta.0+000 - Sta. 0+180 - Sta.0+000 - Sta. 0+920 | Bgy. Caponayan | Cuyo | PEO | 2019 | Supplemental Budget No. 1 | 7854206.1 | 7617456.45 | 104 | 2019-06-26 | NULL | 2019-10-08 | 2020-06-24 | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
681 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 2844298.35 | 2842239.81 | 90 | 2019-08-20 |  | 2019-11-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
682 | Installation of Communication System/Security Monitoring Devices (PABX, INTERCOM,CCTV) |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1100000 |  |  | 2019-06-27 |  | 2019-06-27 |  |  | 100% |  | By contract | Completed
683 | Supply and Installation of Electrical Cables and Metering Accessories |  | Medical Facilities | MEDICAL FACILITIES |  | Rizal District Hospital | Rizal | PEO | 2019 | 20% Development Fund | 1145166 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
684 | Construction of Perimeter Fence Phase III and Concrete Grease Filter in SPPH |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2019 | 20% Development Fund | 1645189.2 |  |  | 2020-02-06 |  | 2020-02-06 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
685 | Construction of Perimeter Fence | B2 SB1 PEO 300-19-06-08778 | Medical Facilities | MEDICAL FACILITIES | Semi concrete fence=158.03m:53 span - Concrete fence=135m; 2.4m(h) x 3.0m(l) x 45.0 span | San Vicente District Hospital | San Vicente | PEO | 2019 | Supplemental Budget No. 1 | 2844298.35 | 2842652.87 | 120 | 2019-08-15 |  | 2019-12-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
686 | Supply & Installation of (47) Air Conditioning units (1.5hp,36/2hp,5/1hp,6) |  | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 3069159.31 | [7 empty] | 100% |  | By contract | Completed | Nand Trading
687 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2019 | 20% Development Fund | 2695067.91 | 2693688.17 | 60 | 2019-08-19 |  | 2019-10-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
688 | Construction of Sewage Treatment Plant |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2019 | 20% Development Fund | 3200000 | 3194886 | 60 | 2019-08-16 |  | 2019-10-15 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
689 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2019 | 20% Development Fund | 2790554.75 | 2789042.41 | 90 | 2019-08-16 |  | 2019-11-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
690 | Supply and Installation of Electrical Cables and Metering Accessories |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2019 | 20% Development Fund | 2120085.3 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
691 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 2713889.6 | 2711998.32 | 90 | 2019-08-16 |  | 2019-11-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
692 | Supply & Installation of 12 Units Air Conditioning units |  | Medical Facilities | MEDICAL FACILITIES | Air-condition: 12 Units | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 719274 | [7 empty] | 100% |  | By contract | Completed
693 | Construction of Sewage Treatment Plant |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 3200000 | 3194888 | 60 | 2019-08-16 |  | 2019-10-15 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
694 | Supply and Installation of Electrical Cables and Metering Accessories |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 1617907.24 | 1617907.24 | 10 | 2019-06-27 |  | 2019-07-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
695 | Const of Three (3) Barrel RCBC with Slope Protection and Pavement at Bgy. Busybees, Taytay | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Busybees | Taytay | PEO | 2019 | 20% Development Fund | 5148622.47 | 4993683.1 | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
696 | Construction of Multi-purpose Pavement | NULL | Other Facilities | MULITI-PURPOSE | NULL | Bgy. Burirao | Narra | PEO | 2019 | ROADS 15 300-19-10-18749 | 515000 | 509846.6 | 30 | 2020-02-23 | NULL | 2020-03-24 | NULL | NULL | 100% | NULL | By contract | Completed | VJ Builders | NULL | NULL
697 | Tubbataha Reef Ranger Station (Main Module, Research Module and Transportation Module) Phase 1 | NULL | Other Facilities | OTHER FACILITIES | NULL | Tubbataha Reef, Cagayancillo, Palawan | Cagayancillo | PEO | 2019 | Trust Fund - TIEZA | 40000000 | 39899535.7 | 365 | 2020-01-14 | NULL | 2021-01-13 | NULL | NULL | 100% | NULL | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
698 | Construction of Caramay Hanging Bridge | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Caramay | Roxas | PEO | 2019 | LGSF- DILG CMGP | 4300000 | 4248791.65 | NULL | 2020-01-07 | NULL | 2020-01-07 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
699 | Concreting of Highway Junction - Tumarbong Road (Intermittent Section) | B2 TF Due to NGAS-DILG/DBM CMGP 2019-19-137 | Transportation Facilities | ROAD | NULL | Roxas, Palawan | Roxas | PEO | 2019 | CMGP | 41442579 | 36319060.55 | 184 | 2019-09-11 | NULL | 2020-03-13 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
700 | Concreting of Ilian - Bagumbayan - Latungay Road | B2 TF Due to NGAS-DILG/DBM CMGP 2019-19-138 | Transportation Facilities | ROAD | 2.092 km | Roxas and Dumaran, Palawan | Roxas | PEO | 2019 | CMGP | 36303969 | 33113435.37 | 155 | 2019-09-25 | NULL | 2020-02-27 | NULL | NULL | 100% | NULL | By contract | Completed | BCT Trading and Construction | TIN 102-698-654 | NULL
701 | Concreting of Pulot III-Tabud Road | NULL | Transportation Facilities | ROAD | NULL | Sofronio Española, Palawan | Sofronio Española | PEO | 2019 | CMGP | 25968806.92 | 25968806.92 | 160 | 2019-09-12 | NULL | 2020-02-19 | NULL | NULL | 100% | NULL | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725 | NULL
702 | Concreting of Tubtub - Amas Road | NULL | Transportation Facilities | ROAD | NULL | NULL | Brooke's Point | PEO | 2019 | CMGP | 29269302 | 26693338.96 | NULL | 2019-08-31 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | Chad Lourence Trading & Construction Services | TIN 919-616-230 | NULL
703 | Concreting of Abongan - Alacalian - Binga - Banbanan Road | B2 TF DUE TO NGAS DILG CMGP 2019 19-184 | Transportation Facilities | ROAD | NULL | Taytay, Palawan | Taytay | PEO | 2019 | CMGP | 51594656 | 51320890.34 | 184 | 2019-12-17 | NULL | 2020-06-18 | NULL | NULL | 100% | NULL | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547 | NULL
704 | Construction of Bids and Awards Committee Office Capitol Compound | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2019 | Locally Funded | 2410530.58 | 2460407.64 | 120 | 2019-06-29 | NULL | 2019-10-27 | NULL | NULL | 100% | NULL | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564 | NULL
705 | Renovation of Capitol Commercial Complex, Capitol Compound, PPC | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 5250000 | 5197482.2 | 180 | 2019-10-07 | NULL | 2020-04-04 | NULL | NULL | 100% | NULL | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240 | NULL
706 | Renovation of Accounting Office | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 999942.1 | 998552.27 | 150 | 2019-10-17 | NULL | 2020-03-15 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
707 | Construction of Warehouse for Disaster Relief Goods/Stockpile (Phase I) | NULL | Other Facilities | PGP FACILITIES | NULL | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 3799000.5 | 3779000.5 | NULL | 2019-10-22 | NULL | 2019-10-22 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
708 | Construction of Perimeter Fence, Lualhati Women Center of Palawan Situated at Provincial Agricultural Center, Bgy. Irawan, Puerto Princesa City | NULL | Other Facilities | AGRICULTURAL FACILITIES | NULL | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 1000000 | 919695.15 | 90 | 2020-01-08 | NULL | 2020-04-07 | NULL | NULL | 100% | NULL | By contract | Completed | Jas Trading and Construction | NULL | NULL
709 | Construction of Giraffe Coral Pen | B2 CSP18 300-19-03-02634 | Other Facilities | ANIMAL FACILITIES | NULL | Calauit Safari Park | Busuanga | PEO | 2019 | General Fund | 549654 | 539384.67 | 60 | 2019-06-27 | NULL | 2019-08-26 | NULL | NULL | NULL | NULL | By contract | For Termination | RDF Trading and Construction | CTC 097-331-47 | NULL
710 | Construction of Zebra Coral Pen | B2 CSP18 300-19-03-02634 | Other Facilities | ANIMAL FACILITIES | NULL | Calauit Safari Park | Busuanga | PEO | 2019 | General Fund | 549654 | 539384.67 | 60 | 2019-06-27 | NULL | 2019-08-26 | NULL | NULL | NULL | NULL | By contract | For Termination | RDF Trading and Construction | CTC 097-331-47 | NULL
711 | Construction of Animal Shed, Construction of Restroom, Rehabilitation of Dormitory Building and Renovation of Information Building, Calauit Safari Park, Busuanga, Palawan | NULL | Other Facilities | ANIMAL FACILITIES | NULL | Calauit Safari Park | Busuanga | PEO | 2019 | General Fund | 5270018.92 | 5247930.02 | 315 | 2019-06-27 | NULL | 2020-05-07 | NULL | NULL | NULL | NULL | By contract | For Termination | Samurai Construction | TIN 919-621-019 | NULL
712 | Construction of Covered Walk & Rehabilitation of Flagpole, Hall of Justice, Sta. Monica Heights, PPC. | NULL | Other Facilities | PGP FACILITIES | NULL | Sta. Monica Heights, Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 459000 | 457981.86 | NULL | 2019-12-17 | NULL | 2019-12-17 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
713 | Construction of One (1) Units Proposed New Banua Institute for Resiliency & Green Growth Center | NULL | Other Facilities | AGRICULTURAL FACILITIES | NULL | Bgy. Pangobilian, Brooke's Point | Bataraza | PEO | 2019 | General Fund | 2366077.52 | 2287036.27 | 120 | 2019-11-29 | NULL | 2020-03-28 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
714 | Construction of Isolation Building |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 3740000 | 3142459.67 | 200 | 2020-02-05 |  | 2020-08-23 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
715 | Construction of Dietary Building | B2 SB4 PEO 300-19-11-21494 | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 3416000 | 3244588.44 | 90 | 2020-02-05 |  | 2020-05-05 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
716 | Construction of Motorpool Building |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 2029000 | 2017036.46 | 150 | 2020-06-02 |  | 2020-10-30 |  |  | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
717 | Construction of Material Recovery Facilities Building |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1073000 | 1064515.62 | 30 | 2020-06-03 |  | 2020-07-03 |  |  | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
718 | Construction of Doctors Quarter Building | B2 SB4 PEO19 300-20-02-00681 | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 5555000 | 5448235.2 | 180 | 2020-06-02 |  | 2020-11-29 |  | 4526600% | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
719 | Construction of Transformer Platform in El Nido District Hospital and Extension of 3 Phase Line |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1299279 | 1289739.41 | 60 | 2020-01-23 |  | 2020-03-23 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
720 | Construction of Elevated Water Tank 300 m^3 with Deepwell/ Water Treatment Plant | B2 SB4 PEO 300-19-11-21499 | Medical Facilities | MEDICAL FACILITIES | Transmission Lines - Deepwell and Pumping Station - Dual Filter Tube and Chlorination System - Chlorination Housing - 300m^3 Spherical Steel Elevated Tank | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 7300000 | 7295796 | 180 | 2020-01-21 |  | 2020-07-19 | Subject for LD |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
721 | Construction of Mortuary Building, El Nido Community Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1135000 | 1125634.27 |  | 2020-07-29 |  | 2020-07-29 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
722 | Installation of Fire Protection and Alarm System, El Nido Community Hospital | B2 SB4 PEO19 300-20-02-00677 | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 3418000 | 2800000 | 64 | 2020-02-24 |  | 2020-04-28 |  |  | 100% |  | By contract | Completed | Warlen Industrial and Sales Corporation
723 | Installation of Communication System/Security Monitoring Devices (PABX, Intercom & CCTV) | B2 SB4 PEO19 300-20-02-00678 | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1090000 | 1081326.15 |  | 2020-11-18 |  | 2020-11-18 |  |  | 100% |  | By contract | Completed
724 | Construction of Elevated Water Tank, Bgy. San Isidro | B2 SB4 PEO 300-19-11-21491 | Medical Facilities | MEDICAL FACILITIES | Transmission Lines - Deepwell and Pumping System - Dual Filter Tube and Chlorination System - Chlorination Housing - 300m^3 Spherical Steel Elevated Tank | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 7300000 | 7295318 | 180 | 2020-07-18 |  | 2021-01-14 |  |  |  |  | By contract | For Termination | Kudz Trading and Construction | TIN 188-527-256 | For Legal Endorsement
725 | Construction of Transformer Platform in San Vicente District Hospital and Extension of 3 Phase Line from Highway to Transformer |  | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1299279 | 1287932.98 |  | 2020-01-24 |  | 2020-01-24 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
726 | Construction of Mortuary Building |  | Medical Facilities | MEDICAL FACILITIES | 1 storey: 6.0m x 6.0m - steel trusses | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1135000 | 1063839.94 | 60 | 2021-02-12 |  | 2021-04-13 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
727 | Construction of Material Recovery Facilities |  | Medical Facilities | MEDICAL FACILITIES | Buildings: 24.00 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1073000 | 1069798.04 | 30 | 2020-01-30 |  | 2020-02-29 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
728 | Construction of Dietary/Linen Building |  | Medical Facilities | MEDICAL FACILITIES | Buildings: 200 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 3416000 | 3402587.7 | 90 | 2020-02-07 |  | 2020-05-07 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
729 | Construction Isolation Building |  | Medical Facilities | MEDICAL FACILITIES | 1 storey: 20.0m(L) x 8.0m(W) - Steel Truss | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 3730033.72 | 3543291.67 | 90 | 2019-11-28 |  | 2020-02-26 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
730 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities | MEDICAL FACILITIES | Buildings: 126 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 2029000 | 1848611.11 | 90 | 2020-04-27 |  | 2020-07-26 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
731 | Construction of Doctors/Nurses Quarter |  | Medical Facilities | MEDICAL FACILITIES | Buildings: 560 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 5555000 | 5381624.42 | 150 | 2020-01-31 |  | 2020-06-29 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
732 | San Vicente District Hospital - Installation of Fire Protection and Alarm System |  | Medical Facilities | MEDICAL FACILITIES | Sprinkler heads: 389 sets - Smoke detector: 50 sets | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 3418000 | 2800000 | 64 | 2020-02-24 |  | 2020-04-28 |  |  | 100% |  | By contract | Completed | Warlen Industrial and Sales Corporation
733 | Installation of Communication System/Security Monitoring Devices (PABX, Intercom & CCTV) |  | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1090000 | 1081326.15 |  | 2020-11-17 |  | 2020-11-17 |  |  | 100% |  | By contract | Completed
734 | Construction of Motorpool Powerhouse Building |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2019 | DBP Loan | 2025246.02 | 2023304.42 |  | 2020-06-20 |  | 2020-06-20 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
735 | Construction of Dietary-Linen Building, Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2019 | DBP Loan | 3414563.6 | 3411525.72 | 230 | 2021-09-10 |  | 2022-04-28 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
736 | Construction of Roxas Water System Phase 2-2 | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | Roxas | PEO | 2019 | NULL | 106000000 | 93339955.29 | NULL | 2020-05-22 | NULL | 2020-05-22 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
737 | Construction of Poblacion Water Pipeline | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | Balabac, Palawan | Balabac | PEO | 2019 | NULL | 8859000 | 8706200.69 | NULL | 2019-10-17 | NULL | 2019-10-17 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
738 | Improvement of Landscaping for Sofronio Española District Hopsital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Pulot Center, Sofronio Española, Palawan | Sofronio Española | PEO | 2019 | Supplemental Budget | 900000 | 899029.67 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
739 | Construction of Lamayo Processing Center Phase II | NULL | Other Facilities | AGRICULTURAL FACILITIES | NULL | Sitio Yakal, New Guinlo | Taytay | PEO | 2019 | GAD Fund | 1500000 | 1438997.74 | 60 | 2019-12-16 | NULL | 2020-02-14 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
740 | Construction of Roxas Water System Phase 2-1 | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Roxas, Palawan | Roxas | PEO | 2019 | NULL | 135000000 | 134352788.88 | NULL | 2019-05-18 | NULL | 2019-05-18 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
741 | Renovation/Rehabilitation of Existing Rural Agricultural Center Building and Perimeter Fence | NULL | Other Facilities | AGRICULTURAL FACILITIES | NULL | Sitio Igang, Poblacion | Taytay | PEO | 2020 | NULL | 3000000 | 2,675,106..49 | NULL | 2020-12-17 | NULL | 2020-12-17 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
742 | Construction of Northern Palawan Provincial Hospital (Phase II) |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2020 | Supplemental Budget No. 12 | 30000000 | 29940281.89 | 210 | 2021-07-15 |  | 2022-02-10 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
743 | Construction of Balabac District Hospital Building Phase II |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospita | Balabac | PEO | 2020 | Supplemental Budget No. 12 | 30000000 | 29992169.47 | 180 | 2021-04-06 |  | 2021-10-03 | 2022-01-25 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
744 | Construction of Southern Palawan Provincial Hospital (Construction of Medical Workers Dormitory) |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2020 | 20% Development Fund | 10500000 | 8924986.55 | 135 | 2021-01-11 | 1 | 2021-05-26 | Subject for LD |  | 95.17% |  | By contract | On going | BCL Construction | TIN 308-390-430
745 | Construction of Bataraza District Hospital Perimeter Fence Phase II |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | 20% Development Fund | 3950000 | 3407331.82 |  | 2020-10-01 |  | 2020-10-01 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
746 | Installation of Transformer with Metering Accessories and Main Cable | B2 PEO 300-20-06-07368 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2020 | 20% Development Fund | 2868181.16 | 2861250.46 | 90 | 2020-07-29 |  | 2020-10-27 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
747 | Construction of Narra Municipal Hospital (Additional Ceiling Works inside Main Building) | B2 PEO 300-20-11-16949 | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2020 | 20% Development Fund | 1667256.34 | 1665187.73 | 120 | 2021-01-15 |  | 2021-05-15 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
748 | Construction of Multi-purpose Building with Perimeter Fence, | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Bgy. Bunog, Buliluyan, Bataraza | Bataraza | PEO | 2020 | 20% Development Fund | 6294996.21 | 6292990.05 | NULL | 2020-08-21 | NULL | 2020-08-21 | NULL | NULL | 100% | NULL | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153 | NULL
749 | Construction of Sewage Treatment Plant |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | 20% Development Fund | 3200000 |  |  | 2020-08-10 |  | 2020-08-10 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
750 | Construction of Barangay Health Station |  | Medical Facilities | BHS |  | Brgy. Bunog, Municipality of Rizal, Palawan | Rizal | PEO | 2020 | 20% Development Fund | 2300000 | 2068031.4 | 120 | 2020-10-07 |  | 2021-02-04 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
751 | Construction/Rehabilitation of Maasin Bailey Bridge | NULL | Transportation Facilities | BRIDGES | NULL | Bgy. Maasin | Quezon | PEO | 2020 | 20% Development Fund | 6378906.45 | 6378906.45 | 182 | 2020-05-09 | NULL | 2020-11-07 | NULL | NULL | 100% | NULL | By contract | Completed | RDF Trading and Construction | CTC 097-331-47 | NULL
752 | Upgrading of Cataban Bailey Bridge II to RCDG | B2 PEO 300-20-07-08703 | Transportation Facilities | BRIDGES | NULL | Bgry. Cataban, Taytay | Taytay | PEO | 2020 | 20% Development Fund | 16200000 | 14497276.33 | 197 | 2020-10-06 | NULL | 2021-04-21 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
753 | Construction/Extension of New Guinlo Boat Landing Phase II | B2 PEO 300-20-08-10035 | Ports and Airports | PORTS | NULL | Municipality of Taytay, Palawan | Taytay | PEO | 2020 | 20% Development Fund | 2500000 | 2491169.78 | 90 | 2020-10-05 | NULL | 2021-01-03 | NULL | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
754 | Construction of Barangay Health Station, Lagaoriao | B2 PEO 300-20-06-07373 | Medical Facilities | BHS |  | Bgy. Lagaoriao | Cuyo | PEO | 2020 | 20% Development Fund | 2300000 | 2294294.55 | 120 | 2020-07-28 |  | 2020-11-25 |  | 2022-10-15 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
755 | Construction of Barangay Health Station, Los Angeles |  | Medical Facilities | BHS |  | Bgy.Los Angeles | Magsaysay | PEO | 2020 | 20% Development Fund | 2294294.55 | 2294294.55 | 120 | 2020-07-28 |  | 2020-11-25 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
756 | Construction of Sewage Treatment Plant |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2020 | 20% Development Fund | 3200000 | 3196665.89 | 60 | 2020-08-10 |  | 2020-10-09 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
757 | Construction of Perimeter Fence in Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 4198409.61 | 4198409.61 | 120 | 2020-08-07 |  | 2020-12-05 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
758 | Construction/Rehabilitation of Hospital Buildings and Facilities Quezon Medicare Hospital, Phase III |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 26320104 | 26303910 |  | 2020-08-08 |  | 2020-08-08 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
759 | Final Completion Works of Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 17701415.93 | 17157910.52 | 180 | 2020-11-17 |  | 2021-05-16 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
760 | Construction of Doctors/Nurses' Quarter |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 5800000 | 5761269.01 |  | 2020-10-07 |  | 2020-10-07 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
761 | Construction of Evacuation Center/Multi-Purpose Bldg., Suba ,Cuyo Palawan | B2 PEO 300-20-09-12724 | Other Infrastructure | MULITI-PURPOSE | Floor Area: 9m x 6m = 54 sqm (Two-storey building) | Bgy. Suba, Cuyo, Palawan | Cuyo | PEO | 2020 | 20% Development Fund | 2800000 | 2798739.06 | 150 | 2021-01-04 | NULL | 2021-06-03 | 2021-07-23 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
762 | Construction of Evacuation Center/Multi-Purpose Building , Bunog, Rizal | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Rizal | Rizal | PEO | 2020 | 20% Development Fund | 1532067.65 | 1532067.65 | 120 | 2020-10-07 | NULL | 2021-02-04 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
763 | Concreting of Narra Municipal Hospital (Concreting of Roads Leading to Facilities) |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2020 | 20% Development Fund | 1332743.66 | 1330246.98 |  | 2021-04-06 |  | 2021-04-06 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
764 | Construction of Bataraza Distict Hospital (Installation of Airconditioning Units) |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | 20% Development Fund | 3454659 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
765 | Concreting of El Nido Community Hospital Road Network | B2 PEO 300-20-06-07385 | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 5921673.6 | 5908042.26 | 120 | 2020-09-03 |  | 2021-01-01 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
766 | Construction of El Nido Community Hospital (Installation of Airconditioning Units) |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 3454659 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
767 | Construction of Sewage Treatment Plan in El Nido Community Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 3196665.89 | 3150728.39 | 60 | 2019-08-10 |  | 2019-10-09 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
768 | Construction of Two (2) Additional rooms in Doctors Quarter Building | B2 PEO20 300-21-02-00390 | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2020 | 20% Development Fund | 1100000 | 1084825.82 | 120 | 2021-04-08 |  | 2021-08-06 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
769 | Final Completion Works of Coron District Hospital Building | B2 PEO20 300-21-00389 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital Building | Coron | PEO | 2020 | 20% Development Fund | 11100000 | 11098723.94 | 180 | 2021-04-16 |  | 2021-10-13 |  |  |  |  | By contract | For Termination | Smmiley Builders and Trading | TIN 936-564-958
770 | Construction of Coron District Hospital (Installation of Distribution Panel Board, Main Cable and Other Electrical Material for the Main Building and Other Facilities) |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2020 | 20% Development Fund | 2702601 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
771 | Construction of San Juan hanging Bridge | NULL | Transportation Facilities | BRIDGES | (A) Hanging Bridge: 60m (l) x 2.10m (w) | San Juan, Aborlan | Aborlan | PEO | 2020 | 20% Development Fund | 3502950.19 | 3498698.24 | 120 | 2020-08-14 | NULL | 2020-12-12 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
772 | Rehabilitation of Magbabadil Bridge I | B2 PEO 300-20-06-07376 | Transportation Facilities | BRIDGES | NULL | Bgy. Mabini | Aborlan | PEO | 2020 | 20% Development Fund | 3196665.89 | 3136392.17 | 177 | 2020-08-12 | NULL | 2021-02-05 | NULL | NULL | 100% | NULL | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215 | NULL
773 | Construction/Rehabilitation of RCBC with Slope Protection in National High way-Tabud Road | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Panitian | Quezon | PEO | 2020 | 20% Development Fund | 2320000 | 2315541.32 | NULL | 2020-08-13 | NULL | 2020-08-13 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
774 | Construction of Candis RCDG Bridge | B2 PEO 300-20-11-16447 | Transportation Facilities | BRIDGES | Approach:6m x 6m (both sides) - Bridge: 14ln.m - RC Slope: 6m x 4 sides - PCCP: 30ln.m | Dumaran, Palawan | Dumaran | PEO | 2020 | 20% Development Fund | 10342148.11 | 8583616.78 | 182 | 2021-01-18 | NULL | 2021-07-19 | Subject for LD | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
775 | Construction of two (2) Barrel RCBC with concrete slope protection | NULL | Other Infrastructure | DRAINAGE | NULL | Magsaysay, Dumaran | Dumaran | PEO | 2020 | 20% Development Fund | 3729963.8 | 3721400.59 | 300 | 2020-08-15 | NULL | 2021-06-11 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
776 | Upgrading of Cataban Bailey Bridge II to RCDG | NULL | Transportation Facilities | BRIDGES | NULL | Brgy. Cataban, Taytay, Palawan | Taytay | PEO | 2020 | 20% Development Fund | 16200000 | 14497276.33 | 197 | 2020-10-06 | NULL | 2021-04-21 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
777 | Concreting of Pulot Shore Provincial Road | NULL | Transportation Facilities | ROAD | NULL | NULL | Sofronio Española | PEO | 2020 | 20% Development Fund | 10215663.47 | 10214282.32 | NULL | 2020-11-09 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725 | NULL
778 | Concreting of Magara Bgy. Road, Phase II | NULL | Transportation Facilities | ROAD | NULL | NULL | Roxas | PEO | 2020 | 20% Development Fund | 3211933.56 | 3206891.39 | 60 | 2020-08-14 | NULL | 2020-10-13 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
779 | Concreting of Suba-Pawa-San Carlos Road (Half Lane) | B2 PEO 300-20-06-07379 | Transportation Facilities | ROAD | NULL | Cuyo, Palawan | Cuyo | PEO | 2020 | 20% Development Fund | 5353777.15 | 5345514.9 | 90 | 2020-08-14 | NULL | 2020-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
780 | Construction of Spillway | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Sto. Kalampinay, Pasadena, El Nido | El Nido | PEO | 2020 | 20% Development Fund | 1799450.6 | 1793152.64 | 60 | 2020-08-07 | NULL | 2020-10-06 | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
781 | Construction of Three (3) Barrel RCBC | NULL | Other Infrastructure | DRAINAGE | NULL | Minara, Roxas | Roxas | PEO | 2020 | 20% Development Fund | 4513564.88 | 4505210.5 | NULL | 2020-08-17 | NULL | 2020-08-17 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
782 | Construction of One (1) Barrel RCBC Leading to Borac Port | B2 PEO 300-20-06-07383 | Other Infrastructure | DRAINAGE | NULL | Bgry. Borac, Coron, Palawan | Coron | PEO | 2020 | 20% Development Fund | 3700000 | 3698950.01 | 120 | 2020-09-22 | NULL | 2021-01-20 | NULL | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
783 | Construction of Evacuation Center/Multi-purpose Building | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Kalatagbak, Quezon | Quezon | PEO | 2020 | 20% Development Fund | 850000 | 837906.05 | NULL | 2020-10-01 | NULL | 2020-10-01 | NULL | NULL | 100% | NULL | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708 | NULL
784 | Construction of Covered Court/Evacuation Center Phase I | B2 PEO 300-20-06-07374 | Other Infrastructure | COVERED COURT | NULL | Macaranao, Agutaya | Agutaya | PEO | 2020 | 20% Development Fund | 5270214.07 | 5259935.48 | 150 | 2021-01-21 | NULL | 2021-06-20 | 2022-05-09 | NULL | NULL | NULL | By contract | Terminated | RAK Trading Construction & Supply | NULL | Due to: (-) 10% slippage
785 | Concreting of Barangay Road | NULL | Transportation Facilities | ROAD | NULL | Bunog, Rizal | Rizal | PEO | 2020 | 20% Development Fund | 5161995.31 | 5161995.3 | 86 | 2020-10-07 | NULL | 2021-01-01 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
786 | Construction of Covered Court/Evacuation Center Phase I | NULL | Other Infrastructure | COVERED COURT | Court: 30m(l) x 18m(w) | Sitio Gawid, San Vicente | San Vicente | PEO | 2020 | 20% Development Fund | 5109576.74 | 5073169.82 | 150 | 2020-12-02 | NULL | 2021-05-01 | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
787 | Construction of Sewage Treatment Plant in Cuyo District Hospital | B2 PEO 300-20-08-10036 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2020 | 20% Development Fund | 3200000 | 3198008.58 | 60 | 2020-09-29 |  | 2020-11-28 | 2021-08-12 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
788 | Expansion of SPS Government Center Bancao-Bancao | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Bancao-Bancao | Puerto Princesa City | PEO | 2020 | Supplemental Budget No. 9 | 3411457.86 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000 | NULL
789 | Construction/Improvement of SPS Government Center Bancao-Bancao | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Bancao-Bancao | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 9 | 10330261.87 | 10329196.97 | 360 | 2021-09-23 | 1 | 2022-09-18 | 2022-11-16 | NULL | 100% | NULL | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000 | NULL
790 | Improvement of Hospital Landscaping,Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | Supplemental Budget No. 12 | 2757096.4 | 2757096.4 |  | 2021-03-30 |  | 2021-03-30 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
791 | Improvement of Hospital Landscaping, El Nido Community Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2020 | Supplemental Budget No. 12 | 2769899.3 | 2769899.3 |  | 2021-04-08 |  | 2021-04-08 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
792 | Improvement of Hospital Landscaping, Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | Supplemental Budget No. 12 | 2764220.9 | 2764220.9 |  | 2021-03-30 |  | 2021-03-30 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
793 | Concreting of Parking Area and access leading to Facilities |  | Medical Facilities | MEDICAL FACILITIES | Parking Area=280.60 sq.m - Access Road=270.14 sq.m | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 12 | 1160954.26 | 1159987 | 45 | 2021-04-07 |  | 2021-05-22 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
794 | Construction of Hazardous Waste Vault and Additional Ceiling Works |  | Medical Facilities | MEDICAL FACILITIES | Septic Vault=2m(l) x 2m(w) x 2.5m(h) - Ceiling=697.32 sq.m | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 12 | 550000 | 549935.39 | 60 | 2021-01-13 |  | 2021-03-14 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
795 | Supply and Delivery of Transformer Units ( CT/PT) |  | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 12 | 624810 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
796 | Supply and Delivery of 3 - 50 KVA and Line Hardware of Calandagan Village Electrification Project | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Calandagan, Araceli | Araceli | PEO | 2020 | Supplemental Budget No. 12 | 877675.05 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
797 | Construction of Transformer Platform with Distribution of Three (3) Phase Line at Motorpool Irawan |  | Medical Facilities | MEDICAL FACILITIES |  | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2020 | Supplemental Budget No. 12 | 1627651.97 | 1626057.03 |  | 2021-04-06 |  | 2021-04-06 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
798 | Supply and Installation of Fire Protection for Roxas Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2020 | Supplemental Budget No. 12 | 3400000 | 3390808.37 | 64 | 2021-04-22 |  | 2021-06-25 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
799 | Supply and Installation of Airconditioning Units for Quezon Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon, Palawan | Quezon | PEO | 2020 | Supplemental Budget No. 12 | 3454659 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
800 | Supply and Installation of Hospital Billboards and Markers |  | Medical Facilities | MEDICAL FACILITIES |  | *San Vicente District Hospital *El Nido Community Hospital *Bataraza District Hospital |  | PEO | 2020 | Supplemental Budget No. 12 | 1500000 | [7 empty] | 100% |  | By contract | Completed | Megaprint
801 | Repair of Powerhouse of Calandagan Village Electrification Project | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Calandagan, Araceli | Araceli | PEO | 2020 | Supplemental Budget No. 12 | 499866.12 | 489732.75 | 45 | 2021-01-11 | NULL | 2021-02-25 | NULL | NULL | NULL | NULL | By contract | For Termination | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
802 | Renovation of Provincial Health Office | NULL | Other Facilities | PGP FACILITIES | NULL | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2020 | Supplemental Budget No. 14 | 6443263.19 | 6443753.42 | NULL | 2021-06-23 | NULL | 2021-06-23 | NULL | NULL | 100% | NULL | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958 | NULL
803 | Construction of San Vicente District Hospital Perimeter Fence, Phase II |  | Medical Facilities | MEDICAL FACILITIES | CHB Fence=420ln.m - 2m (height) | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 14 | 4100000 | 4058723.74 | 120 | 2021-04-13 |  | 2021-08-11 |  |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
804 | Construction of Quezon Medicare Hospital STP Tank Phase II |  | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | Supplemental Budget No. 14 | 895627.22 | 895627.22 | 90 | 2021-03-22 |  | 2021-06-20 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
805 | Construction of Multi-Purpose Building | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | NULL | Roxas | PEO | 2020 | Supplemental Budget No. 14 | 1487840.75 | 1487815.75 | NULL | 2021-06-07 | NULL | 2021-06-07 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
806 | Construction of Evacuation Center/ Multi-Purpose Building | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Tenga-Tenga | Cuyo | PEO | 2020 | Supplemental Budget No. 14 | 1500000 | 1499164.73 | 120 | 2021-03-20 | NULL | 2021-07-18 | 2021-11-06 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
808 | Construction of Perimeter Fence in El Nido Community Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 6820933.67 | 6404833 | 180 | 2020-08-14 |  | 2021-02-10 |  |  | 100% |  | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176
809 | Concreting of Panitian - Abokayan Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | ROAD | 1.98 KM | Sofronio Española | Sofronio Española | PEO | 2020 | CMGP | 34173455 | 33650753.97 | 131 | 2021-01-22 | NULL | 2021-06-02 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
810 | Concreting of Panitian - Tabud Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | ROAD | 2.10 KM | Quezon | Quezon | PEO | 2020 | CMGP | 41126334 | 40497286.05 | 205 | 2021-01-22 | NULL | 2021-08-15 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
811 | Concreting of Teresa - Batang Batang Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | ROAD | 1.504 KM | Narra | Narra | PEO | 2020 | CMGP | 26332019 | 26155597.41 | 136 | 2021-01-22 | NULL | 2021-06-07 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
812 | Concreting of Junction Highway - Burirao Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | ROAD | 1.484 KM | Narra | Narra | PEO | 2020 | CMGP | 26437914 | 25777985.84 | 113 | 2021-01-22 | NULL | 2021-05-15 | 2021-06-05 | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
813 | Expansion of Isolation Building and Construction of Hazardous Waste Vault | SB3 HDMP 300-20-06-07206 | Medical Facilities | MEDICAL FACILITIES | No. 1 storey - Floor area: 20.0m(l) x 8.0m(w) - steel truss | Roxas Medicare Hospital | Roxas | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3880000 | 3839182.15 | 150 | 2020-07-13 |  | 2020-12-10 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
814 | Expansion of Isolation Building and Construction of Hazardous Waste Vault (Narra Municipal Hospital) |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3850000 | 3838801.72 | 150 | 2020-07-11 |  | 2020-12-08 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
815 | Construction of TB DOTS, Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2020 | Supplemental Budget No. 3 HDMP | 1637141.17 | 1637141.17 | 120 | 2020-07-29 |  | 2020-11-26 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
816 | Expansion of Isolation Building and Construction of Hazardous Waste Vault | SB3 HDMP 300-20-06-07207 | Medical Facilities | MEDICAL FACILITIES | 1 Storey: Floor Area: 20.00m (l) x 8.00m (w) - Steel Truss | Aborlan Medicare Hospital | Aborlan | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3848742.93 | 3848742.93 | 150 | 2020-07-15 |  | 2020-12-12 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
817 | Construction of TB Dots | SB3 HDMP 300-20-07-08059 | Medical Facilities | MEDICAL FACILITIES | 10.00m x 8.00m TB DOTS Building | Aborlan Medicare Hospital | Aborlan | PEO | 2020 | Supplemental Budget No. 3 HDMP | 1500000 | 1498529.47 | 120 | 2020-09-16 |  | 2021-01-14 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
818 | Expansion of Isolation Building and Construction of Hazardous Waste Vault (Southern Palawan Provincial Hospital) |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3817957.71 | 3808198.5 | 150 | 2020-07-10 |  | 2020-12-07 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
819 | Expansion of Isolation Building and Construction of Hazardous Waste Vault (Southern Palawan Provincial Hospital) | SB3 HDMP 300-20-07-08057 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2020 | Supplemental Budget No. 3 HDMP | 1785000 | 1784000 | 180 | 2020-07-30 |  | 2021-01-26 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
820 | Construction and Upgrading of Junction Salban-Culasian-Magsaysay FMR | PRDP-IB-R04B-PAL-005-000-000-2014-AF | Transportation Facilities | ROAD | NULL | Bgy. Danleg, Culasian, Magsaysay, Dumaran, Palawan | Dumaran | PEO | 2020 | D.A FUND | 218599855.41 | 197209134.68 | 369 | 2020-02-27 | NULL | 2021-03-02 | 2022-06-15 | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
821 | Construction of Kapangyan Water System Retaining Wall | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Bataraza, Palawan | Bataraza | PEO | 2020 | NULL | 1059995.84 | 1059995.84 | NULL | 2020-12-19 | NULL | 2020-12-19 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
822 | Provincial Engineering Office Renovation | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Building, Bgy. Tanglaw | Puerto Princesa City | PEO | 2020 | MOOE PEO | 684993.05 | 684576.77 | NULL | 2021-01-13 | NULL | 2021-01-13 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
823 | Improvement of Capitol Park (Capitol Ground) | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Building, Bgy. Tanglaw | Puerto Princesa City | PEO | 2020 | MOOE PEO | 12000000 | 11952584.52 | NULL | 2021-06-10 | NULL | 2021-06-10 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
824 | Construction of Araceli/Dumaran District Hospital Phase II |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2020 |  | 21001275.07 |  |  | 2021-06-11 |  | 2021-06-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
825 | Constrcution of Free Standing COVID-19 Testing Laboratory with Comfort Rooms and Hazardous Waste Vault | SB3 HDMP 300-20-07-08060 | Medical Facilities | MEDICAL FACILITIES | Single Storey: (a) Laboratory: 12.00m x 10.50m - (b) CR: 6.00m x 3.00m - © Vault: 2.00m x 2.00m | Bgy. Irawan | Puerto Princesa City | PEO | 2020 | HDMP - Supplemental Budget No. 3 | 4273835 | 4272957.06 | 150 | 2020-11-12 |  | 2021-04-11 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction
826 | Construction of Provincial Disaster Operation Center of Palawan Phase II | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Irawan | Puerto Princesa City | PEO | 2020 | NULL | 12657400 | 11380944.78 | NULL | 2021-02-01 | NULL | 2021-02-01 | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
827 | Construction of Roxas Waterworks Office Perimeter Fence and Waterhouse | NULL | Artesian Wells, Reservoir, Pumping and Conduits | IRRIGATION | NULL | NULL | Roxas | PEO | 2021 | NULL | 1399000 | 1397754.67 | 150 | 2021-11-08 | NULL | 2022-04-07 | NULL | NULL | 100% | NULL | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868 | NULL
828 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities | B2 PEO15 300-18-06-09394 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 6613020.87 | 6476855.512 | 90 | 2019-01-08 |  | 2019-04-08 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
829 | Supply and Installation of Fire Protection & Alarm System | B2 PEO15 300-20-08-11261 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 3417513.7 | 3414039.04 | 64 | 2020-11-16 |  | 2021-01-19 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
830 | Installation of Communication System/Security Monitoring Devices (PABX,Intercom & CCTV) |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 1095783 | 1084830.35 |  | 2020-12-17 |  | 2020-12-17 |  |  | 100% |  | By contract | Completed
831 | Concreting of Ramp and Parking Area |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 979315.43 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
832 | Installation of Additional Ceiling (Ward Nursing Station and Const of Canopy from Main Building to Dietary & MHB to Isolation |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 412795.58 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
833 | Construction/Supply and Installation of STP Equipment and Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 1 | 2165056.74 |  | 60 | [5 empty] | 100% |  | By contract | Completed
834 | Improvement of Northern Palawan Provincial Hospital (Installation of Airconditioning Units) |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | 20% Development Fund | 3400000 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
835 | Improvement of Bataraza District Hospital (Installation of Communication System/Security Monitoring Devices (Paging System, PABX,Intercom & CCTV)) |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 1100000 | 1095000 | 75 | 2021-12-06 |  | 2022-02-19 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
836 | Improvement of Bataraza District Hospital (Installation of Fire Protection and Alarm System) |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 3300000 | 3289676.71 | 64 | 2021-06-24 |  | 2021-08-27 | 2022-01-09 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
837 | Construction of Isolation Building in Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 3740000 | 3736267.23 | 200 | 2021-09-22 |  | 2022-04-10 | For approval |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
838 | Construction of Material Recovery Facilities Building in Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 1068780.72 | 1068777.26 |  | 2021-06-21 |  | 2021-06-21 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
839 | Improvement of Araceli/Dumaran District Hospital (Installation of Fire Protection and Alarm System) |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 3296239.21 | 3296239.21 |  | 2021-08-05 |  | 2021-08-05 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
840 | Construction of Isolation Building in Cuyo District Hospital | B2 PEO 300-21-04-03046 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 4200341.76 | 4200281.64 | 200 | 2021-06-07 | 2 | 2021-12-24 | For approval |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
841 | Construction of Material Recovery Facilities Building in Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 1126956.44 | 1126941.84 | 120 | 2021-06-07 |  | 2021-10-05 | 2022-09-21 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
842 | Construction of Doctors/Nurses Quarter Building in Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 6074917.7 | 6014846.48 | 240 | 2021-06-07 | 2 | 2022-02-02 | Subject for LD |  | 70% |  | By contract | On going | Julriz Trading and Construction | TIN 495-740-401
843 | Construction of Dietary/Linen Building in Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 4300000 | 4297123.18 | 180 | 2021-09-16 | 2 | 2022-03-15 | For approval |  |  |  | By contract | For Termination | Julriz Trading and Construction | TIN 495-740-401
844 | Construction of Mortuary Building in Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 1195000 | 1193531.64 | 90 | 2021-09-16 | 2 | 2021-12-15 | For approval | 2023-10-11 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
845 | Improvement of Cuyo District Hospital (Installation of Fire Protection and Alarm System) |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 3500000 | 3497903.33 | 85 | 2021-08-05 |  | 2021-10-29 | 2022-01-12 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
846 | Improvement of Cuyo District Hospital (Installation of Airconditioning Units) |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 3400000 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
847 | Improvement of Hospital Landscaping in Old Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Old Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 488585.9 | 488585.9 | 90 | 2021-07-12 |  | 2021-10-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
848 | Improvement of Hospital Landscaping in Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 2798022.47 |  | 120 | 2021-09-16 |  | 2022-01-14 | 2022-09-25 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
849 | Improvement of Hospital Landscaping in Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 2800000 | 2794861.5 | 120 | 2021-10-28 |  | 2022-02-25 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
850 | Construction of Perimeter Fence in Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 2544672 | 2542436.1 | 120 | 2021-09-16 |  | 2022-01-14 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
851 | Construction of Perimeter Fence Phase III in Dr Jose Rizal District Hospital | B2 PEO 300-21-11-15795 | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2021 | 20% Development Fund | 270000 | 269750 | 93 | 2021-12-17 |  | 2022-03-20 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
852 | Construction of Perimeter Fence in Roxas Medicare Hospital, Phase 3 |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2021 | 20% Development Fund | 2000000 | 1998231.64 | 120 | 2021-12-13 |  | 2022-04-12 | 2022-06-12 |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
853 | Concreting of Road Network Phase II in Dr Jose Rizal District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2021 | 20% Development Fund | 1230000 | 1229971.51 | 60 | 2021-10-06 |  | 2021-12-05 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
854 | Concreting of Road Network Phase II in El Nido Community Hospital | B2 PEO 300-21-05-04027 | Transportation Facilities | ROAD | Roads: PCCP (Road Network): 342.109 sq.m x 0.15m (t) - 236m(l) x 4m(w) x 0.020m(t) - 1m shoulder both side | El Nido Community Hospital | El Nido | PEO | 2021 | 20% Development Fund | 2000000 | 1999230.77 | 120 | 2021-06-21 | NULL | 2021-10-19 | NULL | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
855 | Construction of One (1) Barrel RCBC | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Labog, Sofronio Española, Palawan | Sofronio Española | PEO | 2021 | 20% Development Fund | 2000000 | 1998601.44 | 180 | 2021-07-02 | NULL | 2021-12-29 | NULL | NULL | 100% | NULL | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725 | NULL
856 | Construction of Bridge Slope Protection | NULL | Other Infrastructure | SLOPE PROTECTION | NULL | Pulot Shore | Sofronio Española | PEO | 2021 | 20% Development Fund | 302551.38 | 302551.38 | NULL | 2021-05-21 | NULL | 2021-05-21 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
857 | Repair of Slope Protection in Saraza Bridge | NULL | Other Infrastructure | SLOPE PROTECTION | NULL | Saraza | Brooke's Point | PEO | 2021 | 20% Development Fund | 843042.7 | 841716.59 | 90 | 2021-06-07 | NULL | 2021-09-05 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
858 | Construction of 2-units of One (1) Barrel RCBC with PCCP approach and Slope Protection | NULL | Other Infrastructure | DRAINAGE | RCBC/RC Slope Protection: (a) RCBC 1-3m(h) x 3m(w) x 6.0(l) x 0.30m thk. (b) approach" 2-10m(l) x 6.0m(w) x 0.20m thk x 2 sides ( c) Detour Road 2-12m(l) x 5m(w) with 24'' RCPC (d) Slope Protection 5m (l) x 2m (h) x 0.30m thk x 4 sides | Bgry. Magsaysay, Dumaran, Palawan | Dumaran | PEO | 2021 | 20% Development Fund | 4000000 | 3998116.65 | 300 | 2022-12-23 | NULL | 2023-10-19 | 2023-07-31 | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
859 | Concreting of Cataban - Liminangcong Road (Intermitent Section) | NULL | Transportation Facilities | ROAD | 1.0 km | NULL | Taytay | PEO | 2021 | 20% Development Fund | 10485742.24 | 10484696.85 | NULL | 2021-07-31 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
860 | Concreting of Abongan - Alacalian - Binga Road (Intermitent Section) | NULL | Transportation Facilities | ROAD | 1.0 km | Alacalian - Binga | Taytay | PEO | 2021 | 20% Development Fund | 10500000 | 10492669.72 | NULL | 2021-07-29 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
861 | Concreting of Road from Highway Junction Leading to NPPH Facilities | B2 PEO 300-01-05-05582 | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | 20% Development Fund | 5000000 | 4999088 | 60 | 2021-08-02 |  | 2021-10-01 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
862 | Construction of Powerhouse/ Motorpool Building in Cuyo District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 2700170.25 | 2698173.92 | 90 | 2021-09-16 | 2 | 2021-12-15 | For approval | 2023-09-01 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
863 | Construction of Powerhouse for Bancalaan 1 VEP | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Bancalaan I | Balabac | PEO | 2021 | 20% Development Fund | 1332158.2 | 1330146.46 | 270 | 2021-06-10 | NULL | 2022-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
864 | Construction of Powerhouse for Bancalaan 2 VEP | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Bancalaan 2 | Balabac | PEO | 2021 | 20% Development Fund | 1335815.99 | NULL | 270 | 2021-06-10 | NULL | 2022-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
865 | Construction of Powerhouse for Concepcion VEP | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Concepcion | Agutaya | PEO | 2021 | 20% Development Fund | 1335815.99 | 1331162.16 | 270 | 2021-06-10 | NULL | 2022-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
866 | Construction of Powerhouse for Tara VEP | B2 PEO 300-21-04-03109 | Other Infrastructure | OTHER FACILITIES | NULL | Bgry. Tara, Coron, Palawan | Coron | PEO | 2021 | 20% Development Fund | 1874043.14 | 1330162.22 | 270 | 2021-06-10 | NULL | 2022-03-07 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
867 | Construction of Transformer Platform and Installation of 3 Phase Extension Line from Highway to Transformer in Northern Palawan Provincial Hospital | B2 PEO 300-21-04-033110 | Medical Facilities | MEDICAL FACILITIES | Construction of 3.30 meters x 2.80 meters platform, 0.497 kms 3 phase | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | 20% Development Fund | 1874879.12 | 1874039.44 | 60 | 2021-08-17 |  | 2021-10-16 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
868 | Construction of Transformer Platform and Installation of 3 Phase Extension Line from Highway to Transformer in Araceli/Dumaran District Hospital | B2 PEO 300-21-08-09459 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 1259946 | 1246956.73 | 75 | 2021-09-23 |  | 2021-12-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
869 | Upgrading of Caruray Bridge IV (Aluningan) to RCDG, Caruray | NULL | Transportation Facilities | BRIDGES | 36 m | Caruray, San Vicente, Palawan | San Vicente | PEO | 2021 | 20% Development Fund | 8549250.06 | 8549231.39 | 184 | 2021-10-06 | NULL | 2022-04-08 | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
870 | Concreting of Road Network in Araceli/Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 2594980.91 | 2594977.94 | 120 | 2021-06-21 |  | 2021-10-19 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
871 | Construction of Araceli/Dumaran District Hospital Phase III |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 19053067.47 | 18999413.9 | 270 | 2021-11-10 |  | 2022-08-07 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
872 | Construction of Mortuary Building in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 1135000 | 1128568.14 |  | 2021-07-23 |  | 2021-07-23 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
873 | Construction of Material Recovery Facilities in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 1073000 | 1055395.29 |  | 2021-06-04 |  | 2021-06-04 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
874 | Construction of Doctors's/Nurse's Quarter Building in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 5800000 | 5798531.76 | 240 | 2021-06-07 |  | 2022-02-02 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
875 | Construction of Isolation Building in Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 3740000 | 3739459.65 | 120 | 2021-06-07 |  | 2021-10-05 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
876 | Improvement of Aborlan Medicare Hospital (Canopy, Wash Area, Concreting of Access Road and Drainage Canal) | B2 PEO 300-21-05-04018 | Medical Facilities | MEDICAL FACILITIES | Canopy: 14.60m x 4.60m - Wash Area: 5.90m x 1.8m - Drainage: 0.40m x 0.40m (14units) - Access Roads: 38.50 cu.m - Pavement with ramp: 2.072 cu.m | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | 20% Development Fund | 1048805.07 | 1045012.78 | 90 | 2021-06-29 |  | 2021-09-27 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
877 | Improvement of Aborlan Medicare Hospital (Construction of Waiting Area) |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | 20% Development Fund | 1803941.03 | 1802302.65 | 60 | 2021-11-08 |  | 2022-01-07 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
878 | Construction of Narra Municipal Hospital Perimeter Fence, Phase II | B2 PEO 300-21-05-05585 | Medical Facilities | MEDICAL FACILITIES | 317.80 ln.m - Concrete fence: 106 span | Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 2544672 | 2543632.2 | 90 | 2021-09-15 |  | 2021-12-14 |  |  |  |  | By contract | Suspended | Mazon Engineering and Construction | TIN 273-819-199 | Due to informal settler
879 | Concreting of Parking Area in Old Narra Municipal Hospital | B2 PEO 300-21-05-04019 | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 300000 | 295035.28 | 30 | 2021-06-07 |  | 2021-07-07 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
880 | Concreting of Road Network in Old Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 1200000 | 1199083.16 | 60 | 2021-07-15 |  | 2021-09-13 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
881 | Rehabilitation of Old Narra Municipal Hospital (for Mental Health/PADAC) | B2 PEO 300-21-05-04020 | Medical Facilities | MEDICAL FACILITIES | 42X12.5m Building - 4.15mx1.66m septic tank | Narra Municipal Hospital (for. PADAC) | Narra | PEO | 2021 | 20% Development Fund | 3620000 | 3617003.33 | 120 | 2021-06-29 |  | 2021-10-27 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
882 | Construction of Water Supply System (Calauit Safari Park) | B2 CSP 300-21-00692 | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Calauit Island, Busuanga, Palawan | Busuanga | PEO | 2021 | NULL | 600000 | 598646.31 | 150 | 2021-07-12 | NULL | 2021-12-09 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
883 | Construction of Hospital Building and Facilities at Northern Palawan Provincial Hospital | B2 SB12 PEO20 300-21-02-00393 | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 12 | 30000000 | 24990789.21 |  | 2020-11-16 |  | 2020-11-16 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
884 | Construction of Three (3) Storey Medical Ward Building with Roof Deck for Helipad Phase 2 |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2021 | Supplemental Budget No. 3 | 20000000 | 19994054.3 | 100 | 2021-09-16 |  | 2021-12-25 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
885 | Construction of Three (3) Storey Medical Ward Building with Roof Deck for Helipad Phase 2 |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 1799897.13 | 1799897.13 | 150 | 2021-08-24 |  | 2022-01-21 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
886 | Construction of Oxygen Building in SPPH |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 1799893.15 | 1797226.37 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
887 | Construction of Perimeter Fence in Palawan Technical Vocational School Phase I |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Taytay, Palawan | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 2700000 | 2699000.5 |  | 2021-08-27 |  | 2021-08-27 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
888 | Construction of Cory Park Covered Event Center | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 139901440.31 | 139901440.31 | 333 | 2021-08-28 | NULL | 2022-07-27 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
889 | Vice Governor Francisco F. Ponce de Leon Memorial Hospital: Construction of New Building | B2 SB3 PEO 300-21-07-08628 | Medical Facilities | MEDICAL FACILITIES | Construction limits: Construction of 42 meters x 33.50 meters single storey building with electrical and plumbing system and concreting of 438.34 sq.m road area | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 3 | 25000000 | 24949565.775 | 150 | 2021-10-05 |  | 2022-03-04 | Subject for LD |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
890 | Completion of Three (3) Storey Medical Arts Building Southern Palawan Provincial Hospital, Brooke’s Point, Palawan |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital, Brooke. Palawan | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 11000000 | 10941402.64 | 180 | 2021-10-06 | 1 | 2022-04-04 | Subject for LD |  | 99.22% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
891 | Construction of Three (3) - Storey Medical Arts Building with Roof Deck for Helipad, Phase 1, Aborlan Medicare Hospital | B2 SB3 PEO 300-21-07-08630 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 3 | 20000000 | 19668318.22 | 100 | 2021-09-16 |  | 2021-12-25 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
892 | Completion of Three in One Large Scale Rural Health Unit, Bgy. Panalingaan, Rizal, Palawan |  | Medical Facilities | RHU |  | Bgy. Panalingaan, Rizal, Palawan | Rizal | PEO | 2021 | Supplemental Budget No. 3 | 8000000 | 7383444.79 | 120 | 2021-10-27 |  | 2022-02-24 |  |  |  |  | By contract | For Termination | Nab Construction & Enterprises | TIN 445-503-720
893 | Completion of Three in One Large Scale Rural Health Unit, Bgy. Pancol, Taytay, Palawan | B2 SB3 PEO 300-21-08-09454 | Medical Facilities | RHU |  | Bgy. Pancol, Taytay, Palawan | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 8000000 | 7393850.06 | 120 | 2021-10-27 | 1 | 2022-02-24 | 2022-04-27 |  | 63% |  | By contract | For Termination | Nab Construction & Enterprises | TIN 445-503-720
894 | Expansion of Three in One Large Scale Rural Health Unit, Bgy. Pulot Center, Sofronio Española, Palawan |  | Medical Facilities | RHU |  | Bgy. Pulot Center. Palawan | Sofronio Española | PEO | 2021 | Supplemental Budget No. 3 | 8000000 | 5597498.31 |  | 2021-09-16 |  | 2021-09-16 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
895 | Construction of Northern Palawan Technical Vocational School Phase 2, Taytay, Palawan | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | Northern Palawan Technical Vocational School | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 12000000 | 11994320.26 | NULL | 2021-09-15 | NULL | 2021-09-15 | NULL | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
896 | Construction of Perimeter Fence in Northern Palawan Provincial Hospital, Taytay, Palawan |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospita | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 3398547.28 | 2699000.5 |  | 2021-08-27 |  | 2021-08-27 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
897 | Repair and Rehabilitation of Capitol Building | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 25000000 | 24926014.87 | NULL | 2021-12-28 | NULL | 2021-12-28 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
898 | Construction of Bahay Tuluyan Building, Aborlan Medicare Hospital | B2 SB3 PEO 300-21-07-07263 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 3 | 1800000 | 1797898.92 | 120 | 2021-08-24 |  | 2021-12-22 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
899 | Construction of Bahay Tuluyan Building Annex, Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 1794571 | 1794564.82 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
900 | Centralize Oxygen Plant, Southern Palawan Provincial Hospital | SB3 PEO 300-21-07-08565 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 30000000 | 30000000 |  | 2021-10-25 |  | 2021-10-25 |  |  | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
901 | Centralize Oxygen Plant, Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 30000000 | 30000000 |  | 2021-10-25 |  | 2021-10-25 |  |  | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
902 | Operation of El Nido Sewage & Solid Waste Treatment Plant | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | El Nido | El Nido | PEO | 2021 | Supplemental Budget No. 4 | 20000000 | NULL | 150 | 2021-09-29 | NULL | 2022-02-26 | NULL | NULL | 100% | NULL | By contract | Completed | Hardrock Platinum Development Corporation | TIN 008-625-254 | NULL
903 | Operation of Roxas Water System | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Roxas, Palawan | Roxas | PEO | 2021 | Supplemental Budget No. 4 | 10000000 | 8779866.21 | 150 | 2021-10-21 | NULL | 2022-03-20 | NULL | NULL | 100% | NULL | By contract | Completed | Hardrock Platinum Development Corporation | TIN 008-625-254 | NULL
904 | Supply and Installation of Hospital Billboards and Markers in San Vicente District Hospital, El Nido Community Hospital and Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital and Bataraza District Hospital |  | PEO | 2021 | Supplemental Budget No.12 | 1500000 | [7 empty] | 100% |  | By contract | Completed
905 | Construction of Dietary/Linen Building Phase II |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1819580 | 17929341.27 |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
906 | Construction of Isolation Building |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 3710000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
907 | Construction of Material Recovery Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1073000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
908 | Construction of Mortuary Building |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1135000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
909 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 2029000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
910 | Concreting of Road Networks |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 5089141 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
911 | Construction of Sewage Treatment Plant |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 3100000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
912 | Construction of Doctor's/Nurses Quarter | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 6016000 | 6014518.38 | 160 | 2021-11-29 | 1 |  | 2022-06-07 | 2024-01-26 | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
913 | Construction of Dietary/Linen Building Phase | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3610000 | 3608090.05 | 190 | 2021-11-29 | 1 |  | 2022-07-07 | 2023-12-08 | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
914 | Construction of Isolation Building | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3740000 | 3737758.85 | 120 | 2021-11-29 | 1 |  | 2022-05-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
915 | Construction of Mortuary Building | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1195000 | 1192252.82 | 90 | 2021-11-29 | 1 |  | 2022-04-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
916 | Construction of Powerhouse/Motorpool Building | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 2156000 | 2153353.85 | 90 | 2021-11-29 | 1 |  | 2022-04-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
917 | Construction of Road Network | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 5000000 | 4998207.45 | 90 | 2021-11-29 |  |  |  |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
918 | Construction of Transformer Platform |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 327279 | 325840 | 60 | 2021-12-18 | 1 | 2022-02-16 | 2022-06-15 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
919 | Installation of Fire Protection and Alarm System |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 3300000 | 3281840.63 | 60 | 2021-11-10 |  | 2022-01-09 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
920 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) | B2 SB5 PEO 200-21-09-12140 | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095000 | 50 | 2021-12-15 |  | 2022-02-03 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
921 | Construction of Elevated Water Tank 300 cu.m/ Water Treatment Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 7300000 | 7296574.07 | 180 | 2021-11-29 |  | 2022-05-28 | 2023-01-20 |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
922 | Construction of Perimeter Fence Phase II |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1651945.51 | 1638333.21 | 90 | 2021-12-20 |  | 2022-03-20 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
923 | Improvement of Hospital Landscaping |  | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 2800000 | 2797495.93 |  | 2021-11-12 |  | 2021-11-12 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
924 | Concreting of Road from Highway Junction Leading to NPPH Facilities Phase II | B2 SB5 PEO 300-21-09-12167 | Medical Facilities | MEDICAL FACILITIES | Sta. 0+260 to Sta. 0+370 - 1m shoulder both side | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1063000 | 1061747 | 60 | 2022-05-26 |  | 2022-07-25 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
925 | Construction of Balabac District Hospital, Phase III |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 18025337.58 | 18020270.86 | 120 | 2021-11-29 | 1 | 2022-03-29 | 2022-05-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
926 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095098.48 | 45 | 2021-12-01 |  | 2022-01-15 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
927 | Construction of Material Recovery Facilities |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1051421.68 | 1050283.84 | 60 | 2021-11-15 | 1 | 2022-01-14 | 2022-03-15 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
928 | Construction of Sewage Treatment Plant | B2 SB5 PEO 300-21-09-12153 | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3100000 | 3094987.66 | 60 | 2021-12-07 |  | 2022-02-05 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
929 | Construction of Perimeter Fence Phase I |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3400000 | 3399086.45 | 120 | 2021-11-15 | 1 | 2022-03-15 | 2022-05-14 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
930 | Improvement of Hospital Landscaping | B2 SB5 PEO 300-21-09 | Medical Facilities | MEDICAL FACILITIES | Modern Tropical Garden | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 2800000 | 2799499.88 | 60 | 2021-11-22 | 1 | 2022-01-21 | 2022-06-24 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
931 | Concreting of Road Network Phase II | B2 SB5 PEO 300-21-09-12169 | Transportation Facilities | ROAD | Roads: PCCP (Road Network): 110m(l) x 6m(w) x 0.20m(t) | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 2200000 | 2199787.14 | 60 | 2021-11-22 | 1 | 2022-01-21 | 2022-07-21 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
932 | Installation of 3 Phase Extension Line from Highway to Transformer |  | Medical Facilities | MEDICAL FACILITIES |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1072830.6 | 1067974.94 | 20 | 2021-12-07 |  | 2021-12-27 |  | 2023-06-21 | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
933 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095000 |  | 2021-12-14 |  | 2021-12-14 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
934 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) | B2 SB5 PEO 300-21-09-12136 | Medical Facilities | MEDICAL FACILITIES | Installation: Communication system intercom: Intercom station with Monitor=4 pcs; intercom handset=35 pcs; UPS=1 PC - Securing Monitoring Device (CCTV): 16 channels DVR=1 pc; CCTV Camera=16 pcs; 32'' LED Monitor=1 pc; UPS=1 pc - Communication System (PABX): Telephone Set=30 sets Main control Unit= 1 set; AVR=1 set | Cuyo District Hospital | Cuyo | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095000 | 45 | 2021-12-17 |  | 2022-01-31 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
935 | Completion of Perimeter Fence |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | Supplemental Budget No. 5 | 909000 | 908006.88 | 60 | 2021-10-27 |  | 2021-12-26 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
936 | Improvement of Hospital Landscaping (Facilities Area) Narra Municipal Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2021 | Supplemental Budget No. 5 | 1000000 | 999817.5 |  | 2021-10-27 |  | 2021-10-27 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
937 | Construction of Perimeter Fence Phase I |  | Medical Facilities | MEDICAL FACILITIES |  | Sofronio Española Rural Health Unit | Sofronio Española | PEO | 2021 | Supplemental Budget No. 5 | 804000 | 803469.32 | 60 | 2021-11-03 |  | 2022-01-02 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
938 | Concreting of Road with Parking Area |  | Medical Facilities | MEDICAL FACILITIES |  | Sofronio Española Rural Health Unit | Sofronio Española | PEO | 2021 | Supplemental Budget No. 5 | 1817270 | 1814868.88 |  | 2021-11-12 |  | 2021-11-12 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
939 | Improvement of Landscaping | NULL | Other Facilities | PGP FACILITIES | NULL | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 900000 | 899113.23 | NULL | 2021-10-27 | NULL | 2021-10-27 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
940 | Concreting of Road Network with Parking Area (Molecular Diagnostic Lab) | NULL | Other Facilities | PGP FACILITIES | NULL | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 5500000 | 5479831.8 | 90 | 2021-11-15 | NULL | 2022-02-13 | NULL | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
941 | Extension of 3-Phase Line from Irawan Motorpool to Molecular Diagnostic Laboratory (Covid 19 Testing Center) | B2 SB5 PEO 300-21-09-12155 | Other Facilities | PGP FACILITIES | NULL | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 1550000 | 1547958.44 | NULL | 2021-11-30 | NULL | 2021-11-30 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
942 | Installation of 25 Airconditioning Units | NULL | Other Facilities | PGP FACILITIES | NULL | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 713259.63 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
943 | Improvement of Araceli/Dumaran District Hospital (Installation of 25 Units Airconditioning Units) |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 5 | 1641935 | [7 empty] | 100% |  | By contract | Completed
944 | Concreting of Highway Junction to Barangay Poblacion (Intermittent Section) with Drainage | NULL | Transportation Facilities | ROAD | NULL | Salvacion, Roxas, Palawan | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 8000000 | 7990469.35 | NULL | 2021-12-01 | NULL | #VALUE! | NULL | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
945 | El Nido Sewage and Solid Waste Treatment Plant | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 3370421 | 3366360.33 | 90 | 2021-12-28 | NULL | 2022-03-28 | NULL | NULL | 100% | NULL | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868 | NULL
946 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Bgy. Bato | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-27 | NULL | 2022-02-10 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
947 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Bgy. New Guinlo | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
948 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Bgy. Old Guinlo | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
949 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Pancol | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
950 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Malcampo | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
951 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Mendoza | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
952 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Near Barbacan (Retac) | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
953 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Rizal | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
954 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Salvacion | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
955 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | San Isidro | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
956 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | San Jose | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
957 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Tagumpay | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
958 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Nicanor Zabala | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
959 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Corong-Corong (Barangay 4) | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
960 | Improvement of Covered Court/Evacuation Center (Flooring only) | NULL | Other Infrastructure | COVERED COURT | NULL | Mabini | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
961 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Manlag | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
962 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | San Fernando | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
963 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | Villa Paz | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | NULL | NULL | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
964 | Improvement of Covered Court/Evacuation Center (Flooring only) | NULL | Other Infrastructure | COVERED COURT | NULL | Aberawan | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
965 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure | COVERED COURT | NULL | San Miguel | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 | NULL | 2022-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
966 | Completion of 2-Storey Barangay Hall of Ipilan | NULL | Other Facilities | OTHER FACILITIES | NULL | Bgy. Ipilan | Brooke's Point | PEO | 2021 | Supplemental Budget No. 5 | 3323150.34 | 3313181.35 | 150 | 2021-12-27 | NULL | 2022-05-26 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
967 | Repair of Capitol Building and Provision of Door and Window Grills | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 4223153.86 | 4220152.71 | 180 | 2021-12-27 | NULL | 2022-06-25 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
968 | Upgrading of Omao Bridge | NULL | Transportation Facilities | BRIDGES | 21 m | Bgy. Bagong Bayan, El Nido,Palawan | El Nido | PEO | 2021 | Supplemental Budget No. 6 | 9000000 | 8999582.12 | 184 | 2021-12-10 | NULL | 2022-06-12 | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
969 | Construction of Powerhouse/Motorpool Building, NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 2156000 | 2126703.18 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-04 |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
970 | Construction of Doctor's/Nurses Quarter, NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | MEDICAL FACILITIES | Net length: 31m x 24m (744 sq.m) One Storey Building | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 6016000 | 6012640.25 | 80 | 2021-12-14 |  | 2022-03-04 | Subject for LD |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
971 | Construction of Dietary/Linen Building, NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 3610000 | 3596228.53 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-03 | 2023-08-10 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
972 | Construction of Isolation Building , NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 3740000 | 3730769.95 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-03 | 2023-06-11 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
973 | Construction of Material Recovery Facilities , NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 1128000 | 1087724.2 | 30 | 2021-12-14 |  | 2022-01-13 | 2022-09-03 | 2023-07-15 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
974 | Construction of Mortuary Building , NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 1195000 | 1190355.14 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-03 | 2023-08-10 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
975 | Centralize Oxygen Plant |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2021 | Supplemental Budget No. 6 | 16000000 | 15691385 |  | 2022-06-28 |  | 2022-06-28 |  |  | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
976 | Construction of Linapacan Water Supply Systems | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | Linapacan | PEO | 2021 | Supplemental Budget No. 8 | 265510000 | 262401315.21 | 510 | 2021-12-29 | NULL | 2023-05-23 | NULL | NULL | NULL | NULL | By contract | On going | Ivy Michelle Construction and Trading | TIN 009-492-339 | PEEDO Validate
977 | Installations of 3 Lines 36" Diameter RCPC with Headwall, Pulot Interior | B2 GF PEO 22-02-063 | Other Infrastructure | DRAINAGE | NULL | Provincial Road Pulot Interior | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 329561.05 | 30 | 2022-03-16 | NULL | 2022-04-15 | 2022-06-01 | NULL | 100% | NULL | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000 | NULL
978 | Installations of 15 Lines 36" Diameter RCPC with Headwall, Provincial Road Labog, Naltep | B2 GF PEO 22-02-055 | Other Infrastructure | DRAINAGE | NULL | Provincial Road Labog, Naltap | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 1650000 | 1542671.28 | 90 | 2022-05-11 | NULL | 2022-08-09 | NULL | NULL | NULL | NULL | By contract | Notice to Terminate | R. Narrazid Trading and Construction | TIN 330-975-725 | Waiting for Contractor to received the Notice to Terminate: Unresponsive Contractor
979 | Construction of 3-Barrel Box Culvert with Slope Protection, Provincial Road Isaub | B2 GF PEO 22-02-051 | Other Infrastructure | DRAINAGE | NULL | Bgy. Isaub | Aborlan | PEO | 2021 | Supplemental Budget No. 9 | 4000000 | 3997972.29 | 90 | 2022-05-11 | NULL | 2022-08-09 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
980 | Installations of 3 Lines 36" Diameter RCPC with Headwall, Bgy. Aramaywan | B2 GF PEO 22-02-060 | Other Infrastructure | DRAINAGE | NULL | Bgy. Aramaywan | Quezon | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 328979.73 | 30 | 2022-03-21 | NULL | 2022-04-20 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
981 | Installations of 3 Lines 36" Diameter RCPC with Headwall, Bgy. Panitian | B2 GF PEO 22-02-059 | Other Infrastructure | DRAINAGE | NULL | Bgy. Panitian | Quezon | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 328979.73 | 30 | 2022-03-21 | NULL | 2022-04-20 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
982 | Installations of 7 Lines 36" Diameter RCPC with Headwall, Provincial Road Itangil-Sta. Teresita Road | B2 GF PEO 22-02-064 | Other Infrastructure | DRAINAGE | Construction Limits:Seven (7) 1-L 36" Diameter RCPC x 8.00 Length with Headwall bothsides in different stations | Itangil-Sta.Teresita | Dumaran | PEO | 2021 | Supplemental Budget No. 9 | 730000 | 724491.42 | 45 | 2022-03-15 | NULL | 2022-04-29 | Subject for LD | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
983 | Installation of 2 Lines 36" Diameter RCPC with Headwall, Abaroan FMR | B2 GF PEO 22-02-062 | Other Infrastructure | DRAINAGE | NULL | Abaroan FMR | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 220000 | 219907.52 | 30 | 2022-03-21 | NULL | 2022-04-20 | 2022-03-21 | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
984 | Installation of 3 Lines 36" Diameter RCPC with Headwall,Dumarao FMR | B2 GF PEO 22-02-066 | Other Infrastructure | DRAINAGE | NULL | Dumarao FMR, Roxas | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 324951.69 | 30 | 2022-03-15 | 1 | 2022-04-14 | 2023-01-05 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
985 | Installation of 3 Lines 36" Diameter RCPC with Headwall, Nicanor Zabala | B2 GF PEO 22-02-061 | Other Infrastructure | DRAINAGE | NULL | Nicanor Zabala, Roxas | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 325698.57 | 30 | 2022-03-15 | 1 | 2022-04-14 | 2022-06-24 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
986 | Installation of 2 Lines 36" Diameter RCPC with Headwall, Malaking Patag-Canimango Road | B2 GF PEO 22-02-058 | Other Infrastructure | DRAINAGE | NULL | Provincial Road Malaking Patag-Canimango Road | Culion | PEO | 2021 | Supplemental Budget No. 9 | 220000 | 214948.46 | 30 | 2022-03-15 | NULL | 2022-04-14 | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
987 | Installation of 2 Lines 36" Diameter RCPC with Headwall,Magara-Caruray Road | B2 GF PEO 22-02-065 | Other Infrastructure | DRAINAGE | NULL | Magara-Caruray Road | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 220000 | 215030.87 | 30 | 2022-03-15 | 1 | 2022-04-14 | 2022-06-24 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
988 | Construction of One (1) Barrel Box Culvert Sitio Marimek, Bgy. Aramaywan | B2 GF PEO 22-02-054 | Other Infrastructure | DRAINAGE | NULL | Sitio Marimek, Bgy. Aramaywan | Quezon | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1777488.54 | 90 | 2022-05-11 | NULL | 2022-08-09 | NULL | NULL | NULL | NULL | By contract | For Termination | R. Narrazid Trading and Construction | TIN 330-975-725 | For Legal Endorsement
989 | Construction of One (1) Barrel Box Culvert Sitio Diapla, Bgy. Teneguiban, El Nido | B2 GF PEO 22-02-050 | Other Infrastructure | DRAINAGE | NULL | Bgy. Teneguiban, El Nido | El Nido | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1992229.85 | 90 | 2022-05-11 | NULL | 2022-08-09 | NULL | NULL | 100% | NULL | By contract | Completed | F.F Galang Construction | TIN 188-519-198 | NULL
990 | Construction of PWD Ramp, Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 4300000 | [10 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 3 - 2022
991 | Construction of Bahay Tuluyan |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1996599.15 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
992 | Construction of Perimeter Fence Phase IV | B2 GF PEO 22-02-053 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 1500000 | 1494748.2 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
993 | Improvement of Landscaping for Temporary and Treatment Monitoring Facilities | B2 GF PEO 22-02-079 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 370000 | 369256.78 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
994 | Improvement of Landscaping for Three Storey Medical Arts Building, Aborlan Medicare Hospital | B2 GF PEO 22-03-084 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 329209.44 | 60 | 2022-07-26 |  | 2022-09-24 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
995 | Construction of Oxygen Building for Aborlan Medicare Hospital | B2 GF PEO 22-02-057 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 9 | 1800000 | 1795559.6 | 150 | 2022-05-11 |  | 2022-10-08 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
996 | Improvement of Landscaping for Sofronio Espanola District Hospital | B2 GF PEO 22-02-080 | Medical Facilities | MEDICAL FACILITIES |  | Sofronio Espanola District Hospital | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 900000 | 899029.67 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
997 | Concreting of Road Network Ph 2, Araceli-Dumaran District Hospital | B2 GF PEO 22-02-051 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 9 | 2110000 | 2108233.38 | 120 | 2022-05-11 |  | 2022-09-08 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
998 | Concreting Of Cataban-Liminangcong Road (STA. 9+700 TO Sta. 9+987, Sta. 10+550 to Sta. 11+100 and Sta. 18+400 to Sta. 19+000) | B2 GF PEO 22-02-048 | Transportation Facilities | ROAD | NULL | Cataban-Liminangcong | Taytay | PEO | 2021 | Supplemental Budget No. 9 | 10000000 | 9374893.39 | 90 | 2022-07-19 | 1 | 2022-10-17 | 2022-11-16 | NULL | NULL | NULL | By contract | For Termination | L.M John Construction Supplies Trading | TIN 422-936-808 | NULL
999 | Construction of Three (3) Storey Medical Arts Building with Roofdeck for Helipad Phase I - Coron District Hospital | B2 GF PEO 22-02-046 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2021 | Supplemental Budget No. 9 | 18300000 | 18299211.23 | 180 | 2022-07-19 | 1 | 2023-01-15 | 2023-09-30 |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
1000 | Operation of El Nido Sewage Treatment Plant | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | El Nido Community Hospital | El Nido | PEO | 2021 | Supplemental Budget No. 9 | 1496227 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | On going | NULL | NULL | PEEDO Validate
1001 | Construction of Molecular Laboratory and Swabbing Facilities - Northern Palawan Provincial Hospital | B2 GF PEO 22-02-068 | Medical Facilities | MEDICAL FACILITIES |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 9 | 6000000 | 5996626.6 | 260 | 2022-05-27 | 1 | 2023-02-11 | 2022-02-24 |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1002 | Extension of Four Bays at the Existing Motorpool Building, Irawan | B2 GF PEO 22-02-067 | Other Facilities | PGP FACILITIES | NULL | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1976569.56 | 90 | 2022-05-19 | NULL | 2022-08-17 | 2022-10-31 | NULL | 100% | NULL | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662 | NULL
1003 | Sandoval Water System Staff House and Pipeline Appurtenance | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL |  | Roxas | PEO | 2021 | NULL | 1235992.9 | 1235992.9 | NULL | 2021-04-19 | NULL | 2021-04-19 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
1004 | Concreting Of Farm To Market Road (Sitio Tagpirara II From National Highway To Sea Shore) | NULL | Transportation Facilities | ROAD | NULL | Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 16000000 | 15998583.16 | 60 | 2022-01-14 | NULL | 2022-03-15 | 2022-08-31 | NULL | 100% | NULL | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708 | NULL
1005 | Water System At Sitio Kelwe | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Sitio Kelwe Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 992979.84 | 90 | 2022-01-25 | NULL | 2022-04-25 | 2022-06-10 | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
1006 | Renovation Of Barangay Hall Two (2) Storey Building | NULL | Other Facilities | OTHER FACILITIES | NULL | Sitio Proper, Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 3000000 | 2999477.03 | 150 | 2022-01-14 | NULL | 2022-06-13 | 2022-09-02 | NULL | 100% | NULL | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708 | NULL
1007 | Construction Of Level II Potable Water Supply 50cu.M Elevated Water Tank, 2km (PPE) Pipe Distribution Line 20 Communal Faucets | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 4000000 | 3998421.34 | 90 | 2022-04-25 | NULL | 2022-07-24 | 2022-06-10 | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
1008 | Construction Of (3) Units Multi-Purpose Drying Pavement | NULL | Other Facilities | MULITI-PURPOSE | NULL | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1500000 | 1499400.28 | 75 | 2022-01-14 | NULL | 2022-03-30 | 2022-05-15 | NULL | 100% | NULL | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708 | NULL
1009 | Construction Of One (1) Storey School Building | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Classroom School Building | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2000000 | 1999812.49 | 90 | 2022-01-14 | NULL | 2022-04-14 | 2022-07-04 | NULL | 100% | NULL | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708 | NULL
1010 | Construction Of Health Care Center With Perimeter Fence |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2500000 | 2498317.07 | 120 | 2022-01-14 |  | 2022-05-14 | 2022-06-29 |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1011 | Upgrading & Improvement Of Barangay Road | NULL | Transportation Facilities | ROAD | NULL | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 10000000 | 9999985.71 | 90 | 2022-01-14 | NULL | 2022-04-14 | NULL | NULL | 100% | NULL | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708 | NULL
1012 | Construction Of Health Center Sitio Cabangaan And Proper Two (2) Units Health Center |  | Medical Facilities | MEDICAL FACILITIES |  | Sitio Cabangaan And Sitio Proper, Bgy. Samariñana, Brooke's Point | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 4000000 | 3993206 | 120 | 2022-01-15 |  | 2022-05-15 | 2022-08-03 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1013 | Construction Of (3) Units Multi-Purpose Drying Pavement For Sitio Cabangaan And Proper | NULL | Other Facilities | MULITI-PURPOSE | NULL | Sitio Cabangaan And Sitio Proper, Bgy.Samarinaña, Brooke's Point | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1500000 | 1498504.19 | NULL | 2022-01-15 | NULL | 2022-01-15 | NULL | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1014 | Spring Development In Sitio Cabangaan | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Sitio Cabangaan, Bgy. Samariñana, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2000000 | 1993002.18 | 90 | 2022-01-25 | NULL | 2022-04-25 | 2022-06-10 | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1015 | Concreting Of Access Road Proper 1 And Proper 2 | NULL | Transportation Facilities | ROAD | NULL | Sitio Proper I And Sitio Proper, Bgy. Samarinaña, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 12500000 | 12498074.57 | 90 | 2022-01-14 | NULL | 2022-04-14 | 2022-12-17 | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1016 | Concreting Of Farm To Market Road From National Highway To Sitio Proper | NULL | Transportation Facilities | ROAD | NULL | National Highway To Sitio Proper, Brgy, Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 16000000 | 15998025.86 | 90 | 2022-01-14 | NULL | 2022-04-14 | 2022-08-05 | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1017 | Two (2) Unit Multi-Purpose Drying Pavement at Sitio Proper and Sitio Rabok (15mx10m) Each Project | NULL | Other Facilities | MULITI-PURPOSE | NULL | Sitio Proper And Sitio Rabok, Bgy. Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 498854.05 | 45 | 2022-01-14 | NULL | 2022-02-28 | NULL | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1018 | One (1) School Building Sitio Proper | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Classroom School Building | Sitio Proper, Bgy. Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 998340.77 | 60 | 2022-01-14 | NULL | 2022-03-15 | 2022-05-25 | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1019 | One (1) Unit Multi-Purpose Drying Pavement at Sitio Tagpinasao (20mx30m) | NULL | Other Facilities | MULITI-PURPOSE | NULL | Sitio Tagpinasao, Bgry. Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 496683.42 | 45 | 2022-01-14 | NULL | 2022-02-28 | 2022-06-10 | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1020 | Rehabilitation Of Multi-Purpose Hall At Sitio Proper | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Proper,Brgy Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 496052.8 | 60 | 2022-01-14 | NULL | 2022-03-15 | NULL | NULL | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1021 | Rural Electrification Project From Purok Pag-Asa (Capalan) To Purok Masigla (Kaibulusan) | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Purok Pag-Asa (Capalan) To Purok Masigla (Kaibulusan) | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 6000000 | 5999169.55 | 90 | 2021-12-31 | NULL | 2022-03-31 | 2022-12-22 | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1022 | Rural Electrification Project From National Highway, Sitio Arasan To Sitio Tara-Tara Both In Purok Magtulungan | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Sitio Arasan To Sitio Tara-Tara Both In Purok Magtulungan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999419.71 | 30 | 2021-12-31 | NULL | 2022-01-30 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1023 | Concreting Of Farm To Market Road (FMR) From National Highway To Purok Matiyaga (Malatgao Falls) | NULL | Transportation Facilities | ROAD | NULL | Magara | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 6500000 | 5671259.42 | 60 | 2022-03-01 | NULL | 2022-04-30 | 2022-05-31 | NULL | 100% | NULL | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958 | NULL
1024 | Concreting Of Farm To Market Road (Fmr) From Junction Bagong Silang Elementary School To Sitio Upper Iraan (Interior Iraan) | NULL | Transportation Facilities | ROAD | NULL | Magara | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 5500000 | 4784494.05 | 60 | 2022-03-01 | NULL | 2022-04-30 | 2022-05-31 | NULL | 100% | NULL | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958 | NULL
1025 | Rural Electrification Project From National Highway To Purok Rancheria | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Magara | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999587.99 | 30 | 2021-12-31 | NULL | 2022-01-30 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1026 | Concreting Of Farm To Market Road From Barangay Proper/Poblacion To Sitio Linapawan, Barangay Abaroan | NULL | Transportation Facilities | ROAD | NULL | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 13500000 | 13496644.22 | NULL | 2021-12-31 | NULL | #VALUE! | 2022-05-16 | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
1027 | Rural Electrification Project From Purok Mabuhay To Purok Maagap, Barangay Abaroan | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999516.3 | 45 | 2021-12-31 | NULL | 2022-02-14 | 2022-07-07 | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1028 | Rural Electrification Project From Sitio Ibangan, Purok Maunlad To Sitio Linapawan, Purok Nagkakaisa, Barangay Abaroan | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 3000000 | 2999620.02 | 60 | 2021-12-31 | NULL | 2022-03-01 | 2022-08-06 | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1029 | Construction Of Birthing Clinic With Complete Facilities And Equipment In Purok Bagong Silang (Barangay Proper), Barangay Abaroan |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2000000 | 1994628.3 | 120 | 2021-12-31 |  | 2022-04-30 | 2022-12-09 | 2022-12-26 | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1030 | Water System For Sitio Matalangaw | NULL | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | Sitio Matalangaw | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 499354.96 | 30 | 2022-04-25 | NULL | 2022-05-25 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
1031 | Concreting Of Farm To Market Road From National Highway (Daval Road) Going, Bgy. Poblacion To Purok Ilian-Ilian (Portion Only) | NULL | Transportation Facilities | ROAD | NULL | NULL | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 12500000 | 12496581.46 | 90 | 2022-04-14 | NULL | 2022-07-13 | 2022-07-29 | NULL | 100% | NULL | By contract | Completed | Bicol Goldrock Construction Corporation | TIN 006-098-920 | NULL
1032 | Rural Electrification Project From Sitio Ilian-Ilian | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Dumarao | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999382.43 | 30 | 2021-12-31 | NULL | 2022-01-30 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1033 | Rural Electrification Project At Sitio Lower Subingao | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Sitio Lower Subingao | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999442.73 | 30 | 2021-12-31 | NULL | 2022-01-30 | NULL | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1034 | Rural Electrification Project From Sitio Itabiak To Sitio Salvador | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Sitio Itabiak To Sitio Salvador | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 4000000 | 3999529.88 | 75 | 2021-12-31 | NULL | 2022-03-16 | 2022-11-20 | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1035 | Construction Of 1-Storey 1-Cl School Building At Dumarao National High School | NULL | Educational Facilities | SCHOOL FACILITIES | 1 Classroom School Building | NULL | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1500000 | 1496520.39 | 60 | 2022-04-14 | NULL | 2022-06-13 | 2022-07-10 | NULL | 100% | NULL | By contract | Completed | Bicol Goldrock Construction Corporation | TIN 006-098-920 | NULL
1036 | Road Concreting Of 820 Meters From Purok Bagong Silang To Purok Ugnayan | B2 TF DUE TO NGAS ELCAC 2021 21-050 | Transportation Facilities | ROAD | NULL | Villa Fria (Kemdeng) | San Vicente | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 16400000 | 16393004.74 | 90 | 2022-04-14 | NULL | 2022-07-13 | 2022-07-29 | NULL | NULL | NULL | By contract | Terminated | Bicol Goldrock Construction Corporation | TIN 006-098-920 | Termination for convenience: Transfer of location
1037 | Road Concreting Of 180 Meters At Labrador St. | B2 TF DUE TO NGAS ELCAC 2021 21-050 | Transportation Facilities | ROAD | NULL | Villa Fria (Kemdeng) | San Vicente | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 3600000 | 3596835.09 | 90 | 2022-01-14 | NULL | 2022-04-14 | 2022-07-29 | NULL | 100% | NULL | By contract | Completed | Bicol Goldrock Construction Corporation | TIN 006-098-920 | NULL
1038 | PR of Materials for the Repair and Maintenance of PGP Hospital Roofing |  | Medical Facilities | MEDICAL FACILITIES |  | Dr. Jose Rizal District Hospital, SPPH, Narra Municipal Hospital, Aborlan Medicare Hospital, Roxas Medicare Hospital, San Vicente District Hospital, El Nido Community Hospital |  | PEO | 2021 | MOOE | 2098492.48 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1039 | Repair/Renovation of Registry of Deeds | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2021 | MOOE | 1500000 | 1498806.5 | NULL | 2021-08-24 | NULL | 2021-08-24 | NULL | NULL | 100% | NULL | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564 | NULL
1040 | Rehabilitation and Repair of PGP Property Perimeter Fence | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Irawan, PPC | Puerto Princesa City | PEO | 2021 | MOOE | 1938402 | 1929390.23 | NULL | 2021-09-08 | NULL | 2021-09-08 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1041 | Provincial Engineering Office Renovation (Quality Division) | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2021 | MOOE | 146100.94 | 145276 | NULL | 2021-08-10 | NULL | 2021-08-10 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1042 | Repair/Renovation of Aborlan Medicare Hospital (Ceiling Works) | B2 PEO 200-21-06-07177 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | MOOE | 968141.15 | 955202.03 | 90 | 2021-08-10 |  | 2021-11-08 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1043 | Repair/Renovation of Southern Palawan Provincial Hospital (Ceiling and Tiles) |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | MOOE | 703320.41 | 698373.4 |  | 2021-08-10 |  | 2021-08-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1044 | Repair/Renovation of Roxas Medicare Hospital (Ceiling and Tiles) |  | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2021 | MOOE | 1334346.07 | 1332958.61 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1045 | Repair/Renovation of Bataraza Distirct Hospital (Ceiling) |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | MOOE | 353552.07 | 352508 |  | 2021-08-10 |  | 2021-08-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1046 | Repair/Renovation Dr. Jose Rizal District Hospital (Ceiling) |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2021 | MOOE | 916625.48 | 942662.45 |  | 2021-08-13 |  | 2021-08-13 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1047 | Repair/Renovation of PGP Facilities (DILG-SGLG Compliance) | NULL | Other Facilities | PGP FACILITIES | NULL | NULL | Puerto Princesa City | PEO | 2021 | MOOE | 770441 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
1048 | Repair and Maintenance of Power Take Off of Bisucay Power Plant | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Bisucay | Cuyo | PEO | 2021 | MOOE | 70000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
1049 | Supply and Installation of Hospital Billboards and Markers |  | Medical Facilities | MEDICAL FACILITIES |  |  |  | PEO | 2021 | MOOE | 1500000 | [7 empty] | 100% |  | By contract | Completed | Megaprint
1050 | Construction of Molecular Laboratory and Swabbing Facilities, Coron District Hospital | B2 TF DUE TO NGAS DOH 21-007 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2021 | DOH Fund | 5000000 | 4989044.9 | 230 | 2021-06-28 |  | 2022-02-13 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1051 | Construction of Molecular Laboratory and Swabbing Facilities, El Nido Community Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2021 | DOH Fund | 6000000 | 5999488.45 | 260 | 2021-06-29 |  | 2022-03-16 |  |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
1052 | Construction of Temporary and Treatment and Monitoring Facilities, Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | DOH Fund | 10000000 | 9896366.18 | 180 | 2021-06-30 |  | 2021-12-27 |  |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1053 | Medical Equipment for Molecular Laboratory and Swabbing Facilities, Coron District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2021 | DOH Fund | 5000000 | [7 empty] | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1054 | Medical Equipment for Molecular Laboratory and Swabbing Facilities, El Nido Community Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2021 | DOH Fund | 5000000 | [7 empty] | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
1055 | Construction of Sheltered Port Phase II Bgy. Pag-asa, Municipality of Kalayaan, Palawan | B2 TF DUE TO NGAS - DOTR 21- 006 | Ports and Airports | PORTS | NULL | Bgy. Pag-asa, Municipality of Kalayaan, Palawan | Kalayaan | PEO | 2021 | Trust Fund - DOTr | 220673124.57 | 220569081.3 | 390 | 2021-06-11 | NULL | 2022-07-06 | 2023-04-11 | NULL | 100% | NULL | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
1056 | Construction of El Nido Sewage and Solid Waste Treatment Plant Project Phase 2-2 | B2 SB3 PEO 300-21-07-08567 | Artesian Wells, Reservoir, Pumping and Conduits | WATER SYSTEM | NULL | NULL | El Nido | PEO | 2021 | Supplemental Budget No. 3 | 72000000 | 71950000 | NULL | 2021-09-22 | NULL | 2021-09-22 | NULL | NULL | 100% | NULL | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339 | NULL
1057 | Concreting of Antonio-Maragok-Tanatanaen Road (Intermittent Section) | B2 GF PEO 22-01-001 | Transportation Facilities | ROAD | Section No. 1: 1000 ln.m - Section No. 2: 240ln.m - Section No. 3: 960 ln.m - Total Length: 2.2 km | Dumaran | Dumaran | PEO | 2022 | 20% Development Fund | 23100000 | 19148894.25 | 120 | 2022-05-12 | 3 | 2022-09-09 | 2023-12-03 | NULL | 86% | NULL | By contract | No movement | Leon John Great Builders Construction Corp. | TIN 009-924-271 | No activity on site: Subject for LD
1058 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-037 | Other Infrastructure | DRAINAGE | NULL | Sto. Tomas, Dumaran | Dumaran | PEO | 2022 | 20% Development Fund | 3700000 | 3690707.21 | 120 | 2022-05-16 | 1 | 2022-09-13 | 2022-11-12 | 2023-05-11 | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
1059 | Upgrading of Caruray Bailey Bridge II (Pag-Asa 2) to RCDG | B2 GF PEO 22-01-002 | Transportation Facilities | BRIDGES | 25 m | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 9000000 | 7554570.43 | 184 | 2022-07-01 | 1 | 2023-01-01 | 2023-08-31 | 2024-03-18 | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
1060 | Upgrading of Caruray New Site Bailey Bridge to RCDG | B2 GF PEO 22-01-014 | Transportation Facilities | BRIDGES | 32 m | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 18150000 | 15408362.58 | 197 | 2022-07-01 | 1 | 2023-01-14 | 2023-04-30 | 2024-07-12 | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
1061 | Concreting of Magara-Caruray Road (Intermittent Section) | B2 GF PEO 22-01-003 | Transportation Facilities | ROAD | 2.202 km | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 23100000 | 18281985.6 | 120 | 2022-05-20 | 1 | 2022-09-17 | 2023-04-03 | NULL | 86.2% | NULL | By contract | Suspended | A.P. Consebido Construction & Trading | TIN 931-421-496 | Limited supply of aggregates
1062 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-029 | Other Infrastructure | DRAINAGE | NULL | New Agutaya ,San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 3700000 | 3647836.57 | 120 | 2022-03-17 | 1 | 2022-07-15 | 2023-05-29 | NULL | 100% | NULL | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271 | NULL
1063 | Construction of Hanging Bridge | B2 GF PEO 22-01-004 | Transportation Facilities | BRIDGES | 36 m | New Agutaya ,San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 6000000 | 5924964.76 | 90 | 2022-03-17 | 1 | 2022-06-15 | 2023-05-26 | NULL | 100% | NULL | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271 | NULL
1064 | Construction of Hanging Bridge | B2 GF PEO 22-08-141 | Transportation Facilities | BRIDGES | 36 m | Alimanguan, San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 4500000 | 4002540.76 | 90 | 2022-11-21 | 1 | 2023-02-19 | 2023-06-26 | NULL | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1065 | Construction of Three (3) Barrel Box Culvert - Construction of Spillway | NULL | Other Infrastructure | DRAINAGE | NULL | Alimanguan, San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 6145521.47 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1066 | Construction of 3-Barrel Box Culvert | B2 GF PEO 22-01-039 | Other Infrastructure | DRAINAGE | NULL | New Agutaya ,San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 4500000 | 4449952.28 | 90 | 2022-03-17 | 1 | 2022-06-15 | 2022-11-25 | NULL | 100% | NULL | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271 | NULL
1067 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-038 | Other Infrastructure | DRAINAGE | NULL | San Isidro, San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 3700000 | 3325959.99 | 120 | 2022-07-18 | 1 | 2022-11-15 | 2023-07-14 | NULL | 100% | NULL | By contract | Completed | Furosam Incorporated | TIN 009-062-221 | NULL
1068 | Concreting of Benga - Calapa Road (Intermittent Section) | B2 GF PEO 22-01-026 | Transportation Facilities | ROAD | 1.0 km | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 35805000 | 35698490.36 | 150 | 2022-05-12 | 1 | 2022-10-09 | 2023-01-22 | NULL | 90% | NULL | By contract | Suspended | Leon John Great Builders Construction Corp. | TIN 009-924-271 | Limited supply of aggregates
1069 | Construction of New Guinlo RCDG Bridge | B2 GF PEO 22-01-027 | Transportation Facilities | BRIDGES | 30 m | Bgy. New Guinlo, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 30000000 | 29971024.82 | 180 | 2022-03-10 | NULL | 2022-09-06 | 2022-12-05 | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
1070 | Upgrading of Talugon Bailey Bridge I to RCDG | B2 GF PEO 22-01-005 | Transportation Facilities | BRIDGES | 15 m | Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 9000000 | 7638561.98 | 184 | 2022-07-01 | 1 | 2023-01-01 | 2023-04-06 | NULL | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
1071 | Upgrading of Talugon Bailey Bridge II to RCDG | B2 GF PEO 22-01-023 | Transportation Facilities | BRIDGES | 15 m | Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 7500000 | 6366515.79 | 182 | 2022-07-01 | 1 | 2022-12-30 | 2023-04-04 | 2023-09-26 | 100% | NULL | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647 | NULL
1072 | Upgrading of Talugon Bailey Bridge III to RCDG | B2 GF PEO 22-02-047 | Transportation Facilities | BRIDGES | 15 m | Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 7500000 | 7499774.11 | 182 | 2022-12-09 | 1 | 2023-06-09 | 2023-10-17 | NULL | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1073 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-036 | Other Infrastructure | DRAINAGE | NULL | Sto. Talugon, Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 3700000 | 3690706.71 | 120 | 2022-05-16 | NULL | 2022-09-13 | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
1074 | Upgrading of Orol Bailey Bridge I to RCDG | B2 GF PEO 22-01-006 | Transportation Facilities | BRIDGES | 21 m | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 7500000 | 6044191.6 | 182 | 2022-05-11 | 1 | 2022-11-09 | Subject for LD | NULL | 98% | NULL | By contract | On going | Louiese Trading & Construction | TIN 940-685-564 | NULL
1075 | Upgrading of Orol Bailey Bridge II to RCDG | B2 GF PEO 22-01-008 | Transportation Facilities | BRIDGES | 21 m | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 7500000 | 6044191.6 | 182 | 2022-05-11 | 1 | 2022-11-09 | Subject for LD | NULL | 97% | NULL | By contract | On going | Louiese Trading & Construction | TIN 940-685-564 | NULL
1076 | Upgrading of Orol Bailey Bridge III to RCDG | B2 GF PEO 22-01-007 | Transportation Facilities | BRIDGES | 21 m | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 7150000 | 5702491.3 | 182 | 2022-05-17 | 1 | 2022-11-15 | 2023-02-13 | NULL | 100% | NULL | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564 | NULL
1077 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-034 | Other Infrastructure | DRAINAGE | NULL | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 3700000 | 3690664.21 | 90 | 2022-05-16 | NULL | 2022-08-14 | NULL | 2022-08-05 | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
1078 | Concreting of Linapacan Road | B2 GF PEO 22-01-022 | Transportation Facilities | ROAD | 1.50 km | Linapacan, Palawan | Linapacan | PEO | 2022 | 20% Development Fund | 15750000 | 15749098.26 | 90 | 2022-05-16 | NULL | 2022-08-14 | Subject for LD | NULL | 95% | NULL | By contract | On going | Julriz Trading and Construction | TIN 495-740-401 | NULL
1079 | Concreting of Abaroan Road (Intermittent Section) | B2 GF PEO 22-01-015 | Transportation Facilities | ROAD | 1.098 km | Bgy. Abaroan | Roxas | PEO | 2022 | 20% Development Fund | 11550000 | 11548516.56 | 90 | 2022-03-10 | NULL | 2022-06-08 | 2022-10-22 | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
1080 | Concreting of Lucbuan-Emilod Road | B2 GF PEO 22-01-009 | Transportation Facilities | ROAD | 1.403 km | Magsaysay | Magsaysay | PEO | 2022 | 20% Development Fund | 16800000 | 16799532.15 | 120 | 2022-03-16 | NULL | 2022-07-14 | NULL | NULL | 100% | NULL | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000 | NULL
1081 | Concreting of Plaridel-Apis-Cabigaan Road | B2 GF PEO 22-01-016 | Transportation Facilities | ROAD | 1.0 km | Aborlan | Aborlan | PEO | 2022 | 20% Development Fund | 10500000 | 9197925.23 | 90 | 2022-06-09 | NULL | 2022-09-07 | 2023-01-05 | NULL | 100% | NULL | By contract | Completed | Chad Lourence Trading & Construction Services | TIN 919-616-230 | NULL
1082 | Rehabilitation of Sagpangan Spillway | NULL | Other Infrastructure | OTHER FACILITIES | Spillway=16m(l) x 15m(w) x 1.55m(h) | Sagpangan - Barake Road, Aborlan | Aborlan | PEO | 2022 | 20% Development Fund | 2000000 | NULL | 80 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1083 | Concreting of Cataban - Liminangcong Critical Road (Intermittent Section) | B2 GF PEO 22-01-010 | Transportation Facilities | ROAD | 1.905 km | Taytay | Taytay | PEO | 2022 | 20% Development Fund | 20000000 | 18021396.03 | 120 | 2022-05-18 | 1 | 2022-09-15 | 2023-02-12 | NULL | 100% | NULL | By contract | Completed | L.M John Construction Supplies Trading | TIN 422-936-808 | NULL
1084 | Concreting of Paglaum Itangil to Sta. Teresita | B2 GF PEO 22-01-011 | Transportation Facilities | ROAD | 1.906 km | Dumaran | Dumaran | PEO | 2022 | 20% Development Fund | 20000000 | 17967926.62 | 120 | 2022-05-18 | NULL | 2022-09-15 | Subject for LD | NULL | 100% | NULL | By contract | Completed | L.M John Construction Supplies Trading | TIN 422-936-808 | NULL
1085 | Concreting of 1 km Barotuan to Bucana | B2 GF PEO 22-01-012 | Transportation Facilities | ROAD | 1.0 km | El Nido | El Nido | PEO | 2022 | 20% Development Fund | 10500000 | 10488328.82 | 90 | 2022-05-11 | NULL | 2022-08-09 | 2022-12-13 | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
1086 | Concreting of 1 km Highway to Teneguiban | B2 GF PEO 22-01-017 | Transportation Facilities | ROAD | 1.0 km | El Nido | El Nido | PEO | 2022 | 20% Development Fund | 10500000 | 8521495.96 | 90 | 2022-05-16 | 1 | 2022-08-14 | 2023-01-16 | NULL | 100% | NULL | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496 | NULL
1087 | Concreting of 1 km Pulot Sea Road | B2 GF PEO 22-01-018 | Transportation Facilities | ROAD | 1.0 km | Sofronio Española | Sofronio Española | PEO | 2022 | 20% Development Fund | 10500000 | 8596286.23 | 90 | 2022-07-18 | 1 | 2022-10-16 | 2023-05-04 | 2023-07-03 | 100% | NULL | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176 | NULL
1088 | Concreting of 1 km Labog to Naltep Road | B2 GF PEO 22-01-013 | Transportation Facilities | ROAD | 1.0 km | Sofronio Española | Sofronio Española | PEO | 2022 | 20% Development Fund | 10500000 | 8596286.23 | 90 | 2022-07-18 | 1 | 2022-10-16 | 2023-09-21 | NULL | 100% | NULL | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176 | NULL
1089 | Construction of One (1) Barrel RCBC | B2 GF PEO 22-01-031 | Other Infrastructure | DRAINAGE | RCBC: 1-3m(h) X 3m(w) X 6(l) X 0.30m(thick) Approach: 6m(l) X 0.60m(w) X 0.20m(Thick) X 2 Sides Detour Road: 2-12m(l) 5m(w) w/ 24'' RCPC | Apo-Aporawan, Aborlan | Aborlan | PEO | 2022 | 20% Development Fund | 2000000 | 1862000 | 90 | 2022-06-27 | NULL | 2022-09-25 | 2022-11-09 | NULL | 100% | NULL | By contract | Completed | Palbic Construction and Supply | TIN 128-066-252 | NULL
1090 | Construction of 3-Barrel Box Cuvert | B2 GF PEO 22-01-024 | Other Infrastructure | DRAINAGE | NULL | Sowangan, Quezon | Quezon | PEO | 2022 | 20% Development Fund | 6000000 | 4717681.25 | 120 | 2022-07-08 | NULL | 2022-11-05 | NULL | NULL | 100% | NULL | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176 | NULL
1091 | Construction of Cacarigan Spillway | B2 GF PEO 22-01-020 | Other Infrastructure | OTHER FACILITIES | (A) Spillway: 30m(l) x 9.73m (w) x 3.05m (h) - (B) Approach: 6m (l) x 6m (w) x 0.2 (h) - © Slope protection 5M (L) x 4 sides | Aramaywan, Narra | Narra | PEO | 2022 | 20% Development Fund | 6145521.47 | 5156938.33 | 120 | 2022-05-11 | 1 | 2022-09-08 | 2022-08-17 | NULL | NULL | NULL | By contract | Terminated | N.Sales Construction | TIN 174-694-454 | Please see Notice of Termination
1092 | Concreting of Caguesan Road | B2 GF PEO 22-01-021 | Transportation Facilities | ROAD | 0.8 km | Caguesan, Narra | Narra | PEO | 2022 | 20% Development Fund | 8000000 | 7979873.47 | 90 | 2022-07-08 | NULL | 2022-10-06 | NULL | 2022-09-29 | 100% | NULL | By contract | Completed | Samurai Construction | TIN 919-621-019 | NULL
1093 | Construction of Raang Spillway | B2 GF PEO 22-01-025 | Other Infrastructure | OTHER FACILITIES | NULL | Mainit, Brooke's Point | Brooke's Point | PEO | 2022 | 20% Development Fund | 8600000 | 7215051.97 | 120 | 2022-05-11 | NULL | 2022-09-08 | NULL | NULL | NULL | NULL | By contract | Terminated | N.Sales Construction | TIN 174-694-454 | Termination for convenience: Duplication of project
1094 | Construction of Ugnisan 1 Spillway | B2 GF PEO 22-01-028 | Other Infrastructure | OTHER FACILITIES | NULL | Culion | Culion | PEO | 2022 | 20% Development Fund | 3000000 | 2999218.64 | 90 | 2022-05-16 | NULL | 2022-08-14 | 2022-11-17 | 2023-03-15 | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
1095 | Construction of Ugnisan 2 Spillway | B2 GF PEO 22-01-032 | Other Infrastructure | OTHER FACILITIES | NULL | Culion | Culion | PEO | 2022 | 20% Development Fund | 3000000 | 2999218.64 | 90 | 2022-05-16 | NULL | 2022-08-14 | 2022-11-17 | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
1096 | Construction of Sowangan Hanging Bridge | B2 GF PEO 22-01-033 | Transportation Facilities | ROAD | 60 m | Sowangan, Quezon | Quezon | PEO | 2022 | 20% Development Fund | 4512687.53 | 4507518.61 | 90 | 2022-03-15 | NULL | 2022-06-13 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1097 | Construction of Tagasag Hanging Bridge | B2 GF PEO 22-01-035 | Transportation Facilities | ROAD | 22 m | Canipaan, Rizal | Rizal | PEO | 2022 | 20% Development Fund | 4512687.53 | 4510105.46 | 90 | 2022-03-22 | NULL | 2022-06-20 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1098 | Construction of Provincial Health Office | B2 GF PHO 22-11-207 | Other Facilities | PGP FACILITIES | Floor area (3 storey): 43m x 15m - Porch with ramp: 15.575m x 5.1m - Road Network: 477.44m^2 - Parking Area: 300.84m^2 - Perimeter Fence: 400m | Bgy. Bancao-Bancao | Puerto Princesa City | PEO | 2022 | Capital outlay | 48000000 | 47974854 | 260 | 2023-03-02 | NULL | 2023-11-17 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1099 | Construction of Three (3) Storey Medical Ward Building, Phase II in Aborlan Medicare Hospital | B2 GF PEO 22-02-070 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan, Palawan | Aborlan | PEO | 2022 | Capital outlay | 20000000 | 19427448.22 | 120 | 2022-06-27 |  | 2022-10-25 | 2022-12-14 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1100 | Completion of Bahay Tuluyan and Additional Hazardous Waste Vault Treatment Facilities in Aborlan Medicare Hospital | B2 GF AMH 22-02-072 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan, Palawan | Aborlan | PEO | 2022 | Capital outlay | 4100000 | 4098575.72 | 120 | 2022-06-27 |  | 2022-10-25 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1101 | Centralized Oxygen Generator System |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2022 | Capital outlay | 16000000 | [7 empty] | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
1102 | Construction of Four-Storey Medical Arts Building A Phase II in Southern Palawan Provincial Hospital | B1 GF SPPH 22-02-078 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | Capital outlay | 20000000 |  | 120 | [8 empty] | Reverted
1103 | Construction of Southern Palawan Provincial Hospital (Completion of Medical Workers Dormitory) | B2 GF SPPH 22-02-071 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | Capital outlay | 5000000 | 4997529.45 | 90 | 2022-05-11 |  | 2022-08-09 | Subject for LD |  | 40.2% |  | By contract | On going | RD Abacial Construction | TIN 327-679-690
1104 | Improvement of Coron District Hospital (Concreting of Access Road to Mortuary & Motorpool Parking Area, Construction of Hazardous Waste Vault, Manifold & Perimeter Fence, Additional Works in Molecular Laboratory) | B2 GF CODH 22-08-142 | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2022 | Capital outlay | 6100000 | 5960147.47 | 90 | 2023-03-02 |  | 2023-05-31 |  | 2023-12-28 | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1105 | Construction of Oxygen Building |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2022 | Capital outlay | 1800000 | 1774809.77 | 150 | 2023-02-27 |  | 2023-07-27 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1106 | Completion of Three (3) Storey Medical & Ward Building in Narra Municipal Hospital | B2 GF NMH 22-03-083 | Medical Facilities | MEDICAL FACILITIES | (a) Floor area: 43m x 15m - (b) Ramp up: 24m x 6m - © Oxygen Building: 45.14 sq.m (d) Walkway: 126 ln.m | Narra Municipal Hospital | Narra | PEO | 2022 | Capital outlay | 35000000 | 34984209.43 | 120 | 2022-05-18 | 1 | 2022-09-15 | 2022-12-20 | 2022-12-21 | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
1107 | Centralized Oxygen Generator System |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2022 | Capital outlay | 16000000 | [7 empty] | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
1108 | Construction of Medical Record and Pharmacy Storage in Roxas Medicare Hospital | B2 GF RMH 22-02-073 | Medical Facilities | MEDICAL FACILITIES |  | Roxas Medicare Hospital | Roxas | PEO | 2022 | Capital outlay | 1910000 | 1757426.18 | 90 | 2022-07-11 |  | 2022-10-09 | 2022-12-07 |  | 100% |  | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662
1109 | Centralized Oxygen Generator System |  | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2022 | Capital outlay | 16000000 | [10 empty] | Failure of bidding
1110 | Construction of Manifold, Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan | Aborlan | PEO | 2022 | Supplemental Budget No. 2 | 250000 | [10 empty] | Re-aligned
1111 | Construction of Manifold, Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Brooke's Point | Brooke's Point | PEO | 2022 | Supplemental Budget No. 2 | 250000 | [10 empty] | Re-aligned
1112 | Construction of Manifold, Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 250000 | [10 empty] | Re-aligned
1113 | Construction of Multi-Purpose Building, Aborlan Medicare Hospital | B2 GF SB2 INFRA 22-08-100 | Medical Facilities | MEDICAL FACILITIES |  | Aborlan | Aborlan | PEO | 2022 | Supplemental Budget No. 2 | 2400000 | 1990784.03 | 120 | 2023-01-24 |  | 2023-05-24 |  | 2023-12-30 | 100% |  | By contract | Completed | F.B Murillo Construction | TIN 772-152-432
1114 | Construction of One (1) Box Culvert | B2 GF SB2 INFRA 22-08-117 | Other Infrastructure | DRAINAGE | RCBC/RC Slope Protection: (a) 1-3m(h) x 3m(w) x 6.0m(l) x 0.30m thk (b) 6m(l) x 6.0m(w) x 0.20m (thk) x 2 sides (c ) Detour road 2-12m(l) x 5m(w) w/ 24'' RCPC (d) Slope protection 5m(l) x 2m(h) x 0.30m thk x 4 sides | Sitio Tabud, Panitian, Quezon | Quezon | PEO | 2022 | Supplemental Budget No. 2 | 2000000 | 1997693.49 | 60 | 2023-02-06 | NULL | 2023-04-07 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1115 | Rehabilitation of Bridge Slope Protection at Abutment "A-B" in Tiondunan Bridge | B2 GF INFRA 22-08-099 | Other Infrastructure | SLOPE PROTECTION | Slope protection: 103.89 cu.m | Tiondunan Bridge, Bgy.Mendoza, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 2 | 1477166.85 | 1473973.18 | 60 | 2023-01-12 | 1 | 2023-03-13 | 2023-08-11 | NULL | 100% | NULL | By contract | Completed | MKB Builders and Supply | TIN 262-511-948 | NULL
1116 | Improvement of Molecular Laboratory and Swabbing Facilities (Mechanical Layout) |  | Medical Facilities | MEDICAL FACILITIES |  | Irawan, PPC | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 2 | 1000000 | [9 empty] | By contract | For Termination
1117 | Construction of Transformer Platform in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB2 INFRA 22-09-129 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 2 | 327000 | 326764.24 | 30 | 2023-01-17 |  | 2023-02-16 |  |  | 100% |  | By contract | Completed | New Space Trading and Construction | TIN 010-545-401
1118 | Construction of Transformer Platform in Sofronio Española District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | S. Española | Sofronio Española | PEO | 2022 | Supplemental Budget No. 2 | 327000 | [10 empty] | Re-aligned
1119 | Improvement of Molecular Laboratory and Swabbing Facilities in El Nido Community Hospital (Mechanical Layout) |  | Medical Facilities | MEDICAL FACILITIES |  | El Nido Community Hospital | El Nido | PEO | 2022 | Supplemental Budget No. 2 | 550000 | [10 empty] | Re-aligned |  |  | Fund Re-aligned
1120 | Improvement of Molecular Laboratory and Swabbing Facilities in San Vicente District Hospital (Mechanical Layout) |  | Medical Facilities | MEDICAL FACILITIES |  | San Vicente | San Vicente | PEO | 2022 | Supplemental Budget No. 2 | 550000 | [10 empty] | Re-aligned |  |  | Fund Re-aligned
1121 | Construction of Molecular Laboratory and Swabbing Facilities in Northern Palawan Provincial Hospital (Mechanical Layout) |  | Medical Facilities | MEDICAL FACILITIES |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 550000 | [10 empty] | Re-aligned |  |  | Fund Re-aligned
1122 | Concreting from National Highway to El Nido STP | B2 GF INFRA 22-08-127 | Transportation Facilities | ROAD | Road length: 1140.00 l.m - Drainage-RCPC=2pcs-1Lx8m RCPC with End Protection - RC Box culvert=2 barrel Ht. 2.0m W=3m | El Nido | El Nido | PEO | 2022 | Supplemental Budget No. 2 | 12642822.16 | 10665425.22 | 90 | 2022-01-16 | 2 | 2022-04-16 | 2023-12-17 | NULL | 100% | NULL | By contract | Completed | Diane Construction and Enterprises | TIN 140-882-282 | NULL
1123 | Construction of Northern Palawan Technical Vocational School Phase 3 | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 5810000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1124 | Construction of Perimeter Fence in Palawan Technical Vocational School Phase II | NULL | Educational Facilities | SCHOOL FACILITIES | NULL | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 2700000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1125 | Construction of Multi-purpose Drying Pavement | NULL | Other Facilities | MULITI-PURPOSE | NULL | Dumangueña, Narra | Narra | PEO | 2022 | Supplemental Budget No. 2 | 2250000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1126 | Construction of Multi-purpose Hall Building | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Dumangueña, Narra | Narra | PEO | 2022 | Supplemental Budget No. 2 | 2800000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to Supplemental Budget No. 3 - 2022
1127 | Upgrading from 75 KVA to 250 KVA Transformer and accessories in Southern Palawan Provincial Hospital | B2 GF SB2 INFRA 22-10-157 | Medical Facilities | MEDICAL FACILITIES |  | Brooke's Point | Brooke's Point | PEO | 2022 | Supplemental Budget No. 2 | 10826953.06 | 10770998.78 | 60 | 2023-03-27 |  | 2023-05-26 | 2023-08-14 | 2024-02-03 | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1128 | Supply and Installation of 1 - 500 KVA Generator Set with ATS in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Brooke's Point | Brooke's Point | PEO | 2022 | Supplemental Budget No. 2 | 4200000 | 4193000 | 60 | 2023-02-15 |  | 2023-04-16 |  |  |  |  | By contract | Order of Termination | N-Gines Technology Inc.
1129 | Upgrading from 75 KVA to 250 KVA Transformer and accessories in Northern Palawan Provincial Hospital | B2 GF SB2 INFRA 22-08-156 | Medical Facilities | MEDICAL FACILITIES |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 10826953.06 | 10770998.78 | 60 | 2023-03-27 | 1 | 2023-05-26 | 2023-07-30 | 2023-11-27 | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1130 | Supply and Installation of 1 - 500 KVA Generator Set with ATS in Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 4200000 | 3823000 | 60 | 2023-02-15 |  | 2023-04-16 |  |  |  |  | By contract | Order of Termination | N-Gines Technology Inc.
1131 | Supply and Installation of 1 - 500 KVA Generator Set with ATS in Cory Park Covered Event Center | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 2 | 4200000 | 3823000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | N-Gines Technology Inc. | NULL | For Legal Endorsement
1132 | Construction of Powerhouse in Paly VEP | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 1400000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to Supplemental Budget No. 3 - 2022
1133 | Construction of Sewage Treatment Plant, Aborlan Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Aborlan Medicare Hospital | Aborlan | PEO | 2022 | Supplemental Budget No. 1 | 822000 | [10 empty] | Re-aligned |  |  | Re-aligned for Supplemental Budge No. 5
1134 | Construction of Material Recovery Facilities, Sofronio Española Hopsital | B2 GF SB1 PEO22 24-05-086 | Medical Facilities | MEDICAL FACILITIES | One Storey Building: 24 sq.m | Bgy. Pulot Center | Sofronio Española | PEO | 2022 | Supplemental Budget No. 1 | 1128000 | 1126610.75 | 45 | 2024-07-29 |  | 2024-09-12 | 2024-10-02 |  | 100% |  | By contract | Completed | JD Golez Construction Services | TIN 181-147-186
1135 | Installation of Fire Protection and Alarm System, Quezon Medicare Hospital | B2 GF SB1 PEO 22-11-187 | Medical Facilities | MEDICAL FACILITIES |  | Quezon Medicare Hospital | Quezon | PEO | 2022 | Supplemental Budget No. 1 | 3300000 | 3294749.006 | 60 | 2023-02-16 |  | 2023-04-17 |  | 2023-06-09 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1136 | Installation of Fire Protection and Alarm System, Dr. Jose Rizal Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2022 | Supplemental Budget No. 1 | 3300000 | [10 empty] | Re-aligned
1137 | Construction of Hazardous Waste Vault in Bataraza Medicare Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bataraza Distirct Hospital | Bataraza | PEO | 2022 | Supplemental Budget No. 1 | 56000 | [10 empty] | For Re-bid
1138 | Construction of 100 cu.m Elevated Water Tank with Deepwell and Chlorination System in Balabac District Hospital | B2 GF SB1 PEO22 24-09-106 | Medical Facilities | MEDICAL FACILITIES | 100 cu.m Elevated Water Tank with Deepwell and Chlorination System | Bgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2022 | Supplemental Budget No. 1 | 5000000 | 4994952.68 | [9 empty] | For Award |  |  | NTP on process
1139 | Installation of Fire Protection and Alarm System, Balabac District Hospital | B2 GF SB1 PEO 22-08-135 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2022 | Supplemental Budget No. 1 | 3500000 | 3497307.19 | 64 | 2023-01-23 |  | 2023-03-28 |  | 2023-05-02 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1140 | Construction of Three (3) Storey Building Medical Worker's Dormitory, Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES | Dimension: 21mx11.10m = 233.10 sqm | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 12600000 |  | 115 | [8 empty] | Re-aligned |  |  | Re-aligned to 2-Storey Building (SB NO. 4)
1141 | Construction of Bahay Tuluyan in Northern Palawan Provincial Hospital | B2 GF SB1 PEO22-23-11-147 | Medical Facilities | MEDICAL FACILITIES | Floor area: 27m x 6m - Septic Vault: 3.610m(h) x 1.50m(w) x 1.50m (d) | Sitio Arado, Brgy. Poblacion, Taytay, Palawan | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 3800000 | 3798638.06 | 90 | 2024-02-22 |  | 2024-05-22 |  | 2024-05-14 | 100% |  | By contract | Completed | Cjetzu Lumber & Construction Supply | TIN 920-28-159
1142 | Construction of Additional Two (2) -Rooms in Isolation Building for Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  |  | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 1598389.97 | [10 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 5
1143 | Construction of Bahay Tuluyan Building in El Nido Community Hospital | B2 GF SB1 PEO 22-23-11-148 | Medical Facilities | MEDICAL FACILITIES | Floor area: 27m x 6m - Septic Vault: 3.610m(h) x 1.50m(w) x 1.50m (d) | El Nido Community Hospital | El Nido | PEO | 2022 | Supplemental Budget No. 1 | 3800000 | 3798638.06 | 90 | 2024-02-05 |  | 2024-05-05 |  | 2024-05-05 | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1144 | Construction of 100 cu.m Water Tank with Deepwell and Chlorination System in Cuyo District Hospital | B2 GF SB3 PEO 22-12-213 | Medical Facilities | MEDICAL FACILITIES | 100 cu.m Capacity Tank | Cuyo District Hospital | Cuyo | PEO | 2022 | Supplemental Budget No. 1 | 5500000 | 5489800.07 | 120 | 2023-03-28 | 2 | 2023-07-26 | 2023-10-25 |  | 100% |  | By contract | Completed | M. Luengo Construction | TIN 257-013-134
1145 | Construction of Sewage Treatment Plant in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB1 PEO 22-12-225 | Medical Facilities | MEDICAL FACILITIES | Sewage Treatment Plant | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 3200000 | 3140269.25 | 60 | 2023-03-29 | 1 | 2023-07-27 |  |  |  |  | By contract | No movement | M. Luengo Construction | TIN 010-545-401 | Septic vault is not yet completed - with Suspension No. 1
1146 | Concreting of Road & Parking Area in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB1 PEO 22-09-138 | Medical Facilities | MEDICAL FACILITIES | Road Network: 389.00 sq.m - Parking Area: 140.00 sq.m - Pathwalk: 150.14 sq.m | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1000000 | 999108.91 | 45 | 2023-01-17 |  | 2023-03-03 | Subject for LD |  | 75.56% |  | By contract | On going | New Space Trading and Construction | TIN 010-545-401
1147 | Concreting of Perimeter Fence in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB1 PEO 22-09-149 | Medical Facilities | MEDICAL FACILITIES | Construction limits : (a) Semi concrete=59.70 ln.m - Fence=20.00 Span (b) Concrete fence=33.00 ln.m - 11.00 span | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1000000 | 998585.44 | 60 | 2023-01-17 |  | 2023-03-18 |  |  | 100% |  | By contract | Completed | New Space Trading and Construction | TIN 010-545-401
1148 | Construction of Sewage Treatment Plant in Araceli-Dumaran District Hospital | B2 GF SB1 PEO 22-09-152 | Medical Facilities | MEDICAL FACILITIES | STP | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 3200000 | 3187275.95 | 60 | 2023-02-03 |  | 2023-04-04 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1149 | Construction of 100 cu.m water tank with Deepwell and Chlorination System in Araceli-Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 3500000 | [10 empty] | Re-aligned
1150 | Construction of Mortuary Building in Araceli/Dumaran District Hospital | B2 GF SB1 PEO 22-08-139 | Medical Facilities | MEDICAL FACILITIES | 1 Storey - Floor area: 6.0m x 6.0m - Steel truss | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1135000 | 1067829.52 | 50 | 2023-01-06 |  | 2023-02-25 |  |  | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496
1151 | Construction of Barangay Health Station | B2 GF SB1 PEO 22-08-126 | Medical Facilities | BHS | Floor Area: 8.95m x 11.075m | Pulot Interior | Sofronio Española | PEO | 2022 | Supplemental Budget No. 1 | 2300000 | 2292181.86 | 120 | 2022-11-21 | 1 | 2023-03-21 | 2023-04-21 |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1152 | Improvement of Molecular Laboratory and Swabbing Facility in Southern Palawan Provincial Hospital (Supply and Installation of Mechanical Equipment) |  | Medical Facilities | MEDICAL FACILITIES |  |  | Brooke's Point | PEO | 2022 | Supplemental Budget No. 1 | 550000 | [10 empty] | For Re-alignment
1153 | Construction of Three In One Large Scale Rural Health Unit Phase II |  | Medical Facilities | RHU |  |  | Magsaysay | PEO | 2022 | Supplemental Budget No. 1 | 8000000 |  | 180 | [8 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 4
1154 | Construction of Three In One Large Scale Rural Health Unit Phase II |  | Medical Facilities | RHU |  | Cagayancillo | Cagayancillo | PEO | 2022 | Supplemental Budget No. 1 | 8000000 | [10 empty] | Re-aligned |  |  | Same project Re-aligned to Supplemental Budget No. 4
1155 | Completion of Drainage System in Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  |  | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 2000000 | [10 empty] | Re-aligned
1156 | Construction of Cabinbin River RCDG Bridge | NULL | Transportation Facilities | ROAD | NULL | Bgy. Imulnod | Brooke's Point | PEO | 2022 | Supplemental Budget No. 1 | 8000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1157 | Construction of Perimeter Fence of the Halfway House for Former Rebel & Militia ng Bayan | B2 GF SB1 PEO 22-08-134 | Other Facilities | PGP FACILITIES | Net length: 75.5 lm CHB Perimeter fence - 75 lm Tubular Perimeter fence | Bgy. Irawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 1 | 1500000 | 1497880.18 | 90 | 2022-12-09 | NULL | 2023-03-09 | NULL | NULL | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001 | NULL
1158 | Improvement of Evacuation Center/ Covered Court (Flooring only) | B2 GF SB1 PEO 22-08-120 | Other Infrastructure | COVERED COURT | Court= 30m(L) x 18m(W) | Bgy. Labog | Sofronio Española | PEO | 2022 | Supplemental Budget No. 1 | 872687.19 | 860977.02 | 45 | 2022-11-28 | NULL | 2023-01-12 | NULL | NULL | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1159 | Repair/Restoration of Infrastructure Damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Various barangay in Northern Palawan (Roxas/El Nido/Araceli/Dumaran/Taytay) | NULL | PEO | 2022 | Supplemental Budget No. 1 | 8418965 | 8367374.69 | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1160 | Construction of Power Distribution Lines of Maracanao Village Electrification Project | B2 GF SB1 PEO22-24-05-085 | Power and Energy Development Program | ELECTRIFICATION | CL: 1 PHASE LINE=0.290 KM - U.B LINES=0.290 KM - O.S LINES=0.630 KM | Bgy. Macaranao, Agutaya | Agutaya | PEO | 2022 | Supplemental Budget No. 1 | 1802238.82 | 1797213.67 | 30 | 2024-08-16 | NULL | 2024-09-15 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266 | NULL
1161 | Construction of Power Distribution Lines of Batas Village Electrification Project | B2 GF SB1 PEO 22-10-162 | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Batas, Taytay, Palawan | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 3869919.08 | 2853437.41 | 55 | 2023-02-22 | NULL | 2023-04-18 | NULL | NULL | 100% | NULL | By contract | Completed | One Badajos Construction & Trading Corporation | TIN 010-590-630 | NULL
1162 | Construction of Power Distribution Lines of Debangan Village Electrification Project | B2 GF SB1 PEO 22-08-146 | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Debangan, Taytay, Palawan | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 3681098.4 | 3481969.82 | 80 | 2023-02-15 | NULL | 2023-05-06 | 2023-05-03 | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
1163 | Construction of Power Distribution Lines of Galoc Village Electrification Project | B2 GF SB1 PEO 22-08-147 | Power and Energy Development Program | ELECTRIFICATION | 3 Phase Line=0.884 km - 1 Phase=0.867 km - U.B Lines=1.606 kms O.S lines= 0.617 km | Bgy. Galoc, Culion, Palawan | Culion | PEO | 2022 | Supplemental Budget No. 1 | 4330608.61 | 3642978.53 | 60 | 2023-02-15 | NULL | 2023-04-16 | 2023-06-29 | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
1164 | Construction of Power Distribution Lines of Maglalambay Village Electrification Project | B2 GF SB1 PEO 22-09-155 | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Maglalambay, Busuanga, Palawan | Busuanga | PEO | 2022 | Supplemental Budget No. 1 | 5312904.21 | 3939049.36 | 90 | 2023-01-06 | NULL | 2023-04-06 | 2023-05-20 | NULL | 100% | NULL | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116 | NULL
1165 | Construction of Power Distribution Lines of Ramos Village Electrification Project (Re-bid) | B2 GF SB1 PEO 22-08-148 | Power and Energy Development Program | ELECTRIFICATION | NULL | Bgy. Ramos, Balabac, Palawan | Balabac | PEO | 2022 | Supplemental Budget No. 1 | 5312904.21 | 5303523.47 | 110 | 2023-02-13 | NULL | 2023-06-03 | NULL | NULL | 100% | NULL | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496 | NULL
1166 | Concreting of 1.2 km Farm to Market Road with box culvert/ cross drainage | NULL | Transportation Facilities | ROAD | NULL | Bgy. Malitub | Bataraza | PEO | 2022 | Local Fund (Support to Muslim Communities) | 12000000 | 10499199.69 | 120 | 2022-05-11 | NULL | 2022-09-08 | NULL | NULL | NULL | NULL | By contract | For Termination | R. Narrazid Trading and Construction | TIN 330-975-725 | NULL
1167 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-02-044 | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Sumbiling Proper, Bgy. Sumbiling | Bataraza | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3467728.18 | 90 | 2022-05-13 | NULL | 2022-08-11 | NULL | NULL | 100% | NULL | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153 | NULL
1168 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-02-043 | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Culandanum, Bgy. Canipaan | Rizal | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3467728.18 | 90 | 2022-05-14 | NULL | 2022-08-12 | NULL | NULL | 100% | NULL | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153 | NULL
1169 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-02-042 | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Banise, Bgy. Iraan | Rizal | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3467728.18 | 90 | 2022-05-14 | NULL | 2022-08-12 | NULL | NULL | 100% | NULL | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153 | NULL
1170 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-08-140 | Other Infrastructure | MULITI-PURPOSE | NULL | Sitio Sayab 1, Bgy. Tagnato | Bataraza | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3496738.18 | 90 | 2023-02-15 | NULL | 2023-05-16 | NULL | NULL | 100% | NULL | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153 | NULL
1171 | Construction of Molecular Laboratory and Swabbing Facility, Southern Palawan Provincial Hospital, Brooke's Point, Palawan | B2 TF PDRRMO 22-001 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital, Brooke's Point, Palawan | Brooke's Point | PEO | 2022 | TF LDRRMF 2021-PO 2615-A | 6000000 | 5988215.19 | 120 | 2022-03-10 |  | 2022-07-08 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
1172 | Construction of Molecular Laboratory and Swabbing Facility, San Vicente District Hospital, San Vicente, Palawan | B2 TF PDRRMO 22-002 | Medical Facilities | MEDICAL FACILITIES |  | San Vicente District Hospital | San Vicente | PEO | 2022 | TF LDRRMF 2021-PO 2615-A | 6000000 | 5997742.5 | 260 | 2022-03-18 | 1 | 2022-12-03 | 2023-01-17 |  | 73% |  | By contract | No movement | MG Tan Construction | TIN 113-310-056 | No manpower on site
1173 | Construction of Bahay Tuluyan, Southern Palawan Provincial Hospital | B2 GF PEO 22-02-049 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | 300-22-02-00670 | 2000000 | 1996599.15 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1174 | Construction of Warehouse Rizal, Palawan | B1 GF DRAC21 22-02-074 | Other Facilities | OTHER FACILITIES | NULL | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 5000000 | 4321071.23 | 180 | 2022-07-19 | NULL | 2023-01-15 | For approval | NULL | 36.7% | NULL | By contract | Slow movement | Furosam Incorporated | TIN 009-062-221 | No materials and man power on site
1175 | Concreting of Road Network Rizal, Palawan | B1 GF DRAC21 22-02-075 | Transportation Facilities | ROAD | NULL | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 1500000 | 1262526.62 | 75 | 2022-07-19 | NULL | 2022-10-02 | NULL | NULL | 10% | NULL | By contract | Notice to Terminate | Furosam Incorporated | TIN 009-062-221 | NULL
1176 | Construction of Perimeter Fence Rizal, Palawan | B1 GF DRAC21 22-02-076 | Other Infrastructure | OTHER FACILITIES | NULL | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 2000000 | 1681841.95 | 120 | 2022-07-19 | NULL | 2022-11-16 | NULL | NULL | 100% | NULL | By contract | Completed | Furosam Incorporated | TIN 009-062-221 | NULL
1177 | Construction of Rizal Agricultural Center (RAC) Office | B1 GF DRAC21 22-02-077 | Other Facilities | AGRICULTURAL FACILITIES | NULL | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 5000000 | 4037572.85 | 120 | 2022-06-27 | NULL | 2022-10-25 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1178 | Construction of Sheltered Port,Phase III, Bgy. Pag-asa, Municipality of Kalayaan, Palawan | B2 TF PEO 22-04-085 | Ports and Airports | PORTS | NULL | Bgy. Pag-asa, Municipality of Kalayaan, Palawan | Kalayaan | PEO | 2022 | Trust Fund - DOTr | 470687046.57 | 465973152.12 | 540 | 2022-06-30 | 1 | 2023-12-22 | For approval | NULL | 95.1% | NULL | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
1179 | Improvement/Construction of New Narra Municipal Hospital | B2 TF Due to NGAS-DPWH 20-001 | Medical Facilities | MEDICAL FACILITIES |  | Bgry. Antipuluan, Narra Municiapl Hospital | Narra | PEO | 2020 | DPWH | 3418000 | 3284409.19 | 102 | 2020-06-22 | 1 | 2020-10-02 | 2021-05-15 | 2022-07-27 | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
1180 | Construction of 3 Barrel Box Culvert, Labog to Naltep road | NULL | Other Infrastructure | DRAINAGE | NULL | Bgy. Labog Naltep, Sofronio Española, Palawan | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 4000000 | 3447989.52 | 90 | 2022-08-15 | 1 | 2022-11-13 | 2022-11-13 | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1181 | Construction of 3 Barrel Box Culvert | NULL | Other Infrastructure | DRAINAGE | NULL | Aporawan,Aborlan | Aborlan | PEO | 2021 | NULL | 2785001.66 | NULL | 150 | 2021-03-01 | NULL | 2021-07-29 | 2022-07-02 | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
1182 | Construction/Rehabilitation of Hospital Building and Facilities | B2 SB3 INFRA 15 300-20-11-17054 | Medical Facilities | MEDICAL FACILITIES |  | Brgy. Catadman, Cuyo, Palawan | Cuyo | PEO | 2020 | Supplemental Budget No. 3 | 16000000 | 15972520.31 | 210 | 2021-01-19 | 2 | 2021-08-17 | Subject for LD |  | 95% |  | By contract | On going | Julriz Trading and Construction | TIN 495-740-401
1183 | Construction of Seaweeds Solar Dryer | NULL | Other Facilities | AGRICULTURAL FACILITIES | Farm facilities: Floor area: 6m x 12m=72 sqm (Concrete and Bamboo) - 12mx6.0mx1.2m Solar Dryer | Dumaran Nursery Area | Dumaran | PEO | 2015 | NULL | 150000 | 149464.73 | 40 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Jas Trading and Construction | NULL | NULL
1184 | Construction of Salt Processing Center | NULL | Other Facilities | AGRICULTURAL FACILITIES | One Storey Building: 110.37 sqm (14.15M x 7.80m) | Bgry. Danleg, Dumaran, Palawan | Dumaran | PEO | 2020 | NULL | 2000000 | 1998631.16 | 180 | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401 | NULL
1185 | Construction of Three Storey Building | B2 SB3 PEO 300-21-08-09676 | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 20000000 | 19980869.57 | 360 | 2021-10-14 | NULL | 2022-10-09 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1186 | Construction of Warehouse for Disaster Relief Goods/Stockpile (Phase II) | NULL | Other Facilities | PGP FACILITIES | NULL | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2021 | PDRRMO Fund | 10000000 | 9185703.75 | 120 | 2021-11-09 | 1 | 2022-03-09 | For approval | NULL | 99.2% | NULL | By contract | On going | JB & Sons Trading & Construction | TIN 166-376-497 | NULL
1187 | Construction of Road Network Around Cory Park | B2 SB3 PEO 300-21-07-081007 | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 7488331.75 | 7474996.86 | 90 | 2021-11-26 | NULL | 2022-02-24 | 2021-06-04 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1188 | Construction of Lualhati Women Center Phase II | B2 SB8 LWC202 300-21-09-12041 | Other Facilities | PGP FACILITIES | NULL | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 8 - LWC | 2500000 | 2497817.8 | 150 | 2021-12-16 | NULL | 2022-05-15 | 2022-07-29 | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
1189 | Construction of Highway-Junction Tumarbong Road (Intermittent Section) | NULL | Transportation Facilities | ROAD | 2.42 km | Bgry. Tumarbong, Roxas, Palawan | Roxas | PEO | 2018 | B2 ROADS17 300-21-11-15968 | 8000000 | 7947995.79 | 90 | 2022-01-01 | NULL | 2022-04-01 | 2022-03-31 | NULL | 100% | NULL | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271 | NULL
1190 | Construction of Dried Fruit Processing Center and Innovation Center | NULL | Other Facilities | AGRICULTURAL FACILITIES | NULL | Bgry. Marangas, Bataraza, Palawan | Bataraza | PEO | 2021 | Livelihood Fund | 2000000 | 1993167.01 | 120 | 2021-07-28 | NULL | 2021-11-25 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1191 | Proposed New Banua Institute for Resiliency & Green Growth Center | 30-00-11-9940(2) B CRGGP (Cluster San Vicente and Roxas) | Other Infrastructure | AGRICULTURAL FACILITIES | NULL | Bgry. Kemdeng, San Vicente, Palawan | San Vicente | PEO | 2021 | CRGGP Fund | 2366077.52 | 2245692.82 | 120 | 2021-05-06 | 1 | 2021-09-03 | NULL | NULL | 53% | NULL | By contract | No movement | BCL Construction | TIN 308-390-430 | NULL
1192 | Proposed New Banua Institute for Resiliency & Green Growth Center | 30-00-11-9940(2) B CRGGP (Cluster San Vicente and Roxas) | Other Infrastructure | AGRICULTURAL FACILITIES | NULL | Bgry. Tumarbong, Roxas, Palawan | Roxas | PEO | 2021 | CRGGP Fund | 2366077.52 | 2245692.82 | 120 | 2021-01-05 | 1 | 2021-05-05 | 2021-06-05 | NULL | NULL | NULL | By contract | Suspended | BCL Construction | TIN 308-390-430 | Propose for Termination end user cannot provide location
1193 | Construction of Four-Storey Medical Arts Building A Phase I in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Capital outlay | 20000000 | 19391780.9 | 120 | 2021-12-14 | 1 | 2022-04-13 | Subject for LD |  | 99.27% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1194 | Construction of Three (3) Classroom of School Building. Turda National High School | B2 SEF 300-17-09-14162 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | Bgy. Turda, Coron, Palawan | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2247629.97 | 100 | 2017-11-17 | NULL | 2018-02-25 | NULL | NULL | NULL | NULL | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | NULL
1195 | Concreting of National Highway - Igang Road | B2 GF PEO 22-01-019 | Transportation Facilities | ROAD | 1000 lm | Bgy. Iwahig | Bataraza | PEO | 2022 | 20% Development Fund | 10500000 | 9225486.71 | 90 | 2022-07-28 | 1 | 2022-10-26 | 2024-02-09 | NULL | 100% | NULL | By contract | Completed | N.Sales Construction | TIN 174-694-454 | NULL
1196 | Construction of Three (3) - Storey Medical & Ward Building with Roof Deck for Helipad - Phase II in Southern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | DOH Fund | 8058600 | 8057475.66 | 150 | 2019-12-13 |  | 2020-05-11 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
1197 | Construction of 3 Classroom School Building in San Jose Elementary School | B2 SEF17 300-19-05-07132 | Educational Facilities | SCHOOL FACILITIES | 3 Classroom School Building | San Jose,Coron, Palawan | Coron | PEO | 2017 | Special Education Fund - 2017 | 2250000 | 2247629.97 | 100 | 2017-11-29 | NULL | 2018-03-09 | NULL | NULL | 100% | NULL | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256 | NULL
1198 | Installation of Water and Lights with Plumbing Works | NULL | Other Facilities | OTHER FACILITIES | NULL | RAC, Bono-bono, Bataraza, Palawan | Bataraza | PEO | 2021 | PEEDO Fund | 500000 | 497661.52 | 90 | 2021-12-06 | NULL | 2022-03-06 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1199 | Improvement of Cuyo District Hospital (Installation of Fire Protection and Alarm System) | B2 PEO 300-21-05-04025 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 |  | 3500000 | 3497903.33 | 85 | 2021-08-05 |  | 2021-10-29 | 2022-01-12 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1200 | Bahay Pag-Asa Renovation/Repair | B2 GF BPYV 22-05-086 | Other Facilities | PGP FACILITIES | NULL | Bgy. Irawan, Puerto Pincesa City, Palawan | Puerto Princesa City | PEO | 2022 | BPYC | 328696.71 | 327590.54 | 75 | 2022-11-15 | NULL | 2023-01-29 | NULL | NULL | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001 | NULL
1201 | Completion of Cuyo District Hospital | B2 GF PEO 22-09-150 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 10000000 | 8671749.53 | 180 | 2022-12-16 | 3 | 2023-06-14 | 2023-11-25 |  | 95% |  | By contract | Stop construction | Bacs Construction and Engineering Consultancy | TIN 920-630-716 | No workers and materials on site/upvc supplier delivery delay
1202 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Dumarao, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 73912.27 | 8367374.69 | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1203 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Salvacion, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 187317.27 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1204 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES |  | Brgy. 1, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 1474010.39 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1205 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. San Miguel, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 268738.68 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1206 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Iraan, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 1242718.56 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1207 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. New Barbacan, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 242201 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1208 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Mendoza, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 151847.04 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1209 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Malcampo, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 84174.33 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1210 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Sandoval, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 80442.67 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1211 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Minara, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 1002581.79 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1212 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. San Isidro, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 52455.25 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1213 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. New Guinlo, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 364527.16 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1214 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Old Guinlo, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 569504.96 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1215 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Libertad, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 386027.98 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1216 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Talog, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 335650.61 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1217 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Pamantolon, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 52455.25 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1218 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Magsaysay, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 182652.7 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1219 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Ilian, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 41260.28 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1220 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Sta. Maria, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1043119.71 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1221 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Catep, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 133993.39 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1222 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Bacao, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 83440.58 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1223 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. San Juan, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 62458.48 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1224 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Lumacad, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 254751 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1225 | Repair/restoration of infrastructure damaged by Typhoon Odette | NULL | Other Infrastructure | OTHER FACILITIES | NULL | Brgy. Bebeladan, El Nido | El Nido | PEO | 2022 | Supplemental Budget No. 1 | 48723.59 | NULL | 90 | 2023-03-02 | NULL | 2023-05-31 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1226 | Construction of Covered Court/Evacuation Center | B2 GF SB1 PEO 22-12-214 | Other Infrastructure | COVERED COURT | NULL | Brgy. Tinitian, Roxas, Palawan | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 5525303 | 5500426.25 | 130 | 2023-02-22 | 1 | 2023-07-02 | 2023-07-14 | 2023-07-14 | 100% | NULL | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657 | NULL
1227 | Rehabilitation of Legislative Building | B2 GF SB4 INFRA 22-11-184 | Other Facilities | PGP FACILITIES | NULL | Capitol, PPC | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 10000000 | 9993597.78 | 60 | 2023-01-24 | NULL | 2023-03-25 | NULL | NULL | NULL | NULL | By contract | Terminated | Panaad Construction | TIN 938-375-592 | Termination for convenience: Change scope of work
1228 | Improvement of Capitol Complex Additional Works in Three Storey Building (Tileworks & Electrical) | B2 GF SB4 INFRA 22-11-216 | Other Facilities | PGP FACILITIES | NULL | Provincial Capitol Complex | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 3000000 | 2992970.09 | 75 | 2023-03-02 | NULL | 2023-05-16 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1229 | Improvement of Capitol Complex Establishment of Five (5) Offices in Three Storey Building | B2 GF SB4 INFRA 22-12-217 | Other Facilities | PGP FACILITIES | Net length: 3-storey building Interior Improvement (22.85m x 17.080 m) | Provincial Capitol Complex | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 6000000 | 5933247.74 | 90 | 2023-04-17 | NULL | 2023-07-16 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1230 | Improvement of Prov'l Government of Palawan Convention Center (Supply, Installation, Testing and Commissioning of Transformer, Panel Boards, LEDs and Sound) | NULL | Other Facilities | PGP FACILITIES | NULL | Provincial Capitol Complex | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 22756713.94 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1231 | Construction of Transformer Platform with Genset Room for Electrical Material (PGP Convention Center) | B2 GF SB4 INFRA 22-12-208 | Other Facilities | PGP FACILITIES | NULL | PGP Convention Center | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 7380407.22 | 7275532.31 | 60 | 2023-02-26 | NULL | 2023-04-27 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
1232 | Supply and Installation of Air Conditioning Unit for VIP Room and Dressing Room of the PGP Convention Center | NULL | Other Facilities | PGP FACILITIES | NULL | PGP Convention Center | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 538954.84 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
1233 | Restoration and Rehabilitation of Governor's Residence | B2 GF SB5 INFRA22 23-02-053 | Other Facilities | PGP FACILITIES | Three storey Building | M. Quezon, Barangay Matiyaga, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 8000000 | 7938086.78 | 180 | 2023-06-13 | NULL | 2023-12-10 | NULL | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1234 | Construction of Multi-Purpose Room, PGP Event Center | B2 GF SB5 INFRA 22 23-02-053 | Other Facilities | MULITI-PURPOSE | NULL | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 1500000 | 1496127.97 | 60 | 2023-07-25 | NULL | 2023-09-23 | NULL | 2023-09-22 | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1235 | Construction of Day Care Center, PGP Event Center | B2 GF SB5 INFRA22 23-09-118 | Other Facilities | PGP FACILITIES | 12M X 0.6M Construction | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 1200000 | 1189982.77 | 60 | 2023-12-11 | NULL | 2024-02-09 | NULL | 2024-04-03 | 100% | NULL | By contract | Completed | TCC Powerserve Trading and Engineering Services | NULL | NULL
1236 | Improvement of the Office of the Vice Governor & SP Session Hall | B2 GF SB5 INFRA 22-23-02-052 | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 2750000 | 2749051.25 | 100 | 2023-08-11 | NULL | 2023-11-19 | NULL | 2024-10-11 | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1237 | Renovation/Repair of Provincial Human Respurce Management Office | B2 GF PEO 23-03-052 | Other Facilities | PGP FACILITIES | NULL | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 1780000 | 1776314.78 | 90 | 2023-08-03 | NULL | 2023-11-01 | NULL | 2024-04-26 | 100% | NULL | By contract | Completed | RD Abacial Construction | NULL | NULL
1238 | Repair / Rehabilitation of Paly VEP | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Paly | Taytay | PEO | 2022 | MOOE 2022 | 312859 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | NULL | Completed | NULL | NULL | NULL
1239 | Repair / Rehabilitation of GSO Building | B2 GF PEO 22-11-197 | Other Facilities | PGP FACILITIES | NULL | Bgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 1042320.84 | 1039700.89 | 75 | 2023-01-24 | NULL | 2023-04-09 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1240 | Repair / Rehabilitation of Ground Floor Capitol Commercial Complex Building | B2 GF PEO 22-11-196 | Other Facilities | PGP FACILITIES | NULL | Bgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 1500000 | 1498532.62 | 90 | 2023-01-25 | NULL | 2023-04-25 | NULL | NULL | 100% | NULL | By contract | Completed | F.B Murillo Construction | TIN 327-679-690 | NULL
1241 | Repair / Rehabilitation of PJMP Annex Building Kitchen Area | B2 GF PEO 22-11-208 | Other Facilities | PGP FACILITIES | NULL | Bancao-bancao | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 440000 | 439796.33 | 45 | 2023-01-24 | NULL | 2023-03-10 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1242 | Repair / Rehabiitation of Interior Walls of Capitol Complex | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 4079129.39 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned: SB No. 2 - 2023
1243 | Procument of Signages in PDRRMO Building | NULL | Other Facilities | PGP FACILITIES | NULL | Irawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 606173.19 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1244 | Repair and Maintenance of Hospitals (PWD FACILITIES) | PO-PEO 2023-11-1273 | Other Facilities | OTHER FACILITIES | PWD Facilities | ADDH,CODH ,NMH,RMH,SEDH | NULL | PEO | 2022 | MOOE 2022 | 144689.13 | 143920 | 14 | 2024-02-12 | NULL | 2024-02-26 | For approval | NULL | NULL | NULL | By contract | On going | E.C Timbancaya Enterprises | NULL | NULL
1245 | Repair/Rehabilitation of PEO (Installation of Glass Wall Partition) | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 104742.3 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | NULL | NULL | NULL
1246 | Repair of COVID-19 Laboratory (Staff Quarters Ceiling) | B2 GF PEO 22-11-209 | Medical Facilities | MEDICAL FACILITIES |  | Irawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 140588.15 | 140520 | 45 | 2023-02-13 |  | 2023-03-30 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1247 | Construction of Dietary/Linen Building in Sofronio Española District Hospital |  | Medical Facilities | MEDICAL FACILITIES |  | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2022 | SFVIP 2022 | 4300000 | 4293301.72 | 90 | 2022-08-24 | 1 | 2022-11-22 | 2023-04-22 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1248 | Construction of Mortuary Building in Sofronio Española District Hospital | B2 GF SFVIP22 24-05-084 | Medical Facilities | MEDICAL FACILITIES | Net Length: Single Storey: 6.0m x 6.0m (36 sq.m) | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2022 | SFVIP 2022 | 1195000 | 1183455.92 | 60 | 2024-08-28 |  | 2024-10-27 | For approval |  | 95% |  | By contract | On going | Maximmus Construction
1249 | Construction of Sewage Treatment Plant in Sofronio Española District Hospital | B2 GF SFVIP 22-11-206 | Medical Facilities | MEDICAL FACILITIES | Sewage Treatment Plant | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2022 | SFVIP 2022 | 3200000 | 3195278.33 | 60 | 2023-02-22 |  | 2023-04-23 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1250 | Improvement of Cory Park Covered Event Center (Installation of Air-conditioning Units) | NULL | Other Facilities | PGP FACILITIES | NULL | Capitol Building, PPC | Puerto Princesa City | PEO | 2022 | SFVIP 2022 | 13366500 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1251 | Construction of Two (2) Units Multipurpose Building | NULL | Other Infrastructure | MULITI-PURPOSE | NULL | Sito Bagto, Bgy. Sandoval, Roxas | Roxas | PEO | 2022 | SFVIP 2022 | 4000000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Termination | NULL | NULL | NULL
1252 | Construction of Two (2) Storey Dormitory in Aborlan Medicare Hospital | B2 GF SFVIP 22-08-145 | Medical Facilities | MEDICAL FACILITIES | CL: 20m(L) x 10m(W) x 9.4m(H) | Aborlan | Aborlan | PEO | 2022 | SFVIP 2022 | 4000000 | 3981380.54 | 180 | 2023-02-15 |  | 2023-08-14 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1253 | Renovation of Provincial Jail Management Division Records Office with Cabinets | NULL | Other Facilities | PGP FACILITIES | NULL | Bgy. Bancao-, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2020 | PJMD Fund | 350000 | 349129.83 | 60 | 2020-12-30 | NULL | 2021-02-28 | NULL | NULL | 100% | NULL | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318 | NULL
1254 | Construction of Three (3) - Storey Medical & Ward Building with Roof Deck for Helipad - Phase I |  | Medical Facilities | MEDICAL FACILITIES |  | Narra Municipal Hospital | Narra | PEO | 2018 | DOH Fund | 7326000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1255 | Construction of Barangay Health Station, Maligaya |  | Medical Facilities | BHS |  | Bgy. Maligaya, El Nido | El Nido | PEO | 2016 | Trust Fund - DOH | 1990000 | [9 empty] | By contract | Cancelled | E.V Villaos Trading and Construction Supply | TIN 142-914-104
1256 | Construction of 2nd and 3rd Floor of Main Building, Phase 3 |  | Medical Facilities | MEDICAL FACILITIES |  | Coron District Hospital | Coron | PEO | 2018 | Trust Fund - DOH | 18135810 | [7 empty] | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
1257 | Construction of Rural Agricultural Center | B2 GF DRAC 22-07-154 | Other Facilities | AGRICULTURAL FACILITIES | NULL | Bgy. Sta. Teresita | Dumaran | PEO | 2022 | RAC Fund | 3500000 | 2968937.64 | 180 | 2023-01-24 | NULL | 2023-07-23 | NULL | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1258 | Repair and Maitenance of Palawan Cooperative Center | B2 GF PCDP 22-09-151 | Other Facilities | PGP FACILITIES | NULL | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | PCDP Fund | 1300492.5 | 1078123.59 | 75 | 2022-12-27 | NULL | 2023-03-12 | NULL | NULL | 100% | NULL | By contract | Completed | Luis YC Builders & Supply | TIN 120-420-502-006 | NULL
1259 | Repair and Covid-19 Laboratory and Staff Quarters | B2 GF PEO 22-11-209 | Medical Facilities | MEDICAL FACILITIES |  | Bgy. Irawan. Puerto Princesa City | Puerto Princesa City | PEO | 2022 | General Fund | 140588.15 | 140520 | 45 | 2023-02-22 |  | 2023-04-08 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1260 | Renovation of PJMD Main Building | B2 GF JMFDP 22-11-170 | Other Facilities | PGP FACILITIES | NULL | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | PJMD Fund | 1156000 | 1154321.3 | 75 | 2023-01-23 | NULL | 2023-04-08 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1261 | Construction of PGP Solid Waste Management Central Material Recovery Facility | B2 GF SWM 22-11-171 | Other Facilities | PGP FACILITIES | NULL | Bgy. Iraawan, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | General Fund | 400000 | 398972.71 | 45 | 2023-02-16 | NULL | 2023-04-02 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1262 | Repair/Rehabilitation of Main Building & Facilities (Iso Bldg. Medical Annex Bldg. and Extension of Iso Bldg.) in SPPH | B2 GF SPPH 22-10-165/166/167/168 | Medical Facilities | MEDICAL FACILITIES |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | Capital outlay | 2247629.97 | 1990364.45 | 180 | 2023-01-23 | 2 | 2023-07-22 | For approval |  | 94.43% |  | By contract | On going | F.B Murillo Construction | TIN 772-152-432
1263 | Repair and Maintenance of Aborlan Medicare Hospital, Aborlan, Palawan |  | Medical Facilities | MEDICAL FACILITIES | Road Network: 112m(l) x 4m(w) x 0.15m (t) - Main Building: 60m x 60m - E.R Complex: 2.5m x 19m - Isolation Building: 8m x 20m - Dietary Building: 10m x 20m | Aborlan Medicare Hospital | Aborlan | PEO | 2022 | Aborlan Medical Hospital Fund | 5000000 | 4775580.89 | 120 | 2023-01-17 |  | 2023-05-17 | 2023-07-16 | 2023-09-01 | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
1264 | Construction of Proposed 11m x 12.5m Bunk House | B2 SB2 POP19 300-20-03-02965 | Other Facilities | OTHER FACILITIES | NULL | Bgy. Apurawan, Aborlan, Palawan | Aborlan | PEO | 2020 | Supplemental Budget No. 2 POP | 2999999.24 | 2631826.62 | 150 | 2020-10-02 | NULL | 2021-03-01 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
1265 | Construction of Proposed 11m x 12.5m Bunk House | B2 SB2 POP19 300-20-03-02966 | Other Facilities | PGP FACILITIES | NULL | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2020 | POP Fund | 2999999.24 | 2631826.62 | 150 | 2020-10-02 | NULL | 2021-03-01 | NULL | NULL | 100% | NULL | By contract | Completed | Beta-J Construction | 159-232-934 | NULL
1266 | Concreting of Road Network in Cuyo District Hospital | B2 PEO 300-21-08-09452 | Medical Facilities | MEDICAL FACILITIES |  | Cuyo, Palawan | Cuyo | PEO | 2021 | 20% Development Fund | 2000000 | 1999504.21 | 90 | 2021-10-06 | 2 | 2022-01-04 | 2022-02-03 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1267 | Improvement of Intesive Juvenile Intervention Support Center (IJSC) | B2 GF BPTC 22-05-089 | Other Facilities | PGP FACILITIES | Floor Area: Construction of Multi-purpose hall=175.64 sqm. - Floor Area: Construction of Perimater Fence=24.3 - Length=Renovation of Main Building=144.87 sq.m | Barangay Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Other fund | 5500000 | 5169583.32 | 180 | 2023-03-29 | NULL | 2023-09-25 | 2023-12-09 | 2024-02-07 | 100% | NULL | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662 | NULL
1268 | Construction of Tubbataha Reef Ranger Station (Main Module) (Research Module) (Transportation Module) Phase II | B2 TF PEO 23-01-005 | Other Facilities | OTHER FACILITIES | Construction of structural concrete, installation of structural metal, fabricated metal and decking including metal painting works for Ranger Station Building | Tubbataha Reef, Cagayancillo, Palawan | Cagayancillo | PEO | 2022 | DENR - TIEZA (Trust Fund 2022) | 58375080 | 58234005.51 | 365 | 2023-04-18 | NULL | 2024-04-17 | 2025-01-10 | NULL | 93.56% | NULL | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
1269 | Construction of Covered Court with Stage at Lualhati Women Center | B1 GF LWC21 22-09-133 | Other Facilities | PGP FACILITIES | Net length: 9.0m x 15.0m Covered court - 4.20m x 6.30m stage | Bgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Trust Fund | 1497000 | 1489722.6 | 120 | 2023-01-25 | NULL | 2023-05-25 | NULL | NULL | NULL | NULL | By contract | Terminated | HNT Builders & Enterprises | TIN 909-572-814 | Termination for convenience: RA 11361
1270 | Rehabilitation Of Magbabadil Bridge (Approach, PCCP & Slope Protection) | B2 GF PEO 23-02-030 | Other Infrastructure | SLOPE PROTECTION | 7 M X 6 M | Bgy. Mabini | Aborlan | PEO | 2023 | 20% Development Fund | 1500000 | 1477901 | 90 | 2023-05-05 | NULL | 2023-08-03 | NULL | NULL | 100% | NULL | By contract | Completed | AMLC Builders Construction and Supply | TIN 428-298-201 | NULL
1271 | Repair Of Road From National Highway - Jose Rizal | B2 GF PEO 23-02-025 | Transportation Facilities | ROAD | 2 Pccp Blocks: L=4.5 M; W=2.0 M, T=0.20, With 1-L-36'' Diameter X 7 Rcpc With Headwall B.S | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 220000 | 219180.99 | 45 | 2023-05-26 | NULL | 2023-07-10 | NULL | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1272 | Repair & Rehabilitation Of Bridge Slope Protection In Saraza Bridge | B2 GF PEO 23-04-079 | Other Infrastructure | SLOPE PROTECTION | 10m(L),6.10m(W),0.20m(T) | Bgy. Saraza | Brooke's Point | PEO | 2023 | 20% Development Fund | 5400000 | 5391830.43 | 205 | 2023-08-30 | NULL | 2024-03-22 | Subject for LD | NULL | 99.65% | NULL | By contract | On going | MVP Construction and Trdaing Inc. | TIN 616-777-887 | NULL
1273 | Construction Of Riverbank Protection/Flood Control At Tamlang Bridge | NULL | Other Infrastructure | SLOPE PROTECTION | Sp:236.88 Cu.M - 15m (L) X 0.30m (T)-30 Gabions | Bgy. Saraza | Brooke's Point | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 5 | 5000000 | NULL | 120 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to 2023 Supplemental Budget No. 5
1274 | Construction Of Cabinbin River Flat Slab Bridge | NULL | Transportation Facilities | ROAD | 6m X 4m (Bothsides) - Bridge (4.40mx30ln.M) Rc Slope (68.24) Riprap (237.44 Cu.M) Pccp 30 Ln.M | Bgy. Imulnod | Brooke's Point | PEO | 2023 | 20% Development Fund | 18000000 | NULL | 182 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to 2023 Supplemental Budget No. 3
1275 | Rehabilitation Of Pulot Shore Bridge Slope Protection | B2 GF PEO 23-04-078 | Other Infrastructure | SLOPE PROTECTION | 156.58 Cu.M; 28 Gabions (1mx1mx2m) | S. Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 3000000 | 2986642.2 | 115 | 2023-09-09 | NULL | 2024-01-02 | NULL | 2023-12-29 | 100% | NULL | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887 | NULL
1276 | Rehabilitation Of Panitian Bridge Slope Protection | B2 GF PEO 23-04-059 | Other Infrastructure | SLOPE PROTECTION | 273.42 Cu.M; 38 Gabions (1mx1mx2m) | S. Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 5000000 | 4046838.42 | 115 | 2023-06-19 | 1 | 2023-10-12 | 2023-12-11 | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1277 | Restoration/Repair of Tagumpay RCDG Bridge 2 (Approach) | B2 GF PEO 23-02-022 | Transportation Facilities | ROAD | 1 Side - 6m X 6.1 M | Bgy. Tagumpay, Dumaran, Palawan | Dumaran | PEO | 2023 | 20% Development Fund | 300000 | 298884.7 | 60 | 2023-06-05 | NULL | 2023-08-04 | NULL | 2023-08-04 | 100% | NULL | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000 | NULL
1278 | Rehabilitation Of Bridge Slope Protection At Abutment "A-B" In Latungay Bridge | B2 GF PEO 23-02-044 | Other Infrastructure | SLOPE PROTECTION | Bridge Slope Protection: Volume (cu.m): 124.7352 - Approach Slope Protection: 4.7m both sides of upstream | Bgy. Ilian, Dumaran, Palawan | Dumaran | PEO | 2023 | 20% Development Fund | 2500000 | 2490641.44 | 113 | 2023-05-29 | NULL | 2023-09-19 | 2023-12-07 | 2024-03-11 | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1279 | Rehabilitation Of Bridge Slope Protection At Abutment "A-B" In Sta. Maria Bridge II | B2 GF PEO 23-02-046 | Other Infrastructure | SLOPE PROTECTION | Bridge Slope Protection: Volume (cu.m): 124.74 - 12.8m Both Sides Of Upstream | Bgy. Sta. Maria, Dumaran, Palawan | Dumaran | PEO | 2023 | 20% Development Fund | 3000000 | 2520934.12 | 113 | 2023-05-30 | NULL | 2023-09-20 | 2023-12-07 | 2024-03-11 | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1280 | Rehabilitation Of Caramay Hanging Bridge | B2 GF PEO 23-04-058 | Transportation Facilities | ROAD | 101.10 Ln.M | Bgy. Caramay, Roxas, Palawan | Roxas | PEO | 2023 | 20% Development Fund | 2000000 | 1989843.27 | 60 | 2023-07-19 | NULL | 2023-09-17 | For approval | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1281 | Installation Of 5 Lines - 36" Diameter Rcpc With Headwall In Tigman Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 5 Units Of 5 Lines - 36" Diameter Rcpc With Headwall In Tigman Road | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 600000 | NULL | 45 | 2023-06-15 | NULL | NULL | For approval | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1282 | Construction Of Spillway | B2 GF PEO 23-05-093 | Other Infrastructure | OTHER FACILITIES | Spillway: 15mlx9.70mwx3.05mh | Isaub | Aborlan | PEO | 2023 | 20% Development Fund | 3000000 | 2994333.15 | 115 | 2023-07-10 | NULL | 2023-11-02 | NULL | 2023-10-18 | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1283 | Installation Of 1 Line - 36" Diameter Rcpc With Headwall In Linamen - Batang Batang Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 1-L 36'' Diameter Rcpc X 8.00 Length With Headawall Bothsides In Different Stations | Municipality Of Narra | Narra | PEO | 2023 | 20% Development Fund | 120000 | 119804.55 | 30 | 2023-06-15 | NULL | NULL | Subject for LD | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1284 | Installation Of 2 Lines - 36" Diameter Rcpc With Headwall In Aramaywan Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 2 (Two) 1-L 36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Municipality Of Narra | Narra | PEO | 2023 | 20% Development Fund | 240000 | 239004.35 | 45 | 2023-06-15 | NULL | NULL | Subject for LD | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1285 | Rehabilitation Of 2-Barrel Box Culvert, Aramaywan Road | B2 GF PEO 23-04-085 | Other Infrastructure | DRAINAGE | 2.8m(H) X 5.60m(W) X 8m(L) X 0.30m Thk With Slope Protection And Approach | Narra, Palawan | Narra | PEO | 2023 | 20% Development Fund | 3550000 | 2981117.03 | 113 | 2023-06-30 | 1 | 2023-10-21 | 2024-01-24 | NULL | 100% | NULL | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199 | NULL
1286 | Installation Of 5 Lines - 36" Diameter Rcpc With Headwall In Agis Agis Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 5 Units 1l-36'' Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 600000 | NULL | 45 | 2023-06-15 | NULL | NULL | 2023-09-28 | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1287 | Installation Of 6 Lines - 36" Diameter Rcpc With Headwall In Abokayan Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 6 Units 1l-36''diameter Rcpc With Headwall Bothsides In Different Station | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 720000 | NULL | 75 | 2023-06-15 | 1 | NULL | 2023-09-28 | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1288 | Installation Of 4 Lines - 36" Diameter Rcpc With Headwall In Iraray Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 4 Units 1-L36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 480000 | NULL | 45 | 2023-06-15 | NULL | NULL | 2023-09-28 | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1289 | Installation Of 10 Lines - 36" Diameter Rcpc With Headwall In Panitian Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 10 Units 1l-36''diameter Rcpc With Headwall Bothsides In Different Station | Quezon, Palawan | Quezon | PEO | 2023 | 20% Development Fund | 1200000 | 1199269.65 | 75 | 2023-06-15 | NULL | 2023-08-29 | NULL | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1290 | Installation Of 2 Lines - 36" Diameter Rcpc With Headwall In Inogbong Feeder Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 2 (Two) 1-L 36 Diamteter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Municipality Of Bataraza | Bataraza | PEO | 2023 | 20% Development Fund | 240000 | 239004.37 | 45 | 2023-06-15 | 1 | NULL | For approval | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1291 | Installation Of 4 Lines - 36" Diameter Rcpc With Headwall In Iwahig - Igang Igang - Sarong Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 4 Units 1l-36''diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Station | Bataraza, Palawan | Bataraza | PEO | 2023 | 20% Development Fund | 480000 | 478714.67 | 45 | 2023-06-15 | NULL | NULL | For approval | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1292 | Construction Of RCDG Bridge | B2 GF PEO 23-04-068 | Transportation Facilities | ROAD | Approach: 4m X 6m (Bothsides) - Bridge: 15ln.m - RC Slope (cu.m) 97.35 | Sandoval | Bataraza | PEO | 2023 | 20% Development Fund | 8652821.98 | 7311536 | 180 | 2023-07-06 | NULL | 2024-01-02 | NULL | NULL | 100% | NULL | By contract | Completed | KIR Konstructicon Builders and Supply | TIN 010-605-480 | NULL
1293 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) | B2 GF PEO 23-03-057 | Other Infrastructure | DRAINAGE | 1-3m (H) - 3.56m (W) - 6.6(L) - 0.30m Thick With Approach And Slope Prtotection | Bunog, Rizal, Palawan | Rizal | PEO | 2023 | 20% Development Fund | 2000000 | 1682824.11 | 115 | 2023-06-30 | NULL | 2023-10-23 | NULL | 2023-09-10 | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1294 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) | B2 GF PEO 23-04-086 | Other Infrastructure | DRAINAGE | 1-3m (H) - 3.56m (W) - 6.6(L) - 0.30m Thick With Approach And Slope Prtotection | TDC, Port Barton | San Vicente | PEO | 2023 | 20% Development Fund | 2000000 | 1765317.29 | 115 | 2023-06-30 | NULL | 2023-10-23 | NULL | NULL | 100% | NULL | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887 | NULL
1295 | Construction Of Spillway | B2 GF PEO 23-05-091 | Other Infrastructure | OTHER FACILITIES | 10m(L) X 9.60m (W) X 3.05m (H) | Tinitian, Roxas, Palawan | Roxas | PEO | 2023 | 20% Development Fund | 2000000 | 1991735.49 | 115 | 2023-07-17 | NULL | 2023-11-09 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1296 | Installation Of 6 Lines - 36" Diameter Rcpc With Headwall In Barotuan - Bucana Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | DRAINAGE | 6 Units 1l-36''diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Station | El Nido, Palawan | El Nido | PEO | 2023 | 20% Development Fund | 720000 | NULL | 60 | 2023-06-15 | NULL | NULL | For approval | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1297 | Replacement Of Timber Bridge To Two (2) Barrel RCBC - (2 Units), National Highway - Old Guinlo Road | B2 GF PEO 23-03-069 | Other Infrastructure | DRAINAGE | 2 Units In Different Location/Station 3m(H)X6.9m(W)X8.5(L)X0.30m Thick | So. Pagkakaisa & So.Campo, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 8000000 | 7990227.82 | 144 | 2023-06-29 | NULL | 2023-11-20 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1298 | Construction Of Two (2) Barrel RCBC And Installation Of 4-Lines 36" Dia RCPC | B2 GF PEO 23-03-059 | Other Infrastructure | DRAINAGE | 1 Unit -3m (H) X 6.9m (W)X8.5m(L)X0.30m(Thick) With Slope Protection And Approach | Brgy. Guadalupe, Coron, Palawan | Coron | PEO | 2023 | 20% Development Fund | 5800000 | 5795648.4 | 144 | 2023-06-29 | NULL | 2023-11-20 | NULL | 2024-01-12 | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1299 | Concreting Of Road Network In Capitol Ville Subdivision | NULL | Other Facilities | PGP FACILITIES | NULL | Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 11100000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to 2023 Supplemental Budget No. 3
1300 | Concreting Of Slab & Road Network In Warehouse For Disaster Relief Goods/Stockpile | B2 GF PEO 23-02-028 | Other Facilities | PGP FACILITIES | (A) Road Network: 78m x 5m - (B) Concrete Slab: 75m x 20m x 0.1m - (C) 36'' RCPC: 4 Lines - 7 ln.m - (D) Grouted Riprap: 91 ln.m | Bgy. Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 4600000 | 3175553.72 | 120 | 2023-05-12 | 1 | 2023-09-09 | For approval | NULL | 100% | NULL | By contract | Completed | West Blue Builders | NULL | NULL
1301 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Magara | Roxas | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1302 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Liminangcong | Taytay | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | NULL | 2024-04-28 | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1303 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 (B2 TF PEO 23-08-109) | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Poblacion | Araceli | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | For approval | NULL | 80% | NULL | By contract | On going | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1304 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Brgy. 3 | Coron | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | 1 | NULL | 2023-12-30 | 2024-01-13 | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1305 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Bgy. Cocoro | Magsaysay | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | Subject for LD | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1306 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Panlaitan | Busuanga | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | 2024-08-01 | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1307 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Tagumpay | Roxas | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | NULL | 2024-05-02 | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1308 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Jolo | Roxas | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | NULL | 2024-05-01 | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1309 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | COVERED COURT | 30 m (l) x 18m (w) | Culasian | Dumaran | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | NULL | NULL | NULL | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1310 | Construction Of Multi-Purpose Building (Livelihood Center) | B2 GF PEO 23-04-083 | Other Infrastructure | MULITI-PURPOSE | 320 Sqm | Roxas | Roxas | PEO | 2023 | 20% Development Fund | 8000000 | 6951109.51 | 210 | 2023-07-10 | 1 | 2024-02-05 | 2024-04-04 | NULL | 100% | NULL | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001 | NULL
1311 | Construction Of Multi-Purpose Building (Livelihood Center) | B2 GF PEO 23-04-055 | Other Infrastructure | MULITI-PURPOSE | 320 Sqm | Taytay | Taytay | PEO | 2023 | 20% Development Fund | 8000000 | 7114928.25 | 210 | 2023-09-26 | 1 | 2024-04-23 | For approval | NULL | 85% | NULL | By contract | On going | Jaica Construction Services | NULL | NULL
1312 | Construction Of Multi-Purpose Building (Livelihood Center) | B2 GF PEO 23-04-054 | Other Infrastructure | MULITI-PURPOSE | 320 Sqm | El Nido | El Nido | PEO | 2023 | 20% Development Fund | 8000000 | 6799453.44 | 210 | 2023-07-24 | NULL | 2024-02-19 | Subject for LD | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1313 | Construction Of Four (4) Model Unit In Capitol Ville | NULL | Other Facilities | PGP FACILITIES | NULL | Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 7200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to 2023 Supplemental Budget No. 3
1314 | Construction Of Multi-Purpose Building, Phase II | B2 GF PEO 23-02-024 | Other Infrastructure | MULITI-PURPOSE | 6.5m X 11 M Two-Storey Building Second Floor | Tenga-Tenga | Cuyo | PEO | 2023 | 20% Development Fund | 2000000 | 1880491.65 | 90 | 2023-05-12 | 2 | 2023-08-10 | For approval | NULL | 100% | NULL | By contract | Completed | Bat's Construction Services | TIN 491-731-278 | NULL
1315 | Construction Of Two (2) Storey Dormitory Phase II, Aborlan Medicare Hospital | B2 GF PEO 23-34-03-076 | Medical Facilities | MEDICAL FACILITIES | 20m(l) X 10m(w) X 9.4m(h) | Municipality Of Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 6000000 | 5982386.64 | 210 | 2024-07-16 |  | 2025-02-11 |  |  | 86.2% |  | By contract | On going | ZYK Construction
1316 | Construction Of PWD Ramp For Three (3) Storey Medical Arts Building, Aborlan Medicare Hospital | B2 GF PEO 23-04-086 | Medical Facilities | MEDICAL FACILITIES | 24m x 6m | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 4950000 | 4896891.5 | 150 | 2023-07-06 | 1 | 2023-12-03 | Subject for LD |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1317 | Supply And Installation Of Fire Protection System For Three (3) Storey Medical Arts Building, Aborlan Medicare Hospital | B2 GF PEO 23-05-092 | Medical Facilities | MEDICAL FACILITIES | n/a | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 3450000 | 3441716.25 | 75 | 2023-07-17 |  | 2023-09-30 | Subject for LD | 2024-07-31 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1318 | Construction Of Three (3) Storey Medical Arts Building Phase III | B2 GF PEO 23-04-084 | Medical Facilities | MEDICAL FACILITIES | 43m x 15m | Municipality Of Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 10000000 | 9904303.69 | 150 | 2023-07-06 | 1 | 2023-12-03 | Subject for LD |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1319 | Improvement Of Landscaping For Medical Arts Building | B2 GF PEO-28-02-051 | Medical Facilities | MEDICAL FACILITIES | Modern Tropical Garden | Municipality Of Narra | Narra | PEO | 2023 | 20% Development Fund | 350000 | 346663.63 | 45 | 2023-05-17 |  | 2023-07-01 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1320 | Supply And Installation Of 1-125 Kva Generator Set With Automatic Transfer Switch (Ats), Sofronio Española District Hospital | Hospital Facilities | Medical Facilities | MEDICAL FACILITIES | Supply and Installation | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 1375000 | [7 empty] | 100% |  | By contract | Completed
1321 | Supply And Installation Of 200 Mm² Copper Wire Power Cable, Sofronio Española District Hospital |  | Medical Facilities | MEDICAL FACILITIES | Supply and Installation | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 654000 | [10 empty] | Failure of bidding |  |  | Failure of Bidding: For re-construction of Financial Documents of Procurement - Insufficient Fund
1322 | Supply And Installation Of Four (4) Units Of Air Conditioned, Sofronio Española District Hospital |  | Medical Facilities | MEDICAL FACILITIES | Aircon: 4 Units | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 254080.49 | [7 empty] | 100% |  |  | Completed
1323 | Construction Of Two (2) Storey Dormitory Phase II, Sofronio Española District Hospital | Hospital Facilities | Medical Facilities | MEDICAL FACILITIES | 12.0 X 10.50M Building concrete laundry and patio | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 2500000 |  | 210 | [8 empty] | Re-aligned |  |  | Re-aligned to 2023 Supplemental Budget No. 3
1324 | Construction Of Retaining Wall, Sofronio Española District Hospital | B2 GF PEO 23-02-047 | Other Infrastructure | SLOPE PROTECTION | 69.58 m (l) | Municipality Of Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 5000000 | 4988002.69 | 90 | 2023-05-10 | 1 | 2023-08-08 | 2023-11-21 | NULL | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1325 | Supply And Installation Of Automatic Voltage Regulator For The Generator Set, Bataraza District Hospital |  | Medical Facilities | MEDICAL FACILITIES | Supply and Installation | Bataraza Distirct Hospital | Bataraza | PEO | 2023 | 20% Development Fund | 52500 | [10 empty] | Failure of bidding |  |  | Failure of Bidding: For re-construction of Financial Documents of Procurement - Insufficient Fund
1326 | Supply And Installation Of Twenty Five (25) Units Of Air Conditioned, Balabac District Hospital | Hospital Facilities | Medical Facilities | MEDICAL FACILITIES | Supply and Installation | Catagupan | Balabac | PEO | 2023 | 20% Development Fund | 1576511.53 | [7 empty] | 100% |  |  | Completed
1327 | Construction Of Perimeter Fence Phase II, Balabac District Hospital | B2 GF PEO 23-02-050 | Medical Facilities | MEDICAL FACILITIES | 273 l.m X 91 Span | Catagupan | Balabac | PEO | 2023 | 20% Development Fund | 2800000 | 2741746.82 | 120 | 2023-06-13 |  | 2023-10-11 | 2024-01-09 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
1328 | Construction Of Drainage Structure In Northern Palawan Technical Vocational School, Phase II | B2 GF PEO 23-04-056 | Other Infrastructure | DRAINAGE | 67.50 Ln.m | Arado, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 900000 | 899323.55 | 75 | 2023-05-29 | 1 | 2023-08-12 | 2023-08-13 | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1329 | Construction Of Three In One Large Scale Rural Health Unit, Phase II | B2 GF PEO 23-04-077 | Medical Facilities | RHU | 981 Sq.M | Aporawan | Aborlan | PEO | 2023 | 20% Development Fund | 9500000 | 9138883.9 | 150 | 2023-08-29 | 2 | 2024-01-26 | 2024-03-26 |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1330 | Construction Of Perimeter Fence Phase I, Panalingaan Rural Health Unit | B2 GF PEO 23-02-043 | Medical Facilities | RHU | 120 Ln. M - 40.00 Span | Panalingaan, Rizal, Palawan | Rizal | PEO | 2023 | 20% Development Fund | 1500000 | 1499006.75 | 120 | 2023-08-30 |  | 2023-12-28 |  | 2024-02-05 | 100% |  | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887
1331 | Concreting Of Road With Parking Area, Panalingaan Rural Health Unit | B2 GF PEO 23-02-035 | Medical Facilities | RHU | L=109 M; W=5.0m; T=0.15m | Panalingaan, Rizal, Palawan | Rizal | PEO | 2023 | 20% Development Fund | 2000000 | 1995469.45 | 90 | 2023-07-17 |  | 2023-10-15 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1332 | Construction Of Three In One Large Scale Rural Health Unit, Phase II | B2 GF PEO 23-04-076 | Medical Facilities | RHU | 981 Sqm | Municipality Of Agutaya | Agutaya | PEO | 2023 | 20% Development Fund | 9500000 | 9494438.33 | 180 | 2023-07-10 | 2 | 2024-09-02 | For approval |  | 92% |  | By contract | On going | Maryjonica Construction | TIN 350-458-389
1333 | Construction Of Three In One Large Scale Rural Health Unit, Phase II | B2 GF PEO 23-04-081 | Medical Facilities | RHU | 981 Sqm | Linapacan | Linapacan | PEO | 2023 | 20% Development Fund | 9500000 | 9450000 | 180 | 2023-08-04 |  | 2024-01-31 | For approval |  | 85% |  | By contract | On going | JBS Abia Construction | TIN 428-617-369
1334 | Concreting Of Access Road With RCPC & Parking Area In Busuanga Rural Health Unit | B2 GF PEO 23-02-026 | Medical Facilities | RHU | L=135 M; W=5.0m; T=0.15m | Busuanga | Busuanga | PEO | 2023 | 20% Development Fund | 3000000 | 2998119.82 | 90 | 2023-06-13 |  | 2023-09-11 |  |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1335 | Construction Of Barangay Health Station |  | Medical Facilities | BHS | 8.95m X 11.075m | Green Island | Roxas | PEO | 2023 | 20% Development Fund | 2500000 |  | 120 | [8 empty] | Re-aligned |  |  | Re-aligned: to Imulnod Bridge - Re-aligned: Supplemental Budget No. 3 - 2023
1336 | Repair And Upgrading Of Calandagan VEP Power Distribution | B2 GF PEO 23-02-048 | Power and Energy Development Program | ELECTRIFICATION | 3 Phase Line = 960 Mts - Ub Lines=960 Mts | Calandagan | Araceli | PEO | 2023 | 20% Development Fund | 2500000 | 2498766.63 | 60 | 2023-06-05 | 1 | 2023-08-04 | 2023-09-03 | 2023-08-14 | 100% | NULL | By contract | Completed | One Badajos Construction & Trading Corporation | TIN 010-590-630 | NULL
1337 | Construction Of Power Distribution Lines Of Biton VEP, Phase II | B2 GFPEO 23-02-037 | Power and Energy Development Program | ELECTRIFICATION | 1 Phase Line = 360 Mts - Ub Lines=360 Mts - Os Lines=1,120 Mts | Bgy. Biton, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 1800000 | 1798596.36 | 60 | 2023-09-15 | NULL | 2023-11-14 | NULL | 2024-02-02 | 100% | NULL | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496 | NULL
1338 | Completion Of Powerhouse In Biton Vep | B2 GF PEO 23-04-060 | Power and Energy Development Program | ELECTRIFICATION | 30mx20m Co0mpletion/Repair | Biton | Taytay | PEO | 2023 | 20% Development Fund | 1200000 | 1160350.11 | 75 | 2023-08-09 | NULL | 2023-10-23 | NULL | NULL | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
1339 | Construction Of Power Distribution Lines, Phase II In Casian Vep | B2 GF PEO 23-02-036 | Power and Energy Development Program | ELECTRIFICATION | 3 Phase Line=1275 Mts - 1 Phase Line=726 Mts - Up Lines=2001 Mts - Os Lines=337 Mts | Bgy. Casian, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 3300000 | 3052145.85 | 85 | 2024-02-28 | NULL | 2024-05-23 | 2024-06-22 | NULL | 100% | NULL | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496 | NULL
1340 | Repair Of Bisucay Island Village Electrification Project | B2 GF PEO 23-02-049 | Power and Energy Development Program | ELECTRIFICATION | 3 Phase Line =2760 Mts - 1 Phase Line=2741 Mts - Ub Lines=5501 Mts - Os Lines=1962 Mts | Bisucay Island, Cuyo, Palawan | Cuyo | PEO | 2023 | 20% Development Fund | 1300000 | 1261785.47 | 30 | 2023-05-29 | NULL | 2023-06-28 | NULL | 2023-06-28 | 100% | NULL | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000 | NULL
1341 | Construction Of Perimeter Fence Of The Halfway House For Former Rebel & Militia Ng Bayan, Phase II | B2 GF PEO 23-02-042 | Other Facilities | PGP FACILITIES | Painting Masonry (557.33 Sqm) - Painting Metal (136.33 Sqm) - Cemwnt Plaster (165 Sqm) | Bgy. Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 300000 | 299495.35 | 30 | 2023-05-29 | NULL | 2023-06-28 | NULL | NULL | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001 | NULL
1342 | Construction Of 2-Classroom School Building, Diapila National Highschool | B2 GF SEF 23-05-096 | Educational Facilities | SCHOOL FACILITIES | 2 CL - 22.5 M (L) X 7 M (W) | El Nido Del Norte District, El Nido, Palawan | El Nido | PEO | 2023 | Special Education Fund - 2022 | 5666000 | 5600000 | 155 | 2023-08-04 | NULL | 2024-01-06 | For Approval | NULL | 100% | NULL | By contract | Completed | JBS Abia Construction | TIN 428-617-369 | NULL
1343 | Construction Of 2-Classroom School Building,Buliluyan National Highschool | B2 GF SEF 23-05-095 | Educational Facilities | SCHOOL FACILITIES | 2 CL - 22.5 M (L) X 7 M (W) | Bataraza District, Bataraza, Palawan | Bataraza | PEO | 2023 | Special Education Fund - 2022 | 5666000 | 5647876.35 | 155 | 2023-08-09 | NULL | 2024-01-11 | For Approval | NULL | 46.01% | NULL | By contract | No movement | F.B Murillo Construction | TIN 772-152-432 | No presence of manpower on site. No materials were stored on site
1344 | Construction Of 2-Classroom School Building,Maringian Elementary School | B2 GF SEF 23-05-095 | Educational Facilities | SCHOOL FACILITIES | 2 CL - 22.5 M (L) X 7 M (W) | Cuyo District, Cuyo | Cuyo | PEO | 2023 | Special Education Fund - 2022 | 5666000 | 5665458.08 | 155 | 2023-09-26 | NULL | 2024-02-28 | Subject for LD | NULL | 100% | NULL | By contract | Completed | M. Luengo Construction | TIN 257-013-134 | NULL
1345 | Construction Of 2-Classroom School Building,Decalachao Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Decalachao | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1346 | Construction Of 2-Classroom School Building,Sta. Monica Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Guadalupe | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1347 | Construction Of 2-Classroom School Building,Bulalacao Integrated School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Bulalacao | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5485260.73 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1348 | Construction Of 2-Classroom School Building,Bintuan Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Bintuan | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1349 | Construction Of 2-Classroom School Building,Borac Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Borac | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | 2024-01-08 | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1350 | Construction Of 2-Classroom School Building,Concepcion Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Concepcion | Busuanga | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | For approval | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1351 | Construction Of 2-Classroom School Building,Bogtong Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Bogtong | Busuanga | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5457405.08 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1352 | Construction Of 2-Classroom School Building,New Culaylayan Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. New Culaylayan | Linapacan | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5485260.73 | 140 | 2023-07-10 | NULL | 2023-11-27 | For approval | NULL | 50% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1353 | Construction Of 2-Classroom School Building, Sandoval Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Taytay | Taytay | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5466687.58 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-01-17 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1354 | Construction Of 2-Classroom School Building, Jose Rizal Apoc-Apoc National Highschool | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Apoc-Apoc | Aborlan | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5410798.05 | 140 | 2023-07-24 | 1 | 2023-12-11 | 2024-05-10 | 2024-03-17 | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1355 | Construction Of 2-Classroom School Building, Panacan Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Narra | Narra | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5418026 | 140 | 2023-07-24 | 1 | 2023-12-11 | 2024-01-22 | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1356 | Construction Of 2-Classroom School Building, Cacarigan Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Narra, Palawan | Narra | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5418026 | 140 | 2023-07-24 | NULL | 2023-12-11 | NULL | 2023-12-29 | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1357 | Construction Of 2-Classroom School Building, Busay Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Taburi, Rizal, Palawan | Rizal | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5509839.05 | 140 | 2023-07-24 | 1 | 2023-12-11 | NULL | 2023-12-29 | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1358 | Construction Of 2-Classroom School Building, Rizal Central School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5509839.05 | 140 | 2023-07-24 | NULL | 2023-12-11 | NULL | 2023-11-27 | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1359 | Construction Of 2-Classroom School Building, Bulalacao Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bataraza | Bataraza | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5509839.05 | 140 | 2023-07-24 | NULL | 2023-12-11 | For Approval | NULL | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1360 | Construction Of 2-Classroom School Building, Luntab Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | SCHOOL FACILITIES | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Pulot Shore | Sofronio Española | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5418026 | 140 | 2023-07-24 | NULL | 2023-12-11 | NULL | 2024-03-17 | 100% | NULL | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1361 | Restoration / Repair Of Northern Palawan Provincial Hospital And Facilities | B2 TF PEO 23-07-101 | Medical Facilities | MEDICAL FACILITIES | Main Building - 1,090.20 Sqm; Ceiling: Dietary-132 Sqm - Ceiling Oxygen -222 Ln M - Motorpool 6 Ln.M | Sitio Arado, Bgy. Poblacion, Taytay, Palawan | Taytay | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 2602202.98 | 2596793.65 | 90 | 2023-11-06 |  | 2024-02-04 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
1362 | Restoration/Renovation Of Roxas Medicare Hospital | B2 TF PEO 23-07-106 | Medical Facilities | MEDICAL FACILITIES | Main Building 3600 M2 - New Isolation Building 160m2 - Old Isolation 160m2 - Dietary Building 200m2 - Motorpool Building 243.5m2 - Dq - 464 M2 | Roxas Medicare Hospital | Roxas | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 4527738.54 | 3984249.25 | 120 | 2023-09-26 |  | 2024-01-24 | 2024-02-23 |  | 100% |  | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662
1363 | Restoration/Repair Of San Vicente District Hospital And Facilities | B2 TF PEO 23-07-107 | Medical Facilities | MEDICAL FACILITIES | Main Building - 606.53 Sqm, Dietary/Linen Building - 36.0 Sqm, Isolation Building - 54.34 Sqm | San Vicente, Palawan | San Vicente | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 1872951.35 | 1856547.55 | 90 | 2023-11-05 |  | 2024-02-03 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
1364 | Restoration/Repair Of Cuyo District Hospital | B2 TF PEO 23-07-104 | Medical Facilities | MEDICAL FACILITIES | Single Storey 60m X 60m Hospital Building | Municipality Of Cuyo, Palawan | Cuyo | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 561123.17 | 546483.36 | 30 | 2023-11-06 |  | 2023-12-06 |  |  | 100% |  | By contract | Completed | M. Luengo Construction | TIN 257-013-134
1365 | Restoration/Repair Of Araceli-Dumaran District Hospital | B2 TF PEO 23-07-102 | Medical Facilities | MEDICAL FACILITIES | 60m X 60m | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 1104052.3 | 1102998.48 | 78 | 2023-09-26 |  | 2023-12-13 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1366 | Restoration/Repair Of El Nido Community Hospital And Facilities | B2 GF PEO 23-04-103 | Medical Facilities | MEDICAL FACILITIES | 60m X 60m | El Nido | El Nido | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 1710672.2 | 1587322 | 120 | 2023-09-25 |  | 2024-01-23 |  |  | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1367 | Repair/Rehabilitation Of Coron District Hospital & Facilities | B2 TF PEO 23-07-105 | Medical Facilities | MEDICAL FACILITIES | 360 Square Meters 151.20 Square Meter Chb 168 Square Meter Roofing | Coron | Coron | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 2621259.36 | 2600216.03 | 90 | 2023-09-26 |  | 2023-12-25 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1368 | Concreting Of Road From Highway Junction - Brgy. Mendoza | B2 GF SFVIP 23-04-090 | Transportation Facilities | ROAD | 687 Lm | Roxas, Palawan | Roxas | PEO | 2023 | SFVIP | 12000000 | 11819999.2 | 120 | 2023-07-19 | NULL | 2023-11-16 | NULL | NULL | 100% | NULL | By contract | Completed | Seven Digit Construction and Supplies | TIN 183-661-696 | NULL
1369 | Concreting Of Balala-Malaking Patag Road (Sta. 5+913.80-Sta. 6+071.80) | B2 GF SFVIP 23-04-089 | Transportation Facilities | ROAD | Road Network=158 Ln.M - W=6.10m - T=0.20m - Shoulder 1m B.S | Culion, Palawan | Culion | PEO | 2023 | SFVIP | 4000000 | 3956976.52 | 90 | 2023-08-29 | NULL | 2023-11-27 | NULL | NULL | NULL | NULL | By contract | Not yet started | Maximmus Construction | TIN 925-322-134 | NULL
1370 | Concreting Of New Busuanga-Quezon-Cheey | B2 GF SFVIP 23-09-117 | Transportation Facilities | ROAD | 620 Ln.M - W=6.10, Thick=0.20m, Shoulder=1m B.S | Municipality Of Busuanga | Busuanga | PEO | 2023 | SFVIP | 12000000 | 11993006.64 | 120 | 2024-01-15 | NULL | 2024-05-14 | 2024-06-03 | NULL | 100% | NULL | By contract | Completed | Maryjonica Construction | TIN 350-458-389 | NULL
1371 | Concreting Of Labog-Naltep Road, Phase II | B2 GF SFVIP 23-09-119 | Transportation Facilities | ROAD | Road Network: 405 Lm - W=6.10m - Thk=0.20m - Shoulder=1m - B.S: Slope Protection Lm=8m - Ht=2.2m | Municipality Of Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | SFVIP | 8000000 | 7976821.91 | 155 | 2023-12-12 | NULL | 2024-05-15 | NULL | 2024-05-14 | 100% | NULL | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887 | NULL
1372 | Concreting/Upgrading Of Aramaywan-Cacarigan FMR (PGP Counterpart) | NULL | Transportation Facilities | ROAD | NULL | Narra, Palawan | Narra | PEO | 2023 | Supplemental Budget No. 2 | 12910000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For preparation (POW and DED) | NULL | NULL | NULL
1373 | Improvement Of Capitol Building (Rehab Of Interior Walls) | NULL | Other Facilities | PGP FACILITIES | 4,902.22 Square Meter: Removal Of Interioir Marble Stone Bricks Wall - Plastering And Painting On Interior Wall - Repaint Of Genset Room Exterioir Wall - Repaint Of Pavillion Column | Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 2 | 4079130 | NULL | 210 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1374 | Renovation Of Palawan Provincial Crime Laboratory Office In Brgy. Tiniguiban, Puerto Princesa City | B2 GF SB2 PEO 23-07-098 | Other Facilities | PGP FACILITIES | 22.10m X 12.00m Renovation/Improvement | Brgy. Tiniguiban, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 2 | 2016000 | 2010648.96 | 90 | 2023-12-11 | NULL | 2024-03-10 | NULL | 2024-03-10 | 100% | NULL | By contract | Completed | One Badajos Construction & Trading Corporation | TIN 010-590-630 | NULL
1375 | Concreting of Road Network Phase II, Sofronio Española,Palawan | B2 GF SB3 PDP 23-11-141 | Medical Facilities | MEDICAL FACILITIES | Road Network: 4700075 lm (w=4,t=0.20m) - Drainage: 24" diameter RCPC x 8m - Line canal = 20.14m | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 800000 | 789452.4 | 45 | 2024-01-29 |  | 2024-03-14 |  |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1376 | Construction of STP Vault and Drainage Structure Phase I, Capitol Ville Subdivision | B2 GF SB3 PDP 23-11-140 | Other Facilities | PGP FACILITIES | Construction Limits: Stp Vault=9.6(L) X 4.6(W) - Catch Basins:43 Pcs - 610mm Dia. Rcpc: 829 Lm - 910mm Rcpc: 417 L.M - 1220mm Dia Rcpc: 165 L.M | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 11000000 | 10996710.08 | 205 | 2024-04-01 | NULL | 2024-10-23 | For approval | NULL | 70% | NULL | By contract | On going | FSD Construction | NULL | NULL
1377 | Concreting of Road Network and Parking Area Phase I, Provincial Health Office | B2 GF SB3 PDP23 24-06-093 | Other Facilities | PGP FACILITIES | Acess Road: 737.64 Sqm - Parking 204.25 Sq.M - Sidewalk 93.18sq.M | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 3000000 | 2984327.39 | 59 | 2024-10-02 | NULL | 2024-11-30 | For approval | NULL | 60% | NULL | By contract | On going | Luis YC Builders & Supply | TIN 120-420-502-00006 | NULL
1378 | Improvement of Provincial Health Office Landscaping | B2 GF SB3 PDP 23-10-124 | Other Facilities | PGP FACILITIES | Modern tropical garden | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 500000 | 469656.85 | 45 | 2024-01-23 | NULL | 2024-03-08 | For approval | NULL | NULL | NULL | By contract | Suspended | RD Abacial Construction | TIN 327-679-690 | NULL
1379 | Repair and Rehabilitation of Coron District Hospital | B2 GFSB3 PDP 23-11-146 | Medical Facilities | MEDICAL FACILITIES | Area: 24m(w) x 60m(l) Three Storey | Coron, Palawan | Coron | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 2400000 | 2398120.74 | 120 | 2024-02-19 |  | 2024-06-18 | For Approval |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
1380 | Repair and Rehabilitation of El Nido Community Hospital | B2 GF SB3 PDP 23-10-125 | Medical Facilities | MEDICAL FACILITIES | Main Building: 60m x 60m | El Nido Community Hospital | El Nido | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 4700000 | 4686055.78 | 90 | 2023-12-29 |  | 2024-03-28 | For Approval | 2024-03-28 | 100% |  | By contract | Completed | Maximmus Construction | TIN 497-273-240
1381 | Improvement of PGP Event Center (Supply and Installation of Acoustic Treatment Noise Management) | NULL | Other Facilities | PGP FACILITIES | NULL | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 5300000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Re-alignment | NULL | NULL | NULL
1382 | Construction of Elevated Water Tank/Water Treatment Facilities, Bataraza District Hospital | B2 GF SB3 PDP23 24-06-092 | Medical Facilities | MEDICAL FACILITIES | 100 cu.m Capacity Tank | Bataraza Distirct Hospital | Bataraza | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 6000000 | 5996737.48 | 120 | 2024-11-29 |  | 2025-03-29 |  |  | 0% |  | By contract | Not yet started | Lea and Sons Trading and Construction
1383 | Construction of Sewage Treatment Plant Equipment and Facilities, PJMD | B2 GF SB3 PDP 23-11-145 | Other Facilities | PGP FACILITIES | Sewage Treatment Plant | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 4000000 | 3999999.98 | 90 | 2024-04-26 | NULL | 2024-07-25 | For approval | NULL | 100% | NULL | By contract | Completed | Gth Builders and Developers | NULL | NULL
1384 | Constructrion of Septic Vault | B2 GF SB3 PDP 23-10-123 | Other Facilities | PGP FACILITIES | Septic Vault= 6m x 2m x 2.5m | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 400000 | 399999.59 | 60 | 2024-01-23 | NULL | 2024-03-23 | NULL | 2024-03-23 | 100% | NULL | By contract | Completed | JD Golez Construction Services | TIN 340-084-699 | NULL
1385 | Improvement of Provincial Health Office (Supply and Installation of Fire Protection and Alarm System) | NULL | Other Facilities | PGP FACILITIES | Supply,Installation Testing And Commissioning Of Fire Protection Alarm System | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 3200000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Failure of bidding | NULL | NULL | Failure of Bidding: For re-construction of Financial Documents of Procurement
1386 | Improvement of Governor's Residence | B2 GF CADP 23-05-097 | Other Facilities | PGP FACILITIES | Coffee shop - 203 sq.m - Landscape - 1,596.8 sq.m - Perimeter Fence - 191.86 ln.m | Brgy. Matiyaga, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PGO Fund | 10000000 | 9931452.76 | 240 | 2023-08-10 | NULL | 2024-04-06 | For approval | NULL | 98% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1387 | Restoration/Repair Of Lamayo Processing Center | B2 GF SB4 INFRA 23-11-137 | Other Facilities | AGRICULTURAL FACILITIES | 18m x 23.25m building | Brgy. New Guinlo, Municipality Of Taytay Palawan | Taytay | PEO | 2023 | Supplemental Budget No. 4 | 500000 | 498037.45 | 30 | 2024-01-29 | NULL | 2024-02-28 | NULL | 2024-02-25 | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1388 | Renovation Of Provincial Budget Office | B2 GF SB4 INFRA 23-11-135 | Other Facilities | PGP FACILITIES | Construction of floor extension, circular stair, and 2 - additional exit doors | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 950000 | 948450.21 | 75 | 2024-01-29 | NULL | 2024-04-13 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1389 | Improvement Of Capitol Building (Rehab Of Interior Walls) | B2 GF SB24 INFRA 23-11-139 | Other Facilities | PGP FACILITIES | Removal of interior marble stone bricks wall - plastering and painting of inetrior wall - repaint of genset room exterior wall - repaint of pavillon column | Capitol Compound, Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 4079130 | 4075412.74 | 210 | 2024-02-19 | NULL | 2024-09-16 | For approval | NULL | 73% | NULL | By contract | On going | RC Gadiano Construction | TIN 342-792-217 | NULL
1390 | Improvement Of Governor's Residence (Landscaping Enhancement) | B2 GF SB4 INFRA 23 24 08 099 | Other Facilities | PGP FACILITIES | Landscape | M. Quezon, Bgy. Matiyaga, PPC | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 1100000 | 1092800.3 | 90 | 2024-10-16 | NULL | 2025-01-14 | NULL | NULL | 80% | NULL | By contract | On going | RD Abacial Construction | TIN 327-679-690 | NULL
1391 | Improvement Of Capitol Complex - Improvement Of Landscaping | B2 GF SB4 INFRA 23-11-138 | Other Facilities | PGP FACILITIES | Modern tropical garden | Pgp Event Center, Bgy. Tanglaw, PPC | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 900000 | 898936.71 | 45 | 2024-01-29 | NULL | 2024-03-14 | NULL | 2024-04-14 | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1392 | Expansion Of Provincial Accounting Office | B2 GF SB4 23-11-136 | Other Facilities | PGP FACILITIES | 15mx16m - repair and repaint of mezzanine floor, walls and ceiling | Capitol Compound, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 3000000 | 2950314.99 | 60 | 2024-03-05 | NULL | 2024-05-04 | NULL | 2024-07-10 | 100% | NULL | By contract | Completed | Maryjonica Construction | TIN 350-458-389 | NULL
1393 | Enhancement Of Three Storey Building | B2 GF SB4 INFRA 24-03-073 | Other Facilities | PGP FACILITIES | n/a | Capitol Compound, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 950000 | 948786.68 | 90 | 2024-06-04 | NULL | 2024-09-02 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1394 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-131 | Medical Facilities | RHU | Area: 981 sq.m | So. Tabudniayo, Brgy. Bancalaan, Balabac | Balabac | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7988698.33 | 180 | 2024-01-29 |  | 2024-07-27 | For approval |  | 67% |  | By contract | On going | Hadiyah Construction | TIN 324-356-720
1395 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-132 | Medical Facilities | RHU | Area: 981 sq.m | Brgy. Mangsee, Balabac | Balabac | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7992569.97 | 180 | 2024-02-12 |  | 2024-08-10 | 2025-02-07 |  | 70% |  | By contract | On going | Breis Construction | TIN 010-590-630
1396 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-130 | Medical Facilities | RHU | Area: 801 sqm | Cagayancillo | Cagayancillo | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7995037.24 | 180 | 2024-03-18 |  | 2024-09-14 | For approval |  | 95% |  | By contract | On going | J.JH Construction Supplies Trading
1397 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-133 | Medical Facilities | RHU | Area: 981 sq.m | Magsaysay | Magsaysay | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7988124.79 | 180 | 2024-02-14 |  | 2024-08-12 | 2024-10-11 |  | 100% |  | By contract | Completed | Bat's Construction Services | TIN 491-731-278
1398 | Construction Of Two (2) Storey Building Medical Worker's Dormitory | B2 GF SB4 INFRA 23-11-134 | Medical Facilities | MEDICAL FACILITIES | Dimension: 21mx11.10m = 233.10 sqm | Sitio Arado, Taytay | Taytay | PEO | 2023 | Supplemental Budget No. 4 | 12600000 | 12595349.02 | 115 | 2024-03-18 |  | 2024-07-11 | 2024-10-09 |  | 100% |  | By contract | Completed | J.JH Construction Supplies Trading
1399 | Construction of Evacuation Center/ Covered Court with Bleachers | B2 TF PEO 23-08-115 | Other Infrastructure | COVERED COURT | Covered Court: 540 sq.m - Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Talaga | Cagayancillo | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 17062500 | 17007253.74 | 280 | 2023-12-11 | NULL | 2024-09-16 | For approval | NULL | 95% | NULL | By contract | On going | J.JH Construction Supplies Trading | NULL | NULL
1400 | Construction of Evacuation Center/ Covered Court with Bleachers | B2 TF PEO 23-08-116 | Other Infrastructure | COVERED COURT | Covered Court: 540 sq.m - Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Abaroan | Roxas | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 17062500 | 17034102.69 | 280 | 2024-01-19 | 1 | 2024-10-25 | 2024-12-24 | NULL | 95.3% | NULL | By contract | On going | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1401 | Construction of Evacuation Center/ Covered Court with Bleachers | B2 TF PEO 23-08-114 | Other Infrastructure | COVERED COURT | Covered Court: 540 sq.m - Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. New Agutaya | San Vicente | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 17062500 | 17055628.75 | 280 | 2023-11-24 | NULL | 2024-08-30 | 2024-12-15 | NULL | 70% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1402 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-112 | Other Infrastructure | COVERED COURT | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Culasian | Dumaran | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9759392.95 | 130 | 2023-11-06 | NULL | 2024-03-15 | 2024-04-29 | NULL | 100% | NULL | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1403 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-111 | Other Infrastructure | COVERED COURT | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Tinitian | Roxas | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9758126.68 | 130 | 2023-11-24 | 1 | 2024-04-02 | For approval | NULL | 90.2% | NULL | By contract | On going | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1404 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-109 | Other Infrastructure | COVERED COURT | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Poblacion | Araceli | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9759592.98 | 130 | 2024-03-20 | NULL | 2024-07-28 | For approval | NULL | 94.25% | NULL | By contract | On going | Cjetzu Lumber & Construction Supply | NULL | NULL
1405 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-110 | Other Infrastructure | COVERED COURT | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Sto. Tomas | Dumaran | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9674458.78 | 130 | 2023-11-25 | NULL | 2024-04-03 | For approval | NULL | 98% | NULL | By contract | On going | F.F Galang Construction | TIN 188-519-198 | NULL
1406 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-113 | Other Infrastructure | COVERED COURT | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Sandoval | Taytay | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9752298.49 | 130 | 2023-10-23 | NULL | 2024-03-01 | For approval | 2024-03-01 | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1407 | Construction Of Slope Protection In Latungay-Sta. Teresita Road | B2 TF PDRRMO 24-04-079 | Other Infrastructure | SLOPE PROTECTION | Slope Protection: Volume (Cu/M)=72.12 - Length 25.90 M | Dumaran, Palawan | Dumaran | PEO | 2023 | PDRRMO Fund | 1500000 | 1496944.74 | 93 | 2024-09-26 | NULL | 2024-12-28 | NULL | NULL | 100% | NULL | By contract | Completed | RL Abia Construction | TIN 274-260-467 | NULL
1408 | Construction Of Slope Protection, Malague Elementary School | B2 GF DPF 23-09-120 | Other Infrastructure | SLOPE PROTECTION | Slope Protection: Volume (Cu/M)=7422.15 - Length (1 Side) 46.20 M | Brgy. Sta. Teresita, Dumaran, Palawan | Dumaran | PEO | 2023 | PDRRMO Fund | 7500000 | 7449998.76 | 128 | 2024-01-20 | NULL | 2024-05-27 | NULL | 2024-05-10 | 100% | NULL | By contract | Completed | Seven Digit Construction and Supplies | TIN 008-664-275 | NULL
1409 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection, Panitian - Abokayan Road | B2 TF PDRRMO 24-05-089 | Other Infrastructure | DRAINAGE | Rcbc: 1-2m (H) X 3.56m (W) X 8.30(L) X 0.28m Thnk With Approach And Slope Protection | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | PDRRMO Fund | 3000000 | 2976044.19 | 115 | 2024-08-01 | NULL | 2024-11-24 | NULL | 2024-10-18 | 100% | NULL | By contract | Completed | Maximmus Construction | NULL | NULL
1410 | Installation Of 6 Lines - 36" Diameter RCPC With Headwall, Latongay - Bagumbayan Road | B2 GF DPF 23-11-153 | Other Infrastructure | DRAINAGE | Cl: 6 Units 1l-36'' Diameter Rcpc X 8.00 Length With Headwall Bothsides In Differrent Stations | Dumaran, Palawan | Dumaran | PEO | 2023 | PDRRMO Fund | 900000 | 890247.42 | 60 | 2024-01-19 | NULL | 2024-03-19 | For approval | 2024-03-01 | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1411 | Installation Of 11 Lines - 36" Diameter RCPC With Headwall, Dumarao FMR (Phase 2) | B2 GF DPF 23-11-155 | Other Infrastructure | DRAINAGE | Cl: 11 Units 1l-36'' Diameter Rcpc X 8.00 Length With Headwall Bothsides In Differrent Stations | Roxas, Palawan | Roxas | PEO | 2023 | PDRRMO Fund | 1600000 | 1599325.76 | 90 | 2024-01-29 | NULL | 2024-04-28 | NULL | 2024-03-25 | 100% | NULL | By contract | Completed | Azarraga Construction | TIN 418-292-176 | NULL
1412 | Installation Of 7 Lines - 36" Diameter RCPC With Headwall, Abongan -Alacalian-Kawakayan-Binga Road | B2 GF DPF 23-11-152 | Other Infrastructure | DRAINAGE | Cl: 7 Units 1l-36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Taytay, Palawan | Taytay | PEO | 2023 | PDRRMO Fund | 1050000 | 1049456.91 | 90 | 2024-01-29 | NULL | 2024-04-28 | NULL | 2024-03-21 | 100% | NULL | By contract | Completed | Azarraga Construction | TIN 418-292-176 | NULL
1413 | Installation Of 5 Lines - 36" Diameter RCPC With Headwall, Comalibongbong-Calawag Road | B2 GF DPF 23-11-157 | Other Infrastructure | DRAINAGE | Cl: 5 Units 1l-36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Taytay, Palawan | Taytay | PEO | 2023 | PDRRMO Fund | 750000 | 690155.32 | 60 | 2024-01-19 | 1 | 2024-03-19 | For approval | 2024-03-03 | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1414 | Construction Of 3-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection , Dumarao - Ilian Ilian Road | B2 GF DPF 23-11-160 | Other Infrastructure | DRAINAGE | Rcbc: 1-3m (H) X 3.56m(W) X 8.30(L) X 0.30m Thick With Approach And Slope Protection And Slope Protection | Roxas, Palawan | Roxas | PEO | 2023 | PDRRMO Fund | 6700000 | 6683961.47 | 202 | 2024-02-05 | NULL | 2024-08-25 | NULL | 2024-06-28 | 100% | NULL | By contract | Completed | Hadiyah Construction | TIN 324-356-720 | NULL
1415 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) With Pccp Approach And Slope Protection Dumarao-Subingao Road | B2 GF DPF 23-11-151 | Other Infrastructure | DRAINAGE | Rcbc 1-2.5m(H) X 3.56m(W) X 8.30(L) X 0.30m Thk With Approach Annd Slope | Roxas, Palawan | Roxas | PEO | 2023 | PDRRMO Fund | 4500000 | 4493833.32 | 144 | 2024-02-12 | NULL | 2024-07-05 | NULL | 2024-06-28 | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1416 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) With Pccp Approach And Slope Protection, Sibaltan - Siwangwang Road | B2 GF DPF 23-11-156 | Other Infrastructure | DRAINAGE | Rcbc- 1-3m(H) X 3.56m (W) X 8.30(L) X 0.28m Thk. With Approach And Slope Protection | El Nido, Palawan | El Nido | PEO | 2023 | PDRRMO Fund | 4500000 | 4489450.11 | 115 | 2024-02-12 | NULL | 2024-06-06 | NULL | 2024-05-13 | 100% | NULL | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814 | NULL
1417 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) With Pccp Approach And Slope Protection | B2 GF DPF 23-11-154 | Other Infrastructure | DRAINAGE | 1-3m(H) X 3.56m(W) X 8.30(L) X 0.30m Thk With Approach And Slope Protection | Highway Jct. Tagumpay - Maliko Road | Roxas | PEO | 2023 | PDRRMO Fund | 4500000 | 4464014.51 | 144 | 2024-01-29 | NULL | 2024-06-21 | NULL | 2024-06-18 | 100% | NULL | By contract | Completed | Hadiyah Construction | TIN 324-356-720 | NULL
1418 | Construction Of PDRRMO Warehouse Phase III | B2 TF PDRRMO 24-01-002 | Other Facilities | PGP FACILITIES | Pavement Road - 177.53m (L) X 6.10m(W) - Grouted Rip Rap - 4.24m (W) X 88.50m (L) - Concrete Culvert 24'' Diameter - 7 Mtrs | Barangay Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PDRRMO Fund | 7122529.21 | 7083101.28 | 150 | 2024-05-27 | NULL | 2024-10-24 | For approval | NULL | 50% | NULL | By contract | On going | Luis YC Builders & Supply | NULL | NULL
1419 | Construction Of Seacraft Motorpool | NULL | Other Facilities | PGP FACILITIES | 18m X 10m Motorpool | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PDRRMO Fund | 3500000 | NULL | 150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1420 | Construction of IT Room (Command Center) | B2 TF PDRRMO 24-03-025 | Other Facilities | PGP FACILITIES | Buildings: Net Length: 17.60m X 9.20m - Addition Of Emergency Operation Center Office(It Room) | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PDRRMO Fund | 3500000 | 3312409.51 | 95 | 2024-08-20 | NULL | 2024-11-23 | For approval | NULL | 60% | NULL | By contract | On going | RC Gadiano Construction | TIN 342-792-217 | NULL
1421 | Construction Of Seacraft Operation Base With Slipway | B2 TF PDRRMO 24-03-024 | Other Facilities | OTHER FACILITIES | Building: 18mx6m - Spillway: 6.50mx7.50m | Buliluyan, Batarza, Palawan | Bataraza | PEO | 2023 | PDRRMO Fund | 2500000 | 2494994.82 | 141 | 2024-05-31 | NULL | 2024-10-19 | 2024-12-31 | NULL | 61.04% | NULL | By contract | On going | Global Teleconstruction Specialist Inc. | NULL | NULL
1422 | Construction Of Seacraft Operation Base With Slipway | B2 TF PDRRMO 24-03-026 | Other Facilities | OTHER FACILITIES | Building: 18mx6m - Spillway: 6.50mx7.50m | Dipnay, El Nido | El Nido | PEO | 2023 | PDRRMO Fund | 2500000 | 2496259.43 | 201 | 2024-06-28 | NULL | 2025-01-15 | NULL | NULL | 53% | NULL | By contract | On going | Global Teleconstruction Specialist Inc. | TIN 218-601-693-00000 | NULL
1423 | Renovation of Provincial Administrator's Office | B2 GF SB5 PGO 23-10-121 | Other Facilities | PGP FACILITIES | Renovation | Capitol Building, Brgy. Tanglaw, PPC | Puerto Princesa City | PEO | 2023 | Admin Fund | 536378.96 | 536169.43 | 60 | 2023-12-13 | NULL | 2024-02-11 | NULL | NULL | 100% | NULL | By contract | Completed | Gth Builders and Developers | NULL | NULL
1424 | Construction of Calauit Safari Park Improvement Works, Brgy. Buluang, Busuanga, Palawan | B2 GF SB4 CSPMP 23-11-150 | Other Infrastructure | ANIMAL FACILITIES | Net length as plan | Brgy. Buluang, Busuanga, Palawan | Busuanga | PEO | 2023 | Supplmental Budget No. 4 (CSPMP) | 6050000 | 6022332.85 | 200 | 2024-02-21 | NULL | 2024-09-08 | For approval | NULL | 92% | NULL | By contract | On going | Rabb Construction & Supply | TIN 325-261-868 | NULL
1425 | Renovation/Repair of Provincial Cooperative Development Office | B2 GF SB4 PCDO 23-11-158 | Other Facilities | PGP FACILITIES | Arc Length: 10.50m x 6.20m (w) with mezanine floor | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 (PCDO) | 500000 | 497678.01 | 90 | 2024-01-02 | NULL | 2024-04-01 | NULL | 2024-04-29 | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1426 | Renovation of Coron Bay Development Project Phase I, Luwalhati, Coron, Palawan | B2 GF CBDP 23-11-149 | Other Infrastructure | OTHER FACILITIES | 2-Storey Building | Luwalhati, Coron, Palawan | Coron | PEO | 2023 | Supplemental Budget No. 2 | 6604484 | 6602769.52 | 200 | 2024-01-29 | NULL | 2024-08-16 | For approval | NULL | 81.23% | NULL | By contract | On going | Triplestone Construction and Development Corporation | TIN 009-149-175 | NULL
1427 | Repair and Maintenance Building and Other Structures, Bgy. Bancao-Bancao, PPC | B2 GF PJMD 23-11-162 | Other Facilities | PGP FACILITIES | Net length: 16m x 16m Building Renovation New Tileworks, Partition wall, ceiling, renovation of comfort rooms & canopy roofing | Bgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PJMD Fund | 500000 | 497207.74 | 60 | 2024-01-19 | NULL | 2024-03-19 | NULL | 2024-04-29 | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1428 | Repair of Commission on Audit (Repainting of Wall and Ceiling) | B2 GF SB2 PGO 23-11-158 | Other Facilities | PGP FACILITIES | COA Office and stockrooms: 11m x 8.5m, 15m x 3.1m, 10m x 6.5m - Repainting of wall and ceiling | Capitol Compound, Brgy. Tanglaw & PEO compound, Bancao-bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | PGO Fund - Supplemental Budget No. 2 | 200000 | 148123.4 | 45 | 2024-02-12 | NULL | 2024-03-28 | NULL | 2024-05-13 | 100% | NULL | By contract | Completed | JD Golez Construction Services | TIN 340-084-699 | NULL
1429 | Repair and Rehabilitation of Southern Palawan Provincial Hospital, Bgy. Tub-tub, Brooke's Point, Palawan | B2 GF SPPH 23-10-129 | Medical Facilities | MEDICAL FACILITIES | Area: 60m (w) x 60m (l) | Bgy. Tub-tub, Brooke's Point, Palawan | Brooke's Point | PEO | 2023 | SPPH | 3172472.55 | 3170715.3 | 120 | 2024-01-17 |  | 2024-05-16 | Subject for LD |  | 100% |  | By contract | Completed | FSD Construction
1430 | Completoin of New Provincial Economic Enterprise Development Office, Capitol Complex, Puerto Princesa City | B2 GF WDP22 23-10-122 | Other Facilities | PGP FACILITIES | 8.80m x 20.85m - 1 storey building | Capitol Complex, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | PEEDO Fund | 700000 | 644754 | 45 | 2023-12-29 | NULL | 2024-02-12 | NULL | NULL | 100% | NULL | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868 | NULL
1431 | Replacement of BPYC Main Building and Multi-purpose Hall Roofing, Bgy. Irawan, PPC | B2 GF SB1 BPYC 23-07-108 | Other Facilities | MULITI-PURPOSE | Roof Area: 378.20 sqm - 1 Storey Building | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | BPYC | 700000 | 689813.5 | 60 | 2023-10-04 | NULL | 2023-12-03 | NULL | NULL | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001 | NULL
1432 | Upgrading of Timber Bridge to RCDG Bridge, Tanatanaen - Maragok Road | B2 GF PEO 24-02-009 | Transportation Facilities | ROAD | Bridge: Net Length Approach: 9.2mx4m (Both Sides) - Bridge: 9.52m X 30.60 Ln.M - Rc Slope (Cu.M) 159.40 - Pccp: 8 Ln.M | Dumaran | Dumaran | PEO | 2024 | 20% Development Fund 2024 | 30000000 | 28946467 | 214 | 2024-06-29 | NULL | 2025-01-29 | NULL | NULL | 30% | NULL | By contract | On going | Global Teleconstruction Specialist Inc. | NULL | NULL
1433 | Concreting of Highway Junction-Tumarbong, Phase 2 | B2 GF PEO 24-02-006 | Transportation Facilities | ROAD | Road Length: 1,260m(L) X 0.20m(T) X 6.10m(W) - 1 Line Rcpc 36" Dia - Existing Half Lane Pccp Left Side - Sta. 0+000 - Sta.0+060 | Roxas | Roxas | PEO | 2024 | 20% Development Fund 2024 | 25000000 | 24875000 | 178 | 2024-05-22 | NULL | 2024-11-16 | For approval | NULL | 98.6% | NULL | By contract | On going | Seven Digit Construction and Supplies | TIN 183-661-696 | NULL
1434 | Concreting of Access Road going to San Fernando Port | B2 GF PEO 24-02-007 | Transportation Facilities | ROAD | Net Length (Cu.M) Pccp Road A -367m X 6.70m X 0.25m Thk. Shoulder Width 1.00m B.S Road B-31.16m X 8.00m X 0.25m Thk - V-Shaped Lined Canal - 140m On R.S | El Nido | El Nido | PEO | 2024 | 20% Development Fund 2024 | 12641215 | 12634124.84 | 120 | 2024-05-22 | NULL | 2024-09-19 | NULL | NULL | 100% | NULL | By contract | Completed | Mamsar Construction & Industrial Corporation | NULL | NULL
1435 | Concreting of Access Road going to Pier - Marikit Road | B2 GF PEO 24-02-019 (Re-bid) | Transportation Facilities | ROAD | Road Length:900m(L) X 0.25m(T) X 6.10m(W) - 2 Rcbc H=1.41m X 6m - Seawall L=80m | Aborlan | Aborlan | PEO | 2024 | 20% Development Fund 2024 | 18000000 | 15770700 | 121 | 2024-08-05 | NULL | 2024-12-04 | NULL | NULL | 65% | NULL | By contract | On going | Palbic Construction and Supply | NULL | NULL
1436 | Construction of Evacuation Center/ Covered Court, Phase I | B2 GF PEO 24-02-004 | Other Infrastructure | COVERED COURT | Court: 30m(L) X 18m(W) | Nicanor Zabala | Roxas | PEO | 2024 | 20% Development Fund 2024 | 7300000 | 7267765.51 | 150 | 2024-05-02 | NULL | 2024-09-29 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | NULL | NULL
1437 | Construction of Evacuation Center/ Covered Court, Phase I | B2 GF PEO 24-02-011 | Other Infrastructure | COVERED COURT | Court: 30m(L) X 18m(W) | Lajala | Coron | PEO | 2024 | 20% Development Fund 2024 | 7300000 | 7292134.71 | 150 | 2024-05-15 | NULL | 2024-10-12 | For approval | NULL | 71.11% | NULL | By contract | On going | Maximmus Construction | NULL | NULL
1438 | Construction of Evacuation Center/ Covered Court, Phase I | B2 GF PEO 24-02-010 (Re-bid) | Other Infrastructure | COVERED COURT | Court: 30m(L) X 18m(W) | Brgy. Tumbod | Taytay | PEO | 2024 | 20% Development Fund 2024 | 7300000 | 7285118.06 | 150 | 2024-08-15 | NULL | 2025-01-12 | NULL | NULL | 65% | NULL | By contract | On going | RD Abacial Construction | NULL | NULL
1439 | Construction of Drainage System,Aborlan Medicare Hospital | B2 GF PEO 24-02-016 (Re-bid) | Other Infrastructure | DRAINAGE | Length Of Rc Canal: 118m - Earthen Canal: 400m - Length Of 1 Line: 12'' - 8m | Municipality of Aborlan, Palawan | Aborlan | PEO | 2024 | 20% Development Fund 2024 | 2000000 | 1650000 | 96 | 2024-07-29 | NULL | 2024-11-02 | NULL | NULL | 100% | NULL | By contract | Completed | Mark Dennis Deniel Trading and Construction | NULL | NULL
1440 | Construction of Three Phase Line Power Supply, Balabac District Hospital | B2 GF PEO 24-02-008 | Medical Facilities | MEDICAL FACILITIES | 3 Phase Line = 7.50kms - Transformer Banking - Cl: Power Cable Installation And Termination | Brgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2024 | 20% Development Fund 2024 | 16500000 | 16454913.37 | 150 | 2024-06-18 |  | 2024-11-15 | For approval |  | 95% |  | By contract | On going | TCC Powerserve Trading and Engineering Services
1441 | Construction of Oxygen Building with Centralized Oxygen Generator System, Balabac District Hospital | B2 GF PEO 24-03-22 | Medical Facilities | MEDICAL FACILITIES | Net Length: 9.50m (L) X 9.00m (W) | Brgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2024 | 20% Development Fund 2024 | 21500000 | 21495048.38 | 180 | 2024-07-22 |  | 2025-01-18 | 2025-04-19 |  | 87% |  | By contract | On going | Lea and Sons Trading and Construction
1442 | Construction of Drainage System,Roxas Medicare Hospital | B2 GF PEO 24-02-015 | Other Infrastructure | DRAINAGE | Length of RC Canal: 340.92M - Length of 1 LINE: 12'' - 53m | Municipality of Roxas, Palawan | Roxas | PEO | 2024 | 20% Development Fund 2024 | 3000000 | 2947022.62 | 102 | 2024-04-06 | NULL | 2024-07-17 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | NULL | NULL
1443 | Construction of Drainage System, Dr. Jose Rizal District Hospital | B2 GF PEO 24-02-005 | Other Infrastructure | DRAINAGE | Drainage: Length Of 362.52m - Length Of 1 Line: 12" - 37.0m | Municipality of Rizal, Palawan | Rizal | PEO | 2024 | 20% Development Fund 2024 | 3000000 | 2984456.53 | 102 | 2024-05-29 | NULL | 2024-09-08 | NULL | NULL | 100% | NULL | By contract | Completed | Luis YC Builders & Supply | NULL | NULL
1444 | Construction of Three (3) - Storey Medical Arts Building with Roof Deck for Helipad, Northern Palawan Provincial Hospital | B2 GF PEO 24-05-083 | Medical Facilities | MEDICAL FACILITIES | Buildings: Floor Area:43m x 15m - Porch:5mx4m - Ramp up: 24mx6m- Water Tank: 5,249 liters x 3 sets - Others: Fire Pro, Fire tank, Oxygen Piping, CCTV and PABX and accessories | Northern Palawan Provincial Hospital | Taytay | PEO | 2024 | 20% Development Fund 2024 | 80000000 | 79997834.99 | 283 | 2024-08-16 |  | 2025-05-26 |  |  | 30% |  | By contract | On going | One Hundred Percent and Development Corp.
1445 | Construction of Three (3) - Storey Medical Arts Building with Roof Deck for Helipad phase II, Coron District Hospital | B2 GF PEO 24-05-087 | Medical Facilities | MEDICAL FACILITIES | Building: Floor area: 43m x x15m - Ramp Up: 24m x 6m - Water tank: 5,259 liters x 3 sets - Others: Fire pro, fire tank, Oxygen Piping, CCTV and PABX, and accessories | Coron District Hospital | Coron | PEO | 2024 | 20% Development Fund 2024 | 60000000 | 59989673.59 | 258 | 2024-08-16 |  | 2025-05-01 |  |  | 55% |  | By contract | On going | St. Timothy Construction Corporation | TIN 008-813-669-000
1446 | Supply and Installation of 30 KW Hybrid Solar System, Araceli-Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES | Supply and Installation of 2-30 KW Hybrid Solar System | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2024 | 20% Development Fund 2024 | 17500000 |  | 120 | [8 empty] | Re-aligned |  |  | Re-aligned to 3 projects
1447 | Construction of Three In One Large Scale Rural Health Unit Phase III | B2 GF PEO 24-02-017 | Medical Facilities | RHU | Area: 981 sq.m | So. Tabudniayo, Brgy. Bancalaan, Balabac | Balabac | PEO | 2024 | 20% Development Fund 2024 | 4100000 | 4097793.64 | 150 | 2024-05-06 |  | 2024-10-03 | For approval |  | 70% |  | By contract | On going | Hadiyah Construction | TIN 324-356-720
1448 | Construction of Three In One Large Scale Rural Health Unit Phase III | B2 GF PEO 24-02-013 | Medical Facilities | RHU | Area: 981 sq.m | Brgy. Mangsee, Balabac | Balabac | PEO | 2024 | 20% Development Fund 2024 | 4100000 | 4098229.98 | 150 | 2024-08-02 |  | 2024-12-30 | 2025-03-31 |  | 70% |  | By contract | On going | Breis Construction
1449 | Construction of Power Plant and Distribution Lines of Green Island VEP | NULL | Power and Energy Development Program | ELECTRIFICATION | NULL | Green Island | Roxas | PEO | 2024 | 20% Development Fund 2024 | 5630000 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | Re-aligned to 2 projects
1450 | Improvement Of Legislative Building | B2 GF SFVIP 24-03-023 | Other Facilities | PGP FACILITIES | Legislative 76M(L) - 26.50M(W) - 14.47M(H) - Building - 2 Storey | Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | SFVIP | 20000000 | 19966832.32 | 225 | 2024-05-27 | NULL | 2025-01-07 | NULL | NULL | 83.5% | NULL | By contract | On going | One Hundred Percent and Development Corp. | NULL | NULL
1451 | Construction Of PEO Sub-Office Building | B2 GF SFVIP 24-02-021 | Other Facilities | OTHER FACILITIES | Net Length: Two-Storey Office Building (26.29m X 7.20m) | San Jose, Roxas, Palawan | Roxas | PEO | 2024 | SFVIP | 7000000 | 6990216.86 | 165 | 2024-06-24 | NULL | 2024-12-06 | NULL | NULL | 65.2% | NULL | By contract | On going | M. Luengo Construction | NULL | NULL
1452 | Improvement Of Motorpool Building (Expansion Of Office Area) | B2 GF PEO 24-02-012 | Other Facilities | PGP FACILITIES | 126 Sq.M | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | SFVIP | 2200000 | 2192113.38 | 120 | 2024-07-03 | NULL | 2024-10-31 | For approval | NULL | 75% | NULL | By contract | On going | RL Abia Construction | NULL | NULL
1453 | Extension Of Drainage Structure In Northern Palawan Technical Vocational School | B2 GF PEO 24-02-014 | Other Infrastructure | DRAINAGE | Open Line Canal: 112 Lm - Ushape Line Canal With Steel Cover: 160 Lm | Taytay, Palawan | Taytay | PEO | 2024 | SFVIP | 2500000 | 2495641.81 | 90 | 2024-05-06 | NULL | 2024-08-04 | NULL | 2024-08-25 | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | NULL | NULL
1454 | Improvement Of Provincial Capitol Building (Lactation Station And Nutrition Clinic) | NULL | Other Facilities | PGP FACILITIES | Net Length: 3.12m X 2.77m - Renovation | Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | SFVIP | 200000 | NULL | 45 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | Re-aligned | NULL | NULL | NULL
1455 | Repair Of Taradungan Spillway | B2 GF PEO 24-02-015 | Other Infrastructure | OTHER FACILITIES | Rc Slope (Cu.M) - 29.38 Cu.M | Roxas, Palawan | Roxas | PEO | 2024 | SFVIP | 500000 | 496502.2 | 113 | 2024-04-06 | NULL | 2024-07-28 | NULL | 2024-05-10 | 100% | NULL | By contract | Completed | Maximmus Construction | NULL | NULL
1456 | Rehabilitation Of Cabigsing Bridge | B2 GF SFVIP 24-08-098 | Transportation Facilities | ROAD | Pccp Approach: 7.80m X 4.50m (Right Side Inly) - Bridge: 6.7m X 6 Ln.M - Rc Slope: 19.70 Cu.M | Cuyo, Palawan | Cuyo | PEO | 2024 | SFVIP | 3600000 | 3595528.9 | 177 | 2024-10-11 | NULL | 2025-04-06 | NULL | NULL | 35% | NULL | By contract | On going | EG Batiancilla Construction | NULL | NULL
1457 | Construction Of Riverbank Protection/Flood Control At Tamlang Bridge | B2 GF SB5 PDP23 24-03-075 (Re-bid) | Other Infrastructure | SLOPE PROTECTION | Slope Ptotection: 244.30 cu.m - (4) sides: 13m(l) x 0.30m(t) - 26 Gabions | Sitio Tamlang, Bgy. Saraza, Brooke's Point | Brooke's Point | PEO | 2023 | Supplemental Budget No. 5 | 5000000 | 4974854.7 | 120 | 2024-08-14 | NULL | 2024-12-12 | For approval | NULL | 48.92% | NULL | By contract | On going | KIR Konstructicon Builders and Supply | NULL | NULL
1458 | Information and Communication Technology Equipment | NULL | Supply | SUPPLY | Supply | PEO, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 6 | 731576 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | 100% | NULL | NULL | Completed | NULL | NULL | NULL
1459 | Construction of Evacuation Center/Covered Court, Suba, Cuyo | B2 GF SB6 INFRA 23 24 -04-077 | Other Infrastructure | COVERED COURT | 30m (L) X 18m (W) | Cuyo, Palawan | Cuyo | PEO | 2023 | Supplemental Budget No. 6 | 7300000 | 7136684.87 | 170 | 2024-08-05 | NULL | 2025-01-22 | NULL | NULL | 65% | NULL | By contract | On going | J.JH Construction Supplies Trading | NULL | NULL
1460 | Construction/Supply and Installation of STP Equipment & Facilities, Aborlan Medicare Hospital, Aborlan | B2 GF SB6 INFRA 23-24-24-078 | Medical Facilities | MEDICAL FACILITIES | Installation and Termination of Power Cable = 133 Meters | Aborlan, Palawan | Aborlan | PEO | 2023 | Supplemental Budget No. 6 | 4000000 | 3999999.97 | 30 | 2024-08-01 |  | 2024-08-31 | For approval |  | 15.56% |  | By contract | On going | Gth Builders and Developers
1461 | Installation of Fire Protection and Alarm System, Dr. Jose Rizal District Hospital, Rizal | B2 GF SB6 INFRA23 24-03-074 (Re-bid) | Medical Facilities | MEDICAL FACILITIES | Sprinkler Heads = 256 Stes - Smoke Detector = 67 Sets | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2023 | Supplemental Budget No. 6 | 4500000 | 4491319.14 | 120 | 2024-08-15 |  | 2024-12-13 | 2025-01-12 |  | 90% |  | By contract | On going | RD Abacial Construction
1462 | Supply and Installation of Main Cable of Fire Protection, Aborlan Medicare Hospital, Aborlan | B2 GF SB6 INFRA23-24-04-081 | Medical Facilities | MEDICAL FACILITIES | Installation and Termination of Power Cable = 133 Meters | Aborlan, Palawan | Aborlan | PEO | 2023 | Supplemental Budget No. 6 | 500000 | 479600 | 30 | 2024-07-04 |  | 2024-08-03 |  | 2024-07-31 | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services
1463 | Concreting Of Plaridel-Apis-Cabigaan Road Phase II | B2 GF SB1 INFRA 24-03-028 | Transportation Facilities | ROAD | Road Length: Pccp: 1,000m (L) X 0.20m (T) X 6.10m (W) - Drainage: 1 Line Rcpc 36" Dia. | Plaridel, Aborlan, Palawan | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 15000000 | 13331968.07 | 123 | 2024-09-05 | NULL | 2025-01-06 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | St. Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1464 | Concreting Of Aporawan-Daan-Cabigaan Road | B2 GF SB1 INFRA 24-03-027 | Transportation Facilities | ROAD | Road: Net Volume Road Length: 4.750m(L) X 0.20m (T) X 6.10m (W) - 6 Lines Rcpc 36" Diameter | Brgy. Cabigaan, Aborlan, Palawan | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 85500000 | 85380611.71 | 280 | 2024-10-11 | NULL | 2025-07-18 | NULL | NULL | 21.02% | NULL | By contract | On going | Mamsar Construction & Industrial Corporation | NULL | NULL
1465 | Concreting Of Panacan Sea Road | B2 GF SB1 INFRA 24-03-057 | Transportation Facilities | ROAD | Road: Net Volume (Cu.M): Pccp 1.310mx5.00mx0.20m Thk Shoulder Width 1.00b.S - 29 Lm 24" Dia Rcpcw/ Shw On L.S - 490m Concrete Slope Protection | Panacan, Narra, Palawan | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 27000000 | 25621153.38 | 180 | 2024-07-29 | NULL | 2025-01-25 | NULL | NULL | NULL | NULL | By contract | Not yet started | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1466 | Concreting Of Suring - Lada Road | B2 GF SB1 INFRA 24-03-036 | Transportation Facilities | ROAD | Road Length: 1890m (L) X 6.10 (W) X 0.20m (T) | Pangobilian, Brooke's Point | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 28350000 | 26904762.92 | 190 | 2024-07-29 | NULL | 2025-02-04 | NULL | NULL | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | NULL | NULL
1467 | Concreting Of Sandoval - Igang Igang - Sarong Road | NULL | Transportation Facilities | ROAD | Road Length: 5954.71m (L)X6.1m(W) X 0.20m(T) No. Of Rcpc: 10 Lines Rcpc 36: Dia | Sandoval & Iwahig, Bataraza, Palawan | Bataraza | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 90000000 | NULL | 299 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1468 | Concreting Of Ocayan Road | B2 GF SB1 INFRA 24-03-046 | Transportation Facilities | ROAD | Pccp: 3,330m (L) X 0.20m(T) X 6.10m(W) - Line Canal: 470.82m (L) 0.40m(W) X 0.70m (H) - 9 Lines Rcpc 36" Diameter | Ocayan, Bataraza | Bataraza | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 49950000 | 46274408.02 | 222 | 2024-08-19 | NULL | 2025-03-29 | NULL | NULL | 15% | NULL | By contract | On going | Goldrock Construction & Development Corp. | NULL | NULL
1469 | Concreting Of Panitian - Tabud Road Phase II | B2 GF PEO SB1 INFRA 24-03-033 | Transportation Facilities | ROAD | Net Volume: Pccp-4,820m X 6.10m X 0.20mthk., Shoulder Wdth 1.00 B.S - 103 Lm 36" Dia. Rcpc With 216lm Concrete Slope Protection And 70m Line Canal | Brgy. Panitian, Quezon, Palawan | Quezon | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 74899526.39 | 226 | 2024-08-16 | NULL | 2025-03-30 | NULL | NULL | 22% | NULL | By contract | On going | Ivy Michelle Construction and Trading | TIN 008-664-275 | NULL
1470 | Concreting Of Pulot I - Pulot III Road | NULL | Transportation Facilities | ROAD | Pccp: Sta. 0+000.00-Sta. 1+860 - 5260m(L) X 6.10m: Sta. 1+960-Sta.3+480 - (W) X0.20m Thck Sta.4+700 - Sta 6+531.225 - Rcpc 101 Lm (36''diameter) - Stone Masonry H-1mxl-3m | Pulot I - Pulot III, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 84450000 | NULL | 299 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1471 | Concreting Of Pulot Sea Road | B2 GF SB1 INFRA 24-03-056 | Transportation Facilities | ROAD | Total Length: 2,679 M - Stone Masonry: 486 Cu.M - Rcpc:36" Diameter: 65m | Pulot Shore, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 47250000 | 47232174.89 | 216 | 2024-07-29 | NULL | 2025-03-02 | NULL | NULL | 30% | NULL | By contract | On going | Yurich Builders & Construction Supply | TIN 258-921-757-00001 | NULL
1472 | Concreting Of Tanatanaen - Maragok Road | B2 GF SB1 INFRA 24-03-060 | Transportation Facilities | ROAD | Net Volume: Pccp-3,500mx6.10mx0.20m Thk., Shoulder Width 1.00 B.S - 18lm - 36" Dia Rcpc W/ S.H.W. On B.S -160 Lm Stone Masonsry Slope Protection - Road | Tanatanaen, Dumaran, Palawan | Dumaran | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 66000000 | 65800000 | 255 | 2024-08-02 | NULL | 2025-04-14 | NULL | NULL | 20.45% | NULL | By contract | No movement | Seven Digit Construction and Supplies | NULL | NULL
1473 | Concreting Of Magsaysay - Itangil Road (Critical Section) | B2 GF SB1 INFRA 24-03-055 | Transportation Facilities | ROAD | Road Length: 2000m(L) X 0.20m (T) X 5.00m(W) - Drainage: 9 Lines Rcpc 36' Dia | Magsaysay,Dumaran, Palawan | Dumaran | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 30000000 | 29959595.93 | 190 | 2024-09-09 | NULL | 2025-03-18 | NULL | NULL | 30.45% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 009-446-039 | NULL
1474 | Concreting Of Itangil-Layok Road | B2 GF SB1 INFRA 24-03-058 | Transportation Facilities | ROAD | Road Length: 1,590m(L) X 0.20m(T) X 6.10m(W) - Drainage: 5 Lines Rcpc 36" Dia(Length Varies) - 45.00lm | Itangil, Dumaran, Palawan | Dumaran | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 30000000 | 29700011.64 | 185 | 2024-08-19 | NULL | 2025-02-20 | NULL | NULL | 30.54% | NULL | By contract | On going | F.F Galang Construction | NULL | NULL
1475 | Concreting Of Tumarbong - Antonino Road | B2 GF SB1 INFRA 24-03-072 | Transportation Facilities | ROAD | Road: 3,900m(L) X 0.20m(T) X 6.10m(W) - Drainage: 2 Lines Rcpc 36" Dia. | Bgy. Antonino, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 61903822.78 | 266 | 2024-08-19 | NULL | 2025-05-12 | NULL | NULL | 15% | NULL | By contract | On going | One Hundred Percent and Development Corp. | NULL | NULL
1476 | Concreting Of Highway Junction Little Caramay - Caruray Road B | B2 GF SB1 INFRA 24-03-071 | Transportation Facilities | ROAD | Road: Net Volume: Road Length: 5,100m X 0.20m(T) X 6.10m(W) - Drainage:7 Lines Rcpc 36"Dia. | Brgy. Magara,Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 105000000 | 104977978.39 | 300 | 2024-08-19 | NULL | 2025-06-15 | NULL | NULL | 9% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 009-446-039 | NULL
1477 | Concreting Of Highway Junction New Cuyo - Rizal Road | B2 GF SB1 INFRA 24-03-061 | Transportation Facilities | ROAD | Total Length: 3,971m(L) X 6.1m(W) X 0.2m (T) - Rccp: 26ln.M Rcpc 36" Dia. | New Cuyo, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 74800000 | 278 | 2024-08-22 | NULL | 2025-05-27 | NULL | NULL | 8% | NULL | By contract | On going | Seven Digit Construction and Supplies | TIN 183-661-696 | NULL
1478 | Concreting Of Highway Junction Calawag Road | B2 GF SB1 INFRA 24-03-038 | Transportation Facilities | ROAD | Road : Road Length: 3.940m(L) X 0.20m(T)X6.10m(W) - 58.09 Cu.M Stone Masonry - Drainage: 7 Lines Rcpc 36" Dia | Calawag,Taytay, Palawan | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 74974286.89 | 280 | 2024-09-09 | NULL | 2025-06-16 | NULL | NULL | 20% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 009-446-039 | NULL
1479 | Concreting Of Sto. Niño - New Canipo - Binga Road | B2 GF SB1 INFRA 24 - 03- 062 | Transportation Facilities | ROAD | Road Length: 4970m(L) X 0.20m(T) X 6.10m(W) - Drainage: 9 Lines Rcpc 36" Diameter | New Canipo, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 105000000 | 104982513.5 | 310 | 2024-08-16 | NULL | 2025-06-22 | NULL | NULL | 62% | NULL | By contract | On going | Yurich Builders & Construction Supply | TIN 258-921-757-00001 | NULL
1480 | Concreting Of Highway Junction Little Caramay - Caruray Road A | B2 GF SB1 INFRA 24-03-063 | Transportation Facilities | ROAD | Road Length: 4100m(L) X 0.20m(T) X 6.10m (W) - Remove And Replace 2 Units Of 1-L Rcpc 36" Diameter | Caruray,San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 90000000 | 89975752 | 286 | 2024-08-19 | NULL | 2025-06-01 | NULL | NULL | NULL | NULL | By contract | Not yet started | One Hundred Percent and Development Corp. | TIN 009-446-039 | NULL
1481 | Concreting Of Canadcan - Alimanguan Road | B2 GF SB1 INFRA 24-03-068 | Transportation Facilities | ROAD | Road Length: 900m (L) X 6.10(W) X 0.20m(T) | Alimanguan, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 17850000 | 17468919.39 | 143 | 2024-07-29 | NULL | 2024-12-19 | NULL | NULL | 100% | NULL | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-00001 | NULL
1482 | Concreting Of Alimanguan - Sto. Niño Road | B2 GF SB1 INFRA 24 - 03- 067 | Transportation Facilities | ROAD | Road Length: 4.740m (L) X 0.20m(T) X 6.10m (W) - 38.05 Cu.M Stone Masonry - Drainage: 6 Lines Rcpc 36" Dia | Alimanguan & Sto. Niño, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 88500000 | 88489305.39 | 280 | 2024-08-16 | NULL | 2025-05-23 | NULL | NULL | 70% | NULL | By contract | On going | Yurich Builders & Construction Supply | TIN 258-921-757-00001 | NULL
1483 | Concreting Of Araceli-Dumaran Road A | B2 GF SB1 INFRA 24-03-064 | Transportation Facilities | ROAD | Road Concreting: 2860m(L) X 6.1m(W) X 0.2m(T) | Mauringen, Araceli, Palawan | Araceli | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 58830000 | 49962469.74 | 247 | 2024-08-30 | NULL | 2025-05-04 | NULL | NULL | 38.61% | NULL | By contract | On going | Maryknoll Construction and Supply | NULL | NULL
1484 | Concreting Of Cuyo - Suba - San Carlos Road | B2 GF SB1 INFRA 24-03-032 | Transportation Facilities | ROAD | Road Length: 640m (L) X 6.10(W) X 0.20 (T) | Pawa & San Carlos, Cuyo, Palawan | Cuyo | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 13155000 | 12497142.11 | 125 | 2024-08-12 | NULL | 2024-12-15 | For approval | NULL | 15% | NULL | By contract | On going | Crishelle Construction | TIN 133-967-996-00000 | NULL
1485 | Concreting Of New Busuanga - New Quezon Rd | B2 GF SB1 INFRA 24-03-069 | Transportation Facilities | ROAD | Net Volume(Cu.M): Pccp 1,470m X 6.10m X0.20m Thl - Shoulder Width 1.00m (B.S) - 2l 36" Dia. Rcpc X 8m W/ Shw On B.S | Brgy. New Quezon, Busuanga, Palawan | Busuanga | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 30300000 | 25738892.41 | 185 | 2024-08-08 | NULL | 2025-02-09 | NULL | NULL | 92.42% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1486 | Concreting Of New Quezon - Cheey Road | B2 GF SB1 INFRA 24-03-066 | Transportation Facilities | ROAD | Road Concreting: 1840m (L) X 6.10m(W) X 0.2m(T) | Cheey, Busuanga, Palawan | Busuanga | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 37865000 | 37849431.08 | 233 | 2024-07-29 | NULL | 2025-03-19 | NULL | NULL | 10% | NULL | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730 | NULL
1487 | Installlation Of 2-Lines 36" Rcpc With Headwall, Plaridel - Apis - Cabigaan Road | NULL | Transportation Facilities | ROAD | 2 Lines 36" Diameter Rcpc X 8.00 Length With F. Headwall And Riprap B.S | Brgy. Plaridel | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 400000 | NULL | 45 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1488 | Construction Of 40m(L)X3(M) Height Retaining Wall At San Jose Cojamco Sr. Road | B2 GF SB1 INFRA 24-03-049 | Transportation Facilities | ROAD | Rw: 230.73 - Length: 1 Side: 40m(L) 2m(H) | Brgy. Magbabadil | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1000000 | 995566 | 113 | 2024-06-03 | NULL | 2024-09-24 | NULL | 2024-07-31 | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1489 | Removal And Construction Of 60m(L) X6m Height Of Slope Protection Along Jose Cojamco Sr. Road | B2 GF SB1 INFRA 24-03-048 | Transportation Facilities | ROAD | Slope Protection - (Cu.M) - 156.60 - Length I Side - 601m (L) X 6m (H) | Brgy. Magbabadil | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 2500000 | 2444702.86 | 113 | 2024-07-22 | NULL | 2024-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | TIN 925-322-134 | NULL
1490 | Rehabilitation Of Slope Protection Structures In Teresa - Batang Batang Road | B2 GF SB1 INFRA 24-03-050 (Re-bid) | Transportation Facilities | ROAD | Slope Protection: 76.28 Cu.M - Length Sp Approach: 2 Sides=10m - Abutment A=11.5m - Abutmebt B=8.00m | Brgy. Batang Batang | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1700000 | 1689828.38 | 94 | 2024-07-30 | NULL | 2024-11-01 | For approval | NULL | 94.85% | NULL | By contract | On going | R.R Leoncio Construction | NULL | NULL
1491 | Rehabilitation Of Drainage And Slope Protection Structures In Highway Junction - Burirao Road | B2 GF SB1 INFRA 24-03-070 | Transportation Facilities | ROAD | Sp: 248.21 Cu.M - Length Sp: 211.6 M - Length Shoulder: 211.6 M | Brgy. Burirao | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 6250000 | 6020143.26 | 121 | 2024-08-16 | NULL | 2024-12-15 | NULL | NULL | NULL | NULL | By contract | Not yet started | Mamsar Construction & Industrial Corporation | NULL | NULL
1492 | Construction Of Slope Protection, Caguisan Feeder Road | B2 GF SB1 INFRA 24-03-052 | Transportation Facilities | ROAD | Net Length: 114 Ln.M - 57 Ln.M Both Sides | Brgy. Caguisan | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 2000000 | 1997936.71 | 113 | 2024-07-22 | NULL | 2024-11-12 | NULL | NULL | 100% | NULL | By contract | Completed | Maryjonica Construction | NULL | NULL
1493 | Construction Of Seawall Protection | B2 GF SB1 INFRA 24-03-31 | Transportation Facilities | ROAD | Seawall: Net Length: 806 Ln.M - H=1.70m | Brgy. Pangobilian, Brooke's Point, Palawan | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 35900000 | 35889368.03 | 240 | 2024-08-16 | NULL | 2025-04-13 | NULL | NULL | 85% | NULL | By contract | On going | St.Timothy Construction Corporation | NULL | NULL
1494 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) With PCCP Approach Slope And Protection | B2 GF SB1 INFRA 24-03-043 | Transportation Facilities | ROAD | (A) Rcbc = 1 Unit - 2.2m(H) - 3.06m(W) X 7.0m(L) X 0.25m (Thck) With Slope Protection And Approach | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 5000000 | 4404685.8 | 113 | 2024-05-31 | NULL | 2024-09-21 | NULL | NULL | 100% | NULL | By contract | Completed | Hadiyah Construction | NULL | NULL
1495 | Construction Of Riverbank Protection/ Flood Control, Mainit Spillway | B2 GF SB1 INFRA 24-03-30 | Transportation Facilities | ROAD | Slope Protection: 1426.52 Cu.M - 565 M (L) - 0.30m (T) - 283 Gabions - 1m X 1m X 2m | Bgy. Mainit, Brooke's Point | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 30000000 | 29995508.97 | 213 | 2024-08-16 | NULL | 2025-03-17 | For approval | NULL | 80% | NULL | By contract | On going | St.Timothy Construction Corporation | NULL | NULL
1496 | Construction Of Riverbank Protection/Flood Control, Imulnod Bridge | NULL | Transportation Facilities | BRIDGES | Riverbank: Slope Protection: 736.32 Cu.M - 207.20m(L) X 0.30m (T) - 104 Gabions - 1mx1mx2m | Imulnod, Brooke's Point | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 15000000 | NULL | 158 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1497 | Construction Of Riverbank Protection/Flood Control At Tamlang Bridge, Phase 2 | NULL | Transportation Facilities | BRIDGES | Sp: 497.35 Cu.M - 4 Sides: 31 M(L) X 0.30 M(T) - 62 Gabions - 1m X 1m X 2m | Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 10000000 | NULL | 145 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1498 | Construction Of Riverbank Protection/Flood Control | NULL | Transportation Facilities | ROAD | Slope Protection: 996.65 Cu.M - 305.20m(L) X 0.30m (T) - 153 Gabions - 1m X 1m X 2m | Pulot Shore, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 20000000 | NULL | 177 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1499 | Construction Of Riverbank Protection/Flood Control, Panitian-Abokayan Road | B2 GF SB1 SB1 INFRA 24-03-29 | Transportation Facilities | ROAD | 873.85 Cu.M - 324 M (L) X 0.30m (T)-162 Gabions -1m X 1m X 2m | Brgy. Panitian, Sofronio Española | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 18000000 | 17799135.86 | 145 | 2024-08-16 | NULL | 2025-01-08 | NULL | NULL | 100% | NULL | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1500 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) w/ PCCP Approach And Slope Protection, Panitian Seashore Road | B2 GF SB1 INFRA 24-03-040 | Transportation Facilities | ROAD | Rcbc: 1 Unit - 3.56m(H) - 3.56m(W) - 9.10m(L) - X 0.28m Thk With Slope Protection And Approach | Brgy. Panitian, Sofronio Española | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 3000000 | 2813152.52 | 113 | 2024-07-04 | NULL | 2024-10-25 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | NULL | NULL
1501 | Construction Of Drainage Structure And Slope Protection, Pulot Interior Road | B2 GF SB1 INFRA 24-03-051 | Transportation Facilities | ROAD | Slope Protection/Drainage: Net Length: 125 Ln.M - H:3m | Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 4500000 | 3985957.46 | 118 | 2024-06-24 | NULL | 2024-10-20 | NULL | 2024-09-02 | 100% | NULL | By contract | Completed | Hadiyah Construction | NULL | NULL
1502 | Rehabilitation Of Box Culvert | B2 GF SB1 INFRA 24-03-045 | Transportation Facilities | ROAD | Rehabilitation Of Wingwall And Construction Of Slope Protection | Bgy.Iraray, Sofrionio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1050000 | 1046240.98 | 59 | 2024-07-04 | NULL | 2024-09-01 | NULL | 2024-07-29 | 100% | NULL | By contract | Completed | Hadiyah Construction | NULL | NULL
1503 | Construction Of Riverbank Protection/Flood Control | B2 GF SB1 INFRA 24-03-059 | Transportation Facilities | ROAD | Sp: 761.21 Cu.M - 2 Sides (128m (L) X 0.30 M) - 128 Gabions - 1mx1mx2m | Bgy. Sowangan, Quezon, Palawan | Quezon | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 16000000 | 15569150.17 | 145 | 2024-08-16 | NULL | 2025-01-08 | NULL | NULL | NULL | NULL | By contract | Not yet started | Mamsar Construction & Industrial Corporation | NULL | NULL
1504 | Construction Of Sea Wall Protection | B2 GF SB1 INFRA 24-03-054 | Transportation Facilities | ROAD | Seawall - Net Length=159 Ln.M - H=1.70m | Bgy. Cocoro, Magsaysay, Palawan | Magsaysay | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 7500000 | 7491074.54 | 128 | 2024-09-05 | NULL | 2025-01-11 | NULL | NULL | NULL | NULL | By contract | On going | St. Timothy Construction Corporation | TIN 008-813-669-000 | NULL
1505 | Construction Of Sea Wall Protection, Sitio Pescadores | B2 GF SB1 INFRA 24-03-042 | Transportation Facilities | ROAD | Seawall - Net Lenght=38 Ln.M - | Bgy. Osmeña, Culion, Palawan | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 4100000 | 4085777.32 | 118 | 2024-08-30 | NULL | 2024-12-26 | NULL | NULL | 78.21% | NULL | By contract | On going | Luis YC Builders & Supply | NULL | NULL
1506 | Construction Of Seawall | B2 GF SB1 INFRA 24-03-053 | Transportation Facilities | ROAD | Net Length=17 Ln.M - H=1.70m | Bgy. Libis, Culion, Palawan | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1000000 | 997052.1 | 118 | 2024-08-30 | NULL | 2024-12-26 | NULL | NULL | 15% | NULL | By contract | On going | Luis YC Builders & Supply | NULL | NULL
1507 | Construction Of Slope Protection | B2 GF SB1 INFRA 24-03-037 | Transportation Facilities | ROAD | Slope Protection: Volume (Cu.M): 159.04 - Length:1 Side=20m | Balala, Culion, Palawan | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 3500000 | 3484197.27 | 105 | 2024-08-30 | NULL | 2024-12-13 | NULL | NULL | 15% | NULL | By contract | On going | Luis YC Builders & Supply | NULL | NULL
1508 | Construction Of Slope Protection & Lined Canal In Balala - Malaking Patag Road | B2 GF SB1 INFRA 24-03-039 | Transportation Facilities | ROAD | Slope Protection - Slope Protection Volume: 210.61 Cu.M - Length S.P: 1side: 43.60m - Length Line Canal: 1 Side: 43.6m | Balala, Baldat, Malaking Patag | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 5000000 | 4976942.63 | 113 | 2024-10-02 | NULL | 2025-01-23 | NULL | NULL | 15% | NULL | By contract | On going | Luis YC Builders & Supply | TIN 120-420-502-00006 | NULL
1509 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection | B2 GF SB1 INFRA 24-03-044 | Transportation Facilities | ROAD | 1 Unit: Rcbc: 3.56m(H) X 3.56(W) X 9.10m(L) X 0.28m Thk | Bgy. San Jose, Coron, Palawan | Coron | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 3000000 | 2995965.57 | 113 | 2024-06-03 | NULL | 2024-09-24 | NULL | NULL | 100% | NULL | By contract | Completed | Maximmus Construction | NULL | NULL
1510 | Construction Of Slope Protection In Paglaum-Itangil Road | NULL | Transportation Facilities | ROAD | Slope Protection: Sp Volume (Cu.M)=519.75 - Length Sp (Both Sides): 192.50 M - Shoulder (Both Sides): 192.50 M | Brgy. Talog, Taytay | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 11700000 | NULL | 153 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1511 | Construction Of Sea Wall Protection | B2 GF SB1 INFRA 24-03-035 | Transportation Facilities | ROAD | Net Length=101 Ln.M - H=1.70m | Bancal & Cambian, Agutaya | Agutaya | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 5000000 | 4996829.56 | 118 | 2024-05-27 | NULL | 2024-09-22 | 2024-11-21 | NULL | 100% | NULL | By contract | Completed | J.JH Construction Supplies Trading | NULL | NULL
1512 | Construction Of Spillway, Phase II | B2 GF SB1 INFRA 24-03-034 (Re-bid) | Transportation Facilities | ROAD | Spillway - (A) Spillway=10m(L) X 9.60m(W) X 3.05m(H) - (B) Approach= 6.50m(L) X 6m(W) X 0.20m(T) © Slope Protection= 13m(L) X 1.50m(Sh) - 4 Sides | Brgy. Tinitian, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 2400000 | 2132585.14 | 115 | 2024-08-22 | NULL | 2024-12-15 | NULL | NULL | 85% | NULL | By contract | On going | RD Abacial Construction | TIN 327-679-690 | NULL
1513 | Construction Of Spillway | NULL | Transportation Facilities | ROAD | (A) Spillway=30m(L) X 9.74m(W) X 3.05m(H) (B) Appproach=10m(L) X 6.10m(W) X 0.20(T) - © Slope Protection 15(L) X 3.80m(Sh) - 4 Sides | Brgy. Nicanor Zabala, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 9000000 | NULL | 205 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1514 | Construction Of Slope Protection, Magara Little Caramay - Magara Road | B2 GF SB1 INFRA 24-03-041 | Transportation Facilities | ROAD | Slope Protection: Sp: 366.24.32 Cu.M - Length: 1 Side: 70m | Bgy. Magara, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 7000000 | 6993408.68 | 126 | 2024-08-16 | NULL | 2024-12-20 | NULL | NULL | 100% | NULL | By contract | Completed | Mamsar Construction & Industrial Corporation | NULL | NULL
1515 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection, Alimanguan - Sto. Niño Road | NULL | Transportation Facilities | ROAD | Rcbc: (A) Rcbc - 1 Unit 3.0m(H) X 6.9m(W) X 9.1(L) X 0.30m Thk With Slope Protection And Approch | Sto. Niño, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 6000000 | NULL | 120 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1516 | Construction Of 3-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection, Alimanguan - Sto. Niño Road | NULL | Transportation Facilities | ROAD | (A) Rcbc = 1 Unit 3.0m (H) X 10.20m (W) X 9.1 (L) X 0.30m Thk With Slope Protection And Approach | Sto. Niño, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 8000000 | NULL | 131 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1517 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) W/ PCCP Approach And Slope Protection, National Highway - Old Guinlo Road (4 Units) | NULL | Transportation Facilities | ROAD | Rcbc: (A) Rcbc; 4 Units In Different Location 3m(H) X 6.9m(W) X 9.10m(L) X 0.30m (Thck) With Slope Protection And Approach | Old Guinlo And Poblacio, Taytay | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 24000000 | NULL | 208 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1518 | Upgrading of Barotuan Bailey Bridge to RCDG Bridge | B2 GF SB1 INFRA 24-03-047 | Transportation Facilities | BRIDGES | Bridge: Approach: 9.22m X 4m (Both Sides) - Bridge: 9.52m X 32 Ln.M - Rc Slope (Cu.M): 147.60 Cu.M - Pccp:8 Ln.M | Barotuan, El Nido, Palawan | El Nido | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 30500000 | 30458698.76 | 226 | 2024-08-19 | NULL | 2025-04-02 | NULL | NULL | 48% | NULL | By contract | On going | Seven Digit Construction and Supplies | TIN 008-664-275 | NULL
1519 | Construction Of Forward Operating Bases/PGP Government Center | B2 GF SB1 INFRA 24-08-103 | Other Facilities | OTHER FACILITIES | 60M (W) X 90M(L) | Abo-abo, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Building) | 150000000 | 146964646.78 | 300 | 2024-11-25 | NULL | 2025-09-21 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | Arlustre Construction Corporation | NULL | NULL
1520 | Construction Of Forward Operating Bases/PGP Government Center | B2 GF SB1 INFRA 24 - 08 - 102 | Other Facilities | OTHER FACILITIES | Building: 60m (w) x 90m (l) | Poblacion, Taytay, Palawan | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Building) | 150000000 | 146988960.14 | 300 | 2024-11-25 | NULL | 2025-09-21 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | Arlustre Construction Corporation | NULL | Buildimg Permit on process
1521 | Construction of TB DOTS |  | Medical Facilities | MEDICAL FACILITIES | 1.00m x 8.00m TB DOTS Building - Concrete Pathwalk (L=5.00m, W=2.50m) | Coron, Palawan | Coron | PEO | 2020 | Covid-19 Fund SB3 | 1785000 |  | 120 | [5 empty] | 100% |  |  | Completed
1522 | Construction of Balabac Waterworks Offic (Re-bid) | B2 GF BWS 23-01-007 | NULL | WATER SYSTEM | NULL | Poblacion, Balabac, Palawan | Balabac | NULL | 2023 | PEEDO Fund | 2600000 | 2598151.01 | 90 | 2023-07-17 | NULL | 2023-10-15 | NULL | NULL | NULL | NULL | NULL | PEEDO Validate | Rabb Construction and Supply | NULL | NULL
1523 | Installation of Brackish Reverse Osmosis Desalination System, Bancalaan, Balabac | B2 GF BWS 23-01-002 | NULL | WATER SYSTEM | NULL | Bgy. Bancalaan, Balabac | Balabac | NULL | 2023 | PEEDO Fund | 5464987.5 | 5460092.98 | 100 | 2023-07-24 | NULL | 2023-11-01 | NULL | NULL | NULL | NULL | NULL | PEEDO Validate | Sparkotech Engineering Solution Inc. | NULL | NULL
1524 | Installation of Mobile Platform Floating Dock | B2 GF SB4 CSPMP 24-01-003 | Other Infrastructure | OTHER FACILITIES | Mobile Platform Floating Dock (Specifications: 50cm x 50cm x 40cm) | Bgy. Buluang, Busuanga, Palawan | Busuanga | NULL | 2024 | PEEDO Fund | 6225000 | 5630000 | 60 | 2024-05-16 | NULL | 2024-07-15 | NULL | NULL | 100% | NULL | By contract | Completed | Tektwin Marketing Corporation | NULL | NULL
1525 | Concreting of Provincial Disaster Operation Center of Palawan Road Network with Parking Area | B2 DPF 300-21-10-14114 | Transportation Facilities | ROAD | 367.24m x 5.00m Road Network - 50.46m x 10.00m Parking - 3-L=4.00M x 2.50m, L=14.00m x 2.50m Concrete Pathwalk | Bgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2021 | Disaster Preparedness Fund (PDRRMO Fund) | 5000000 | 4989988.73 | 60 | 2021-12-20 | NULL | 2022-02-18 | NULL | NULL | 100% | NULL | By contract | Completed | Smmiley Builders and Trading | NULL | NULL
1526 | Construction of Magsaysay Water System Pipiline Expansion | B2 GF MWS 23-01-001 | NULL | WATER SYSTEM | NULL | Magsaysay, Palawan | Magsaysay | PEEDO | 2023 | PEEDO Fund | 1900000 | 1898531.1 | 120 | 2023-05-24 | NULL | 2023-09-21 | NULL | NULL | 100% | NULL | By contract | Completed | Rabb Construction and Supply | NULL | NULL
1527 | Construction of Staff Quarter's, Reservoir Tank and Perimeter Fence for Free Standing Covid-19 Testing Laboratory | SB3 HDMP 300-20-07-08061 | Medical Facilities | MEDICAL FACILITIES | (a) Staff Qaurter's: 20.00m x 8.00m - (b) Reservoir Tank: 3.50m diameter x 4.05m © Perimeter Fence - CHB Tubular Fence and Gate: 68.20m x 2.00m | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2020 | HDMP - Supplemental Budget No. 3 | 6226165 | 6225165 | 180 | 2020-07-30 |  | 2021-01-26 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
1528 | Repair and Maintenance of Southern Palawan Provincial Hospital, Brooke's Point | B2 GF SPPH 24-05-082 | Medical Facilities | MEDICAL FACILITIES | Road And Drainage: Rc Canal With Steel Cover: (L)=133m - Rcpc (L)=18m - Rc Canal With Concrete Cover (L)=36m - Canopy Pathwalk (L)= 83.58m - Pathwalk (Lxwxt) = 83.58m(L) - Varies X 150mm | Brooke's Point | Brooke's Point |  | 2024 | SPPH Fund | 4000000 | 3995944.41 | 155 | 2024-08-15 |  | 2025-01-17 | For approval |  | 90.43% |  | By Contract | On going | FSD Construction
1529 | Airport Development/Expansion of Pag-Asa Island Airport (Extension of Runway Strip), Brgy. Pag-Asa,Kalayaan, Palawan | B2 TF PEO 24-05-088 | Transportation Facilities | ROAD | Extension of Runway Strip | Kalayaan, Palawan | Kalayaan | NULL | 2024 | Trust Fund - DOTr | 1454910037.53 | 1453565284.74 | 540 | 2024-07-09 | NULL | 2025-12-31 | NULL | NULL | 30% | NULL | By Contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
1530 | Construction of Retaining Wall, Roxas Medicare Hospital | B2 GF SB3 PDP 24-09-109 | Medical Facilities | MEDICAL FACILITIES | Retaining wall: 44.20m (L) x 3.0M (H) - CHD Fence; 64.20m (L) x 2.0M (H) | Roxas Medicare Hospital | Roxas | PEO | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 2630000 | 2140036.43 | 118 | 2024-11-25 |  | 2025-03-23 |  |  | 20% |  | By contract | On going | RL Abia Construction
1531 | Supply and Installation of Fire Protection System, Vice Governor Ponce De Leon Memorial Hospital |  | Medical Facilities | MEDICAL FACILITIES | Supply, Installation, Testing and Comissioning of Fire Detection and Alarm System (FDAS) | Vice Governor Ponce De Leon Memorial Hospital | Dumaran |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 3000000 | [10 empty] | For Bidding
1532 | Construction of Elevated Water Tank with Deepwell System, Araceli-Dumaran District Hospital |  | Medical Facilities | MEDICAL FACILITIES | 100.00 cu.m Capacity Tank | Araceli-Dumaran District Hospital | Dumaran |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 8000000 | [10 empty] | For Bidding
1533 | Construction of WaterTank and Water Facility, Vice Governor Ponce De Leon Memorial Hospital |  | Medical Facilities | MEDICAL FACILITIES | 100.00 cu.m Capacity Tank | Vice Governor Ponce De Leon Memorial Hospital | Dumaran |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 8000000 | [10 empty] | For Bidding
1534 | Construction of Cistern Tank, Northern Palawan Provincial Hospital |  | Medical Facilities | MEDICAL FACILITIES | Cistern Tank: 100 cu.m capacity tank | Northern Palawal Provincial Hospital | Taytay |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 1500000 |  | 60 | [8 empty] | For Bidding
1535 | Renovation of Offices (Provincial Employment Service Office and SPS Alay sa Kabataan Office) | NULL | Other Facilities | PGP FACILITIES | Building: 14.95m X 13.12m - Installation Of Partition Wall Fabrication Of Tables And Cabinets | Capitol Building, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | NULL | 2024 | Supplemental Budget No. 2 | 1400000 | NULL | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1536 | Construction of Visitor's Lounge, Palawan Police Provincial Office | NULL | Other Infrastructure | PGP FACILITIES | 1 Storey Building: 10m X 7.5m (Lounge) | Palawan Police Provincial Office | Puerto Princesa City | NULL | 2024 | Supplemental Budget No. 2 | 2500000 | NULL | 90 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1537 | Improvenment of Provincial Security Group Office (Supply and Installation of Airconditioning Units & Tileworks) | B2 GF SB2 PEO 24 - 09 - 108 | Other Facilities | PGP FACILITIES | PSG: Installation Of Airconditioning Unit And Floor Tiles. Ceiling And Interior Walls (For Repainting) | Capitol Building, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | NULL | 2024 | Supplemental Budget No. 2 | 370000 | 366718 | 60 | 2024-11-21 | NULL | 2025-01-20 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | ZYK Construction | NULL | NULL
1538 | Supply and Installation of Securing Monitoring Devices (CCTV System), Provincial Engineering Office | NULL | Other Facilities | PGP FACILITIES | Supply, Installation, Testing and Comissioning | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | SFVIP | 200000 | NULL | 30 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1539 | Construction of PDRRMO Mini Motorpool, Brgy. Irawan, PPC | B2 GP DPF 24-05-090 | Other Infrastructure | PGP FACILITIES | Building: 2 storey (24mx6m) | Brgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | PDRRMO Fund | 5000000 | 4444748.95 | 183 | 2024-08-19 | NULL | 2025-02-18 | NULL | NULL | 60% | NULL | By contract | On going | RC Gadiano Construction | TIN 342-792-217 | NULL
1540 | Construction of DRRM Training Center (A) Combatt Battle Quarter (B) Fitness Training Center © Rapelling Tower | B2 TF PDRRMO 24-04-080 | Other Infrastructure | PGP FACILITIES | Combat Battle Quarter: Floor area 101.25 sq.m of 5 storey - Physical Fitness Training Range: Floor area 21.00m x 37.50m - Rapelling tower: Floor area 112 sq.m - 4 storey | Brgy. Irawan, Puerto Princesa City | Puerto Princesa City | NULL | 2024 | PDRRMO Fund | 7000000 | 5745560.71 | NULL | NULL | NULL | NULL | NULL | NULL | 0% | NULL | By contract | For Award | Luis YC Builders & Supply | NULL | NTP on process
1541 | Palawan Forest Restoration Network Program (Construction of Green House and Potting Shed) Brgy. Sagpangan, Aborlan, Palawan | BF GF PFRNP 24-08-101 | Other Infrastructure | AGRICULTURAL FACILITIES | 1 Storey Building: Potting Shed 4.0m (l) x 4.0m(w), Greenhouse 10.0m (l) x 8.0m (w) | Brgy. Sagpangan, Aborlan, Palawan | Aborlan | NULL | 2024 | BF GF PFRNP 24-08-101 | 500000 | 497978.04 | 62 | 2024-11-04 | NULL | 2025-01-05 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | RL Abia Construction | NULL | NULL
1542 | Construction of Shelterd Port at Lawak, Palawan Island, Municipality of Kalayaan | B2 TF PEO 24-07-096 | Other Infrastructure | OTHER FACILITIES | Port: Concrete Pavement Area: 1,040.03 sq.m and Unpaved Back Up Area: 14,525.26 sq.m | Municipality of Kalayaan | Kalayaan | NULL | 2024 | Trust Fund - DOTr | 766143904.23 | 765118981.36 | 600 | 2024-10-12 | NULL | 2026-06-04 | NULL | NULL | 4.5% | NULL | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | NULL
1543 | Enhancement Of Provincial Budget Office, Brgy. Tanglaw, PPC | B2 GF SB3 PBO 24-08-104 | Other Facilities | PGP FACILITIES | Buildings: GF: 14.80M X 6.05M - 2F:14.80M X 10.55M | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | PBO - SB. No. 3 | 1000000 | 998169.59 | 60 | 2024-09-27 | NULL | 2024-11-26 | NULL | NULL | 100% | NULL | By contract | Completed | RD Abacial Construction | TIN 327-679-690 | NULL
1544 | Repair and Maintenance of Narra Municipal Hospital | B2 GF NMH 24-06-094 | Medical Facilities | MEDICAL FACILITIES | NMH:60m (W) X 60m(L) - Mental Health Clinic: 42m(W) X 12.5m(L) - Motorpool: 21.2m(W) X 5.8m (L) | Brgy. Antipuluan, Narra | Narra | PEO | 2024 | NMH Fund | 3000000 | 2950000 | 150 | 2024-08-28 |  | 2025-01-25 |  |  | 100% |  | By contract | Completed | Maximmus Construction
1545 | Construction of Embedment Mooring System | B2 GF SB4 TPMB23 24-07-095 | Other Infrastructure | OTHER FACILITIES | Port | Cagayancillo, Palawan | Cagayancillo | NULL | 2023 | Supplemental Budget No. 4 - Tubbataha Fund | 1352000 | 1351035 | 30 | 2024-08-29 | NULL | 2024-09-28 | For approval | NULL | NULL | NULL | By contract | Not yet started | E.C Timbancaya Enterprises | NULL | NULL
1546 | Repair & Maintenance - Building & Other Structures, PJMD | B2 GF DB3 JMFDP 24-08-097 | Other Facilities | PGP FACILITIES | Remove & Replace 585.40 sq.m Roofing, Roof Eaves Ceiling with C-Purlins Fascia Board and Downspout - Cyclone Wire Fence, Door and Window - Tubular Door | Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | PJMD Fund | 1500000 | 1499096.52 | 90 | 2024-10-28 | NULL | 2025-01-26 | NULL | NULL | 75% | NULL | By contract | On going | E.C Timbancaya Enterprises | NULL | NULL
1547 | Renovation of Provincial Administrator's Office (Addiitonal Works) | B2 GF SB2 ADM 24-08-100 | Other Facilities | PGP FACILITIES | Building: 15.1m x 11.35m (a) Repainting, Replacement of tile and plumbing fixtures | Capitol Building, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | NULL | 2024 | Admin Fund | 1200000 | 1199997.71 | 60 | 2024-08-31 | NULL | 2024-10-30 | NULL | NULL | 100% | NULL | By contract | Completed | Gth Builders and Developers | NULL | NULL
1548 | Medical Waste Sterilization System with Housing Facility |  | Medical Facilities | MEDICAL FACILITIES |  | SPPH, Brooke's Point | Brooke's Point | PEO | 2023 | SPPH Fund | 25000000 | 25000000 | 60 | 2023-12-27 |  | 2024-02-25 |  |  | 97.5% |  | By contract | On going | The Clean O2 Eco-Friendly Corporation
1549 | Development of Rural Agricultural Center (Construction of Water Supply System) | B2 GF DRAC 24-09-105 | Other Infrastructure | AGRICULTURAL FACILITIES | Water Tank: 2000 L Water Tank - Solar Pumping System | Brgy. Danleg, Dumaran, Palawan | Dumaran | NULL | 2024 | PAO Fund (Agri) | 600000 | 594681.7 | 60 | 2024-11-22 | NULL | 2025-01-21 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | J.JH Construction Supplies Trading | NULL | NULL
1550 | Supply and Installation of Fiber Reinforced Plasric (FRP) Filters for Linapacan Deepwell System, Brgy. San Miguel, Linapacan | B2 GF LWS 24-11-124 | Other Facilities | OTHER FACILITIES | 8 Units of Fiber Reinforced Plastic (FRP) Filter - 4 Units Bag Filter | Brgy. San Miguel, Linapacan | Linapacan | NULL | 2024 | PEEDO Fund | 998563.85 | 991600 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | Sparkotech Engineering Solution Inc. | NULL | NULL
1551 | Repair and Maintenance of the Intensive Juvenile Intervention Support Center (IJISC) | B2 GF BPYC 24 - 09 -111 | Other Facilities | PGP FACILITIES | Outer wall: 254.88 sqm - Ceiling: 294.215 sqm | Brgy. Irawan, Puerto Princesa City | Puerto Princesa City | NULL | 2024 | PJMD Fund | 500000 | 495057.2 | 60 | 2024-11-21 | NULL | 2025-01-20 | NULL | NULL | NULL | NULL | By contract | Recently Awarded | ZYK Construction | NULL | NULL
1552 | Supply and Installation of 140 KW Grid Tied Solar PV System at Three (3) Storey Building, Capitol Compound, Brgy. Tanglaw, PPC | B2 GF PZC 24 - 09 - 107 | Other Facilities | PGP FACILITIES | Solar PV: 268 pcs - Inverter: 8 Units | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | NULL | 20000000 | 19877760 | 150 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | Macspower Construction Supply and Services Corporation | NULL | NTP on process
1553 | Repair and Re-varnish of Seven (7) Narra Tables and Re-upholstery of One (1) Long Sofa and Two (2) 1 Seater Sofa of Provincial Auditor's Office, brgy. Tanglaw, Puerto Princesa City | B2 GF COA 24 - 11 - 131 | Other Facilities | PGP FACILITIES | Repainting of Office Tables (2 Tables) | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | COA Fund | 50000 | 49568 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | RD Abacial Construction | NULL | NTP on process
1554 | Repair and Maintenance of Two (2) Stocks Rooms and Two (2) Container Vans of Provincial Auditor's Office, Brgy. Tanglaw. PPC | B2 GF COA 24 - 11 - 137 | Other Facilities | PGP FACILITIES | 30 sq.m | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | COA Fund | 200000 | 198987.62 | 90 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | RD Abacial Construction | NULL | NTP on process
1555 | Construction of Hazardous Waste Storage Building (AMH) | B2 GF HDMP 24-11-132 | Medical Facilities | MEDICAL FACILITIES | Area: 6m x 4m (1 Storey Building) | Aborlan Medicare Hospital | Aborlan |  | 2024 | HDMP Fund | 650000 | 648521.44 | 120 | [7 empty] | By contract | For Award | Maximmus Construction |  | NTP on process
1556 | Construction of El Nido STP Staffhouse for Operations in Brgy. Villa Liibertad, El Nido, Palawan | B2 GF ENSWT 24-11-126 | Other Facilities | OTHER FACILITIES | Area: 11m x 7m Building | Brgy. Villa Libertad , El Nido, Palawan | El Nido | NULL | 2024 | PEEDO Fund | 1000000 | 997743.03 | 100 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | RD Abacial Construction | NULL | NTP on process
1557 | Supply and Installation of Solar Power System for Linapacan Reverse Osmosis Desalination Water System, Brgy. Nangalao and Cabunlawan, Linapacan, Palawan | B2 GF LWS 24-11-122 | Other Facilities | OTHER FACILITIES | 2 sets of 39 pcs Solar Panel (600w) | Brgy. Nangalao and Cabunlawan, Linapacan, Palawan | Linapacan | NULL | 2024 | PEEDO Fund | 3399511.83 | 3385815.82 | 120 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | J.JH Construction Supplies Trading | NULL | NTP on process
1558 | Construction of Magsaysay Waterworks Office, Magsaysay, Palawan | B2 GF MWS 24-11-123 | Other Facilities | OTHER FACILITIES | 1 unit 10m x 8m Building | NULL | Magsaysay | NULL | 2024 | PEEDO Fund | 5000000 | 4996671.21 | 180 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | J.JH Construction Supplies Trading | NULL | NTP on process
1559 | Repair and Rehabilitaion of Water Supply System (PJMD), PEO Road, Brgy. Bancao-bancao, Puerto Princesa City, Palawan | B2 GF PJMD 24-11-130 | Other Facilities | PGP FACILITIES | New waterline connection, 2 vertical water tank (7.70 cu.m each) with water pump and cistern tank | PEO Road, Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | PJMD Fund | 2000000 | 1999520.27 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | E.C Timbancaya Enterprises | NULL | NTP on process
1560 | Repair and Rehabilitation of Primary Line Including Line Hardwares, Brgy. Bancao-Bancao, Puerto Princesa City | B2 GF SB4 PGSO 24-11-136 | Other Facilities | PGP FACILITIES | 3 Phase line: 600 meters - 1 Phase Line: 600 meters | Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | PJMD - PGSO Fund (Supplemental Budget. No. 4) | 4677283.09 | 4634162.36 | 60 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | TCC Powerserve Trading and Engineering Services | NULL | NTP on process
1561 | Repair and Maintenance of Provincial Jail Annex Building (Provincial Jail Management Division SPS Government Center) | B2 GF PJMD 24-11-134 | Other Facilities | PGP FACILITIES | (a) Repair of Ceiling and Roofing: Ceiling: 264.82 SQ.M - Roofing: 45MX33M - Trench Drain Cover: 24 sets | Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City | NULL | 2024 | PJMD Fund | 3000000 | 2544446.69 | 135 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | RD Abacial Construction | NULL | NTP on process
1562 | Construction of Warehouse with OpCen Phase I | NULL | Other Infrastructure | OTHER FACILITIES | Building: Fo Phase I: Area: 20m(L) x 10m (W) - 200 sq.m | Cuyo, Palawan | Cuyo | NULL | 2024 | PDRRMO - Special Trust Fund | 5000000 | NULL | 258 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1563 | Construction of 2 Barrel Reinforced Concrete Box Culvert (RCBC), Highway Jct. Tagumpay - Maliko Road | B2 TF PDRRMO 24-11-166 | Other Infrastructure | DRAINAGE | (A) RCBC: 3.30M (h) X 6.0M (w) X 8.30M (l) - (B) Slope Protection: 17.32M ( C) Gabions: 12.66M | Brgy. Tagumpay, Roxas, Palawan | Roxas | NULL | 2024 | PDRRMO - Special Trust Fund | 3800000 | 3778641.37 | 113 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | By contract | For Award | Maximmus Construction | NULL | NTP on process
1564 | Construction Of Seawall | NULL | Other Infrastructure | OTHER FACILITIES | Seawall Protection: 100 LN.M | Brgy. Teresita, Dumaran, Palawan | Dumaran | NULL | 2024 | PDRRMO - Special Trust Fund | 6000000 | NULL | 122 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1565 | Construction of 2 Barrel Reinforced Concrete Box Culvert (RCBC) with Slope Protection | NULL | Other Infrastructure | DRAINAGE | (A) RCBC: 3.30M (h) X 6.0M (w) X 8.30M (l) - (B) Slope Protection: 21.32M ( C) Gabions: 13.56M | So. Banglen, Brgy. Taloto, Dumaran, Palawan | Dumaran | NULL | 2024 | PDRRMO - Special Trust Fund | 4200000 | NULL | 113 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1566 | Completion of Evacuation Center/Covered Court Phase I | NULL | Other Infrastructure | COVERED COURT | Court: 30m (l) x 18m (w) | Quezon, Busuanga, Palawan | Busuanga | NULL | 2024 | PDRRMO - Special Trust Fund | 4000000 | NULL | 170 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1567 | Completion of Covered Court/Evacuation Center | NULL | Other Infrastructure | COVERED COURT | Court: 30m (l) x 18m (w) | Santo Niño, Araceli, Palawan | Araceli | NULL | 2024 | PDRRMO - Special Trust Fund | 4000000 | NULL | 170 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1568 | Construction of Warehouse for South | NULL | Other Infrastructure | OTHER FACILITIES | 20M (l) x 10.00M (w) | Brgy. Punta Baja, Rizal, Palawan | Rizal | NULL | 2024 | PDRRMO - Special Trust Fund | 5000000 | NULL | 258 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
1569 | Construction of Warehouse for North | NULL | Other Infrastructure | OTHER FACILITIES | 20M (l) x 10.00M (w) | San Vicente, Palawan | San Vicente | NULL | 2024 | PDRRMO - Special Trust Fund | 5000000 | NULL | 258 | NULL | NULL | NULL | NULL | NULL | NULL | NULL | NULL | For Bidding | NULL | NULL | NULL
Formulas:
TARGET COMPLETION DATE = [NTP DATE]+[C.D]

## SUB TABLE
SUB CATEGORY | ID | CATEGORY | ID | YEAR | ID | MUNICIPALITY | ID | FUND | ID | OFFICE | ID | REMARKS | ID | CONTRACTOR | TIN NUMBER | ID
Road | 1 | Transportation Facilities | 1 | 2014 | 1 | Aborlan | 1 | 20% Development Fund | 1 | PEEDO | 1 | Cancelled | 1 | Hardrock Platinum Development Corporation | TIN 008-625-254 | 1
Bridges | 2 | Medical Facilties | 2 | 2015 | 2 | Coron | 2 | 20% Development Fund - Re-aligned to SB No. 3 | 2 | PEO | 2 | Completed | 2 | A.C. Rivero Development Corp | TIN 001-355-547 | 2
Rhu | 3 | Educational Facilities | 3 | 2016 | 3 | Dumaran | 3 | 20% Development Fund 2023 - Realigned to SB No. 3 | 3 |  |  | Failure of bidding | 3 | A.P. Consebido Construction & Trading | TIN 931-421-496 | 3
Bhs | 4 | Power and Energy Development Program | 4 | 2017 | 4 | Magsaysay | 4 | 20% Development Fund 2023 - Realigned to SB No. 5 | 4 |  |  | For Award | 4 | Agency to Agency Agreement | NULL | 4
Medical Facilities | 5 | Ports and Airports | 5 | 2018 | 5 | Quezon | 5 | 20% Development Fund 2024 | 5 |  |  | For Bidding | 5 | AMLC Builders Construction and Supply | TIN 428-298-201 | 5
School Facilities | 6 | Artesian Wells, Reservoir, Pumping and Conduits | 6 | 2019 | 6 | Rizal | 6 | 20% Development Fund and DOH | 6 |  |  | For preparation (POW and DED) | 6 | Apollo Construction & Enterprises | TIN 181-140-662 | 6
Electrification | 7 | Other Facilities | 7 | 2020 | 7 | Taytay | 7 | 20% Development Fund-Savings | 7 |  |  | For Re-alignment | 7 | Arlustre Construction Corporation | NULL | 7
Ports | 8 | Other Infrastructure | 8 | 2021 | 8 | Agutaya | 8 | 2016-DILG - BUB / LGSF | 8 |  |  | For Re-bid | 8 | Atlanta Construction Company Inc. | NULL | 8
Airports | 9 | Supply | 9 | 2022 | 9 | Araceli | 9 | 2017-DILG - BUB/LGSF | 9 |  |  | For reversion | 9 | Azarraga Construction | TIN 418-292-176 | 9
Irrigation | 10 |  |  | 2023 | 10 | Balabac | 10 | 2024 - DBP Loan Projects (Building) | 10 |  |  | For Termination | 10 | Bacs Construction and Engineering Consultancy | TIN 920-630-716 | 10
Water System | 11 |  |  | 2024 | 11 | Bataraza | 11 | 2024 - DBP Loan Projects (Concreting) | 11 |  |  | For Validation | 11 | Bat's Construction Services | TIN 491-731-278 | 11
PGP Facilities | 12 |  |  | 2025 | 12 | Brooke's Point | 12 | 2024 - DBP Loan Projects (Flood Control) | 12 |  |  | Issued Notice to Terminate | 12 | BCL Construction | TIN 308-390-430 | 12
Agricultural Facilities | 13 |  |  | 2026 | 13 | Busuanga | 13 | 300-22-02-00670 | 13 |  |  | No movement | 13 | BCT Trading and Construction | TIN 102-698-654 | 13
Animal Facilities | 14 |  |  | 2027 | 14 | Cagayancillo | 14 | Aborlan Medical Hospital Fund | 14 |  |  | Not yet started | 14 | Beta-J Construction | 159-232-934 | 14
Covered Court | 15 |  |  | 2028 | 15 | Culion | 15 | Aborlan Medicare Hospital | 15 |  |  | Notice to Terminate | 15 | Bicol Goldrock Construction Corporation | TIN 006-098-920 | 15
Drainage | 16 |  |  | 2029 | 16 | Cuyo | 16 | Admin Fund | 16 |  |  | On going | 16 | Breis Construction | TIN 010-590-630 | 16
Muliti-Purpose | 17 |  |  | 2030 | 17 | El Nido | 17 | B2 ROADS17 300-21-11-15968 | 17 |  |  | Order of Termination | 17 | Breis Construction | NULL | 17
Other Pacilities | 18 |  |  | 2031 | 18 | Kalayaan | 18 | BF GF PFRNP 24-08-101 | 18 |  |  | PEEDO Validate | 18 | Brilliant Metal Industrial Corp. | TIN 143-754-742-000 | 18
Slope Protection | 19 |  |  | 2032 | 19 | Linapacan | 19 | BPYC | 19 |  |  | Re-aligned | 19 | By Admin | NULL | 19
Supply | 20 |  |  | 2033 | 20 | Narra | 20 | BUB/LGSF | 20 |  |  | Recently Awarded | 20 | Carina Electrical Construction Supply | TIN 188-374-116 | 20
|  |  |  | 2034 | 21 | Puerto Princesa City | 21 | Capital outlay | 21 |  |  | Reverted | 21 | Chad Lourence Trading & Construction Services | TIN 919-616-230 | 21
|  |  |  | 2035 | 22 | Roxas | 22 | CMGP | 22 |  |  | Slow movement | 22 | Cjetzu Lumber & Construction Supply | TIN 920-28-159 | 22
|  |  |  | 2036 | 23 | San Vicente | 23 | COA Fund | 23 |  |  | Stop construction | 23 | Cjetzu Lumber & Construction Supply | NULL | 23
|  |  |  | 2037 | 24 | Sofronio Española | 24 | Covid-19 Fund SB3 | 24 |  |  | Subject for Reversion | 24 | Conte Builders and Construction Supply | TIN 923-929-215 | 24
|  |  |  | 2038 | 25 |  |  | CRGGP Fund | 25 |  |  | Suspended | 25 | Crishelle Construction | TIN 133-967-996-00000 | 25
|  |  |  | 2039 | 26 |  |  | D.A FUND | 26 |  |  | Terminated | 26 | CRMMD Trading and Construction | TIN 183-461-224 | 26
|  |  |  | 2040 | 27 |  |  | DBP Loan | 27 |  |  |  |  | Diane Construction and Enterprises | TIN 140-882-282 | 27
|  |  |  | 2041 | 28 |  |  | Debt Servicing Under 20% DF (2014-2015-2016) | 28 |  |  |  |  | E.C Timbancaya Enterprises | TIN 142-914-153 | 28
|  |  |  | 2042 | 29 |  |  | DENR - TIEZA (Trust Fund 2022) | 29 |  |  |  |  | E.C Timbancaya Enterprises | NULL | 29
|  |  |  | 2043 | 30 |  |  | Department of Agriculture | 30 |  |  |  |  | E.M Abin Trading & Construction | CTC 936-562-132-000 | 30
|  |  |  | 2044 | 31 |  |  | DILG - BUB / LGSF | 31 |  |  |  |  | E.V Villaos Trading and Construction Supply | TIN 134-897-002 | 31
|  |  |  | 2045 | 32 |  |  | DILG - BUB/LGSF | 32 |  |  |  |  | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | 32
|  |  |  | 2046 | 33 |  |  | DILG -Kalasada Program | 33 |  |  |  |  | Eddmari Construction & Trading | TIN 141-763-814 | 33
|  |  |  | 2047 | 34 |  |  | Disaster Preparedness Fund (PDRRMO Fund) | 34 |  |  |  |  | EG Batiancilla Construction | NULL | 34
|  |  |  | 2048 | 35 |  |  | DOH | 35 |  |  |  |  | EM Paule Construction and Trading | NULL | 35
|  |  |  | 2049 | 36 |  |  | DOH - HFEP | 36 |  |  |  |  | F.B Murillo Construction | TIN 327-679-690 | 36
|  |  |  | 2050 | 37 |  |  | DOH Fund | 37 |  |  |  |  | F.B Murillo Construction | TIN 772-152-432 | 37
|  |  |  | 2051 | 38 |  |  | DOH Fund (Typhoon Odette) - 2021 | 38 |  |  |  |  | F.F Galang Construction | TIN 188-519-198 | 38
|  |  |  | 2052 | 39 |  |  | DOH-Trust Fund | 39 |  |  |  |  | F.F Galang Construction | NULL | 39
|  |  |  | 2053 | 40 |  |  | DPWH | 40 |  |  |  |  | FSD Construction | NULL | 40
|  |  |  | 2054 | 41 |  |  | Energy Development Program | 41 |  |  |  |  | Furosam Incorporated | TIN 009-062-221 | 41
|  |  |  | 2055 | 42 |  |  | GAD Fund | 42 |  |  |  |  | GB Jade Construction and Trading | TIN 940-685-564 | 42
|  |  |  | 2056 | 43 |  |  | General Fund | 43 |  |  |  |  | Global Teleconstruction Specialist Inc. | TIN 218-601-693-00000 | 43
|  |  |  | 2057 | 44 |  |  | HDMP - Supplemental Budget No. 3 | 44 |  |  |  |  | Global Teleconstruction Specialist Inc. | NULL | 44
|  |  |  | 2058 | 45 |  |  | HDMP Fund | 45 |  |  |  |  | Goldrock Construction & Development Corp. | NULL | 45
|  |  |  | 2059 | 46 |  |  | Kalsada | 46 |  |  |  |  | Gth Builders and Developers | NULL | 46
|  |  |  | 2060 | 47 |  |  | LGSF- DILG CMGP | 47 |  |  |  |  | Hadiyah Construction | TIN 324-356-720 | 47
|  |  |  | 2061 | 48 |  |  | Livelihood Fund | 48 |  |  |  |  | Hadiyah Construction | NULL | 48
|  |  |  | 2062 | 49 |  |  | Local Fund (Support to Muslim Communities) | 49 |  |  |  |  | Hardshell Design and Construction | TIN 211-391-300-001 | 49
|  |  |  | 2063 | 50 |  |  | Locally Funded | 50 |  |  |  |  | High Riser Construction & Trading | TIN 928-603-901 | 50
|  |  |  | 2064 | 51 |  |  | Locally Funded - Supplemental Budget No. 6 | 51 |  |  |  |  | HNT Builders & Enterprises | TIN 909-572-814 | 51
|  |  |  | 2065 | 52 |  |  | MOOE | 52 |  |  |  |  | I. Marcelo Builders Incorporated | TIN 008-755-657 | 52
|  |  |  | 2066 | 53 |  |  | MOOE 2022 | 53 |  |  |  |  | Ian and Jayson Construction | TIN 182-291-537 | 53
|  |  |  | 2067 | 54 |  |  | MOOE PEO | 54 |  |  |  |  | IKM Builders & Construction Supply | NULL | 54
|  |  |  | 2068 | 55 |  |  | NA | 55 |  |  |  |  | Ivy Michelle Construction and Trading | TIN 008-664-275 | 55
|  |  |  | 2069 | 56 |  |  | NHA Fund | 56 |  |  |  |  | Ivy Michelle Construction and Trading | TIN 009-492-339 | 56
|  |  |  | 2070 | 57 |  |  | NMH Fund | 57 |  |  |  |  | J.JH Construction Supplies Trading | NULL | 57
|  |  |  | 2071 | 58 |  |  | Other fund | 58 |  |  |  |  | Jaica Construction Services | NULL | 58
|  |  |  | 2072 | 59 |  |  | PAO Fund (Agri) | 59 |  |  |  |  | Jas Trading and Construction | NULL | 59
|  |  |  | 2073 | 60 |  |  | PBO - SB. No. 3 | 60 |  |  |  |  | JB & Sons Trading & Construction | TIN 166-376-497 | 60
|  |  |  | 2074 | 61 |  |  | PCDP Fund | 61 |  |  |  |  | JBS Abia Construction | TIN 428-617-369 | 61
|  |  |  | 2075 | 62 |  |  | PCF 2015 (DILG) | 62 |  |  |  |  | JD Golez Construction Services | TIN 181-147-186 | 62
|  |  |  | 2076 | 63 |  |  | PDRRMO - Special Trust Fund | 63 |  |  |  |  | JD Golez Construction Services | TIN 340-084-699 | 63
|  |  |  | 2077 | 64 |  |  | PDRRMO Fund | 64 |  |  |  |  | JFR Construction | NULL | 64
|  |  |  | 2078 | 65 |  |  | PEEDO Fund | 65 |  |  |  |  | Johnstar Trading and Construction Supply | TIN 912-843-647 | 65
|  |  |  | 2079 | 66 |  |  | Performance Challenge Fund | 66 |  |  |  |  | Julriz Trading and Construction | TIN 495-740-401 | 66
|  |  |  | 2080 | 67 |  |  | PGO Fund | 67 |  |  |  |  | Kayano Trading and Construction | TIN 497-273-240 | 67
|  |  |  | 2081 | 68 |  |  | PGO Fund - Supplemental Budget No. 2 | 68 |  |  |  |  | Keilana Resources and DF Corporation | NULL | 68
|  |  |  | 2082 | 69 |  |  | Philippines Veterans Bank Loan | 69 |  |  |  |  | KIR Konstructicon Builders and Supply | TIN 010-605-480 | 69
|  |  |  | 2083 | 70 |  |  | Philippines Veterans Bank Loan 2018 | 70 |  |  |  |  | KIR Konstructicon Builders and Supply | NULL | 70
|  |  |  | 2084 | 71 |  |  | Philippines Veterans Bank Loan 2019 | 71 |  |  |  |  | Kudz Trading and Construction | TIN 188-527-256 | 71
|  |  |  | 2085 | 72 |  |  | PJMD - PGSO Fund (Supplemental Budget. No. 4) | 72 |  |  |  |  | L.M John Construction Supplies Trading | TIN 422-936-808 | 72
|  |  |  | 2086 | 73 |  |  | PJMD Fund | 73 |  |  |  |  | LB Leoncio Trading and Construction | TIN 181-143-624 | 73
|  |  |  | 2087 | 74 |  |  | POP Fund | 74 |  |  |  |  | Lea & Sons Trading & Construction | TIN 134-897-002 | 74
|  |  |  | 2088 | 75 |  |  | RAC Fund | 75 |  |  |  |  | Lea and Sons Trading and Construction | NULL | 75
|  |  |  | 2089 | 76 |  |  | ROADS 15 300-19-10-18749 | 76 |  |  |  |  | Leon John Great Builders Construction Corp. | TIN 009-924-271 | 76
|  |  |  | 2090 | 77 |  |  | Roads and Bridges Dev. Program-TF (2016) | 77 |  |  |  |  | Louiese Trading & Construction | TIN 940-685-564 | 77
|  |  |  | 2091 | 78 |  |  | SB No. 6 - Debt Servicing Under 20% DF (2014-2015-2016) | 78 |  |  |  |  | Luis YC Builders & Supply | TIN 120-420-502-00006 | 78
|  |  |  | 2092 | 79 |  |  | SBDP-NTF-ELCAC 2021 | 79 |  |  |  |  | Luis YC Builders & Supply | TIN 120-420-502-006 | 79
|  |  |  | 2093 | 80 |  |  | SFVIP | 80 |  |  |  |  | Luis YC Builders & Supply | NULL | 80
|  |  |  | 2094 | 81 |  |  | SFVIP 2022 | 81 |  |  |  |  | M. Luengo Construction | TIN 010-545-401 | 81
|  |  |  | 2095 | 82 |  |  | Special Education Fund | 82 |  |  |  |  | M. Luengo Construction | TIN 257-013-134 | 82
|  |  |  | 2096 | 83 |  |  | Special Education Fund - 2017 | 83 |  |  |  |  | M. Luengo Construction | NULL | 83
|  |  |  | 2097 | 84 |  |  | Special Education Fund - 2022 | 84 |  |  |  |  | Macspower Construction Supply and Services Corporation | NULL | 84
|  |  |  | 2098 | 85 |  |  | SPPH | 85 |  |  |  |  | Maintin Construction and Supply | TIN 488-730-176 | 85
|  |  |  | 2099 | 86 |  |  | SPPH Fund | 86 |  |  |  |  | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | 86
|  |  |  | 2100 | 87 |  |  | Supplemental Budget | 87 |  |  |  |  | Mamsar Construction & Industrial Corporation | NULL | 87
[8 empty] | Supplemental Budget No. 1 | 88 |  |  |  |  | Mark Dennis Deniel Trading and Construction | NULL | 88
[8 empty] | Supplemental Budget No. 12 | 89 |  |  |  |  | Maryjonica Construction | TIN 350-458-389 | 89
[8 empty] | Supplemental Budget No. 14 | 90 |  |  |  |  | Maryjonica Construction | NULL | 90
[8 empty] | Supplemental Budget No. 2 | 91 |  |  |  |  | Maryknoll Builders and Supply | TIN 105-802-318 | 91
[8 empty] | Supplemental Budget No. 2 POP | 92 |  |  |  |  | Maryknoll Construction and Supply | NULL | 92
[8 empty] | Supplemental Budget No. 3 HDMP | 93 |  |  |  |  | Maximmus Construction | TIN 497-273-240 | 93
[8 empty] | Supplemental Budget No. 4 | 94 |  |  |  |  | Maximmus Construction | TIN 925-322-134 | 94
[8 empty] | Supplemental Budget No. 4 - Tubbataha Fund | 95 |  |  |  |  | Maximmus Construction | NULL | 95
[8 empty] | Supplemental Budget No. 4 (PCDO) | 96 |  |  |  |  | Mazon Engineering and Construction | TIN 273-819-199 | 96
[8 empty] | Supplemental Budget No. 5 | 97 |  |  |  |  | Megaprint | NULL | 97
[8 empty] | Supplemental Budget No. 6 | 98 |  |  |  |  | Megaprint | NULL | 98
[8 empty] | Supplemental Budget No. 8 | 99 |  |  |  |  | MG Tan Construction | TIN 113-310-056 | 99
[8 empty] | Supplemental Budget No. 8 - LWC | 100 |  |  |  |  | MGB Construction and Trading | NULL | 100
[8 empty] | Supplemental Budget No. 9 | 101 |  |  |  |  | MKB Builders and Supply | TIN 262-511-948 | 101
[8 empty] | Supplemental Budget No.12 | 102 |  |  |  |  | MVP Construction and Trdaing Inc. | TIN 616-777-887 | 102
[8 empty] | Supplmental Budget No. 4 (CSPMP) | 103 |  |  |  |  | N.Sales Construction | TIN 174-694-454 | 103
[8 empty] | TF - DOH HFEP 2014 | 104 |  |  |  |  | Nab Construction & Enterprises | TIN 445-503-720 | 104
[8 empty] | TF LDRRMF 2021-PO 2615-A | 105 |  |  |  |  | Nale Construction | NULL | 105
[8 empty] | Trust Fund | 106 |  |  |  |  | Nand Trading | NULL | 106
[8 empty] | Trust Fund - (OCD FUNDS) | 107 |  |  |  |  | New Space Trading and Construction | TIN 010-545-401 | 107
[8 empty] | Trust Fund - DOH | 108 |  |  |  |  | N-Gines Technology Inc. | NULL | 108
[8 empty] | Trust Fund - DOTr | 109 |  |  |  |  | NRNS Trading And Construction Supply | TIN 922-390-708 | 109
[8 empty] | Trust Fund - TIEZA | 110 |  |  |  |  | Octagon Concrete Solution | TIN 901-128-486 | 110
[8 empty] | Trust Fund- Cong. Alvarez | 111 |  |  |  |  | One Badajos Construction & Trading Corporation | TIN 010-590-630 | 111
[8 empty] | Trust Fund -DOH | 112 |  |  |  |  | One Hundred Percent and Development Corp. | TIN 009-446-039 | 112
[8 empty] | Typhoon Odette Financial Assistance (Office of the President) - 100M | 113 |  |  |  |  | One Hundred Percent and Development Corp. | TIN 168-154-730 | 113
[14 empty] | One Hundred Percent and Development Corp. | NULL | 114
[14 empty] | Palbic Construction and Supply | TIN 128-066-252 | 115
[14 empty] | Palbic Construction and Supply | NULL | 116
[14 empty] | Panaad Construction | TIN 938-375-592 | 117
[14 empty] | Premium Megastructures Inc. | NULL | 118
[14 empty] | R. Narrazid Trading and Construction | TIN 330-975-725 | 119
[14 empty] | R.R Leoncio Construction | NULL | 120
[14 empty] | Rabb Construction & Supply | TIN 325-261-868 | 121
[14 empty] | Rabb Construction and Supply | NULL | 122
[14 empty] | RAK Trading Construction & Supply | NULL | 123
[14 empty] | RC Gadiano Construction | TIN 342-792-217 | 124
[14 empty] | RD Abacial Construction | TIN 327-679-690 | 125
[14 empty] | RD Abacial Construction | NULL | 126
[14 empty] | RD Abacial Construction | TIN 327-679-690 | 127
[14 empty] | RDF Trading and Construction | CTC 097-331-47 | 128
[14 empty] | RDF Trading and Construction | NULL | 129
[14 empty] | Reinastar Trading and Construction | TIN 944-093-894-001 | 130
[14 empty] | Rhodamay Construction and Supply | 322-759-45 | 131
[14 empty] | Rhodamay Construction and Supply | TIN 944-093-894-001 | 132
[14 empty] | RL Abia Construction | TIN 274-260-467 | 133
[14 empty] | RL Abia Construction | NULL | 134
[14 empty] | Samurai Construction | TIN 919-621-019 | 135
[14 empty] | Samurai Construction | TIN 919-621-019 | 136
[14 empty] | Seven Digit Construction and Supplies | TIN 008-664-275 | 137
[14 empty] | Seven Digit Construction and Supplies | TIN 183-661-696 | 138
[14 empty] | Seven Digit Construction and Supplies | NULL | 139
[14 empty] | Smmiley Builders and Trading | TIN 936-564-958 | 140
[14 empty] | Smmiley Builders and Trading | NULL | 141
[14 empty] | Sparkotech Engineering Solution Inc. | NULL | 142
[14 empty] | St. Timothy Construction Corporation | TIN 008-813-669-000 | 143
[14 empty] | St.Timothy Construction Corporation | TIN 008-813-669-000 | 144
[14 empty] | St.Timothy Construction Corporation | NULL | 145
[14 empty] | Synchros Power Solutions | TIN 134-545-266 | 146
[14 empty] | Synchros Power Solutions | TIN 134-545-266-000 | 147
[14 empty] | TCC Powerserve Trading and Engineering Services | TIN 931-421-496 | 148
[14 empty] | TCC Powerserve Trading and Engineering Services | NULL | 149
[14 empty] | Tektwin Marketing Corporation | NULL | 150
[14 empty] | The Clean O2 Eco-Friendly Corporation | NULL | 151
[14 empty] | Triplestone Construction and Development Corporation | TIN 009-149-175 | 152
[14 empty] | UGM Construction | TIN 102-967-201 | 153
[14 empty] | VCH Construction and Trading | TIN 924-818-554 | 154
[14 empty] | VJ Builders | NULL | 155
[14 empty] | Warlen Industrial and Sales Corporation | NULL | 156
[14 empty] | Werr Corporation International | NULL | 157
[14 empty] | West Blue Builders | NULL | 158
[14 empty] | Western Fortune | NULL | 159
[14 empty] | Yurich Builders & Construction Supply | TIN 258-921-757-00001 | 160
[14 empty] | Yurich Builders & Construction Supply | TIN 258-921-757-001 | 161
[14 empty] | Yurich Builders & Construction Supply | NULL | 162
[14 empty] | ZYK Construction | NULL | 163

## PIVOT
|  |  |  | SUB CATEGORY |  | CATEGORY |  | MUNICIPALITY |  | FUND |  | OFFICE |  | REMARKS
PROJECT NUMBER | SUB CATEGORY | Row Labels | Count of PROJECT NUMBER | Row Labels | Count of NO | Row Labels | Count of NO | Row Labels | Count of NO | Row Labels | Count of NO | Row Labels | Count of NO | Row Labels | Count of NO
1 | ROAD | AGRICULTURAL FACILITIES | 15 | AGRICULTURAL FACILITIES | 15 | Artesian Wells, Reservoir, Pumping and Conduits | 33 | Aborlan | 1 | 20% Development Fund | 448 | Artesian Wells, Reservoir, Pumping and Conduits | 33 | Cancelled | 3 | PROJECT CONTRACTOR | TIN NUMBER | Count of NO
2 | ROAD | AIRPORTS | 2 | AIRPORTS | 2 | Educational Facilities | 81 | Coron | 3 | 20% Development Fund | 1 | IRRIGATION | 10 | Completed | 1209 | Hardrock Platinum Development Corporation | TIN 008-625-254 | 4
3 | ROAD | ANIMAL FACILITIES | 4 | ANIMAL FACILITIES | 4 | Medical Facilties | 552 | Dumaran | 1 | 20% Development Fund - Re-aligned to SB No. 3 | 5 | WATER SYSTEM | 23 | Failure of bidding | 4 | A.C. Rivero Development Corp | TIN 001-355-547 | 4
4 | ROAD | BHS | 87 | BHS | 87 | Other Facilities | 162 | Magsaysay | 1 | 20% Development Fund 2023 - Realigned to SB No. 3 | 11 | Educational Facilities | 81 | For Award | 14 | A.P. Consebido Construction & Trading | TIN 931-421-496 | 15
5 | WATER SYSTEM | BRIDGES | 70 | BRIDGES | 70 | Other Infrastructure | 434 | Quezon | 1 | 20% Development Fund 2023 - Realigned to SB No. 5 | 1 | SCHOOL FACILITIES | 81 | For Bidding | 27 | Agency to Agency Agreement | (blank) | 7
6 | WATER SYSTEM | COVERED COURT | 215 | COVERED COURT | 215 | Ports and Airports | 12 | Rizal | 5 | 20% Development Fund 2024 | 18 | Medical Facilties | 552 | For preparation (POW and DED) | 1 | AMLC Builders Construction and Supply | TIN 428-298-201 | 1
7 | WATER SYSTEM | DRAINAGE | 85 | DRAINAGE | 85 | Power and Energy Development Program | 33 | Taytay | 6 | 20% Development Fund and DOH | 10 | BHS | 87 | For Re-alignment | 2 | Apollo Construction & Enterprises | TIN 181-140-662 | 4
8 | MEDICAL FACILITIES | ELECTRIFICATION | 33 | ELECTRIFICATION | 33 | Supply | 1 | Aborlan | 91 | 20% Development Fund-Savings | 1 | MEDICAL FACILITIES | 431 | For Re-bid | 1 | Arlustre Construction Corporation | (blank) | 2
9 | MEDICAL FACILITIES | IRRIGATION | 10 | IRRIGATION | 10 | Transportation Facilities | 257 | Agutaya | 13 | 2016-DILG - BUB / LGSF | 3 | RHU | 34 | For reversion | 1 | Atlanta Construction Company Inc. | (blank) | 1
10 | SCHOOL FACILITIES | MEDICAL FACILITIES | 431 | MEDICAL FACILITIES | 431 | (blank) | 3 | Araceli | 38 | 2017-DILG - BUB/LGSF | 1 | Other Facilities | 162 | For Termination | 42 | Azarraga Construction | TIN 418-292-176 | 2
11 | SCHOOL FACILITIES | MULITI-PURPOSE | 57 | MULITI-PURPOSE | 57 | Grand Total | 1568 | Balabac | 57 | 2024 - DBP Loan Projects (Building) | 2 | AGRICULTURAL FACILITIES | 11 | For Validation | 4 | Bacs Construction and Engineering Consultancy | TIN 920-630-716 | 1
12 | SCHOOL FACILITIES | OTHER FACILITIES | 85 | OTHER FACILITIES | 85 |  |  | Bataraza | 49 | 2024 - DBP Loan Projects (Concreting) | 24 | ANIMAL FACILITIES | 3 | Issued Notice to Terminate | 2 | Bat's Construction Services | TIN 491-731-278 | 2
13 | ROAD | PGP FACILITIES | 117 | PGP FACILITIES | 117 |  |  | Brooke's Point | 88 | 2024 - DBP Loan Projects (Flood Control) | 32 | MULITI-PURPOSE | 10 | No movement | 6 | BCL Construction | TIN 308-390-430 | 3
14 | ROAD | PORTS | 10 | PORTS | 10 |  |  | Busuanga | 35 | 300-22-02-00670 | 1 | OTHER FACILITIES | 24 | Not yet started | 7 | BCT Trading and Construction | TIN 102-698-654 | 86
15 | ROAD | RHU | 34 | RHU | 34 |  |  | Cagayancillo | 19 | Aborlan Medical Hospital Fund | 1 | PGP FACILITIES | 114 | Notice to Terminate | 22 | Beta-J Construction | 159-232-934 | 19
16 | ROAD | ROAD | 187 | ROAD | 187 |  |  | Coron | 71 | Aborlan Medicare Hospital | 5 | Other Infrastructure | 434 | On going | 97 | Bicol Goldrock Construction Corporation | TIN 006-098-920 | 4
17 | BRIDGES | SCHOOL FACILITIES | 81 | SCHOOL FACILITIES | 81 |  |  | Culion | 27 | Admin Fund | 2 | AGRICULTURAL FACILITIES | 4 | On going | 1 | Breis Construction | TIN 010-590-630 | 9
18 | BRIDGES | SLOPE PROTECTION | 18 | SLOPE PROTECTION | 18 |  |  | Cuyo | 54 | B2 ROADS17 300-21-11-15968 | 1 | ANIMAL FACILITIES | 1 | Order of Termination | 11 |  | (blank) | 1
19 | BRIDGES | SUPPLY | 1 | SUPPLY | 1 |  |  | Dumaran | 106 | BF GF PFRNP 24-08-101 | 1 | COVERED COURT | 215 | PEEDO Validate | 2 | Brilliant Metal Industrial Corp. | TIN 143-754-742-000 | 5
20 | BRIDGES | WATER SYSTEM | 26 | WATER SYSTEM | 26 |  |  | El Nido | 81 | BPYC | 2 | DRAINAGE | 85 | Re-aligned | 37 | By Admin | (blank) | 3
21 | SCHOOL FACILITIES | (blank) |  | Grand Total | 1568 |  |  | Kalayaan | 5 | BUB/LGSF | 7 | MULITI-PURPOSE | 47 | Recently Awarded | 7 | Carina Electrical Construction Supply | TIN 188-374-116 | 48
22 | MEDICAL FACILITIES | Grand Total | 1568 |  |  |  |  | Linapacan | 22 | Capital outlay | 14 | OTHER FACILITIES | 61 | Reverted | 4 | Chad Lourence Trading & Construction Services | TIN 919-616-230 | 2
23 | MEDICAL FACILITIES | [6 empty] | Magsaysay | 22 | CMGP | 9 | PGP FACILITIES | 3 | Slow movement | 1 | Cjetzu Lumber & Construction Supply | TIN 920-28-159 | 1
24 | MEDICAL FACILITIES | [6 empty] | Narra | 70 | COA Fund | 2 | SLOPE PROTECTION | 18 | Stop construction | 1 |  | (blank) | 1
25 | MEDICAL FACILITIES | [6 empty] | Narra | 1 | Covid-19 Fund SB3 | 1 | Ports and Airports | 12 | Subject for Reversion | 10 | Conte Builders and Construction Supply | TIN 923-929-215 | 32
26 | BHS | [6 empty] | Puerto Princesa City | 130 | CRGGP Fund | 2 | AIRPORTS | 2 | Suspended | 5 | Crishelle Construction | TIN 133-967-996-00000 | 1
27 | BHS | [6 empty] | Quezon | 51 | D.A FUND | 1 | PORTS | 10 | Terminated | 47 | CRMMD Trading and Construction | TIN 183-461-224 | 4
28 | BHS | [6 empty] | Quezon | 1 | DBP Loan | 28 | Power and Energy Development Program | 33 | Grand Total | 1568 | Diane Construction and Enterprises | TIN 140-882-282 | 1
29 | BHS | [6 empty] | Rizal | 74 | Debt Servicing Under 20% DF (2014-2015-2016) | 11 | ELECTRIFICATION | 33 |  |  | E.C Timbancaya Enterprises | TIN 142-914-153 | 10
30 | BHS | [6 empty] | Rizal | 2 | DENR - TIEZA (Trust Fund 2022) | 1 | Supply | 1 |  |  |  | (blank) | 4
31 | BHS | [6 empty] | Roxas | 170 | Department of Agriculture | 3 | SUPPLY | 1 |  |  | E.M Abin Trading & Construction | CTC 936-562-132-000 | 7
32 | MEDICAL FACILITIES | [6 empty] | San Vicente | 62 | DILG - BUB / LGSF | 9 | Transportation Facilities | 257 |  |  | E.V Villaos Trading and Construction Supply | TIN 134-897-002 | 1
33 | MEDICAL FACILITIES | [6 empty] | Sofronio Española | 55 | DILG - BUB/LGSF | 2 | BRIDGES | 70 |  |  |  | TIN 142-914-104 | 148
34 | MEDICAL FACILITIES | [6 empty] | Taytay | 150 | DILG -Kalasada Program | 3 | ROAD | 187 |  |  | Eddmari Construction & Trading | TIN 141-763-814 | 5
35 | MEDICAL FACILITIES | [6 empty] | (blank) | 6 | Disaster Preparedness Fund (PDRRMO Fund) | 1 | (blank) | 3 |  |  | EG Batiancilla Construction | (blank) | 1
36 | MEDICAL FACILITIES | [6 empty] | Grand Total | 1568 | DOH | 1 | WATER SYSTEM | 3 |  |  | EM Paule Construction and Trading | (blank) | 12
37 | MEDICAL FACILITIES | [8 empty] | DOH - HFEP | 11 | Grand Total | 1568 |  |  | F.B Murillo Construction | TIN 327-679-690 | 1
38 | MEDICAL FACILITIES | [8 empty] | DOH Fund | 7 | [5 empty] | TIN 772-152-432 | 3
39 | OTHER FACILITIES | [8 empty] | DOH Fund (Typhoon Odette) - 2021 | 7 |  |  |  |  | F.F Galang Construction | TIN 188-519-198 | 2
40 | ROAD | [8 empty] | DOH-Trust Fund | 4 | [5 empty] | (blank) | 1
41 | BHS | [8 empty] | DOH-Trust Fund | 4 |  |  |  |  | FSD Construction | (blank) | 3
42 | BHS | [8 empty] | DPWH | 1 |  |  |  |  | Furosam Incorporated | TIN 009-062-221 | 4
43 | BHS | [8 empty] | Energy Development Program | 4 |  |  |  |  | GB Jade Construction and Trading | TIN 940-685-564 | 4
44 | MULITI-PURPOSE | [8 empty] | GAD Fund | 1 |  |  |  |  | Global Teleconstruction Specialist Inc. | TIN 218-601-693-00000 | 1
45 | MULITI-PURPOSE | [8 empty] | General Fund | 10 | [5 empty] | (blank) | 2
46 | MULITI-PURPOSE | [8 empty] | HDMP - Supplemental Budget No. 3 | 2 |  |  |  |  | Goldrock Construction & Development Corp. | (blank) | 1
47 | MULITI-PURPOSE | [8 empty] | HDMP Fund | 1 |  |  |  |  | Gth Builders and Developers | (blank) | 4
48 | BHS | [8 empty] | Kalsada | 16 |  |  |  |  | Hadiyah Construction | TIN 324-356-720 | 4
49 | BHS | [8 empty] | LGSF- DILG CMGP | 1 | [5 empty] | (blank) | 3
50 | BHS | [8 empty] | Livelihood Fund | 1 |  |  |  |  | Hardshell Design and Construction | TIN 211-391-300-001 | 21
51 | BHS | [8 empty] | Local Fund (Support to Muslim Communities) | 5 |  |  |  |  | High Riser Construction & Trading | TIN 928-603-901 | 2
52 | BHS | [8 empty] | Locally Funded | 26 |  |  |  |  | HNT Builders & Enterprises | TIN 909-572-814 | 13
53 | BHS | [8 empty] | Locally Funded | 6 |  |  |  |  | I. Marcelo Builders Incorporated | TIN 008-755-657 | 12
54 | BHS | [8 empty] | Locally Funded - Supplemental Budget No. 6 | 13 |  |  |  |  | Ian and Jayson Construction | TIN 182-291-537 | 2
55 | BHS | [8 empty] | MOOE | 12 |  |  |  |  | IKM Builders & Construction Supply | (blank) | 1
56 | MULITI-PURPOSE | [8 empty] | MOOE 2022 | 9 |  |  |  |  | Ivy Michelle Construction and Trading | TIN 008-664-275 | 1
57 | OTHER FACILITIES | [8 empty] | MOOE PEO | 2 | [5 empty] | TIN 009-492-339 | 123
58 | OTHER FACILITIES | [8 empty] | NA | 3 |  |  |  |  | J.JH Construction Supplies Trading | (blank) | 8
59 | PGP FACILITIES | [8 empty] | NHA Fund | 1 |  |  |  |  | Jaica Construction Services | (blank) | 1
60 | ROAD | [8 empty] | NMH Fund | 1 |  |  |  |  | Jas Trading and Construction | (blank) | 5
61 | ROAD | [8 empty] | Other fund | 1 |  |  |  |  | JB & Sons Trading & Construction | TIN 166-376-497 | 1
62 | ROAD | [8 empty] | PAO Fund (Agri) | 1 |  |  |  |  | JBS Abia Construction | TIN 428-617-369 | 2
63 | ROAD | [8 empty] | PBO - SB. No. 3 | 1 |  |  |  |  | JD Golez Construction Services | TIN 181-147-186 | 1
64 | ROAD | [8 empty] | PCDP Fund | 1 | [5 empty] | TIN 340-084-699 | 2
65 | ROAD | [8 empty] | PCF 2015 (DILG) | 1 |  |  |  |  | JFR Construction | (blank) | 5
66 | ROAD | [8 empty] | PDRRMO - Special Trust Fund | 8 |  |  |  |  | Johnstar Trading and Construction Supply | TIN 912-843-647 | 55
67 | ROAD | [8 empty] | PDRRMO Fund | 19 |  |  |  |  | Julriz Trading and Construction | TIN 495-740-401 | 44
68 | ROAD | [8 empty] | PEEDO Fund | 10 |  |  |  |  | Kayano Trading and Construction | TIN 497-273-240 | 6
69 | ROAD | [8 empty] | Performance Challenge Fund | 4 |  |  |  |  | Keilana Resources and DF Corporation | (blank) | 1
70 | ROAD | [8 empty] | PGO Fund | 1 |  |  |  |  | KIR Konstructicon Builders and Supply | TIN 010-605-480 | 1
71 | ROAD | [8 empty] | PGO Fund - Supplemental Budget No. 2 | 1 | [5 empty] | (blank) | 1
72 | ROAD | [8 empty] | Philippines Veterans Bank Loan | 1 |  |  |  |  | Kudz Trading and Construction | TIN 188-527-256 | 41
73 | ROAD | [8 empty] | Philippines Veterans Bank Loan 2018 | 163 |  |  |  |  | L.M John Construction Supplies Trading | TIN 422-936-808 | 3
74 | MULITI-PURPOSE | [8 empty] | Philippines Veterans Bank Loan 2019 | 1 |  |  |  |  | LB Leoncio Trading and Construction | TIN 181-143-624 | 1
75 | MULITI-PURPOSE | [8 empty] | PJMD - PGSO Fund (Supplemental Budget. No. 4) | 1 |  |  |  |  | Lea & Sons Trading & Construction | TIN 134-897-002 | 11
76 | MULITI-PURPOSE | [8 empty] | PJMD Fund | 7 |  |  |  |  | Lea and Sons Trading and Construction | (blank) | 2
77 | MULITI-PURPOSE | [8 empty] | POP Fund | 1 |  |  |  |  | Leon John Great Builders Construction Corp. | TIN 009-924-271 | 6
78 | PGP FACILITIES | [8 empty] | RAC Fund | 1 |  |  |  |  | Louiese Trading & Construction | TIN 940-685-564 | 7
79 | PGP FACILITIES | [8 empty] | ROADS 15 300-19-10-18749 | 1 |  |  |  |  | Luis YC Builders & Supply | TIN 120-420-502-00006 | 2
80 | PGP FACILITIES | [8 empty] | Roads and Bridges Dev. Program-TF (2016) | 1 | [5 empty] | TIN 120-420-502-006 | 1
81 | OTHER FACILITIES | [8 empty] | SB No. 6 - Debt Servicing Under 20% DF (2014-2015-2016) | 1 | [5 empty] | (blank) | 6
82 | MEDICAL FACILITIES | [8 empty] | SBDP-NTF-ELCAC 2021 | 34 |  |  |  |  | M. Luengo Construction | TIN 010-545-401 | 1
83 | MEDICAL FACILITIES | [8 empty] | SFVIP | 1 | [5 empty] | TIN 257-013-134 | 3
84 | PORTS | [8 empty] | SFVIP | 11 | [5 empty] | (blank) | 1
85 | PORTS | [8 empty] | SFVIP 2022 | 6 |  |  |  |  | Macspower Construction Supply and Services Corporation | (blank) | 1
86 | PORTS | [8 empty] | Special Education Fund | 39 |  |  |  |  | Maintin Construction and Supply | TIN 488-730-176 | 4
87 | PORTS | [8 empty] | Special Education Fund - 2017 | 1 |  |  |  |  | Mamsar Construction & Industrial Corporation | TIN 273-578-000 | 17
88 | WATER SYSTEM | [8 empty] | Special Education Fund - 2022 | 19 | [5 empty] | (blank) | 5
89 | BHS | [8 empty] | SPPH | 1 |  |  |  |  | Mark Dennis Deniel Trading and Construction | (blank) | 1
90 | BHS | [8 empty] | SPPH Fund | 2 |  |  |  |  | Maryjonica Construction | TIN 350-458-389 | 7
91 | BHS | [8 empty] | Supplemental Budget | 1 | [5 empty] | (blank) | 1
92 | RHU | [8 empty] | Supplemental Budget No. 1 | 61 |  |  |  |  | Maryknoll Builders and Supply | TIN 105-802-318 | 57
93 | BHS | [8 empty] | Supplemental Budget No. 12 | 15 |  |  |  |  | Maryknoll Construction and Supply | (blank) | 1
94 | BHS | [8 empty] | Supplemental Budget No. 14 | 5 |  |  |  |  | Maximmus Construction | TIN 497-273-240 | 1
95 | RHU | [8 empty] | Supplemental Budget No. 2 | 30 | [5 empty] | TIN 925-322-134 | 10
96 | BHS | [8 empty] | Supplemental Budget No. 2 POP | 1 | [5 empty] | (blank) | 11
97 | BHS | [8 empty] | Supplemental Budget NO. 3 | 4 |  |  |  |  | Mazon Engineering and Construction | TIN 273-819-199 | 21
98 | OTHER FACILITIES | [8 empty] | Supplemental Budget No. 3 | 18 |  |  |  |  | Megaprint | (blank) | 1
99 | MULITI-PURPOSE | [8 empty] | Supplemental Budget No. 3 HDMP | 7 |  |  |  |  | Megaprint | (blank) | 1
100 | MULITI-PURPOSE | [8 empty] | Supplemental Budget No. 4 | 19 |  |  |  |  | MG Tan Construction | TIN 113-310-056 | 1
101 | MULITI-PURPOSE | [8 empty] | Supplemental Budget No. 4 - Tubbataha Fund | 1 |  |  |  |  | MGB Construction and Trading | (blank) | 2
102 | BRIDGES | [8 empty] | Supplemental Budget No. 4 (PCDO) | 1 |  |  |  |  | MKB Builders and Supply | TIN 262-511-948 | 1
103 | BRIDGES | [8 empty] | Supplemental Budget No. 5 | 69 |  |  |  |  | MVP Construction and Trdaing Inc. | TIN 616-777-887 | 5
104 | DRAINAGE | [8 empty] | Supplemental Budget No. 6 | 14 |  |  |  |  | N.Sales Construction | TIN 174-694-454 | 3
105 | DRAINAGE | [8 empty] | Supplemental Budget No. 8 | 1 |  |  |  |  | Nab Construction & Enterprises | TIN 445-503-720 | 2
106 | DRAINAGE | [8 empty] | Supplemental Budget No. 8 - LWC | 1 |  |  |  |  | Nale Construction | (blank) | 1
107 | DRAINAGE | [8 empty] | Supplemental Budget No. 9 | 29 |  |  |  |  | Nand Trading | (blank) | 2
108 | DRAINAGE | [8 empty] | Supplemental Budget No.12 | 1 |  |  |  |  | New Space Trading and Construction | TIN 010-545-401 | 3
109 | ROAD | [8 empty] | Supplemental Budget No.4 | 2 |  |  |  |  | N-Gines Technology Inc. | (blank) | 3
110 | BRIDGES | [8 empty] | Supplemetnal Budget No. 4 | 6 |  |  |  |  | NRNS Trading And Construction Supply | TIN 922-390-708 | 7
111 | BRIDGES | [8 empty] | Supplmental Budget No. 4 (CSPMP) | 1 |  |  |  |  | Octagon Concrete Solution | TIN 901-128-486 | 2
112 | ROAD | [8 empty] | TF - DOH HFEP 2014 | 1 |  |  |  |  | One Badajos Construction & Trading Corporation | TIN 010-590-630 | 3
113 | BRIDGES | [8 empty] | TF LDRRMF 2021-PO 2615-A | 2 |  |  |  |  | One Hundred Percent and Development Corp. | TIN 009-446-039 | 4
114 | ROAD | [8 empty] | Trust Fund | 2 | [5 empty] | TIN 168-154-730 | 54
115 | SCHOOL FACILITIES | [8 empty] | Trust Fund - (OCD FUNDS) | 3 | [5 empty] | (blank) | 3
116 | PGP FACILITIES | [8 empty] | Trust Fund - DOH | 76 |  |  |  |  | Palbic Construction and Supply | TIN 128-066-252 | 1
117 | PORTS | [8 empty] | Trust Fund - DOTr | 6 | [5 empty] | (blank) | 1
118 | PGP FACILITIES | [8 empty] | Trust Fund - TIEZA | 1 |  |  |  |  | Panaad Construction | TIN 938-375-592 | 1
119 | SCHOOL FACILITIES | [8 empty] | Trust Fund- Cong. Alvarez | 2 |  |  |  |  | Premium Megastructures Inc. | (blank) | 1
120 | SCHOOL FACILITIES | [8 empty] | Trust Fund -DOH | 1 |  |  |  |  | R. Narrazid Trading and Construction | TIN 330-975-725 | 8
121 | SCHOOL FACILITIES | [8 empty] | Typhoon Odette Financial Assistance (Office of the President) - 100M | 8 |  |  |  |  | R.R Leoncio Construction | (blank) | 1
122 | SCHOOL FACILITIES | [8 empty] | (blank) | 26 |  |  |  |  | Rabb Construction & Supply | TIN 325-261-868 | 6
123 | SCHOOL FACILITIES | [8 empty] | Grand Total | 1568 |  |  |  |  | Rabb Construction and Supply | (blank) | 2
124 | SCHOOL FACILITIES | [14 empty] | RAK Trading Construction & Supply | (blank) | 5
125 | SCHOOL FACILITIES | [14 empty] | RC Gadiano Construction | TIN 342-792-217 | 3
126 | SCHOOL FACILITIES | [14 empty] | RD Abacial Construction | TIN 327-679-690 | 61
127 | SCHOOL FACILITIES | [15 empty] | (blank) | 7
128 | SCHOOL FACILITIES | [14 empty] | RD Abacial Construction | TIN 327-679-690 | 1
129 | SCHOOL FACILITIES | [14 empty] | RDF Trading and Construction | CTC 097-331-47 | 7
130 | MULITI-PURPOSE | [15 empty] | (blank) | 1
131 | MULITI-PURPOSE | [14 empty] | Reinastar Trading and Construction | TIN 944-093-894-001 | 23
132 | MULITI-PURPOSE | [14 empty] | Rhodamay Construction and Supply | 322-759-45 | 17
133 | PGP FACILITIES | [15 empty] | TIN 944-093-894-001 | 1
134 | PGP FACILITIES | [14 empty] | RL Abia Construction | TIN 274-260-467 | 1
135 | MEDICAL FACILITIES | [15 empty] | (blank) | 3
136 | MEDICAL FACILITIES | [14 empty] | Samurai Construction | TIN 919-621-019 | 25
137 | MEDICAL FACILITIES | [14 empty] | Samurai Construction | TIN 919-621-019 | 1
138 | BRIDGES | [14 empty] | Seven Digit Construction and Supplies | TIN 008-664-275 | 2
139 | MEDICAL FACILITIES | [15 empty] | TIN 183-661-696 | 5
140 | MEDICAL FACILITIES | [15 empty] | (blank) | 1
141 | MEDICAL FACILITIES | [14 empty] | Smmiley Builders and Trading | TIN 936-564-958 | 7
142 | SCHOOL FACILITIES | [15 empty] | (blank) | 1
143 | SCHOOL FACILITIES | [14 empty] | Sparkotech Engineering Solution Inc. | (blank) | 2
144 | SCHOOL FACILITIES | [14 empty] | St. Timothy Construction Corporation | TIN 008-813-669-000 | 3
145 | PGP FACILITIES | [14 empty] | St.Timothy Construction Corporation | TIN 008-813-669-000 | 21
146 | PGP FACILITIES | [15 empty] | (blank) | 2
147 | PGP FACILITIES | [14 empty] | Synchros Power Solutions | TIN 134-545-266 | 1
148 | PGP FACILITIES | [15 empty] | TIN 134-545-266-000 | 14
149 | MEDICAL FACILITIES | [14 empty] | TCC Powerserve Trading and Engineering Services | TIN 931-421-496 | 4
150 | PGP FACILITIES | [15 empty] | (blank) | 4
151 | MEDICAL FACILITIES | [14 empty] | Tektwin Marketing Corporation | (blank) | 1
152 | MEDICAL FACILITIES | [14 empty] | The Clean O2 Eco-Friendly Corporation | (blank) | 1
153 | MEDICAL FACILITIES | [14 empty] | Triplestone Construction and Development Corporation | TIN 009-149-175 | 37
154 | MEDICAL FACILITIES | [14 empty] | UGM Construction | TIN 102-967-201 | 1
155 | MEDICAL FACILITIES | [14 empty] | VCH Construction and Trading | TIN 924-818-554 | 5
156 | MEDICAL FACILITIES | [14 empty] | VJ Builders | (blank) | 1
157 | MEDICAL FACILITIES | [14 empty] | Warlen Industrial and Sales Corporation | (blank) | 2
158 | MEDICAL FACILITIES | [14 empty] | Werr Corporation International | (blank) | 2
159 | BRIDGES | [14 empty] | West Blue Builders | (blank) | 1
160 | BRIDGES | [14 empty] | Western Fortune | (blank) | 1
161 | BRIDGES | [14 empty] | Yurich Builders & Construction Supply | TIN 258-921-757-00001 | 4
162 | BRIDGES | [15 empty] | TIN 258-921-757-001 | 6
163 | BRIDGES | [15 empty] | (blank) | 2
164 | BRIDGES | [14 empty] | ZYK Construction | (blank) | 3
165 | BRIDGES | [14 empty] | (blank) | (blank) | 145
166 | BHS | [14 empty] | Grand Total |  | 1568
167 | MULITI-PURPOSE
168 | ELECTRIFICATION
169 | ROAD
170 | ROAD
171 | ROAD
172 | MEDICAL FACILITIES
173 | BRIDGES
174 | SLOPE PROTECTION
175 | ROAD
176 | ROAD
177 | DRAINAGE
178 | MULITI-PURPOSE
179 | MULITI-PURPOSE
180 | MULITI-PURPOSE
181 | MULITI-PURPOSE
182 | MEDICAL FACILITIES
183 | MEDICAL FACILITIES
184 | MEDICAL FACILITIES
185 | MEDICAL FACILITIES
186 | BRIDGES
187 | OTHER FACILITIES
188 | OTHER FACILITIES
189 | SLOPE PROTECTION
190 | ROAD
191 | OTHER FACILITIES
192 | DRAINAGE
193 | ROAD
194 | DRAINAGE
195 | DRAINAGE
196 | OTHER FACILITIES
197 | OTHER FACILITIES
198 | MEDICAL FACILITIES
199 | MEDICAL FACILITIES
200 | IRRIGATION
201 | MEDICAL FACILITIES
202 | MEDICAL FACILITIES
203 | MEDICAL FACILITIES
204 | MEDICAL FACILITIES
205 | MEDICAL FACILITIES
206 | MEDICAL FACILITIES
207 | MEDICAL FACILITIES
208 | BRIDGES
209 | ROAD
210 | MULITI-PURPOSE
211 | MEDICAL FACILITIES
212 | MEDICAL FACILITIES
213 | AGRICULTURAL FACILITIES
214 | OTHER FACILITIES
215 | RHU
216 | RHU
217 | RHU
218 | RHU
219 | RHU
220 | RHU
221 | RHU
222 | RHU
223 | RHU
224 | RHU
225 | RHU
226 | RHU
227 | MEDICAL FACILITIES
228 | SCHOOL FACILITIES
229 | MEDICAL FACILITIES
230 | ELECTRIFICATION
231 | IRRIGATION
232 | IRRIGATION
233 | DRAINAGE
234 | OTHER FACILITIES
235 | ROAD
236 | ROAD
237 | ROAD
238 | OTHER FACILITIES
239 | SLOPE PROTECTION
240 | MEDICAL FACILITIES
241 | MEDICAL FACILITIES
242 | MEDICAL FACILITIES
243 | MEDICAL FACILITIES
244 | MEDICAL FACILITIES
245 | MULITI-PURPOSE
246 | MULITI-PURPOSE
247 | MULITI-PURPOSE
248 | DRAINAGE
249 | MULITI-PURPOSE
250 | MULITI-PURPOSE
251 | OTHER FACILITIES
252 | ROAD
253 | BRIDGES
254 | BRIDGES
255 | BRIDGES
256 | BRIDGES
257 | MULITI-PURPOSE
258 | BRIDGES
259 | BRIDGES
260 | BRIDGES
261 | BRIDGES
262 | BHS
263 | BHS
264 | BHS
265 | BHS
266 | BHS
267 | BHS
268 | BHS
269 | BHS
270 | BHS
271 | BHS
272 | BHS
273 | BHS
274 | BHS
275 | BHS
276 | BHS
277 | BHS
278 | BHS
279 | BHS
280 | BHS
281 | BHS
282 | BHS
283 | BHS
284 | BHS
285 | BHS
286 | BHS
287 | BHS
288 | BHS
289 | BHS
290 | BHS
291 | BHS
292 | BHS
293 | BHS
294 | BHS
295 | BHS
296 | BHS
297 | BHS
298 | BHS
299 | BHS
300 | BHS
301 | BHS
302 | BHS
303 | BHS
304 | BHS
305 | BHS
306 | BHS
307 | BHS
308 | BHS
309 | BHS
310 | BHS
311 | BHS
312 | BHS
313 | BHS
314 | BHS
315 | BHS
316 | MEDICAL FACILITIES
317 | MEDICAL FACILITIES
318 | MEDICAL FACILITIES
319 | OTHER FACILITIES
320 | OTHER FACILITIES
321 | OTHER FACILITIES
322 | OTHER FACILITIES
323 | PGP FACILITIES
324 | SCHOOL FACILITIES
325 | SCHOOL FACILITIES
326 | PGP FACILITIES
327 | MEDICAL FACILITIES
328 | MEDICAL FACILITIES
329 | MEDICAL FACILITIES
330 | ROAD
331 | ROAD
332 | ROAD
333 | ROAD
334 | DRAINAGE
335 | SLOPE PROTECTION
336 | DRAINAGE
337 | DRAINAGE
338 | OTHER FACILITIES
339 | DRAINAGE
340 | DRAINAGE
341 | DRAINAGE
342 | BRIDGES
343 | BRIDGES
344 | BRIDGES
345 | BRIDGES
346 | BRIDGES
347 | BRIDGES
348 | BRIDGES
349 | DRAINAGE
350 | DRAINAGE
351 | ROAD
352 | ROAD
353 | DRAINAGE
354 | ROAD
355 | BRIDGES
356 | AIRPORTS
357 | BRIDGES
358 | MULITI-PURPOSE
359 | ROAD
360 | ROAD
361 | ROAD
362 | ROAD
363 | ROAD
364 | ROAD
365 | ROAD
366 | ROAD
367 | ROAD
368 | SCHOOL FACILITIES
369 | SCHOOL FACILITIES
370 | SCHOOL FACILITIES
371 | SCHOOL FACILITIES
372 | RHU
373 | BHS
374 | RHU
375 | BHS
376 | RHU
377 | SCHOOL FACILITIES
378 | SCHOOL FACILITIES
379 | SCHOOL FACILITIES
380 | DRAINAGE
381 | WATER SYSTEM
382 | IRRIGATION
383 | WATER SYSTEM
384 | IRRIGATION
385 | WATER SYSTEM
386 | IRRIGATION
387 | IRRIGATION
388 | IRRIGATION
389 | ROAD
390 | SCHOOL FACILITIES
391 | SCHOOL FACILITIES
392 | SCHOOL FACILITIES
393 | SCHOOL FACILITIES
394 | SCHOOL FACILITIES
395 | SCHOOL FACILITIES
396 | SCHOOL FACILITIES
397 | SCHOOL FACILITIES
398 | SCHOOL FACILITIES
399 | SCHOOL FACILITIES
400 | SCHOOL FACILITIES
401 | SCHOOL FACILITIES
402 | SCHOOL FACILITIES
403 | SCHOOL FACILITIES
404 | SCHOOL FACILITIES
405 | MULITI-PURPOSE
406 | BRIDGES
407 | MEDICAL FACILITIES
408 | MEDICAL FACILITIES
409 | MEDICAL FACILITIES
410 | MULITI-PURPOSE
411 | BRIDGES
412 | BRIDGES
413 | ELECTRIFICATION
414 | MEDICAL FACILITIES
415 | MEDICAL FACILITIES
416 | MEDICAL FACILITIES
417 | MEDICAL FACILITIES
418 | MEDICAL FACILITIES
419 | MEDICAL FACILITIES
420 | MEDICAL FACILITIES
421 | AIRPORTS
422 | MEDICAL FACILITIES
423 | MEDICAL FACILITIES
424 | MEDICAL FACILITIES
425 | MEDICAL FACILITIES
426 | MEDICAL FACILITIES
427 | MEDICAL FACILITIES
428 | MEDICAL FACILITIES
429 | MEDICAL FACILITIES
430 | MEDICAL FACILITIES
431 | MEDICAL FACILITIES
432 | MEDICAL FACILITIES
433 | MEDICAL FACILITIES
434 | MEDICAL FACILITIES
435 | MEDICAL FACILITIES
436 | MEDICAL FACILITIES
437 | MEDICAL FACILITIES
438 | MEDICAL FACILITIES
439 | MEDICAL FACILITIES
440 | MEDICAL FACILITIES
441 | COVERED COURT
442 | COVERED COURT
443 | COVERED COURT
444 | COVERED COURT
445 | COVERED COURT
446 | COVERED COURT
447 | COVERED COURT
448 | COVERED COURT
449 | COVERED COURT
450 | COVERED COURT
451 | COVERED COURT
452 | COVERED COURT
453 | COVERED COURT
454 | COVERED COURT
455 | COVERED COURT
456 | COVERED COURT
457 | COVERED COURT
458 | COVERED COURT
459 | COVERED COURT
460 | COVERED COURT
461 | COVERED COURT
462 | COVERED COURT
463 | COVERED COURT
464 | COVERED COURT
465 | COVERED COURT
466 | COVERED COURT
467 | COVERED COURT
468 | COVERED COURT
469 | COVERED COURT
470 | COVERED COURT
471 | COVERED COURT
472 | COVERED COURT
473 | COVERED COURT
474 | COVERED COURT
475 | COVERED COURT
476 | COVERED COURT
477 | COVERED COURT
478 | COVERED COURT
479 | COVERED COURT
480 | COVERED COURT
481 | COVERED COURT
482 | COVERED COURT
483 | COVERED COURT
484 | COVERED COURT
485 | COVERED COURT
486 | COVERED COURT
487 | COVERED COURT
488 | COVERED COURT
489 | COVERED COURT
490 | COVERED COURT
491 | COVERED COURT
492 | COVERED COURT
493 | COVERED COURT
494 | COVERED COURT
495 | COVERED COURT
496 | COVERED COURT
497 | COVERED COURT
498 | COVERED COURT
499 | COVERED COURT
500 | COVERED COURT
501 | COVERED COURT
502 | COVERED COURT
503 | COVERED COURT
504 | COVERED COURT
505 | COVERED COURT
506 | COVERED COURT
507 | COVERED COURT
508 | COVERED COURT
509 | COVERED COURT
510 | COVERED COURT
511 | COVERED COURT
512 | COVERED COURT
513 | COVERED COURT
514 | COVERED COURT
515 | COVERED COURT
516 | COVERED COURT
517 | COVERED COURT
518 | COVERED COURT
519 | COVERED COURT
520 | COVERED COURT
521 | COVERED COURT
522 | COVERED COURT
523 | COVERED COURT
524 | COVERED COURT
525 | COVERED COURT
526 | COVERED COURT
527 | COVERED COURT
528 | COVERED COURT
529 | COVERED COURT
530 | COVERED COURT
531 | COVERED COURT
532 | COVERED COURT
533 | COVERED COURT
534 | COVERED COURT
535 | OTHER FACILITIES
536 | COVERED COURT
537 | COVERED COURT
538 | COVERED COURT
539 | COVERED COURT
540 | COVERED COURT
541 | COVERED COURT
542 | COVERED COURT
543 | COVERED COURT
544 | COVERED COURT
545 | COVERED COURT
546 | COVERED COURT
547 | COVERED COURT
548 | COVERED COURT
549 | COVERED COURT
550 | COVERED COURT
551 | COVERED COURT
552 | COVERED COURT
553 | COVERED COURT
554 | COVERED COURT
555 | COVERED COURT
556 | COVERED COURT
557 | COVERED COURT
558 | COVERED COURT
559 | COVERED COURT
560 | COVERED COURT
561 | COVERED COURT
562 | COVERED COURT
563 | COVERED COURT
564 | COVERED COURT
565 | COVERED COURT
566 | COVERED COURT
567 | COVERED COURT
568 | COVERED COURT
569 | COVERED COURT
570 | COVERED COURT
571 | COVERED COURT
572 | COVERED COURT
573 | COVERED COURT
574 | COVERED COURT
575 | COVERED COURT
576 | COVERED COURT
577 | COVERED COURT
578 | COVERED COURT
579 | COVERED COURT
580 | COVERED COURT
581 | COVERED COURT
582 | COVERED COURT
583 | COVERED COURT
584 | COVERED COURT
585 | COVERED COURT
586 | COVERED COURT
587 | COVERED COURT
588 | COVERED COURT
589 | COVERED COURT
590 | COVERED COURT
591 | COVERED COURT
592 | COVERED COURT
593 | COVERED COURT
594 | COVERED COURT
595 | COVERED COURT
596 | COVERED COURT
597 | COVERED COURT
598 | COVERED COURT
599 | COVERED COURT
600 | COVERED COURT
601 | COVERED COURT
602 | COVERED COURT
603 | COVERED COURT
604 | COVERED COURT
605 | COVERED COURT
606 | COVERED COURT
607 | COVERED COURT
608 | COVERED COURT
609 | ELECTRIFICATION
610 | SCHOOL FACILITIES
611 | SCHOOL FACILITIES
612 | MEDICAL FACILITIES
613 | MEDICAL FACILITIES
614 | MEDICAL FACILITIES
615 | MEDICAL FACILITIES
616 | PORTS
617 | PORTS
618 | SCHOOL FACILITIES
619 | SCHOOL FACILITIES
620 | SCHOOL FACILITIES
621 | SCHOOL FACILITIES
622 | SCHOOL FACILITIES
623 | SCHOOL FACILITIES
624 | SCHOOL FACILITIES
625 | SCHOOL FACILITIES
626 | ROAD
627 | ROAD
628 | ROAD
629 | ROAD
630 | ROAD
631 | ROAD
632 | ROAD
633 | ROAD
634 | WATER SYSTEM
635 | ROAD
636 | OTHER FACILITIES
637 | MEDICAL FACILITIES
638 | ELECTRIFICATION
639 | MEDICAL FACILITIES
640 | MEDICAL FACILITIES
641 | MEDICAL FACILITIES
642 | MEDICAL FACILITIES
643 | MEDICAL FACILITIES
644 | MEDICAL FACILITIES
645 | MEDICAL FACILITIES
646 | MEDICAL FACILITIES
647 | MEDICAL FACILITIES
648 | MEDICAL FACILITIES
649 | MEDICAL FACILITIES
650 | MEDICAL FACILITIES
651 | MEDICAL FACILITIES
652 | MEDICAL FACILITIES
653 | MEDICAL FACILITIES
654 | MEDICAL FACILITIES
655 | MEDICAL FACILITIES
656 | MEDICAL FACILITIES
657 | ELECTRIFICATION
658 | MEDICAL FACILITIES
659 | MEDICAL FACILITIES
660 | MEDICAL FACILITIES
661 | MEDICAL FACILITIES
662 | MULITI-PURPOSE
663 | MULITI-PURPOSE
664 | MEDICAL FACILITIES
665 | ELECTRIFICATION
666 | COVERED COURT
667 | MEDICAL FACILITIES
668 | DRAINAGE
669 | BRIDGES
670 | BRIDGES
671 | BRIDGES
672 | BRIDGES
673 | BRIDGES
674 | BRIDGES
675 | ELECTRIFICATION
676 | BRIDGES
677 | MEDICAL FACILITIES
678 | MEDICAL FACILITIES
679 | MEDICAL FACILITIES
680 | ROAD
681 | MEDICAL FACILITIES
682 | MEDICAL FACILITIES
683 | MEDICAL FACILITIES
684 | MEDICAL FACILITIES
685 | MEDICAL FACILITIES
686 | MEDICAL FACILITIES
687 | MEDICAL FACILITIES
688 | MEDICAL FACILITIES
689 | MEDICAL FACILITIES
690 | MEDICAL FACILITIES
691 | MEDICAL FACILITIES
692 | MEDICAL FACILITIES
693 | MEDICAL FACILITIES
694 | MEDICAL FACILITIES
695 | DRAINAGE
696 | MULITI-PURPOSE
697 | OTHER FACILITIES
698 | BRIDGES
699 | ROAD
700 | ROAD
701 | ROAD
702 | ROAD
703 | ROAD
704 | PGP FACILITIES
705 | PGP FACILITIES
706 | PGP FACILITIES
707 | PGP FACILITIES
708 | AGRICULTURAL FACILITIES
709 | ANIMAL FACILITIES
710 | ANIMAL FACILITIES
711 | ANIMAL FACILITIES
712 | PGP FACILITIES
713 | AGRICULTURAL FACILITIES
714 | MEDICAL FACILITIES
715 | MEDICAL FACILITIES
716 | MEDICAL FACILITIES
717 | MEDICAL FACILITIES
718 | MEDICAL FACILITIES
719 | MEDICAL FACILITIES
720 | MEDICAL FACILITIES
721 | MEDICAL FACILITIES
722 | MEDICAL FACILITIES
723 | MEDICAL FACILITIES
724 | MEDICAL FACILITIES
725 | MEDICAL FACILITIES
726 | MEDICAL FACILITIES
727 | MEDICAL FACILITIES
728 | MEDICAL FACILITIES
729 | MEDICAL FACILITIES
730 | MEDICAL FACILITIES
731 | MEDICAL FACILITIES
732 | MEDICAL FACILITIES
733 | MEDICAL FACILITIES
734 | MEDICAL FACILITIES
735 | MEDICAL FACILITIES
736 | WATER SYSTEM
737 | IRRIGATION
738 | MEDICAL FACILITIES
739 | AGRICULTURAL FACILITIES
740 | WATER SYSTEM
741 | AGRICULTURAL FACILITIES
742 | MEDICAL FACILITIES
743 | MEDICAL FACILITIES
744 | MEDICAL FACILITIES
745 | MEDICAL FACILITIES
746 | MEDICAL FACILITIES
747 | MEDICAL FACILITIES
748 | MULITI-PURPOSE
749 | MEDICAL FACILITIES
750 | BHS
751 | BRIDGES
752 | BRIDGES
753 | PORTS
754 | BHS
755 | BHS
756 | MEDICAL FACILITIES
757 | MEDICAL FACILITIES
758 | MEDICAL FACILITIES
759 | MEDICAL FACILITIES
760 | MEDICAL FACILITIES
761 | MULITI-PURPOSE
762 | MULITI-PURPOSE
763 | MEDICAL FACILITIES
764 | MEDICAL FACILITIES
765 | MEDICAL FACILITIES
766 | MEDICAL FACILITIES
767 | MEDICAL FACILITIES
768 | MEDICAL FACILITIES
769 | MEDICAL FACILITIES
770 | MEDICAL FACILITIES
771 | BRIDGES
772 | BRIDGES
773 | DRAINAGE
774 | BRIDGES
775 | DRAINAGE
776 | BRIDGES
777 | ROAD
778 | ROAD
779 | ROAD
780 | OTHER FACILITIES
781 | DRAINAGE
782 | DRAINAGE
783 | MULITI-PURPOSE
784 | COVERED COURT
785 | ROAD
786 | COVERED COURT
787 | MEDICAL FACILITIES
788 | PGP FACILITIES
789 | PGP FACILITIES
790 | MEDICAL FACILITIES
791 | MEDICAL FACILITIES
792 | MEDICAL FACILITIES
793 | MEDICAL FACILITIES
794 | MEDICAL FACILITIES
795 | MEDICAL FACILITIES
796 | ELECTRIFICATION
797 | MEDICAL FACILITIES
798 | MEDICAL FACILITIES
799 | MEDICAL FACILITIES
800 | MEDICAL FACILITIES
801 | ELECTRIFICATION
802 | PGP FACILITIES
803 | MEDICAL FACILITIES
804 | MEDICAL FACILITIES
805 | MULITI-PURPOSE
806 | MULITI-PURPOSE
808 | MEDICAL FACILITIES
809 | ROAD
810 | ROAD
811 | ROAD
812 | ROAD
813 | MEDICAL FACILITIES
814 | MEDICAL FACILITIES
815 | MEDICAL FACILITIES
816 | MEDICAL FACILITIES
817 | MEDICAL FACILITIES
818 | MEDICAL FACILITIES
819 | MEDICAL FACILITIES
820 | ROAD
821 | WATER SYSTEM
822 | PGP FACILITIES
823 | PGP FACILITIES
824 | MEDICAL FACILITIES
825 | MEDICAL FACILITIES
826 | PGP FACILITIES
827 | IRRIGATION
828 | MEDICAL FACILITIES
829 | MEDICAL FACILITIES
830 | MEDICAL FACILITIES
831 | MEDICAL FACILITIES
832 | MEDICAL FACILITIES
833 | MEDICAL FACILITIES
834 | MEDICAL FACILITIES
835 | MEDICAL FACILITIES
836 | MEDICAL FACILITIES
837 | MEDICAL FACILITIES
838 | MEDICAL FACILITIES
839 | MEDICAL FACILITIES
840 | MEDICAL FACILITIES
841 | MEDICAL FACILITIES
842 | MEDICAL FACILITIES
843 | MEDICAL FACILITIES
844 | MEDICAL FACILITIES
845 | MEDICAL FACILITIES
846 | MEDICAL FACILITIES
847 | MEDICAL FACILITIES
848 | MEDICAL FACILITIES
849 | MEDICAL FACILITIES
850 | MEDICAL FACILITIES
851 | MEDICAL FACILITIES
852 | MEDICAL FACILITIES
853 | MEDICAL FACILITIES
854 | ROAD
855 | DRAINAGE
856 | SLOPE PROTECTION
857 | SLOPE PROTECTION
858 | DRAINAGE
859 | ROAD
860 | ROAD
861 | MEDICAL FACILITIES
862 | MEDICAL FACILITIES
863 | OTHER FACILITIES
864 | OTHER FACILITIES
865 | OTHER FACILITIES
866 | OTHER FACILITIES
867 | MEDICAL FACILITIES
868 | MEDICAL FACILITIES
869 | BRIDGES
870 | MEDICAL FACILITIES
871 | MEDICAL FACILITIES
872 | MEDICAL FACILITIES
873 | MEDICAL FACILITIES
874 | MEDICAL FACILITIES
875 | MEDICAL FACILITIES
876 | MEDICAL FACILITIES
877 | MEDICAL FACILITIES
878 | MEDICAL FACILITIES
879 | MEDICAL FACILITIES
880 | MEDICAL FACILITIES
881 | MEDICAL FACILITIES
882 | WATER SYSTEM
883 | MEDICAL FACILITIES
884 | MEDICAL FACILITIES
885 | MEDICAL FACILITIES
886 | MEDICAL FACILITIES
887 | MEDICAL FACILITIES
888 | PGP FACILITIES
889 | MEDICAL FACILITIES
890 | MEDICAL FACILITIES
891 | MEDICAL FACILITIES
892 | RHU
893 | RHU
894 | RHU
895 | SCHOOL FACILITIES
896 | MEDICAL FACILITIES
897 | PGP FACILITIES
898 | MEDICAL FACILITIES
899 | MEDICAL FACILITIES
900 | MEDICAL FACILITIES
901 | MEDICAL FACILITIES
902 | WATER SYSTEM
903 | WATER SYSTEM
904 | MEDICAL FACILITIES
905 | MEDICAL FACILITIES
906 | MEDICAL FACILITIES
907 | MEDICAL FACILITIES
908 | MEDICAL FACILITIES
909 | MEDICAL FACILITIES
910 | MEDICAL FACILITIES
911 | MEDICAL FACILITIES
912 | MEDICAL FACILITIES
913 | MEDICAL FACILITIES
914 | MEDICAL FACILITIES
915 | MEDICAL FACILITIES
916 | MEDICAL FACILITIES
917 | MEDICAL FACILITIES
918 | MEDICAL FACILITIES
919 | MEDICAL FACILITIES
920 | MEDICAL FACILITIES
921 | MEDICAL FACILITIES
922 | MEDICAL FACILITIES
923 | MEDICAL FACILITIES
924 | MEDICAL FACILITIES
925 | MEDICAL FACILITIES
926 | MEDICAL FACILITIES
927 | MEDICAL FACILITIES
928 | MEDICAL FACILITIES
929 | MEDICAL FACILITIES
930 | MEDICAL FACILITIES
931 | ROAD
932 | MEDICAL FACILITIES
933 | MEDICAL FACILITIES
934 | MEDICAL FACILITIES
935 | MEDICAL FACILITIES
936 | MEDICAL FACILITIES
937 | MEDICAL FACILITIES
938 | MEDICAL FACILITIES
939 | PGP FACILITIES
940 | PGP FACILITIES
941 | PGP FACILITIES
942 | PGP FACILITIES
943 | MEDICAL FACILITIES
944 | ROAD
945 | WATER SYSTEM
946 | COVERED COURT
947 | COVERED COURT
948 | COVERED COURT
949 | COVERED COURT
950 | COVERED COURT
951 | COVERED COURT
952 | COVERED COURT
953 | COVERED COURT
954 | COVERED COURT
955 | COVERED COURT
956 | COVERED COURT
957 | COVERED COURT
958 | COVERED COURT
959 | COVERED COURT
960 | COVERED COURT
961 | COVERED COURT
962 | COVERED COURT
963 | COVERED COURT
964 | COVERED COURT
965 | COVERED COURT
966 | OTHER FACILITIES
967 | PGP FACILITIES
968 | BRIDGES
969 | MEDICAL FACILITIES
970 | MEDICAL FACILITIES
971 | MEDICAL FACILITIES
972 | MEDICAL FACILITIES
973 | MEDICAL FACILITIES
974 | MEDICAL FACILITIES
975 | MEDICAL FACILITIES
976 | WATER SYSTEM
977 | DRAINAGE
978 | DRAINAGE
979 | DRAINAGE
980 | DRAINAGE
981 | DRAINAGE
982 | DRAINAGE
983 | DRAINAGE
984 | DRAINAGE
985 | DRAINAGE
986 | DRAINAGE
987 | DRAINAGE
988 | DRAINAGE
989 | DRAINAGE
990 | MEDICAL FACILITIES
991 | MEDICAL FACILITIES
992 | MEDICAL FACILITIES
993 | MEDICAL FACILITIES
994 | MEDICAL FACILITIES
995 | MEDICAL FACILITIES
996 | MEDICAL FACILITIES
997 | MEDICAL FACILITIES
998 | ROAD
999 | MEDICAL FACILITIES
1000 | WATER SYSTEM
1001 | MEDICAL FACILITIES
1002 | PGP FACILITIES
1003 | WATER SYSTEM
1004 | ROAD
1005 | WATER SYSTEM
1006 | OTHER FACILITIES
1007 | WATER SYSTEM
1008 | MULITI-PURPOSE
1009 | SCHOOL FACILITIES
1010 | MEDICAL FACILITIES
1011 | ROAD
1012 | MEDICAL FACILITIES
1013 | MULITI-PURPOSE
1014 | WATER SYSTEM
1015 | ROAD
1016 | ROAD
1017 | MULITI-PURPOSE
1018 | SCHOOL FACILITIES
1019 | MULITI-PURPOSE
1020 | MULITI-PURPOSE
1021 | ELECTRIFICATION
1022 | ELECTRIFICATION
1023 | ROAD
1024 | ROAD
1025 | ELECTRIFICATION
1026 | ROAD
1027 | ELECTRIFICATION
1028 | ELECTRIFICATION
1029 | MEDICAL FACILITIES
1030 | WATER SYSTEM
1031 | ROAD
1032 | ELECTRIFICATION
1033 | ELECTRIFICATION
1034 | ELECTRIFICATION
1035 | SCHOOL FACILITIES
1036 | ROAD
1037 | ROAD
1038 | MEDICAL FACILITIES
1039 | PGP FACILITIES
1040 | PGP FACILITIES
1041 | PGP FACILITIES
1042 | MEDICAL FACILITIES
1043 | MEDICAL FACILITIES
1044 | MEDICAL FACILITIES
1045 | MEDICAL FACILITIES
1046 | MEDICAL FACILITIES
1047 | PGP FACILITIES
1048 | ELECTRIFICATION
1049 | MEDICAL FACILITIES
1050 | MEDICAL FACILITIES
1051 | MEDICAL FACILITIES
1052 | MEDICAL FACILITIES
1053 | MEDICAL FACILITIES
1054 | MEDICAL FACILITIES
1055 | PORTS
1056 | WATER SYSTEM
1057 | ROAD
1058 | DRAINAGE
1059 | BRIDGES
1060 | BRIDGES
1061 | ROAD
1062 | DRAINAGE
1063 | BRIDGES
1064 | BRIDGES
1065 | DRAINAGE
1066 | DRAINAGE
1067 | DRAINAGE
1068 | ROAD
1069 | BRIDGES
1070 | BRIDGES
1071 | BRIDGES
1072 | BRIDGES
1073 | DRAINAGE
1074 | BRIDGES
1075 | BRIDGES
1076 | BRIDGES
1077 | DRAINAGE
1078 | ROAD
1079 | ROAD
1080 | ROAD
1081 | ROAD
1082 | OTHER FACILITIES
1083 | ROAD
1084 | ROAD
1085 | ROAD
1086 | ROAD
1087 | ROAD
1088 | ROAD
1089 | DRAINAGE
1090 | DRAINAGE
1091 | OTHER FACILITIES
1092 | ROAD
1093 | OTHER FACILITIES
1094 | OTHER FACILITIES
1095 | OTHER FACILITIES
1096 | ROAD
1097 | ROAD
1098 | PGP FACILITIES
1099 | MEDICAL FACILITIES
1100 | MEDICAL FACILITIES
1101 | MEDICAL FACILITIES
1102 | MEDICAL FACILITIES
1103 | MEDICAL FACILITIES
1104 | MEDICAL FACILITIES
1105 | MEDICAL FACILITIES
1106 | MEDICAL FACILITIES
1107 | MEDICAL FACILITIES
1108 | MEDICAL FACILITIES
1109 | MEDICAL FACILITIES
1110 | MEDICAL FACILITIES
1111 | MEDICAL FACILITIES
1112 | MEDICAL FACILITIES
1113 | MEDICAL FACILITIES
1114 | DRAINAGE
1115 | SLOPE PROTECTION
1116 | MEDICAL FACILITIES
1117 | MEDICAL FACILITIES
1118 | MEDICAL FACILITIES
1119 | MEDICAL FACILITIES
1120 | MEDICAL FACILITIES
1121 | MEDICAL FACILITIES
1122 | ROAD
1123 | SCHOOL FACILITIES
1124 | SCHOOL FACILITIES
1125 | MULITI-PURPOSE
1126 | MULITI-PURPOSE
1127 | MEDICAL FACILITIES
1128 | MEDICAL FACILITIES
1129 | MEDICAL FACILITIES
1130 | MEDICAL FACILITIES
1131 | PGP FACILITIES
1132 | ELECTRIFICATION
1133 | MEDICAL FACILITIES
1134 | MEDICAL FACILITIES
1135 | MEDICAL FACILITIES
1136 | MEDICAL FACILITIES
1137 | MEDICAL FACILITIES
1138 | MEDICAL FACILITIES
1139 | MEDICAL FACILITIES
1140 | MEDICAL FACILITIES
1141 | MEDICAL FACILITIES
1142 | MEDICAL FACILITIES
1143 | MEDICAL FACILITIES
1144 | MEDICAL FACILITIES
1145 | MEDICAL FACILITIES
1146 | MEDICAL FACILITIES
1147 | MEDICAL FACILITIES
1148 | MEDICAL FACILITIES
1149 | MEDICAL FACILITIES
1150 | MEDICAL FACILITIES
1151 | BHS
1152 | MEDICAL FACILITIES
1153 | RHU
1154 | RHU
1155 | MEDICAL FACILITIES
1156 | ROAD
1157 | PGP FACILITIES
1158 | COVERED COURT
1159 | OTHER FACILITIES
1160 | ELECTRIFICATION
1161 | ELECTRIFICATION
1162 | ELECTRIFICATION
1163 | ELECTRIFICATION
1164 | ELECTRIFICATION
1165 | ELECTRIFICATION
1166 | ROAD
1167 | MULITI-PURPOSE
1168 | MULITI-PURPOSE
1169 | MULITI-PURPOSE
1170 | MULITI-PURPOSE
1171 | MEDICAL FACILITIES
1172 | MEDICAL FACILITIES
1173 | MEDICAL FACILITIES
1174 | OTHER FACILITIES
1175 | ROAD
1176 | OTHER FACILITIES
1177 | AGRICULTURAL FACILITIES
1178 | PORTS
1179 | MEDICAL FACILITIES
1180 | DRAINAGE
1181 | DRAINAGE
1182 | MEDICAL FACILITIES
1183 | AGRICULTURAL FACILITIES
1184 | AGRICULTURAL FACILITIES
1185 | PGP FACILITIES
1186 | PGP FACILITIES
1187 | PGP FACILITIES
1188 | PGP FACILITIES
1189 | ROAD
1190 | AGRICULTURAL FACILITIES
1191 | AGRICULTURAL FACILITIES
1192 | AGRICULTURAL FACILITIES
1193 | MEDICAL FACILITIES
1194 | SCHOOL FACILITIES
1195 | ROAD
1196 | MEDICAL FACILITIES
1197 | SCHOOL FACILITIES
1198 | OTHER FACILITIES
1199 | MEDICAL FACILITIES
1200 | PGP FACILITIES
1201 | MEDICAL FACILITIES
1202 | OTHER FACILITIES
1203 | OTHER FACILITIES
1204 | OTHER FACILITIES
1205 | OTHER FACILITIES
1206 | OTHER FACILITIES
1207 | OTHER FACILITIES
1208 | OTHER FACILITIES
1209 | OTHER FACILITIES
1210 | OTHER FACILITIES
1211 | OTHER FACILITIES
1212 | OTHER FACILITIES
1213 | OTHER FACILITIES
1214 | OTHER FACILITIES
1215 | OTHER FACILITIES
1216 | OTHER FACILITIES
1217 | OTHER FACILITIES
1218 | OTHER FACILITIES
1219 | OTHER FACILITIES
1220 | OTHER FACILITIES
1221 | OTHER FACILITIES
1222 | OTHER FACILITIES
1223 | OTHER FACILITIES
1224 | OTHER FACILITIES
1225 | OTHER FACILITIES
1226 | COVERED COURT
1227 | PGP FACILITIES
1228 | PGP FACILITIES
1229 | PGP FACILITIES
1230 | PGP FACILITIES
1231 | PGP FACILITIES
1232 | PGP FACILITIES
1233 | PGP FACILITIES
1234 | MULITI-PURPOSE
1235 | PGP FACILITIES
1236 | PGP FACILITIES
1237 | PGP FACILITIES
1238 | ELECTRIFICATION
1239 | PGP FACILITIES
1240 | PGP FACILITIES
1241 | PGP FACILITIES
1242 | PGP FACILITIES
1243 | PGP FACILITIES
1244 | OTHER FACILITIES
1245 | PGP FACILITIES
1246 | MEDICAL FACILITIES
1247 | MEDICAL FACILITIES
1248 | MEDICAL FACILITIES
1249 | MEDICAL FACILITIES
1250 | PGP FACILITIES
1251 | MULITI-PURPOSE
1252 | MEDICAL FACILITIES
1253 | PGP FACILITIES
1254 | MEDICAL FACILITIES
1255 | BHS
1256 | MEDICAL FACILITIES
1257 | AGRICULTURAL FACILITIES
1258 | PGP FACILITIES
1259 | MEDICAL FACILITIES
1260 | PGP FACILITIES
1261 | PGP FACILITIES
1262 | MEDICAL FACILITIES
1263 | MEDICAL FACILITIES
1264 | OTHER FACILITIES
1265 | PGP FACILITIES
1266 | MEDICAL FACILITIES
1267 | PGP FACILITIES
1268 | OTHER FACILITIES
1269 | PGP FACILITIES
1270 | SLOPE PROTECTION
1271 | ROAD
1272 | SLOPE PROTECTION
1273 | SLOPE PROTECTION
1274 | ROAD
1275 | SLOPE PROTECTION
1276 | SLOPE PROTECTION
1277 | ROAD
1278 | SLOPE PROTECTION
1279 | SLOPE PROTECTION
1280 | ROAD
1281 | DRAINAGE
1282 | OTHER FACILITIES
1283 | DRAINAGE
1284 | DRAINAGE
1285 | DRAINAGE
1286 | DRAINAGE
1287 | DRAINAGE
1288 | DRAINAGE
1289 | DRAINAGE
1290 | DRAINAGE
1291 | DRAINAGE
1292 | ROAD
1293 | DRAINAGE
1294 | DRAINAGE
1295 | OTHER FACILITIES
1296 | DRAINAGE
1297 | DRAINAGE
1298 | DRAINAGE
1299 | PGP FACILITIES
1300 | PGP FACILITIES
1301 | COVERED COURT
1302 | COVERED COURT
1303 | COVERED COURT
1304 | COVERED COURT
1305 | COVERED COURT
1306 | COVERED COURT
1307 | COVERED COURT
1308 | COVERED COURT
1309 | COVERED COURT
1310 | MULITI-PURPOSE
1311 | MULITI-PURPOSE
1312 | MULITI-PURPOSE
1313 | PGP FACILITIES
1314 | MULITI-PURPOSE
1315 | MEDICAL FACILITIES
1316 | MEDICAL FACILITIES
1317 | MEDICAL FACILITIES
1318 | MEDICAL FACILITIES
1319 | MEDICAL FACILITIES
1320 | MEDICAL FACILITIES
1321 | MEDICAL FACILITIES
1322 | MEDICAL FACILITIES
1323 | MEDICAL FACILITIES
1324 | SLOPE PROTECTION
1325 | MEDICAL FACILITIES
1326 | MEDICAL FACILITIES
1327 | MEDICAL FACILITIES
1328 | DRAINAGE
1329 | RHU
1330 | RHU
1331 | RHU
1332 | RHU
1333 | RHU
1334 | RHU
1335 | BHS
1336 | ELECTRIFICATION
1337 | ELECTRIFICATION
1338 | ELECTRIFICATION
1339 | ELECTRIFICATION
1340 | ELECTRIFICATION
1341 | PGP FACILITIES
1342 | SCHOOL FACILITIES
1343 | SCHOOL FACILITIES
1344 | SCHOOL FACILITIES
1345 | SCHOOL FACILITIES
1346 | SCHOOL FACILITIES
1347 | SCHOOL FACILITIES
1348 | SCHOOL FACILITIES
1349 | SCHOOL FACILITIES
1350 | SCHOOL FACILITIES
1351 | SCHOOL FACILITIES
1352 | SCHOOL FACILITIES
1353 | SCHOOL FACILITIES
1354 | SCHOOL FACILITIES
1355 | SCHOOL FACILITIES
1356 | SCHOOL FACILITIES
1357 | SCHOOL FACILITIES
1358 | SCHOOL FACILITIES
1359 | SCHOOL FACILITIES
1360 | SCHOOL FACILITIES
1361 | MEDICAL FACILITIES
1362 | MEDICAL FACILITIES
1363 | MEDICAL FACILITIES
1364 | MEDICAL FACILITIES
1365 | MEDICAL FACILITIES
1366 | MEDICAL FACILITIES
1367 | MEDICAL FACILITIES
1368 | ROAD
1369 | ROAD
1370 | ROAD
1371 | ROAD
1372 | ROAD
1373 | PGP FACILITIES
1374 | PGP FACILITIES
1375 | MEDICAL FACILITIES
1376 | PGP FACILITIES
1377 | PGP FACILITIES
1378 | PGP FACILITIES
1379 | MEDICAL FACILITIES
1380 | MEDICAL FACILITIES
1381 | PGP FACILITIES
1382 | MEDICAL FACILITIES
1383 | PGP FACILITIES
1384 | PGP FACILITIES
1385 | PGP FACILITIES
1386 | PGP FACILITIES
1387 | AGRICULTURAL FACILITIES
1388 | PGP FACILITIES
1389 | PGP FACILITIES
1390 | PGP FACILITIES
1391 | PGP FACILITIES
1392 | PGP FACILITIES
1393 | PGP FACILITIES
1394 | RHU
1395 | RHU
1396 | RHU
1397 | RHU
1398 | MEDICAL FACILITIES
1399 | COVERED COURT
1400 | COVERED COURT
1401 | COVERED COURT
1402 | COVERED COURT
1403 | COVERED COURT
1404 | COVERED COURT
1405 | COVERED COURT
1406 | COVERED COURT
1407 | SLOPE PROTECTION
1408 | SLOPE PROTECTION
1409 | DRAINAGE
1410 | DRAINAGE
1411 | DRAINAGE
1412 | DRAINAGE
1413 | DRAINAGE
1414 | DRAINAGE
1415 | DRAINAGE
1416 | DRAINAGE
1417 | DRAINAGE
1418 | PGP FACILITIES
1419 | PGP FACILITIES
1420 | PGP FACILITIES
1421 | OTHER FACILITIES
1422 | OTHER FACILITIES
1423 | PGP FACILITIES
1424 | ANIMAL FACILITIES
1425 | PGP FACILITIES
1426 | OTHER FACILITIES
1427 | PGP FACILITIES
1428 | PGP FACILITIES
1429 | MEDICAL FACILITIES
1430 | PGP FACILITIES
1431 | MULITI-PURPOSE
1432 | ROAD
1433 | ROAD
1434 | ROAD
1435 | ROAD
1436 | COVERED COURT
1437 | COVERED COURT
1438 | COVERED COURT
1439 | DRAINAGE
1440 | MEDICAL FACILITIES
1441 | MEDICAL FACILITIES
1442 | DRAINAGE
1443 | DRAINAGE
1444 | MEDICAL FACILITIES
1445 | MEDICAL FACILITIES
1446 | MEDICAL FACILITIES
1447 | RHU
1448 | RHU
1449 | ELECTRIFICATION
1450 | PGP FACILITIES
1451 | OTHER FACILITIES
1452 | PGP FACILITIES
1453 | DRAINAGE
1454 | PGP FACILITIES
1455 | OTHER FACILITIES
1456 | ROAD
1457 | SLOPE PROTECTION
1458 | SUPPLY
1459 | COVERED COURT
1460 | MEDICAL FACILITIES
1461 | MEDICAL FACILITIES
1462 | MEDICAL FACILITIES
1463 | ROAD
1464 | ROAD
1465 | ROAD
1466 | ROAD
1467 | ROAD
1468 | ROAD
1469 | ROAD
1470 | ROAD
1471 | ROAD
1472 | ROAD
1473 | ROAD
1474 | ROAD
1475 | ROAD
1476 | ROAD
1477 | ROAD
1478 | ROAD
1479 | ROAD
1480 | ROAD
1481 | ROAD
1482 | ROAD
1483 | ROAD
1484 | ROAD
1485 | ROAD
1486 | ROAD
1487 | ROAD
1488 | ROAD
1489 | ROAD
1490 | ROAD
1491 | ROAD
1492 | ROAD
1493 | ROAD
1494 | ROAD
1495 | ROAD
1496 | BRIDGES
1497 | BRIDGES
1498 | ROAD
1499 | ROAD
1500 | ROAD
1501 | ROAD
1502 | ROAD
1503 | ROAD
1504 | ROAD
1505 | ROAD
1506 | ROAD
1507 | ROAD
1508 | ROAD
1509 | ROAD
1510 | ROAD
1511 | ROAD
1512 | ROAD
1513 | ROAD
1514 | ROAD
1515 | ROAD
1516 | ROAD
1517 | ROAD
1518 | BRIDGES
1519 | OTHER FACILITIES
1520 | OTHER FACILITIES
1521 | MEDICAL FACILITIES
1522 | WATER SYSTEM
1523 | WATER SYSTEM
1524 | OTHER FACILITIES
1525 | ROAD
1526 | WATER SYSTEM
1527 | MEDICAL FACILITIES
1528 | MEDICAL FACILITIES
1529 | ROAD
1530 | MEDICAL FACILITIES
1531 | MEDICAL FACILITIES
1532 | MEDICAL FACILITIES
1533 | MEDICAL FACILITIES
1534 | MEDICAL FACILITIES
1535 | PGP FACILITIES
1536 | PGP FACILITIES
1537 | PGP FACILITIES
1538 | PGP FACILITIES
1539 | PGP FACILITIES
1540 | PGP FACILITIES
1541 | AGRICULTURAL FACILITIES
1542 | OTHER FACILITIES
1543 | PGP FACILITIES
1544 | MEDICAL FACILITIES
1545 | OTHER FACILITIES
1546 | PGP FACILITIES
1547 | PGP FACILITIES
1548 | MEDICAL FACILITIES
1549 | AGRICULTURAL FACILITIES
1550 | OTHER FACILITIES
1551 | PGP FACILITIES
1552 | PGP FACILITIES
1553 | PGP FACILITIES
1554 | PGP FACILITIES
1555 | MEDICAL FACILITIES
1556 | OTHER FACILITIES
1557 | OTHER FACILITIES
1558 | OTHER FACILITIES
1559 | PGP FACILITIES
1560 | PGP FACILITIES
1561 | PGP FACILITIES
1562 | OTHER FACILITIES
1563 | DRAINAGE
1564 | OTHER FACILITIES
1565 | DRAINAGE
1566 | COVERED COURT
1567 | COVERED COURT
1568 | OTHER FACILITIES
1569 | OTHER FACILITIES

## PRACTICE
PROJECT NUMBER | SUB CATEGORY | Row Labels | Count of PROJECT NUMBER
1 | ROAD | AGRICULTURAL FACILITIES | 15
2 | ROAD | AIRPORTS | 2
3 | ROAD | ANIMAL FACILITIES | 4
4 | ROAD | BHS | 87
5 | WATER SYSTEM | BRIDGES | 70
6 | WATER SYSTEM | COVERED COURT | 215
7 | WATER SYSTEM | DRAINAGE | 85
8 | MEDICAL FACILITIES | ELECTRIFICATION | 33
9 | MEDICAL FACILITIES | IRRIGATION | 10
10 | SCHOOL FACILITIES | MEDICAL FACILITIES | 431
11 | SCHOOL FACILITIES | MULITI-PURPOSE | 57
12 | SCHOOL FACILITIES | OTHER FACILITIES | 85
13 | ROAD | PGP FACILITIES | 117
14 | ROAD | PORTS | 10
15 | ROAD | RHU | 34
16 | ROAD | ROAD | 187
17 | BRIDGES | SCHOOL FACILITIES | 81
18 | BRIDGES | SLOPE PROTECTION | 18
19 | BRIDGES | SUPPLY | 1
20 | BRIDGES | WATER SYSTEM | 26
21 | SCHOOL FACILITIES | Grand Total | 1568
22 | MEDICAL FACILITIES
23 | MEDICAL FACILITIES
24 | MEDICAL FACILITIES
25 | MEDICAL FACILITIES
26 | BHS
27 | BHS
28 | BHS
29 | BHS
30 | BHS
31 | BHS
32 | MEDICAL FACILITIES
33 | MEDICAL FACILITIES
34 | MEDICAL FACILITIES
35 | MEDICAL FACILITIES
36 | MEDICAL FACILITIES
37 | MEDICAL FACILITIES
38 | MEDICAL FACILITIES
39 | OTHER FACILITIES
40 | ROAD
41 | BHS
42 | BHS
43 | BHS
44 | MULITI-PURPOSE
45 | MULITI-PURPOSE
46 | MULITI-PURPOSE
47 | MULITI-PURPOSE
48 | BHS
49 | BHS
50 | BHS
51 | BHS
52 | BHS
53 | BHS
54 | BHS
55 | BHS
56 | MULITI-PURPOSE
57 | OTHER FACILITIES
58 | OTHER FACILITIES
59 | PGP FACILITIES
60 | ROAD
61 | ROAD
62 | ROAD
63 | ROAD
64 | ROAD
65 | ROAD
66 | ROAD
67 | ROAD
68 | ROAD
69 | ROAD
70 | ROAD
71 | ROAD
72 | ROAD
73 | ROAD
74 | MULITI-PURPOSE
75 | MULITI-PURPOSE
76 | MULITI-PURPOSE
77 | MULITI-PURPOSE
78 | PGP FACILITIES
79 | PGP FACILITIES
80 | PGP FACILITIES
81 | OTHER FACILITIES
82 | MEDICAL FACILITIES
83 | MEDICAL FACILITIES
84 | PORTS
85 | PORTS
86 | PORTS
87 | PORTS
88 | WATER SYSTEM
89 | BHS
90 | BHS
91 | BHS
92 | RHU
93 | BHS
94 | BHS
95 | RHU
96 | BHS
97 | BHS
98 | OTHER FACILITIES
99 | MULITI-PURPOSE
100 | MULITI-PURPOSE
101 | MULITI-PURPOSE
102 | BRIDGES
103 | BRIDGES
104 | DRAINAGE
105 | DRAINAGE
106 | DRAINAGE
107 | DRAINAGE
108 | DRAINAGE
109 | ROAD
110 | BRIDGES
111 | BRIDGES
112 | ROAD
113 | BRIDGES
114 | ROAD
115 | SCHOOL FACILITIES
116 | PGP FACILITIES
117 | PORTS
118 | PGP FACILITIES
119 | SCHOOL FACILITIES
120 | SCHOOL FACILITIES
121 | SCHOOL FACILITIES
122 | SCHOOL FACILITIES
123 | SCHOOL FACILITIES
124 | SCHOOL FACILITIES
125 | SCHOOL FACILITIES
126 | SCHOOL FACILITIES
127 | SCHOOL FACILITIES
128 | SCHOOL FACILITIES
129 | SCHOOL FACILITIES
130 | MULITI-PURPOSE
131 | MULITI-PURPOSE
132 | MULITI-PURPOSE
133 | PGP FACILITIES
134 | PGP FACILITIES
135 | MEDICAL FACILITIES
136 | MEDICAL FACILITIES
137 | MEDICAL FACILITIES
138 | BRIDGES
139 | MEDICAL FACILITIES
140 | MEDICAL FACILITIES
141 | MEDICAL FACILITIES
142 | SCHOOL FACILITIES
143 | SCHOOL FACILITIES
144 | SCHOOL FACILITIES
145 | PGP FACILITIES
146 | PGP FACILITIES
147 | PGP FACILITIES
148 | PGP FACILITIES
149 | MEDICAL FACILITIES
150 | PGP FACILITIES
151 | MEDICAL FACILITIES
152 | MEDICAL FACILITIES
153 | MEDICAL FACILITIES
154 | MEDICAL FACILITIES
155 | MEDICAL FACILITIES
156 | MEDICAL FACILITIES
157 | MEDICAL FACILITIES
158 | MEDICAL FACILITIES
159 | BRIDGES
160 | BRIDGES
161 | BRIDGES
162 | BRIDGES
163 | BRIDGES
164 | BRIDGES
165 | BRIDGES
166 | BHS
167 | MULITI-PURPOSE
168 | ELECTRIFICATION
169 | ROAD
170 | ROAD
171 | ROAD
172 | MEDICAL FACILITIES
173 | BRIDGES
174 | SLOPE PROTECTION
175 | ROAD
176 | ROAD
177 | DRAINAGE
178 | MULITI-PURPOSE
179 | MULITI-PURPOSE
180 | MULITI-PURPOSE
181 | MULITI-PURPOSE
182 | MEDICAL FACILITIES
183 | MEDICAL FACILITIES
184 | MEDICAL FACILITIES
185 | MEDICAL FACILITIES
186 | BRIDGES
187 | OTHER FACILITIES
188 | OTHER FACILITIES
189 | SLOPE PROTECTION
190 | ROAD
191 | OTHER FACILITIES
192 | DRAINAGE
193 | ROAD
194 | DRAINAGE
195 | DRAINAGE
196 | OTHER FACILITIES
197 | OTHER FACILITIES
198 | MEDICAL FACILITIES
199 | MEDICAL FACILITIES
200 | IRRIGATION
201 | MEDICAL FACILITIES
202 | MEDICAL FACILITIES
203 | MEDICAL FACILITIES
204 | MEDICAL FACILITIES
205 | MEDICAL FACILITIES
206 | MEDICAL FACILITIES
207 | MEDICAL FACILITIES
208 | BRIDGES
209 | ROAD
210 | MULITI-PURPOSE
211 | MEDICAL FACILITIES
212 | MEDICAL FACILITIES
213 | AGRICULTURAL FACILITIES
214 | OTHER FACILITIES
215 | RHU
216 | RHU
217 | RHU
218 | RHU
219 | RHU
220 | RHU
221 | RHU
222 | RHU
223 | RHU
224 | RHU
225 | RHU
226 | RHU
227 | MEDICAL FACILITIES
228 | SCHOOL FACILITIES
229 | MEDICAL FACILITIES
230 | ELECTRIFICATION
231 | IRRIGATION
232 | IRRIGATION
233 | DRAINAGE
234 | OTHER FACILITIES
235 | ROAD
236 | ROAD
237 | ROAD
238 | OTHER FACILITIES
239 | SLOPE PROTECTION
240 | MEDICAL FACILITIES
241 | MEDICAL FACILITIES
242 | MEDICAL FACILITIES
243 | MEDICAL FACILITIES
244 | MEDICAL FACILITIES
245 | MULITI-PURPOSE
246 | MULITI-PURPOSE
247 | MULITI-PURPOSE
248 | DRAINAGE
249 | MULITI-PURPOSE
250 | MULITI-PURPOSE
251 | OTHER FACILITIES
252 | ROAD
253 | BRIDGES
254 | BRIDGES
255 | BRIDGES
256 | BRIDGES
257 | MULITI-PURPOSE
258 | BRIDGES
259 | BRIDGES
260 | BRIDGES
261 | BRIDGES
262 | BHS
263 | BHS
264 | BHS
265 | BHS
266 | BHS
267 | BHS
268 | BHS
269 | BHS
270 | BHS
271 | BHS
272 | BHS
273 | BHS
274 | BHS
275 | BHS
276 | BHS
277 | BHS
278 | BHS
279 | BHS
280 | BHS
281 | BHS
282 | BHS
283 | BHS
284 | BHS
285 | BHS
286 | BHS
287 | BHS
288 | BHS
289 | BHS
290 | BHS
291 | BHS
292 | BHS
293 | BHS
294 | BHS
295 | BHS
296 | BHS
297 | BHS
298 | BHS
299 | BHS
300 | BHS
301 | BHS
302 | BHS
303 | BHS
304 | BHS
305 | BHS
306 | BHS
307 | BHS
308 | BHS
309 | BHS
310 | BHS
311 | BHS
312 | BHS
313 | BHS
314 | BHS
315 | BHS
316 | MEDICAL FACILITIES
317 | MEDICAL FACILITIES
318 | MEDICAL FACILITIES
319 | OTHER FACILITIES
320 | OTHER FACILITIES
321 | OTHER FACILITIES
322 | OTHER FACILITIES
323 | PGP FACILITIES
324 | SCHOOL FACILITIES
325 | SCHOOL FACILITIES
326 | PGP FACILITIES
327 | MEDICAL FACILITIES
328 | MEDICAL FACILITIES
329 | MEDICAL FACILITIES
330 | ROAD
331 | ROAD
332 | ROAD
333 | ROAD
334 | DRAINAGE
335 | SLOPE PROTECTION
336 | DRAINAGE
337 | DRAINAGE
338 | OTHER FACILITIES
339 | DRAINAGE
340 | DRAINAGE
341 | DRAINAGE
342 | BRIDGES
343 | BRIDGES
344 | BRIDGES
345 | BRIDGES
346 | BRIDGES
347 | BRIDGES
348 | BRIDGES
349 | DRAINAGE
350 | DRAINAGE
351 | ROAD
352 | ROAD
353 | DRAINAGE
354 | ROAD
355 | BRIDGES
356 | AIRPORTS
357 | BRIDGES
358 | MULITI-PURPOSE
359 | ROAD
360 | ROAD
361 | ROAD
362 | ROAD
363 | ROAD
364 | ROAD
365 | ROAD
366 | ROAD
367 | ROAD
368 | SCHOOL FACILITIES
369 | SCHOOL FACILITIES
370 | SCHOOL FACILITIES
371 | SCHOOL FACILITIES
372 | RHU
373 | BHS
374 | RHU
375 | BHS
376 | RHU
377 | SCHOOL FACILITIES
378 | SCHOOL FACILITIES
379 | SCHOOL FACILITIES
380 | DRAINAGE
381 | WATER SYSTEM
382 | IRRIGATION
383 | WATER SYSTEM
384 | IRRIGATION
385 | WATER SYSTEM
386 | IRRIGATION
387 | IRRIGATION
388 | IRRIGATION
389 | ROAD
390 | SCHOOL FACILITIES
391 | SCHOOL FACILITIES
392 | SCHOOL FACILITIES
393 | SCHOOL FACILITIES
394 | SCHOOL FACILITIES
395 | SCHOOL FACILITIES
396 | SCHOOL FACILITIES
397 | SCHOOL FACILITIES
398 | SCHOOL FACILITIES
399 | SCHOOL FACILITIES
400 | SCHOOL FACILITIES
401 | SCHOOL FACILITIES
402 | SCHOOL FACILITIES
403 | SCHOOL FACILITIES
404 | SCHOOL FACILITIES
405 | MULITI-PURPOSE
406 | BRIDGES
407 | MEDICAL FACILITIES
408 | MEDICAL FACILITIES
409 | MEDICAL FACILITIES
410 | MULITI-PURPOSE
411 | BRIDGES
412 | BRIDGES
413 | ELECTRIFICATION
414 | MEDICAL FACILITIES
415 | MEDICAL FACILITIES
416 | MEDICAL FACILITIES
417 | MEDICAL FACILITIES
418 | MEDICAL FACILITIES
419 | MEDICAL FACILITIES
420 | MEDICAL FACILITIES
421 | AIRPORTS
422 | MEDICAL FACILITIES
423 | MEDICAL FACILITIES
424 | MEDICAL FACILITIES
425 | MEDICAL FACILITIES
426 | MEDICAL FACILITIES
427 | MEDICAL FACILITIES
428 | MEDICAL FACILITIES
429 | MEDICAL FACILITIES
430 | MEDICAL FACILITIES
431 | MEDICAL FACILITIES
432 | MEDICAL FACILITIES
433 | MEDICAL FACILITIES
434 | MEDICAL FACILITIES
435 | MEDICAL FACILITIES
436 | MEDICAL FACILITIES
437 | MEDICAL FACILITIES
438 | MEDICAL FACILITIES
439 | MEDICAL FACILITIES
440 | MEDICAL FACILITIES
441 | COVERED COURT
442 | COVERED COURT
443 | COVERED COURT
444 | COVERED COURT
445 | COVERED COURT
446 | COVERED COURT
447 | COVERED COURT
448 | COVERED COURT
449 | COVERED COURT
450 | COVERED COURT
451 | COVERED COURT
452 | COVERED COURT
453 | COVERED COURT
454 | COVERED COURT
455 | COVERED COURT
456 | COVERED COURT
457 | COVERED COURT
458 | COVERED COURT
459 | COVERED COURT
460 | COVERED COURT
461 | COVERED COURT
462 | COVERED COURT
463 | COVERED COURT
464 | COVERED COURT
465 | COVERED COURT
466 | COVERED COURT
467 | COVERED COURT
468 | COVERED COURT
469 | COVERED COURT
470 | COVERED COURT
471 | COVERED COURT
472 | COVERED COURT
473 | COVERED COURT
474 | COVERED COURT
475 | COVERED COURT
476 | COVERED COURT
477 | COVERED COURT
478 | COVERED COURT
479 | COVERED COURT
480 | COVERED COURT
481 | COVERED COURT
482 | COVERED COURT
483 | COVERED COURT
484 | COVERED COURT
485 | COVERED COURT
486 | COVERED COURT
487 | COVERED COURT
488 | COVERED COURT
489 | COVERED COURT
490 | COVERED COURT
491 | COVERED COURT
492 | COVERED COURT
493 | COVERED COURT
494 | COVERED COURT
495 | COVERED COURT
496 | COVERED COURT
497 | COVERED COURT
498 | COVERED COURT
499 | COVERED COURT
500 | COVERED COURT
501 | COVERED COURT
502 | COVERED COURT
503 | COVERED COURT
504 | COVERED COURT
505 | COVERED COURT
506 | COVERED COURT
507 | COVERED COURT
508 | COVERED COURT
509 | COVERED COURT
510 | COVERED COURT
511 | COVERED COURT
512 | COVERED COURT
513 | COVERED COURT
514 | COVERED COURT
515 | COVERED COURT
516 | COVERED COURT
517 | COVERED COURT
518 | COVERED COURT
519 | COVERED COURT
520 | COVERED COURT
521 | COVERED COURT
522 | COVERED COURT
523 | COVERED COURT
524 | COVERED COURT
525 | COVERED COURT
526 | COVERED COURT
527 | COVERED COURT
528 | COVERED COURT
529 | COVERED COURT
530 | COVERED COURT
531 | COVERED COURT
532 | COVERED COURT
533 | COVERED COURT
534 | COVERED COURT
535 | OTHER FACILITIES
536 | COVERED COURT
537 | COVERED COURT
538 | COVERED COURT
539 | COVERED COURT
540 | COVERED COURT
541 | COVERED COURT
542 | COVERED COURT
543 | COVERED COURT
544 | COVERED COURT
545 | COVERED COURT
546 | COVERED COURT
547 | COVERED COURT
548 | COVERED COURT
549 | COVERED COURT
550 | COVERED COURT
551 | COVERED COURT
552 | COVERED COURT
553 | COVERED COURT
554 | COVERED COURT
555 | COVERED COURT
556 | COVERED COURT
557 | COVERED COURT
558 | COVERED COURT
559 | COVERED COURT
560 | COVERED COURT
561 | COVERED COURT
562 | COVERED COURT
563 | COVERED COURT
564 | COVERED COURT
565 | COVERED COURT
566 | COVERED COURT
567 | COVERED COURT
568 | COVERED COURT
569 | COVERED COURT
570 | COVERED COURT
571 | COVERED COURT
572 | COVERED COURT
573 | COVERED COURT
574 | COVERED COURT
575 | COVERED COURT
576 | COVERED COURT
577 | COVERED COURT
578 | COVERED COURT
579 | COVERED COURT
580 | COVERED COURT
581 | COVERED COURT
582 | COVERED COURT
583 | COVERED COURT
584 | COVERED COURT
585 | COVERED COURT
586 | COVERED COURT
587 | COVERED COURT
588 | COVERED COURT
589 | COVERED COURT
590 | COVERED COURT
591 | COVERED COURT
592 | COVERED COURT
593 | COVERED COURT
594 | COVERED COURT
595 | COVERED COURT
596 | COVERED COURT
597 | COVERED COURT
598 | COVERED COURT
599 | COVERED COURT
600 | COVERED COURT
601 | COVERED COURT
602 | COVERED COURT
603 | COVERED COURT
604 | COVERED COURT
605 | COVERED COURT
606 | COVERED COURT
607 | COVERED COURT
608 | COVERED COURT
609 | ELECTRIFICATION
610 | SCHOOL FACILITIES
611 | SCHOOL FACILITIES
612 | MEDICAL FACILITIES
613 | MEDICAL FACILITIES
614 | MEDICAL FACILITIES
615 | MEDICAL FACILITIES
616 | PORTS
617 | PORTS
618 | SCHOOL FACILITIES
619 | SCHOOL FACILITIES
620 | SCHOOL FACILITIES
621 | SCHOOL FACILITIES
622 | SCHOOL FACILITIES
623 | SCHOOL FACILITIES
624 | SCHOOL FACILITIES
625 | SCHOOL FACILITIES
626 | ROAD
627 | ROAD
628 | ROAD
629 | ROAD
630 | ROAD
631 | ROAD
632 | ROAD
633 | ROAD
634 | WATER SYSTEM
635 | ROAD
636 | OTHER FACILITIES
637 | MEDICAL FACILITIES
638 | ELECTRIFICATION
639 | MEDICAL FACILITIES
640 | MEDICAL FACILITIES
641 | MEDICAL FACILITIES
642 | MEDICAL FACILITIES
643 | MEDICAL FACILITIES
644 | MEDICAL FACILITIES
645 | MEDICAL FACILITIES
646 | MEDICAL FACILITIES
647 | MEDICAL FACILITIES
648 | MEDICAL FACILITIES
649 | MEDICAL FACILITIES
650 | MEDICAL FACILITIES
651 | MEDICAL FACILITIES
652 | MEDICAL FACILITIES
653 | MEDICAL FACILITIES
654 | MEDICAL FACILITIES
655 | MEDICAL FACILITIES
656 | MEDICAL FACILITIES
657 | ELECTRIFICATION
658 | MEDICAL FACILITIES
659 | MEDICAL FACILITIES
660 | MEDICAL FACILITIES
661 | MEDICAL FACILITIES
662 | MULITI-PURPOSE
663 | MULITI-PURPOSE
664 | MEDICAL FACILITIES
665 | ELECTRIFICATION
666 | COVERED COURT
667 | MEDICAL FACILITIES
668 | DRAINAGE
669 | BRIDGES
670 | BRIDGES
671 | BRIDGES
672 | BRIDGES
673 | BRIDGES
674 | BRIDGES
675 | ELECTRIFICATION
676 | BRIDGES
677 | MEDICAL FACILITIES
678 | MEDICAL FACILITIES
679 | MEDICAL FACILITIES
680 | ROAD
681 | MEDICAL FACILITIES
682 | MEDICAL FACILITIES
683 | MEDICAL FACILITIES
684 | MEDICAL FACILITIES
685 | MEDICAL FACILITIES
686 | MEDICAL FACILITIES
687 | MEDICAL FACILITIES
688 | MEDICAL FACILITIES
689 | MEDICAL FACILITIES
690 | MEDICAL FACILITIES
691 | MEDICAL FACILITIES
692 | MEDICAL FACILITIES
693 | MEDICAL FACILITIES
694 | MEDICAL FACILITIES
695 | DRAINAGE
696 | MULITI-PURPOSE
697 | OTHER FACILITIES
698 | BRIDGES
699 | ROAD
700 | ROAD
701 | ROAD
702 | ROAD
703 | ROAD
704 | PGP FACILITIES
705 | PGP FACILITIES
706 | PGP FACILITIES
707 | PGP FACILITIES
708 | AGRICULTURAL FACILITIES
709 | ANIMAL FACILITIES
710 | ANIMAL FACILITIES
711 | ANIMAL FACILITIES
712 | PGP FACILITIES
713 | AGRICULTURAL FACILITIES
714 | MEDICAL FACILITIES
715 | MEDICAL FACILITIES
716 | MEDICAL FACILITIES
717 | MEDICAL FACILITIES
718 | MEDICAL FACILITIES
719 | MEDICAL FACILITIES
720 | MEDICAL FACILITIES
721 | MEDICAL FACILITIES
722 | MEDICAL FACILITIES
723 | MEDICAL FACILITIES
724 | MEDICAL FACILITIES
725 | MEDICAL FACILITIES
726 | MEDICAL FACILITIES
727 | MEDICAL FACILITIES
728 | MEDICAL FACILITIES
729 | MEDICAL FACILITIES
730 | MEDICAL FACILITIES
731 | MEDICAL FACILITIES
732 | MEDICAL FACILITIES
733 | MEDICAL FACILITIES
734 | MEDICAL FACILITIES
735 | MEDICAL FACILITIES
736 | WATER SYSTEM
737 | IRRIGATION
738 | MEDICAL FACILITIES
739 | AGRICULTURAL FACILITIES
740 | WATER SYSTEM
741 | AGRICULTURAL FACILITIES
742 | MEDICAL FACILITIES
743 | MEDICAL FACILITIES
744 | MEDICAL FACILITIES
745 | MEDICAL FACILITIES
746 | MEDICAL FACILITIES
747 | MEDICAL FACILITIES
748 | MULITI-PURPOSE
749 | MEDICAL FACILITIES
750 | BHS
751 | BRIDGES
752 | BRIDGES
753 | PORTS
754 | BHS
755 | BHS
756 | MEDICAL FACILITIES
757 | MEDICAL FACILITIES
758 | MEDICAL FACILITIES
759 | MEDICAL FACILITIES
760 | MEDICAL FACILITIES
761 | MULITI-PURPOSE
762 | MULITI-PURPOSE
763 | MEDICAL FACILITIES
764 | MEDICAL FACILITIES
765 | MEDICAL FACILITIES
766 | MEDICAL FACILITIES
767 | MEDICAL FACILITIES
768 | MEDICAL FACILITIES
769 | MEDICAL FACILITIES
770 | MEDICAL FACILITIES
771 | BRIDGES
772 | BRIDGES
773 | DRAINAGE
774 | BRIDGES
775 | DRAINAGE
776 | BRIDGES
777 | ROAD
778 | ROAD
779 | ROAD
780 | OTHER FACILITIES
781 | DRAINAGE
782 | DRAINAGE
783 | MULITI-PURPOSE
784 | COVERED COURT
785 | ROAD
786 | COVERED COURT
787 | MEDICAL FACILITIES
788 | PGP FACILITIES
789 | PGP FACILITIES
790 | MEDICAL FACILITIES
791 | MEDICAL FACILITIES
792 | MEDICAL FACILITIES
793 | MEDICAL FACILITIES
794 | MEDICAL FACILITIES
795 | MEDICAL FACILITIES
796 | ELECTRIFICATION
797 | MEDICAL FACILITIES
798 | MEDICAL FACILITIES
799 | MEDICAL FACILITIES
800 | MEDICAL FACILITIES
801 | ELECTRIFICATION
802 | PGP FACILITIES
803 | MEDICAL FACILITIES
804 | MEDICAL FACILITIES
805 | MULITI-PURPOSE
806 | MULITI-PURPOSE
808 | MEDICAL FACILITIES
809 | ROAD
810 | ROAD
811 | ROAD
812 | ROAD
813 | MEDICAL FACILITIES
814 | MEDICAL FACILITIES
815 | MEDICAL FACILITIES
816 | MEDICAL FACILITIES
817 | MEDICAL FACILITIES
818 | MEDICAL FACILITIES
819 | MEDICAL FACILITIES
820 | ROAD
821 | WATER SYSTEM
822 | PGP FACILITIES
823 | PGP FACILITIES
824 | MEDICAL FACILITIES
825 | MEDICAL FACILITIES
826 | PGP FACILITIES
827 | IRRIGATION
828 | MEDICAL FACILITIES
829 | MEDICAL FACILITIES
830 | MEDICAL FACILITIES
831 | MEDICAL FACILITIES
832 | MEDICAL FACILITIES
833 | MEDICAL FACILITIES
834 | MEDICAL FACILITIES
835 | MEDICAL FACILITIES
836 | MEDICAL FACILITIES
837 | MEDICAL FACILITIES
838 | MEDICAL FACILITIES
839 | MEDICAL FACILITIES
840 | MEDICAL FACILITIES
841 | MEDICAL FACILITIES
842 | MEDICAL FACILITIES
843 | MEDICAL FACILITIES
844 | MEDICAL FACILITIES
845 | MEDICAL FACILITIES
846 | MEDICAL FACILITIES
847 | MEDICAL FACILITIES
848 | MEDICAL FACILITIES
849 | MEDICAL FACILITIES
850 | MEDICAL FACILITIES
851 | MEDICAL FACILITIES
852 | MEDICAL FACILITIES
853 | MEDICAL FACILITIES
854 | ROAD
855 | DRAINAGE
856 | SLOPE PROTECTION
857 | SLOPE PROTECTION
858 | DRAINAGE
859 | ROAD
860 | ROAD
861 | MEDICAL FACILITIES
862 | MEDICAL FACILITIES
863 | OTHER FACILITIES
864 | OTHER FACILITIES
865 | OTHER FACILITIES
866 | OTHER FACILITIES
867 | MEDICAL FACILITIES
868 | MEDICAL FACILITIES
869 | BRIDGES
870 | MEDICAL FACILITIES
871 | MEDICAL FACILITIES
872 | MEDICAL FACILITIES
873 | MEDICAL FACILITIES
874 | MEDICAL FACILITIES
875 | MEDICAL FACILITIES
876 | MEDICAL FACILITIES
877 | MEDICAL FACILITIES
878 | MEDICAL FACILITIES
879 | MEDICAL FACILITIES
880 | MEDICAL FACILITIES
881 | MEDICAL FACILITIES
882 | WATER SYSTEM
883 | MEDICAL FACILITIES
884 | MEDICAL FACILITIES
885 | MEDICAL FACILITIES
886 | MEDICAL FACILITIES
887 | MEDICAL FACILITIES
888 | PGP FACILITIES
889 | MEDICAL FACILITIES
890 | MEDICAL FACILITIES
891 | MEDICAL FACILITIES
892 | RHU
893 | RHU
894 | RHU
895 | SCHOOL FACILITIES
896 | MEDICAL FACILITIES
897 | PGP FACILITIES
898 | MEDICAL FACILITIES
899 | MEDICAL FACILITIES
900 | MEDICAL FACILITIES
901 | MEDICAL FACILITIES
902 | WATER SYSTEM
903 | WATER SYSTEM
904 | MEDICAL FACILITIES
905 | MEDICAL FACILITIES
906 | MEDICAL FACILITIES
907 | MEDICAL FACILITIES
908 | MEDICAL FACILITIES
909 | MEDICAL FACILITIES
910 | MEDICAL FACILITIES
911 | MEDICAL FACILITIES
912 | MEDICAL FACILITIES
913 | MEDICAL FACILITIES
914 | MEDICAL FACILITIES
915 | MEDICAL FACILITIES
916 | MEDICAL FACILITIES
917 | MEDICAL FACILITIES
918 | MEDICAL FACILITIES
919 | MEDICAL FACILITIES
920 | MEDICAL FACILITIES
921 | MEDICAL FACILITIES
922 | MEDICAL FACILITIES
923 | MEDICAL FACILITIES
924 | MEDICAL FACILITIES
925 | MEDICAL FACILITIES
926 | MEDICAL FACILITIES
927 | MEDICAL FACILITIES
928 | MEDICAL FACILITIES
929 | MEDICAL FACILITIES
930 | MEDICAL FACILITIES
931 | ROAD
932 | MEDICAL FACILITIES
933 | MEDICAL FACILITIES
934 | MEDICAL FACILITIES
935 | MEDICAL FACILITIES
936 | MEDICAL FACILITIES
937 | MEDICAL FACILITIES
938 | MEDICAL FACILITIES
939 | PGP FACILITIES
940 | PGP FACILITIES
941 | PGP FACILITIES
942 | PGP FACILITIES
943 | MEDICAL FACILITIES
944 | ROAD
945 | WATER SYSTEM
946 | COVERED COURT
947 | COVERED COURT
948 | COVERED COURT
949 | COVERED COURT
950 | COVERED COURT
951 | COVERED COURT
952 | COVERED COURT
953 | COVERED COURT
954 | COVERED COURT
955 | COVERED COURT
956 | COVERED COURT
957 | COVERED COURT
958 | COVERED COURT
959 | COVERED COURT
960 | COVERED COURT
961 | COVERED COURT
962 | COVERED COURT
963 | COVERED COURT
964 | COVERED COURT
965 | COVERED COURT
966 | OTHER FACILITIES
967 | PGP FACILITIES
968 | BRIDGES
969 | MEDICAL FACILITIES
970 | MEDICAL FACILITIES
971 | MEDICAL FACILITIES
972 | MEDICAL FACILITIES
973 | MEDICAL FACILITIES
974 | MEDICAL FACILITIES
975 | MEDICAL FACILITIES
976 | WATER SYSTEM
977 | DRAINAGE
978 | DRAINAGE
979 | DRAINAGE
980 | DRAINAGE
981 | DRAINAGE
982 | DRAINAGE
983 | DRAINAGE
984 | DRAINAGE
985 | DRAINAGE
986 | DRAINAGE
987 | DRAINAGE
988 | DRAINAGE
989 | DRAINAGE
990 | MEDICAL FACILITIES
991 | MEDICAL FACILITIES
992 | MEDICAL FACILITIES
993 | MEDICAL FACILITIES
994 | MEDICAL FACILITIES
995 | MEDICAL FACILITIES
996 | MEDICAL FACILITIES
997 | MEDICAL FACILITIES
998 | ROAD
999 | MEDICAL FACILITIES
1000 | WATER SYSTEM
1001 | MEDICAL FACILITIES
1002 | PGP FACILITIES
1003 | WATER SYSTEM
1004 | ROAD
1005 | WATER SYSTEM
1006 | OTHER FACILITIES
1007 | WATER SYSTEM
1008 | MULITI-PURPOSE
1009 | SCHOOL FACILITIES
1010 | MEDICAL FACILITIES
1011 | ROAD
1012 | MEDICAL FACILITIES
1013 | MULITI-PURPOSE
1014 | WATER SYSTEM
1015 | ROAD
1016 | ROAD
1017 | MULITI-PURPOSE
1018 | SCHOOL FACILITIES
1019 | MULITI-PURPOSE
1020 | MULITI-PURPOSE
1021 | ELECTRIFICATION
1022 | ELECTRIFICATION
1023 | ROAD
1024 | ROAD
1025 | ELECTRIFICATION
1026 | ROAD
1027 | ELECTRIFICATION
1028 | ELECTRIFICATION
1029 | MEDICAL FACILITIES
1030 | WATER SYSTEM
1031 | ROAD
1032 | ELECTRIFICATION
1033 | ELECTRIFICATION
1034 | ELECTRIFICATION
1035 | SCHOOL FACILITIES
1036 | ROAD
1037 | ROAD
1038 | MEDICAL FACILITIES
1039 | PGP FACILITIES
1040 | PGP FACILITIES
1041 | PGP FACILITIES
1042 | MEDICAL FACILITIES
1043 | MEDICAL FACILITIES
1044 | MEDICAL FACILITIES
1045 | MEDICAL FACILITIES
1046 | MEDICAL FACILITIES
1047 | PGP FACILITIES
1048 | ELECTRIFICATION
1049 | MEDICAL FACILITIES
1050 | MEDICAL FACILITIES
1051 | MEDICAL FACILITIES
1052 | MEDICAL FACILITIES
1053 | MEDICAL FACILITIES
1054 | MEDICAL FACILITIES
1055 | PORTS
1056 | WATER SYSTEM
1057 | ROAD
1058 | DRAINAGE
1059 | BRIDGES
1060 | BRIDGES
1061 | ROAD
1062 | DRAINAGE
1063 | BRIDGES
1064 | BRIDGES
1065 | DRAINAGE
1066 | DRAINAGE
1067 | DRAINAGE
1068 | ROAD
1069 | BRIDGES
1070 | BRIDGES
1071 | BRIDGES
1072 | BRIDGES
1073 | DRAINAGE
1074 | BRIDGES
1075 | BRIDGES
1076 | BRIDGES
1077 | DRAINAGE
1078 | ROAD
1079 | ROAD
1080 | ROAD
1081 | ROAD
1082 | OTHER FACILITIES
1083 | ROAD
1084 | ROAD
1085 | ROAD
1086 | ROAD
1087 | ROAD
1088 | ROAD
1089 | DRAINAGE
1090 | DRAINAGE
1091 | OTHER FACILITIES
1092 | ROAD
1093 | OTHER FACILITIES
1094 | OTHER FACILITIES
1095 | OTHER FACILITIES
1096 | ROAD
1097 | ROAD
1098 | PGP FACILITIES
1099 | MEDICAL FACILITIES
1100 | MEDICAL FACILITIES
1101 | MEDICAL FACILITIES
1102 | MEDICAL FACILITIES
1103 | MEDICAL FACILITIES
1104 | MEDICAL FACILITIES
1105 | MEDICAL FACILITIES
1106 | MEDICAL FACILITIES
1107 | MEDICAL FACILITIES
1108 | MEDICAL FACILITIES
1109 | MEDICAL FACILITIES
1110 | MEDICAL FACILITIES
1111 | MEDICAL FACILITIES
1112 | MEDICAL FACILITIES
1113 | MEDICAL FACILITIES
1114 | DRAINAGE
1115 | SLOPE PROTECTION
1116 | MEDICAL FACILITIES
1117 | MEDICAL FACILITIES
1118 | MEDICAL FACILITIES
1119 | MEDICAL FACILITIES
1120 | MEDICAL FACILITIES
1121 | MEDICAL FACILITIES
1122 | ROAD
1123 | SCHOOL FACILITIES
1124 | SCHOOL FACILITIES
1125 | MULITI-PURPOSE
1126 | MULITI-PURPOSE
1127 | MEDICAL FACILITIES
1128 | MEDICAL FACILITIES
1129 | MEDICAL FACILITIES
1130 | MEDICAL FACILITIES
1131 | PGP FACILITIES
1132 | ELECTRIFICATION
1133 | MEDICAL FACILITIES
1134 | MEDICAL FACILITIES
1135 | MEDICAL FACILITIES
1136 | MEDICAL FACILITIES
1137 | MEDICAL FACILITIES
1138 | MEDICAL FACILITIES
1139 | MEDICAL FACILITIES
1140 | MEDICAL FACILITIES
1141 | MEDICAL FACILITIES
1142 | MEDICAL FACILITIES
1143 | MEDICAL FACILITIES
1144 | MEDICAL FACILITIES
1145 | MEDICAL FACILITIES
1146 | MEDICAL FACILITIES
1147 | MEDICAL FACILITIES
1148 | MEDICAL FACILITIES
1149 | MEDICAL FACILITIES
1150 | MEDICAL FACILITIES
1151 | BHS
1152 | MEDICAL FACILITIES
1153 | RHU
1154 | RHU
1155 | MEDICAL FACILITIES
1156 | ROAD
1157 | PGP FACILITIES
1158 | COVERED COURT
1159 | OTHER FACILITIES
1160 | ELECTRIFICATION
1161 | ELECTRIFICATION
1162 | ELECTRIFICATION
1163 | ELECTRIFICATION
1164 | ELECTRIFICATION
1165 | ELECTRIFICATION
1166 | ROAD
1167 | MULITI-PURPOSE
1168 | MULITI-PURPOSE
1169 | MULITI-PURPOSE
1170 | MULITI-PURPOSE
1171 | MEDICAL FACILITIES
1172 | MEDICAL FACILITIES
1173 | MEDICAL FACILITIES
1174 | OTHER FACILITIES
1175 | ROAD
1176 | OTHER FACILITIES
1177 | AGRICULTURAL FACILITIES
1178 | PORTS
1179 | MEDICAL FACILITIES
1180 | DRAINAGE
1181 | DRAINAGE
1182 | MEDICAL FACILITIES
1183 | AGRICULTURAL FACILITIES
1184 | AGRICULTURAL FACILITIES
1185 | PGP FACILITIES
1186 | PGP FACILITIES
1187 | PGP FACILITIES
1188 | PGP FACILITIES
1189 | ROAD
1190 | AGRICULTURAL FACILITIES
1191 | AGRICULTURAL FACILITIES
1192 | AGRICULTURAL FACILITIES
1193 | MEDICAL FACILITIES
1194 | SCHOOL FACILITIES
1195 | ROAD
1196 | MEDICAL FACILITIES
1197 | SCHOOL FACILITIES
1198 | OTHER FACILITIES
1199 | MEDICAL FACILITIES
1200 | PGP FACILITIES
1201 | MEDICAL FACILITIES
1202 | OTHER FACILITIES
1203 | OTHER FACILITIES
1204 | OTHER FACILITIES
1205 | OTHER FACILITIES
1206 | OTHER FACILITIES
1207 | OTHER FACILITIES
1208 | OTHER FACILITIES
1209 | OTHER FACILITIES
1210 | OTHER FACILITIES
1211 | OTHER FACILITIES
1212 | OTHER FACILITIES
1213 | OTHER FACILITIES
1214 | OTHER FACILITIES
1215 | OTHER FACILITIES
1216 | OTHER FACILITIES
1217 | OTHER FACILITIES
1218 | OTHER FACILITIES
1219 | OTHER FACILITIES
1220 | OTHER FACILITIES
1221 | OTHER FACILITIES
1222 | OTHER FACILITIES
1223 | OTHER FACILITIES
1224 | OTHER FACILITIES
1225 | OTHER FACILITIES
1226 | COVERED COURT
1227 | PGP FACILITIES
1228 | PGP FACILITIES
1229 | PGP FACILITIES
1230 | PGP FACILITIES
1231 | PGP FACILITIES
1232 | PGP FACILITIES
1233 | PGP FACILITIES
1234 | MULITI-PURPOSE
1235 | PGP FACILITIES
1236 | PGP FACILITIES
1237 | PGP FACILITIES
1238 | ELECTRIFICATION
1239 | PGP FACILITIES
1240 | PGP FACILITIES
1241 | PGP FACILITIES
1242 | PGP FACILITIES
1243 | PGP FACILITIES
1244 | OTHER FACILITIES
1245 | PGP FACILITIES
1246 | MEDICAL FACILITIES
1247 | MEDICAL FACILITIES
1248 | MEDICAL FACILITIES
1249 | MEDICAL FACILITIES
1250 | PGP FACILITIES
1251 | MULITI-PURPOSE
1252 | MEDICAL FACILITIES
1253 | PGP FACILITIES
1254 | MEDICAL FACILITIES
1255 | BHS
1256 | MEDICAL FACILITIES
1257 | AGRICULTURAL FACILITIES
1258 | PGP FACILITIES
1259 | MEDICAL FACILITIES
1260 | PGP FACILITIES
1261 | PGP FACILITIES
1262 | MEDICAL FACILITIES
1263 | MEDICAL FACILITIES
1264 | OTHER FACILITIES
1265 | PGP FACILITIES
1266 | MEDICAL FACILITIES
1267 | PGP FACILITIES
1268 | OTHER FACILITIES
1269 | PGP FACILITIES
1270 | SLOPE PROTECTION
1271 | ROAD
1272 | SLOPE PROTECTION
1273 | SLOPE PROTECTION
1274 | ROAD
1275 | SLOPE PROTECTION
1276 | SLOPE PROTECTION
1277 | ROAD
1278 | SLOPE PROTECTION
1279 | SLOPE PROTECTION
1280 | ROAD
1281 | DRAINAGE
1282 | OTHER FACILITIES
1283 | DRAINAGE
1284 | DRAINAGE
1285 | DRAINAGE
1286 | DRAINAGE
1287 | DRAINAGE
1288 | DRAINAGE
1289 | DRAINAGE
1290 | DRAINAGE
1291 | DRAINAGE
1292 | ROAD
1293 | DRAINAGE
1294 | DRAINAGE
1295 | OTHER FACILITIES
1296 | DRAINAGE
1297 | DRAINAGE
1298 | DRAINAGE
1299 | PGP FACILITIES
1300 | PGP FACILITIES
1301 | COVERED COURT
1302 | COVERED COURT
1303 | COVERED COURT
1304 | COVERED COURT
1305 | COVERED COURT
1306 | COVERED COURT
1307 | COVERED COURT
1308 | COVERED COURT
1309 | COVERED COURT
1310 | MULITI-PURPOSE
1311 | MULITI-PURPOSE
1312 | MULITI-PURPOSE
1313 | PGP FACILITIES
1314 | MULITI-PURPOSE
1315 | MEDICAL FACILITIES
1316 | MEDICAL FACILITIES
1317 | MEDICAL FACILITIES
1318 | MEDICAL FACILITIES
1319 | MEDICAL FACILITIES
1320 | MEDICAL FACILITIES
1321 | MEDICAL FACILITIES
1322 | MEDICAL FACILITIES
1323 | MEDICAL FACILITIES
1324 | SLOPE PROTECTION
1325 | MEDICAL FACILITIES
1326 | MEDICAL FACILITIES
1327 | MEDICAL FACILITIES
1328 | DRAINAGE
1329 | RHU
1330 | RHU
1331 | RHU
1332 | RHU
1333 | RHU
1334 | RHU
1335 | BHS
1336 | ELECTRIFICATION
1337 | ELECTRIFICATION
1338 | ELECTRIFICATION
1339 | ELECTRIFICATION
1340 | ELECTRIFICATION
1341 | PGP FACILITIES
1342 | SCHOOL FACILITIES
1343 | SCHOOL FACILITIES
1344 | SCHOOL FACILITIES
1345 | SCHOOL FACILITIES
1346 | SCHOOL FACILITIES
1347 | SCHOOL FACILITIES
1348 | SCHOOL FACILITIES
1349 | SCHOOL FACILITIES
1350 | SCHOOL FACILITIES
1351 | SCHOOL FACILITIES
1352 | SCHOOL FACILITIES
1353 | SCHOOL FACILITIES
1354 | SCHOOL FACILITIES
1355 | SCHOOL FACILITIES
1356 | SCHOOL FACILITIES
1357 | SCHOOL FACILITIES
1358 | SCHOOL FACILITIES
1359 | SCHOOL FACILITIES
1360 | SCHOOL FACILITIES
1361 | MEDICAL FACILITIES
1362 | MEDICAL FACILITIES
1363 | MEDICAL FACILITIES
1364 | MEDICAL FACILITIES
1365 | MEDICAL FACILITIES
1366 | MEDICAL FACILITIES
1367 | MEDICAL FACILITIES
1368 | ROAD
1369 | ROAD
1370 | ROAD
1371 | ROAD
1372 | ROAD
1373 | PGP FACILITIES
1374 | PGP FACILITIES
1375 | MEDICAL FACILITIES
1376 | PGP FACILITIES
1377 | PGP FACILITIES
1378 | PGP FACILITIES
1379 | MEDICAL FACILITIES
1380 | MEDICAL FACILITIES
1381 | PGP FACILITIES
1382 | MEDICAL FACILITIES
1383 | PGP FACILITIES
1384 | PGP FACILITIES
1385 | PGP FACILITIES
1386 | PGP FACILITIES
1387 | AGRICULTURAL FACILITIES
1388 | PGP FACILITIES
1389 | PGP FACILITIES
1390 | PGP FACILITIES
1391 | PGP FACILITIES
1392 | PGP FACILITIES
1393 | PGP FACILITIES
1394 | RHU
1395 | RHU
1396 | RHU
1397 | RHU
1398 | MEDICAL FACILITIES
1399 | COVERED COURT
1400 | COVERED COURT
1401 | COVERED COURT
1402 | COVERED COURT
1403 | COVERED COURT
1404 | COVERED COURT
1405 | COVERED COURT
1406 | COVERED COURT
1407 | SLOPE PROTECTION
1408 | SLOPE PROTECTION
1409 | DRAINAGE
1410 | DRAINAGE
1411 | DRAINAGE
1412 | DRAINAGE
1413 | DRAINAGE
1414 | DRAINAGE
1415 | DRAINAGE
1416 | DRAINAGE
1417 | DRAINAGE
1418 | PGP FACILITIES
1419 | PGP FACILITIES
1420 | PGP FACILITIES
1421 | OTHER FACILITIES
1422 | OTHER FACILITIES
1423 | PGP FACILITIES
1424 | ANIMAL FACILITIES
1425 | PGP FACILITIES
1426 | OTHER FACILITIES
1427 | PGP FACILITIES
1428 | PGP FACILITIES
1429 | MEDICAL FACILITIES
1430 | PGP FACILITIES
1431 | MULITI-PURPOSE
1432 | ROAD
1433 | ROAD
1434 | ROAD
1435 | ROAD
1436 | COVERED COURT
1437 | COVERED COURT
1438 | COVERED COURT
1439 | DRAINAGE
1440 | MEDICAL FACILITIES
1441 | MEDICAL FACILITIES
1442 | DRAINAGE
1443 | DRAINAGE
1444 | MEDICAL FACILITIES
1445 | MEDICAL FACILITIES
1446 | MEDICAL FACILITIES
1447 | RHU
1448 | RHU
1449 | ELECTRIFICATION
1450 | PGP FACILITIES
1451 | OTHER FACILITIES
1452 | PGP FACILITIES
1453 | DRAINAGE
1454 | PGP FACILITIES
1455 | OTHER FACILITIES
1456 | ROAD
1457 | SLOPE PROTECTION
1458 | SUPPLY
1459 | COVERED COURT
1460 | MEDICAL FACILITIES
1461 | MEDICAL FACILITIES
1462 | MEDICAL FACILITIES
1463 | ROAD
1464 | ROAD
1465 | ROAD
1466 | ROAD
1467 | ROAD
1468 | ROAD
1469 | ROAD
1470 | ROAD
1471 | ROAD
1472 | ROAD
1473 | ROAD
1474 | ROAD
1475 | ROAD
1476 | ROAD
1477 | ROAD
1478 | ROAD
1479 | ROAD
1480 | ROAD
1481 | ROAD
1482 | ROAD
1483 | ROAD
1484 | ROAD
1485 | ROAD
1486 | ROAD
1487 | ROAD
1488 | ROAD
1489 | ROAD
1490 | ROAD
1491 | ROAD
1492 | ROAD
1493 | ROAD
1494 | ROAD
1495 | ROAD
1496 | BRIDGES
1497 | BRIDGES
1498 | ROAD
1499 | ROAD
1500 | ROAD
1501 | ROAD
1502 | ROAD
1503 | ROAD
1504 | ROAD
1505 | ROAD
1506 | ROAD
1507 | ROAD
1508 | ROAD
1509 | ROAD
1510 | ROAD
1511 | ROAD
1512 | ROAD
1513 | ROAD
1514 | ROAD
1515 | ROAD
1516 | ROAD
1517 | ROAD
1518 | BRIDGES
1519 | OTHER FACILITIES
1520 | OTHER FACILITIES
1521 | MEDICAL FACILITIES
1522 | WATER SYSTEM
1523 | WATER SYSTEM
1524 | OTHER FACILITIES
1525 | ROAD
1526 | WATER SYSTEM
1527 | MEDICAL FACILITIES
1528 | MEDICAL FACILITIES
1529 | ROAD
1530 | MEDICAL FACILITIES
1531 | MEDICAL FACILITIES
1532 | MEDICAL FACILITIES
1533 | MEDICAL FACILITIES
1534 | MEDICAL FACILITIES
1535 | PGP FACILITIES
1536 | PGP FACILITIES
1537 | PGP FACILITIES
1538 | PGP FACILITIES
1539 | PGP FACILITIES
1540 | PGP FACILITIES
1541 | AGRICULTURAL FACILITIES
1542 | OTHER FACILITIES
1543 | PGP FACILITIES
1544 | MEDICAL FACILITIES
1545 | OTHER FACILITIES
1546 | PGP FACILITIES
1547 | PGP FACILITIES
1548 | MEDICAL FACILITIES
1549 | AGRICULTURAL FACILITIES
1550 | OTHER FACILITIES
1551 | PGP FACILITIES
1552 | PGP FACILITIES
1553 | PGP FACILITIES
1554 | PGP FACILITIES
1555 | MEDICAL FACILITIES
1556 | OTHER FACILITIES
1557 | OTHER FACILITIES
1558 | OTHER FACILITIES
1559 | PGP FACILITIES
1560 | PGP FACILITIES
1561 | PGP FACILITIES
1562 | OTHER FACILITIES
1563 | DRAINAGE
1564 | OTHER FACILITIES
1565 | DRAINAGE
1566 | COVERED COURT
1567 | COVERED COURT
1568 | OTHER FACILITIES
1569 | OTHER FACILITIES

## Project Number
Project Number | Status
1 | OK | Row Labels | Count of Project Number
2 | OK | Missing | 1
3 | OK | OK | 1568
4 | OK | Grand Total | 1569
5 | OK
6 | OK
7 | OK
8 | OK
9 | OK
10 | OK
11 | OK
12 | OK
13 | OK
14 | OK
15 | OK
16 | OK
17 | OK
18 | OK
19 | OK
20 | OK
21 | OK
22 | OK
23 | OK
24 | OK
25 | OK
26 | OK
27 | OK
28 | OK
29 | OK
30 | OK
31 | OK
32 | OK
33 | OK
34 | OK
35 | OK
36 | OK
37 | OK
38 | OK
39 | OK
40 | OK
41 | OK
42 | OK
43 | OK
44 | OK
45 | OK
46 | OK
47 | OK
48 | OK
49 | OK
50 | OK
51 | OK
52 | OK
53 | OK
54 | OK
55 | OK
56 | OK
57 | OK
58 | OK
59 | OK
60 | OK
61 | OK
62 | OK
63 | OK
64 | OK
65 | OK
66 | OK
67 | OK
68 | OK
69 | OK
70 | OK
71 | OK
72 | OK
73 | OK
74 | OK
75 | OK
76 | OK
77 | OK
78 | OK
79 | OK
80 | OK
81 | OK
82 | OK
83 | OK
84 | OK
85 | OK
86 | OK
87 | OK
88 | OK
89 | OK
90 | OK
91 | OK
92 | OK
93 | OK
94 | OK
95 | OK
96 | OK
97 | OK
98 | OK
99 | OK
100 | OK
101 | OK
102 | OK
103 | OK
104 | OK
105 | OK
106 | OK
107 | OK
108 | OK
109 | OK
110 | OK
111 | OK
112 | OK
113 | OK
114 | OK
115 | OK
116 | OK
117 | OK
118 | OK
119 | OK
120 | OK
121 | OK
122 | OK
123 | OK
124 | OK
125 | OK
126 | OK
127 | OK
128 | OK
129 | OK
130 | OK
131 | OK
132 | OK
133 | OK
134 | OK
135 | OK
136 | OK
137 | OK
138 | OK
139 | OK
140 | OK
141 | OK
142 | OK
143 | OK
144 | OK
145 | OK
146 | OK
147 | OK
148 | OK
149 | OK
150 | OK
151 | OK
152 | OK
153 | OK
154 | OK
155 | OK
156 | OK
157 | OK
158 | OK
159 | OK
160 | OK
161 | OK
162 | OK
163 | OK
164 | OK
165 | OK
166 | OK
167 | OK
168 | OK
169 | OK
170 | OK
171 | OK
172 | OK
173 | OK
174 | OK
175 | OK
176 | OK
177 | OK
178 | OK
179 | OK
180 | OK
181 | OK
182 | OK
183 | OK
184 | OK
185 | OK
186 | OK
187 | OK
188 | OK
189 | OK
190 | OK
191 | OK
192 | OK
193 | OK
194 | OK
195 | OK
196 | OK
197 | OK
198 | OK
199 | OK
200 | OK
201 | OK
202 | OK
203 | OK
204 | OK
205 | OK
206 | OK
207 | OK
208 | OK
209 | OK
210 | OK
211 | OK
212 | OK
213 | OK
214 | OK
215 | OK
216 | OK
217 | OK
218 | OK
219 | OK
220 | OK
221 | OK
222 | OK
223 | OK
224 | OK
225 | OK
226 | OK
227 | OK
228 | OK
229 | OK
230 | OK
231 | OK
232 | OK
233 | OK
234 | OK
235 | OK
236 | OK
237 | OK
238 | OK
239 | OK
240 | OK
241 | OK
242 | OK
243 | OK
244 | OK
245 | OK
246 | OK
247 | OK
248 | OK
249 | OK
250 | OK
251 | OK
252 | OK
253 | OK
254 | OK
255 | OK
256 | OK
257 | OK
258 | OK
259 | OK
260 | OK
261 | OK
262 | OK
263 | OK
264 | OK
265 | OK
266 | OK
267 | OK
268 | OK
269 | OK
270 | OK
271 | OK
272 | OK
273 | OK
274 | OK
275 | OK
276 | OK
277 | OK
278 | OK
279 | OK
280 | OK
281 | OK
282 | OK
283 | OK
284 | OK
285 | OK
286 | OK
287 | OK
288 | OK
289 | OK
290 | OK
291 | OK
292 | OK
293 | OK
294 | OK
295 | OK
296 | OK
297 | OK
298 | OK
299 | OK
300 | OK
301 | OK
302 | OK
303 | OK
304 | OK
305 | OK
306 | OK
307 | OK
308 | OK
309 | OK
310 | OK
311 | OK
312 | OK
313 | OK
314 | OK
315 | OK
316 | OK
317 | OK
318 | OK
319 | OK
320 | OK
321 | OK
322 | OK
323 | OK
324 | OK
325 | OK
326 | OK
327 | OK
328 | OK
329 | OK
330 | OK
331 | OK
332 | OK
333 | OK
334 | OK
335 | OK
336 | OK
337 | OK
338 | OK
339 | OK
340 | OK
341 | OK
342 | OK
343 | OK
344 | OK
345 | OK
346 | OK
347 | OK
348 | OK
349 | OK
350 | OK
351 | OK
352 | OK
353 | OK
354 | OK
355 | OK
356 | OK
357 | OK
358 | OK
359 | OK
360 | OK
361 | OK
362 | OK
363 | OK
364 | OK
365 | OK
366 | OK
367 | OK
368 | OK
369 | OK
370 | OK
371 | OK
372 | OK
373 | OK
374 | OK
375 | OK
376 | OK
377 | OK
378 | OK
379 | OK
380 | OK
381 | OK
382 | OK
383 | OK
384 | OK
385 | OK
386 | OK
387 | OK
388 | OK
389 | OK
390 | OK
391 | OK
392 | OK
393 | OK
394 | OK
395 | OK
396 | OK
397 | OK
398 | OK
399 | OK
400 | OK
401 | OK
402 | OK
403 | OK
404 | OK
405 | OK
406 | OK
407 | OK
408 | OK
409 | OK
410 | OK
411 | OK
412 | OK
413 | OK
414 | OK
415 | OK
416 | OK
417 | OK
418 | OK
419 | OK
420 | OK
421 | OK
422 | OK
423 | OK
424 | OK
425 | OK
426 | OK
427 | OK
428 | OK
429 | OK
430 | OK
431 | OK
432 | OK
433 | OK
434 | OK
435 | OK
436 | OK
437 | OK
438 | OK
439 | OK
440 | OK
441 | OK
442 | OK
443 | OK
444 | OK
445 | OK
446 | OK
447 | OK
448 | OK
449 | OK
450 | OK
451 | OK
452 | OK
453 | OK
454 | OK
455 | OK
456 | OK
457 | OK
458 | OK
459 | OK
460 | OK
461 | OK
462 | OK
463 | OK
464 | OK
465 | OK
466 | OK
467 | OK
468 | OK
469 | OK
470 | OK
471 | OK
472 | OK
473 | OK
474 | OK
475 | OK
476 | OK
477 | OK
478 | OK
479 | OK
480 | OK
481 | OK
482 | OK
483 | OK
484 | OK
485 | OK
486 | OK
487 | OK
488 | OK
489 | OK
490 | OK
491 | OK
492 | OK
493 | OK
494 | OK
495 | OK
496 | OK
497 | OK
498 | OK
499 | OK
500 | OK
501 | OK
502 | OK
503 | OK
504 | OK
505 | OK
506 | OK
507 | OK
508 | OK
509 | OK
510 | OK
511 | OK
512 | OK
513 | OK
514 | OK
515 | OK
516 | OK
517 | OK
518 | OK
519 | OK
520 | OK
521 | OK
522 | OK
523 | OK
524 | OK
525 | OK
526 | OK
527 | OK
528 | OK
529 | OK
530 | OK
531 | OK
532 | OK
533 | OK
534 | OK
535 | OK
536 | OK
537 | OK
538 | OK
539 | OK
540 | OK
541 | OK
542 | OK
543 | OK
544 | OK
545 | OK
546 | OK
547 | OK
548 | OK
549 | OK
550 | OK
551 | OK
552 | OK
553 | OK
554 | OK
555 | OK
556 | OK
557 | OK
558 | OK
559 | OK
560 | OK
561 | OK
562 | OK
563 | OK
564 | OK
565 | OK
566 | OK
567 | OK
568 | OK
569 | OK
570 | OK
571 | OK
572 | OK
573 | OK
574 | OK
575 | OK
576 | OK
577 | OK
578 | OK
579 | OK
580 | OK
581 | OK
582 | OK
583 | OK
584 | OK
585 | OK
586 | OK
587 | OK
588 | OK
589 | OK
590 | OK
591 | OK
592 | OK
593 | OK
594 | OK
595 | OK
596 | OK
597 | OK
598 | OK
599 | OK
600 | OK
601 | OK
602 | OK
603 | OK
604 | OK
605 | OK
606 | OK
607 | OK
608 | OK
609 | OK
610 | OK
611 | OK
612 | OK
613 | OK
614 | OK
615 | OK
616 | OK
617 | OK
618 | OK
619 | OK
620 | OK
621 | OK
622 | OK
623 | OK
624 | OK
625 | OK
626 | OK
627 | OK
628 | OK
629 | OK
630 | OK
631 | OK
632 | OK
633 | OK
634 | OK
635 | OK
636 | OK
637 | OK
638 | OK
639 | OK
640 | OK
641 | OK
642 | OK
643 | OK
644 | OK
645 | OK
646 | OK
647 | OK
648 | OK
649 | OK
650 | OK
651 | OK
652 | OK
653 | OK
654 | OK
655 | OK
656 | OK
657 | OK
658 | OK
659 | OK
660 | OK
661 | OK
662 | OK
663 | OK
664 | OK
665 | OK
666 | OK
667 | OK
668 | OK
669 | OK
670 | OK
671 | OK
672 | OK
673 | OK
674 | OK
675 | OK
676 | OK
677 | OK
678 | OK
679 | OK
680 | OK
681 | OK
682 | OK
683 | OK
684 | OK
685 | OK
686 | OK
687 | OK
688 | OK
689 | OK
690 | OK
691 | OK
692 | OK
693 | OK
694 | OK
695 | OK
696 | OK
697 | OK
698 | OK
699 | OK
700 | OK
701 | OK
702 | OK
703 | OK
704 | OK
705 | OK
706 | OK
707 | OK
708 | OK
709 | OK
710 | OK
711 | OK
712 | OK
713 | OK
714 | OK
715 | OK
716 | OK
717 | OK
718 | OK
719 | OK
720 | OK
721 | OK
722 | OK
723 | OK
724 | OK
725 | OK
726 | OK
727 | OK
728 | OK
729 | OK
730 | OK
731 | OK
732 | OK
733 | OK
734 | OK
735 | OK
736 | OK
737 | OK
738 | OK
739 | OK
740 | OK
741 | OK
742 | OK
743 | OK
744 | OK
745 | OK
746 | OK
747 | OK
748 | OK
749 | OK
750 | OK
751 | OK
752 | OK
753 | OK
754 | OK
755 | OK
756 | OK
757 | OK
758 | OK
759 | OK
760 | OK
761 | OK
762 | OK
763 | OK
764 | OK
765 | OK
766 | OK
767 | OK
768 | OK
769 | OK
770 | OK
771 | OK
772 | OK
773 | OK
774 | OK
775 | OK
776 | OK
777 | OK
778 | OK
779 | OK
780 | OK
781 | OK
782 | OK
783 | OK
784 | OK
785 | OK
786 | OK
787 | OK
788 | OK
789 | OK
790 | OK
791 | OK
792 | OK
793 | OK
794 | OK
795 | OK
796 | OK
797 | OK
798 | OK
799 | OK
800 | OK
801 | OK
802 | OK
803 | OK
804 | OK
805 | OK
806 | OK
807 | Missing
808 | OK
809 | OK
810 | OK
811 | OK
812 | OK
813 | OK
814 | OK
815 | OK
816 | OK
817 | OK
818 | OK
819 | OK
820 | OK
821 | OK
822 | OK
823 | OK
824 | OK
825 | OK
826 | OK
827 | OK
828 | OK
829 | OK
830 | OK
831 | OK
832 | OK
833 | OK
834 | OK
835 | OK
836 | OK
837 | OK
838 | OK
839 | OK
840 | OK
841 | OK
842 | OK
843 | OK
844 | OK
845 | OK
846 | OK
847 | OK
848 | OK
849 | OK
850 | OK
851 | OK
852 | OK
853 | OK
854 | OK
855 | OK
856 | OK
857 | OK
858 | OK
859 | OK
860 | OK
861 | OK
862 | OK
863 | OK
864 | OK
865 | OK
866 | OK
867 | OK
868 | OK
869 | OK
870 | OK
871 | OK
872 | OK
873 | OK
874 | OK
875 | OK
876 | OK
877 | OK
878 | OK
879 | OK
880 | OK
881 | OK
882 | OK
883 | OK
884 | OK
885 | OK
886 | OK
887 | OK
888 | OK
889 | OK
890 | OK
891 | OK
892 | OK
893 | OK
894 | OK
895 | OK
896 | OK
897 | OK
898 | OK
899 | OK
900 | OK
901 | OK
902 | OK
903 | OK
904 | OK
905 | OK
906 | OK
907 | OK
908 | OK
909 | OK
910 | OK
911 | OK
912 | OK
913 | OK
914 | OK
915 | OK
916 | OK
917 | OK
918 | OK
919 | OK
920 | OK
921 | OK
922 | OK
923 | OK
924 | OK
925 | OK
926 | OK
927 | OK
928 | OK
929 | OK
930 | OK
931 | OK
932 | OK
933 | OK
934 | OK
935 | OK
936 | OK
937 | OK
938 | OK
939 | OK
940 | OK
941 | OK
942 | OK
943 | OK
944 | OK
945 | OK
946 | OK
947 | OK
948 | OK
949 | OK
950 | OK
951 | OK
952 | OK
953 | OK
954 | OK
955 | OK
956 | OK
957 | OK
958 | OK
959 | OK
960 | OK
961 | OK
962 | OK
963 | OK
964 | OK
965 | OK
966 | OK
967 | OK
968 | OK
969 | OK
970 | OK
971 | OK
972 | OK
973 | OK
974 | OK
975 | OK
976 | OK
977 | OK
978 | OK
979 | OK
980 | OK
981 | OK
982 | OK
983 | OK
984 | OK
985 | OK
986 | OK
987 | OK
988 | OK
989 | OK
990 | OK
991 | OK
992 | OK
993 | OK
994 | OK
995 | OK
996 | OK
997 | OK
998 | OK
999 | OK
1000 | OK
1001 | OK
1002 | OK
1003 | OK
1004 | OK
1005 | OK
1006 | OK
1007 | OK
1008 | OK
1009 | OK
1010 | OK
1011 | OK
1012 | OK
1013 | OK
1014 | OK
1015 | OK
1016 | OK
1017 | OK
1018 | OK
1019 | OK
1020 | OK
1021 | OK
1022 | OK
1023 | OK
1024 | OK
1025 | OK
1026 | OK
1027 | OK
1028 | OK
1029 | OK
1030 | OK
1031 | OK
1032 | OK
1033 | OK
1034 | OK
1035 | OK
1036 | OK
1037 | OK
1038 | OK
1039 | OK
1040 | OK
1041 | OK
1042 | OK
1043 | OK
1044 | OK
1045 | OK
1046 | OK
1047 | OK
1048 | OK
1049 | OK
1050 | OK
1051 | OK
1052 | OK
1053 | OK
1054 | OK
1055 | OK
1056 | OK
1057 | OK
1058 | OK
1059 | OK
1060 | OK
1061 | OK
1062 | OK
1063 | OK
1064 | OK
1065 | OK
1066 | OK
1067 | OK
1068 | OK
1069 | OK
1070 | OK
1071 | OK
1072 | OK
1073 | OK
1074 | OK
1075 | OK
1076 | OK
1077 | OK
1078 | OK
1079 | OK
1080 | OK
1081 | OK
1082 | OK
1083 | OK
1084 | OK
1085 | OK
1086 | OK
1087 | OK
1088 | OK
1089 | OK
1090 | OK
1091 | OK
1092 | OK
1093 | OK
1094 | OK
1095 | OK
1096 | OK
1097 | OK
1098 | OK
1099 | OK
1100 | OK
1101 | OK
1102 | OK
1103 | OK
1104 | OK
1105 | OK
1106 | OK
1107 | OK
1108 | OK
1109 | OK
1110 | OK
1111 | OK
1112 | OK
1113 | OK
1114 | OK
1115 | OK
1116 | OK
1117 | OK
1118 | OK
1119 | OK
1120 | OK
1121 | OK
1122 | OK
1123 | OK
1124 | OK
1125 | OK
1126 | OK
1127 | OK
1128 | OK
1129 | OK
1130 | OK
1131 | OK
1132 | OK
1133 | OK
1134 | OK
1135 | OK
1136 | OK
1137 | OK
1138 | OK
1139 | OK
1140 | OK
1141 | OK
1142 | OK
1143 | OK
1144 | OK
1145 | OK
1146 | OK
1147 | OK
1148 | OK
1149 | OK
1150 | OK
1151 | OK
1152 | OK
1153 | OK
1154 | OK
1155 | OK
1156 | OK
1157 | OK
1158 | OK
1159 | OK
1160 | OK
1161 | OK
1162 | OK
1163 | OK
1164 | OK
1165 | OK
1166 | OK
1167 | OK
1168 | OK
1169 | OK
1170 | OK
1171 | OK
1172 | OK
1173 | OK
1174 | OK
1175 | OK
1176 | OK
1177 | OK
1178 | OK
1179 | OK
1180 | OK
1181 | OK
1182 | OK
1183 | OK
1184 | OK
1185 | OK
1186 | OK
1187 | OK
1188 | OK
1189 | OK
1190 | OK
1191 | OK
1192 | OK
1193 | OK
1194 | OK
1195 | OK
1196 | OK
1197 | OK
1198 | OK
1199 | OK
1200 | OK
1201 | OK
1202 | OK
1203 | OK
1204 | OK
1205 | OK
1206 | OK
1207 | OK
1208 | OK
1209 | OK
1210 | OK
1211 | OK
1212 | OK
1213 | OK
1214 | OK
1215 | OK
1216 | OK
1217 | OK
1218 | OK
1219 | OK
1220 | OK
1221 | OK
1222 | OK
1223 | OK
1224 | OK
1225 | OK
1226 | OK
1227 | OK
1228 | OK
1229 | OK
1230 | OK
1231 | OK
1232 | OK
1233 | OK
1234 | OK
1235 | OK
1236 | OK
1237 | OK
1238 | OK
1239 | OK
1240 | OK
1241 | OK
1242 | OK
1243 | OK
1244 | OK
1245 | OK
1246 | OK
1247 | OK
1248 | OK
1249 | OK
1250 | OK
1251 | OK
1252 | OK
1253 | OK
1254 | OK
1255 | OK
1256 | OK
1257 | OK
1258 | OK
1259 | OK
1260 | OK
1261 | OK
1262 | OK
1263 | OK
1264 | OK
1265 | OK
1266 | OK
1267 | OK
1268 | OK
1269 | OK
1270 | OK
1271 | OK
1272 | OK
1273 | OK
1274 | OK
1275 | OK
1276 | OK
1277 | OK
1278 | OK
1279 | OK
1280 | OK
1281 | OK
1282 | OK
1283 | OK
1284 | OK
1285 | OK
1286 | OK
1287 | OK
1288 | OK
1289 | OK
1290 | OK
1291 | OK
1292 | OK
1293 | OK
1294 | OK
1295 | OK
1296 | OK
1297 | OK
1298 | OK
1299 | OK
1300 | OK
1301 | OK
1302 | OK
1303 | OK
1304 | OK
1305 | OK
1306 | OK
1307 | OK
1308 | OK
1309 | OK
1310 | OK
1311 | OK
1312 | OK
1313 | OK
1314 | OK
1315 | OK
1316 | OK
1317 | OK
1318 | OK
1319 | OK
1320 | OK
1321 | OK
1322 | OK
1323 | OK
1324 | OK
1325 | OK
1326 | OK
1327 | OK
1328 | OK
1329 | OK
1330 | OK
1331 | OK
1332 | OK
1333 | OK
1334 | OK
1335 | OK
1336 | OK
1337 | OK
1338 | OK
1339 | OK
1340 | OK
1341 | OK
1342 | OK
1343 | OK
1344 | OK
1345 | OK
1346 | OK
1347 | OK
1348 | OK
1349 | OK
1350 | OK
1351 | OK
1352 | OK
1353 | OK
1354 | OK
1355 | OK
1356 | OK
1357 | OK
1358 | OK
1359 | OK
1360 | OK
1361 | OK
1362 | OK
1363 | OK
1364 | OK
1365 | OK
1366 | OK
1367 | OK
1368 | OK
1369 | OK
1370 | OK
1371 | OK
1372 | OK
1373 | OK
1374 | OK
1375 | OK
1376 | OK
1377 | OK
1378 | OK
1379 | OK
1380 | OK
1381 | OK
1382 | OK
1383 | OK
1384 | OK
1385 | OK
1386 | OK
1387 | OK
1388 | OK
1389 | OK
1390 | OK
1391 | OK
1392 | OK
1393 | OK
1394 | OK
1395 | OK
1396 | OK
1397 | OK
1398 | OK
1399 | OK
1400 | OK
1401 | OK
1402 | OK
1403 | OK
1404 | OK
1405 | OK
1406 | OK
1407 | OK
1408 | OK
1409 | OK
1410 | OK
1411 | OK
1412 | OK
1413 | OK
1414 | OK
1415 | OK
1416 | OK
1417 | OK
1418 | OK
1419 | OK
1420 | OK
1421 | OK
1422 | OK
1423 | OK
1424 | OK
1425 | OK
1426 | OK
1427 | OK
1428 | OK
1429 | OK
1430 | OK
1431 | OK
1432 | OK
1433 | OK
1434 | OK
1435 | OK
1436 | OK
1437 | OK
1438 | OK
1439 | OK
1440 | OK
1441 | OK
1442 | OK
1443 | OK
1444 | OK
1445 | OK
1446 | OK
1447 | OK
1448 | OK
1449 | OK
1450 | OK
1451 | OK
1452 | OK
1453 | OK
1454 | OK
1455 | OK
1456 | OK
1457 | OK
1458 | OK
1459 | OK
1460 | OK
1461 | OK
1462 | OK
1463 | OK
1464 | OK
1465 | OK
1466 | OK
1467 | OK
1468 | OK
1469 | OK
1470 | OK
1471 | OK
1472 | OK
1473 | OK
1474 | OK
1475 | OK
1476 | OK
1477 | OK
1478 | OK
1479 | OK
1480 | OK
1481 | OK
1482 | OK
1483 | OK
1484 | OK
1485 | OK
1486 | OK
1487 | OK
1488 | OK
1489 | OK
1490 | OK
1491 | OK
1492 | OK
1493 | OK
1494 | OK
1495 | OK
1496 | OK
1497 | OK
1498 | OK
1499 | OK
1500 | OK
1501 | OK
1502 | OK
1503 | OK
1504 | OK
1505 | OK
1506 | OK
1507 | OK
1508 | OK
1509 | OK
1510 | OK
1511 | OK
1512 | OK
1513 | OK
1514 | OK
1515 | OK
1516 | OK
1517 | OK
1518 | OK
1519 | OK
1520 | OK
1521 | OK
1522 | OK
1523 | OK
1524 | OK
1525 | OK
1526 | OK
1527 | OK
1528 | OK
1529 | OK
1530 | OK
1531 | OK
1532 | OK
1533 | OK
1534 | OK
1535 | OK
1536 | OK
1537 | OK
1538 | OK
1539 | OK
1540 | OK
1541 | OK
1542 | OK
1543 | OK
1544 | OK
1545 | OK
1546 | OK
1547 | OK
1548 | OK
1549 | OK
1550 | OK
1551 | OK
1552 | OK
1553 | OK
1554 | OK
1555 | OK
1556 | OK
1557 | OK
1558 | OK
1559 | OK
1560 | OK
1561 | OK
1562 | OK
1563 | OK
1564 | OK
1565 | OK
1566 | OK
1567 | OK
1568 | OK
1569 | OK