## MAIN
Republic of the Philippines PROVINCIAL GOVERNMENT OF PALAWAN Office of the Provincial Engineer Capitol Complex, Puerto Princesa City, Palawan
Physical Accomplishment Report
FY 2024 Fourth Quarterly Report
NO. | PROVINCIAL GOVERNMENT OF PALAWAN PROJECT NAME | PROJECT ID | PPDO CATEGORY | PROJECT DESCRIPTION | LOCATION | MUNICIPALITY | IMPLEMENTING OFFICE | YEAR | SOURCE OF FUND | PROJECT COST | CONTRACT COST | C.D | NTP DATE | NO. OF EXTENSION | TARGET COMPLETION DATE | REVISED COMPLETION DATE | DATE COMPLETED | AS OF DECEMBER 2024 | TOTAL COST INCURED TO DATE | MODE OF PROCUREMENT | GENERAL REMARKS | PROJECT CONTRACTOR | TIN NUMBER | REASON
1 | Concreting of So. Tagbarasan Bgy. Sagpangan FMR |  | Transportation Facilities | Construction 2 barrel RCBC = 2 units - PCCP L=740m - w=5m - T=0.2m (Station 0+000 to 0+250, Sta. 3+300 - 3+830 | Bgy. Sagpangan | Aborlan | PEO | 2014 | Department of Agriculture | 7700000 |  | 150 | [5 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
2 | Concreting of Sto. Tomas FMR, Sto. Tomas-Maningning-New Rizal, Dumarao | TF 416 DA FMR 15-104 | Transportation Facilities |  | Bgy. Dumarao | Roxas | PEO | 2014 | Department of Agriculture | 7700000 | 7486991.48 | 150 | 2015-07-14 |  | 2015-12-11 |  |  |  |  | By contract | For Termination | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Legal Endorsement
3 | Concreting of Marcilla Road (intermittent Section) |  | Transportation Facilities |  |  | Coron | PEO | 2014 | Department of Agriculture | 5000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
4 | Concreting of Kaybulusan-Decala Rd. w/ 2 Barrel Box Culvert, Bgy. Caruray | TF 416 DILG PCF 2014-16-001 | Transportation Facilities | PCCP L=1020m - W=5.00m - T=0.20m - Shoulder: 1.50m bothsides - 2 barrel box culvert = 6.00m x 5.00m | Bgy. Caruray | San Vicente | PEO | 2014 | Performance Challenge Fund | 7000000 | 6980434.55 | 140 | 2016-10-23 |  | 2017-03-12 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
5 | Rehabilitation of Sandoval Water System, Bgy. Sandoval & Minara |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Sandoval & Minara | Roxas | PEO | 2014 | 20% Development Fund | 4300000 | [7 empty] | 100% |  | By Admin | Completed | By Admin
6 | Improvement of Pamantolon Water System, Bgy. Pamantolon & Poblacion |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Pamantolon & Poblacion | Taytay | PEO | 2014 | 20% Development Fund | 6600000 | [7 empty] | 100% |  | By Admin | Completed | By Admin
7 | Improvement of Puntabaja Water System , Puntabaja |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Punta Baja, Rizal | Rizal | PEO | 2014 | 20% Development Fund | 4800000 | [7 empty] | 100% |  | By Admin | Completed | By Admin
8 | Concreting of Junction National Highway- Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2014 | 20% Development Fund | 3026800 | 2967671.01 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
9 | Concreting of Junction National Highway - Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2014 | 20% Development Fund | 3007873.46 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
10 | Construction of 4CL Building, PSU Rizal |  | Educational Facilities | 4 Classroom School Building | PSU Rizal | Rizal | PEO | 2014 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
11 | Construction of 2CL Building, Nangalao National High School |  | Educational Facilities | 2 Classroom School Building | Nangalao National High School | Linapacan | PEO | 2014 | 20% Development Fund | 1000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
12 | Construction of 2CL Building, Tarumpitao Point Elementary School, Punta Baja |  | Educational Facilities | 2 Classroom School Building | Punta Baja, Rizal | Rizal | PEO | 2014 | 20% Development Fund | 1000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
13 | Road Repair in Cagayancillo |  | Transportation Facilities |  |  | Cagayancillo | PEO | 2014 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
14 | Road Concreting in Agutaya |  | Transportation Facilities |  | Municipality of Agutaya | Agutaya | PEO | 2014 | 20% Development Fund | 1000000 | 965836.63 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
15 | Magsaysay/Cuyo Circumferential Road Concreting |  | Transportation Facilities |  |  | Magsaysay | PEO | 2014 | 20% Development Fund | 2000000 | 1975820.87 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
16 | Road Concreting Binudac |  | Transportation Facilities |  |  | Culion | PEO | 2014 | 20% Development Fund | 1000000 | 965292.13 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
17 | Construction of Wooden Bridge, Bgy. Sto. Niño |  | Transportation Facilities |  | Bgy. Sto. Niño, San Vicente | San Vicente | PEO | 2014 | 20% Development Fund | [8 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
18 | Construction of Detour & Rehabilitation of Tumarbong Bridge |  | Transportation Facilities |  |  | Roxas | PEO | 2014 | 20% Development Fund | 668747.78 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
19 | Redecking of Caruray Bridge |  | Transportation Facilities |  | Bgy. Caruray, San Vicente | San Vicente | PEO | 2014 | 20% Development Fund | 70000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
20 | Repair of Ilian Hanging Bridge |  | Transportation Facilities |  | Bgy. Ilian, Dumara, | Dumaran | PEO | 2014 | 20% Development Fund | 254200 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
21 | Construction of 1CL Building, Nangalao Pre-School |  | Educational Facilities | 1 Classroom School Building | Bgy. Nangalao | Linapacan | PEO | 2014 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
22 | Dr. Jose Rizal District Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2014 | DOH-Trust Fund | 49000000 | 48997422.62 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
23 | Coron District Hospital Rehabilitation/Improvement of Facilities |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2014 | DOH-Trust Fund | 4000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
24 | Construction of NPPH Additional Facility (Isolation Building) |  | Medical Facilities |  | Bgy. Poblacion | Taytay | PEO | 2014 | DOH-Trust Fund | 3000000 | 2997801.43 | 165 | 2017-11-20 |  | 2018-05-04 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
25 | Improvement of Northern Palawan Provincial Hospital (Construction of Motorpool/COOP Store/Storage)Phae I |  | Medical Facilities |  | Bgy. Poblacion | Taytay | PEO | 2014 | DOH-Trust Fund | 2000000 | 1995919.14 | 90 | 2017-11-20 |  | 2018-02-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
26 | Expansion of Barangay Health Station Batang-batang |  | Medical Facilities |  | Bgy. Batang-batang | Narra | PEO | 2014 | DOH - HFEP | 666666.66 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
27 | Expansion of Barangay Health Station Caguisan |  | Medical Facilities |  | Bgy. Caguisan | Narra | PEO | 2014 | DOH - HFEP | 666666.66 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
28 | Expansion of Barangay Health Station Elvita |  | Medical Facilities |  | Bgy. Elvita | Narra | PEO | 2014 | DOH - HFEP | 666666.66 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
29 | Expansion of Barangay Health Station Bemonc ,Calumpang |  | Medical Facilities |  | Bgy. Calumpang | Quezon | PEO | 2014 | DOH - HFEP | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
30 | Expansion of Barangay Health Station Bemonc,Isugod |  | Medical Facilities |  | Bgy. Isugod | Quezon | PEO | 2014 | DOH - HFEP | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
31 | Expansion of Barangay Health Station Bemonc,Panitian |  | Medical Facilities |  | Bgy. Panitian | Quezon | PEO | 2014 | DOH - HFEP | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
32 | Aborlan Medicare Hospital |  | Medical Facilities |  |  | Aborlan | PEO | 2014 | DOH - HFEP | 31384000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
33 | Narra Municipal Hospital |  | Medical Facilities |  | Narra Municapal Hospital | Narra | PEO | 2014 | DOH - HFEP | 10000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
34 | Quezon Municipal Hospital |  | Medical Facilities |  | QuezonMedicare Hospital | Quezon | PEO | 2014 | Trust Fund - DOH | 8000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
35 | Coron District Hospital |  | Medical Facilities |  |  | Coron | PEO | 2014 | DOH - HFEP | 49000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
36 | Cuyo District Hospital |  | Medical Facilities |  | Cuyo, Palawan | Cuyo | PEO | 2014 | DOH - HFEP |  | 26362962.68 | 380 | 2016-11-03 |  | 2017-11-18 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
37 | Roxas Medical Hospital |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2014 | DOH - HFEP | 12300000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
38 | Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2014 | Trust Fund -DOH | 10999080 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
39 | Site Development, Road Concreting and Construction of NHA Yolanda Housing Units | B2 TF 416 NHA CONST OF NHA YOLANDA HOUSING UNIT 17-250 | Other Facilities |  | Bgy. Binudac, Bgy. Galoc, Bgy. Baldat | Culion | PEO | 2014 | NHA Fund | 194700000 | 194699088.21 | 360 | 2018-09-05 |  | 2019-08-31 | 2023-01-21 |  | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
40 | Concreting of Barangay Road of Sitio Sader, Bgy. Bantulan | ROAD 300-15-08-12075 | Transportation Facilities |  | Sitio Sader, Bgy. Bantulan, Taytay | Taytay | PEO | 2015 | 20% Development Fund | 1000000 | 987653.71 | 60 | 2015-10-12 |  | 2015-12-11 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
41 | Construction of Mauringen Barangay Health Station |  | Medical Facilities |  | Bgy. Mauringen | Araceli | PEO | 2015 | 20% Development Fund and DOH | 500000 | 500000 | [8 empty] | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
42 | Construction of Banbanan Barangay Health Station | TF 416 DOH -15-118 | Medical Facilities | 6.50m (w) x 9.00 m (l) Single Storey Building complete with CR and Electrical | Bgy. Banbanan | Taytay | PEO | 2015 | TF - DOH HFEP 2014 | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
43 | Construction of Calawag Barangay Health Station | TF 416 DOH -15-117 | Medical Facilities | 6.50m (w) x 9.00 m (l) Single Storey Building complete with CR and Electrical | Bgy. Calawag | Taytay | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
44 | Construction of 4 units Multi-purpose Bldg. in Gaudencio Abordo Mem. NHS, Agutaya, Palawan |  | Other Infrastructure |  | Gaudencio Abordo Memorial National High School | Agutaya | PEO | 2015 | 20% Development Fund | 2540000 | [9 empty] | By contract | For Validation | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | For Validation: Cancelled
45 | Construction of Multi-Purpose Bldg. in So. Kadulan, Panalingaan, Rizal |  | Other Infrastructure |  | So. Kadulan, Panalingaan, Rizal | Rizal | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
46 | Construction of Multi-Purpose Cumahos Elementary School, Panalingaan |  | Other Infrastructure |  | Bgy. Panalingaan | Rizal | PEO | 2015 | 20% Development Fund | 2140000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
47 | Construction of Multi-Purpose Bldg., Calawag National High School |  | Other Infrastructure |  | Bgy. Calawag, Taytay, Palawan | Taytay | PEO | 2015 | 20% Development Fund | 1605000 | 1553062.08 | 100 | 2015-11-17 |  | 2016-02-25 |  |  |  |  | By contract | For Validation | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Validation: Cancelled
48 | Construction of Bebeledan Barangay Health Station |  | Medical Facilities |  | Bgy. Bebeledan | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
49 | Construction of Bucana Barangay Health Station |  | Medical Facilities |  | Bgy. Bucana | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
50 | Construction of Mabini Barangay Health Station |  | Medical Facilities |  | Bgy. Mabini | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
51 | Construction of Teneguiban Barangay Health Station |  | Medical Facilities |  | Bgy. Teneguiban | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
52 | Construction of Villa Paz Barangay Health Station |  | Medical Facilities |  | Bgy. Paz | El Nido | PEO | 2015 | 20% Development Fund and DOH | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
53 | Construction of Jolo Barangay Health Station |  | Medical Facilities |  | Bgy. Jolo | Roxas | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
54 | Construction of Tumarbong Barangay Health Station |  | Medical Facilities |  | Bgy. Tumarbong | Roxas | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
55 | Construction of Caramay Barangay Health Station | TF 416 DOH -15 - 121 | Medical Facilities |  | Bgy. Caramay | Roxas | PEO | 2015 | 20% Development Fund and DOH | 1000000 | 964050.66 | 90 | 2015-09-11 |  | 2015-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
56 | Construction of Multi-purpose Bldg. Agutaya Phase 3 |  | Other Infrastructure |  | Municipality of Agutaya | Agutaya | PEO | 2015 | 20% Development Fund | 2000000 | 2000000 | [8 empty] | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
57 | Construction of Motorpool |  | Other Facilities |  |  | Rizal | PEO | 2015 | 20% Development Fund | 6900000 | 6637160.49 | 130 | 2016-09-16 |  | 2017-01-24 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
58 | Construction of Motorpool Brooke's Point |  | Other Facilities |  | Bgy. Pangobilian, Brooke's Point | Brooke's Point | PEO | 2015 | 20% Development Fund | 6900000 | [7 empty] | 100% |  | By contract | Completed | Jas Trading and Construction
59 | Construction of Motorpool Phase II, Irawan |  | Other Facilities |  | Bgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 5000000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
60 | Concreting of Road of Roxas Medicare Hospital | ROAD 300-15-09-13154 | Transportation Facilities |  | Barangay III, Roxas, Palawan | Roxas | PEO | 2015 | 20% Development Fund | 500000 | 497887.18 | 30 | 2016-02-04 |  | 2016-03-05 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
61 | Concreting of Road Towards Elnido Medicare Hospital |  | Transportation Facilities |  | Elnido Medicare Hospital | El Nido | PEO | 2015 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
62 | Concreting of Road towards Rizal Municipal/PGP Motorpool |  | Transportation Facilities |  | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2015 | 20% Development Fund | 5000000 | 3501330.96 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
63 | Concreting of Roads towards PGP Motorpool, Irawan |  | Transportation Facilities |  | Bgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 2000000 | 1910798.55 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
64 | Concreting of Circumferential Road, Magsaysay - Cuyo |  | Transportation Facilities |  |  | Magsaysay | PEO | 2015 | 20% Development Fund | 3500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
65 | Concreting of Cagayancillo Circumferential Road | ROAD 300-15-05-07193 | Transportation Facilities | PCCP L=885m - W=2m - T=0.15m : Shoulder=1.00m bothsides - One (1) Lane PCCP | Cagayancillo, Palawan | Cagayancillo | PEO | 2015 | 20% Development Fund | 2000000 | 1975497.2 | 60 | 2015-11-16 |  | 2016-01-15 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
66 | Concreting of Suba - Pawa 2.5m with 2nd Lane, Cuyo |  | Transportation Facilities |  | Cuyo | Cuyo | PEO | 2015 | 20% Development Fund | 2000000 | 1965054.26 | [6 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
67 | Concreting of Zabanal Road, San Vicente |  | Transportation Facilities |  |  | San Vicente | PEO | 2015 | 20% Development Fund | 5000000 | 4995752.1 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
68 | Concreting of Road Bgy. Liminangcong, Taytay |  | Transportation Facilities |  |  | Taytay | PEO | 2015 | 20% Development Fund | 3500000 | 3234305.76 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
69 | Concreting of Road of Bgy. Aramaywan, Narra |  | Transportation Facilities |  | Bgy. Aramaywan | Narra | PEO | 2015 | 20% Development Fund | 1500000 | 1480746.01 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
70 | Concreting of Dumaran Road, Dumaran |  | Transportation Facilities |  | Dumaran | Dumaran | PEO | 2015 | 20% Development Fund | 2000000 | 1908041.04 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
71 | Concreting of Bgy. Road, Minara, Roxas |  | Transportation Facilities |  | Bgy. Minara | Roxas | PEO | 2015 | 20% Development Fund | 640000 | 633860.25 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
72 | Concreting of Bgy. Road, Bgy. Calawag, Taytay |  | Transportation Facilities |  | Bgy. Calawag, Taytay | Taytay | PEO | 2015 | 20% Development Fund | 2424000 | 2360130.36 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
73 | Construction of Detour Road w/ Spillway, Taradungan,Roxas |  | Transportation Facilities |  | Bgy. Taradungan | Roxas | PEO | 2015 | 20% Development Fund | 8000000 | 7861836.42 | [6 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
74 | Construction of Multipurpose Bldg., Underground ES, Alfonso XIII, Quezon |  | Other Infrastructure |  | Bgy. XIII | Quezon | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
75 | Construction of Multipurpose Bldg., Tarumpitao ES, Rizal |  | Other Infrastructure |  | Tarumpitao ES, Rizal | Rizal | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
76 | Construction of Multipurpose Bldg., Aplaya ES, Aborlan |  | Other Infrastructure |  | Aplaya ES, Aborlan | Aborlan | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
77 | Construction of Multipurpose Bldg., Aramaywan II ES, Aramaywan, Narra |  | Other Infrastructure |  | Bgy. Aramaywan | Narra | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
78 | Const. of Bahay Kubo w/ Fencing in PJMD, Bancao2 PPC |  | Other Facilities |  | Bgy. Bancao | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 338000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
79 | Const. of KILN in PJMD Annex Bldg., Banca-bancao, PPC |  | Other Facilities |  | Banca-bancao, PPC | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 300000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
80 | Const. of PEPO Bunkhouse Quarters, Irawan |  | Other Facilities |  | Bgy. Irawan | Puerto Princesa City | PEO | 2015 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | Jas Trading and Construction
81 | Rehabilitation of Narra Gymnasium |  | Other Facilities |  | Bgy. Narra | Narra | PEO | 2015 | 20% Development Fund | 2500000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
82 | Const. of Perimeter Fence of SPPH, Brooke's Point |  | Medical Facilities |  | SPPH, Brooke's Point | Brooke's Point | PEO | 2015 | 20% Development Fund | 1500000 | [7 empty] | 100% |  | By contract | Completed | Jas Trading and Construction
83 | Const. of Perimeter Fence of Roxas Medicare Hospital | ROAD 300-15-08-12073 | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2015 | 20% Development Fund | 1600000 | 1434227.27 | 75 | 2016-02-01 |  | 2016-04-16 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
84 | Const. of Seawall Protection, Bgy. Rizal, Roxas |  | Ports and Airports |  | Bgy. Rizal, Roxas | Roxas | PEO | 2015 | 20% Development Fund | 1800000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
85 | Improvement of Agutaya Sea Port, Agutaya, Palawan |  | Ports and Airports |  | Municipality of Agutaya | Agutaya | PEO | 2015 | 20% Development Fund | 988000 | 987358.13 | [6 empty] | 100% |  | By contract | Completed
86 | Const. of Boat Landing in New Guinlo, Taytay |  | Ports and Airports |  | New Guinlo | Taytay | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
87 | Const. of Boat Landing in Old Guinlo, Taytay |  | Ports and Airports |  | Old Guinlo | Taytay | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
88 | Construction of Water System Project Phase I, Bantulan | B2 ROADS 300-15-05-06875 | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Bantulan | Taytay | PEO | 2015 | 20% Development Fund | 8900000 |  |  | 2017-01-04 |  | 2017-01-04 |  |  | 100% |  | By contract | Completed | Atlanta Construction Company Inc.
89 | Construction of Barangay Health Station, Bagong Bayan |  | Medical Facilities |  | Bagong Bayan, El Nido | El Nido | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
90 | San Vicente Barangay Health Station, Caruray |  | Medical Facilities |  | Caruray, San Vicente | San Vicente | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
91 | San Vicente Barangay Health Station, Alimanguan |  | Medical Facilities |  | Alimanguan, San Vicente | San Vicente | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
92 | Sofronio Española Rural Health Unit |  | Medical Facilities |  |  | Sofronio Española | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
93 | Samareñana Barangay Health Station |  | Medical Facilities |  |  | Brooke's Point | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
94 | Magbabadil Barangay Health Station |  | Medical Facilities |  |  | Aborlan | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
95 | Narra Rural Health Unit |  | Medical Facilities |  |  | Narra | PEO | 2015 | 20% Development Fund | 500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
96 | Construction of Barangay Health Station, Bgy. Mendoza, Roxas | B2 BFIP 300-16-10-14515-14516 (Construction of Barangay Health Station at Bgy. Nicanor Zabala and Bgy. Mendoza, Roxas, Palawan) | Medical Facilities |  | Bgy. Mendoza, Roxas | Roxas | PEO | 2015 | 20% Development Fund | 1000000 | 992639.37 | 150 | 2017-01-16 |  | 2017-06-15 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
97 | Construction of Barangay Health Station ,Bgy Nicanor Zabala,Roxas | B2 BFIP 300-16-10-14515-14516 (Construction of Barangay Health Station at Bgy. Nicanor Zabala and Bgy. Mendoza, Roxas, Palawan) | Medical Facilities |  | Bgy. Nicanor Zabala,Roxas | Roxas | PEO | 2015 | 20% Development Fund | 1000000 | 992639.37 | 150 | 2017-01-16 |  | 2017-06-15 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
98 | Construction of Barangay Hall in Bato-Bato, Narra |  | Other Facilities |  | Bato-Bato, Narra | Narra | PEO | 2015 | 20% Development Fund | 1800000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
99 | Construction of 4 units Multi-Purpose Bldg in Mendoza NHS, Mendoza, Roxas |  | Other Infrastructure |  | Mendoza, Roxas | Roxas | PEO | 2015 | 20% Development Fund | 2140000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
100 | Construction of 2 units Multi-Purpose Building in Mabini ES, Aborlan |  | Other Infrastructure |  | Mabini ES, Aborlan | Aborlan | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
101 | Construction of 2 units Multi-Purpose Building in Labangan ES, Bgy. Bunog, Rizal |  | Other Infrastructure |  | Labangan Elementary School, Bgy. Bunog, Rizal | Rizal | PEO | 2015 | 20% Development Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
102 | Rehabilitation of Saraza Bridge ( Tagbalogo-Saraza Road) Brooke's Point |  | Transportation Facilities |  | Bgy. Brooke's | Brooke's Point | PEO | 2015 | 20% Development Fund | 880000 | 852413.86 | [6 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
103 | Repair of Inalyawan Bailey Bridge (Cataban - Limininangcong Rd. ) |  | Transportation Facilities |  |  | Taytay | PEO | 2015 | 20% Development Fund | 250000 | 249269.92 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
104 | Installation of 1 line - 24" RCPC with concrete headwall ( Bagong Sikat Line 8 Rd. ), Narra |  | Other Infrastructure |  |  | Narra | PEO | 2015 | 20% Development Fund | 50000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
105 | Installation of 1 line - 36" RCCP with concrete headwall ( Sumbiling-Canipaan Rd. ) |  | Other Infrastructure |  |  | Bataraza | PEO | 2015 | 20% Development Fund | 80000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
106 | Installation of 3 lines - 36" RCCP serve as detour for Impatian Bridge ( Paglaum - Itangil Rd. ), Dumaran |  | Other Infrastructure |  |  | Dumaran | PEO | 2015 | 20% Development Fund | 120000 | 112443.4 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
107 | Installation of 1 line (22pcs) - 36" RCCP with concrete headwall ( Plaridel-Apis-Cabigaan Rd. ), Aborlan |  | Other Infrastructure |  |  | Aborlan | PEO | 2015 | 20% Development Fund | 130000 | 128595.94 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
108 | Installation of 6 lines - 24" RCCP with concrete headwall ( Itangil-Magsaysay-Culasian Rd. ), Dumaran |  | Other Infrastructure |  |  | Dumaran | PEO | 2015 | 20% Development Fund | 199168 | 188097.09 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
109 | Concreting of Taritien, Narra - Farm to Market Road |  | Transportation Facilities |  | Narra | Narra | PEO | 2015 | 20% Development Fund | 6470000 | 6412611.41 | [6 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
110 | Construction of RCDG, Kaybulusan Bridge, Purok Masigla, Magara, Roxas |  | Transportation Facilities |  | Bgy. Magara | Roxas | PEO | 2015 | Locally Funded | 4150000 | [7 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
111 | Construction of RCDG, Malebeb Bridge, Purok Masigla, Magara, Roxas |  | Transportation Facilities |  | Bgy. Magara | Roxas | PEO | 2015 | Locally Funded | 3420000 | [7 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
112 | Concreting of Barangay Road, Magara |  | Transportation Facilities |  |  | Roxas | PEO | 2015 | Locally Funded | 1000000 | 987317.01 | [6 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
113 | Repair of Footbridge in Bgy. Silanga |  | Transportation Facilities |  | Bgy. Silanga | Taytay | PEO | 2015 | Locally Funded | 600000 | 600000 | [8 empty] | By contract | For Termination
114 | Concreting of Road from 570th to Main Gate of WESCOM (Golf Course Side) |  | Transportation Facilities |  |  | Puerto Princesa City | PEO | 2015 | Locally Funded | 1900000 | 1900000 | [8 empty] | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
115 | Construction of 2CL Sch. Building in Manamoc ES, Manamoc | ROAD 300-15-08-11724 | Educational Facilities | 2 Classroom School Building | Bgy. Manamoc | Cuyo | PEO | 2015 | Locally Funded | 1270000 | 1226903.21 | 70 | 2015-10-23 |  | 2016-01-01 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
116 | Rehabilitation and Improvement of Capitol Building and Facilities |  | Other Facilities |  | Bgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 7288773 | [7 empty] | 100% |  | By contract | Completed
117 | Improvement of Boat Landing in Banbanan |  | Ports and Airports |  | Bgy. Banbanan | Taytay | PEO | 2015 | Locally Funded | 150000 | [7 empty] | 100% |  | By contract | Completed | EM Paule Construction and Trading
118 | Construction of Fence of PNP Headquarters - Provincial Police Office in Tiniguiban |  | Other Facilities |  | Bgy. Tiniguiban | Puerto Princesa City | PEO | 2015 | Locally Funded | 490000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
119 | Construction of 2 CL School building in Libertad ES Elementary School | SB1 300-15-12-20595 | Educational Facilities | 2 CL - No. of Storey: 1 storey: Floor area: 18.0mx7.0m: Hallway: 18.0m x 1.2m: Type of Truss: Steel Truss | Libertad ES Elementary School | Taytay | PEO | 2015 | Special Education Fund | 1070000 | 1064474.36 | 70 | 2016-03-11 |  | 2016-05-20 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
120 | Construction of 2CL School Building in Agutayan Elementary School |  | Educational Facilities | 2 Classroom School Building | Agutayan Elementary School | Balabac | PEO | 2015 | Special Education Fund | 1270000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
121 | Construction of 2CL School Building in Antipuluan Elementary School |  | Educational Facilities | 2 Classroom School Building | Antipuluan Elementary School | Narra | PEO | 2015 | Special Education Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
122 | Construction of 2CL School Building in Cabuluan Elementary School |  | Educational Facilities | 2 Classroom School Building | Cabuluan Elementary School | Narra | PEO | 2015 | Special Education Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
123 | Construction of 4CL School Building in Tagpait Elementary School |  | Educational Facilities | 4 Classroom School Building | Tagpait Elementary School | Aborlan | PEO | 2015 | Special Education Fund | 2140000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
124 | Construction of 3CL School Building in Pinaglabanan Elementary School |  | Educational Facilities | 3 Classroom School Building | Pinaglabanan Elementary School | Quezon | PEO | 2015 | Special Education Fund | 1605000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
125 | Construction of 2CL School Building in Pinuwasan Elementary School |  | Educational Facilities | 2 Classroom School Building | Pinuwasan Elementary School | Bataraza | PEO | 2015 | Special Education Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
126 | Construction of 2CL School Building in Rafael R. Estiandan Elementary School |  | Educational Facilities | 2 Classroom School Building | Rafael R. Estiandan Elementary School | Brooke's Point | PEO | 2015 | Special Education Fund | 1070000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
127 | Construction of 3CL School Building in Mainit Elementary School |  | Educational Facilities | 3 Classroom School Building | Mainit Elementary School | Brooke's Point | PEO | 2015 | Special Education Fund | 1605000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
128 | Construction of 4CL School Building in Linapacan Elementary School |  | Educational Facilities | 4 Classroom School Building | Linapacan Elementary School | Linapacan | PEO | 2015 | Special Education Fund | 2540000 | 2359957.11 | 200 | 2016-01-05 |  | 2016-07-23 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
129 | Construction of 2 Classroom School Building in Balala Elementary School |  | Educational Facilities | 2 Classroom School Building | Bgy. Balala | Culion | PEO | 2015 | Locally Funded | 1070000 | 1070000 | [8 empty] | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
130 | Construction of Evacuation Center/Multi-Purpose Bldg., Cagayancillo, Palawan |  | Other Infrastructure |  |  | Cagayancillo | PEO | 2015 | Locally Funded | 2738000 | 2738000 | [8 empty] | By contract | For Termination | EM Paule Construction and Trading
131 | Construction of Agutaya Multi-purpose |  | Other Infrastructure |  | Municipality of Agutaya | Agutaya | PEO | 2015 | Trust Fund- Cong. Alvarez | 2970000 | [9 empty] | By contract | On going
132 | Construction of Roxas Multi-Purpose Building |  | Other Infrastructure |  |  | Roxas | PEO | 2015 | Trust Fund- Cong. Alvarez | 4950000 | [9 empty] | By contract | Subject for Reversion
133 | Construction of Pre-fabrication Office Building of Western Command Camp, Tiniguiban, PPC |  | Other Facilities |  | Tiniguiban, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 400000 | 400000 | [8 empty] | By contract | For Termination
134 | Construction of PSWD Building, Puerto Princesa City |  | Other Facilities |  | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 3000000 | 3000000 | [8 empty] | By contract | For Termination
135 | Construction of Material Recovery Facilities Building |  | Medical Facilities |  | Narra Municapal Hospital | Narra | PEO | 2015 | DBP Loan | 600000 | 586100.28 | [6 empty] | 100% |  | By contract | Completed
136 | Construction of Dietary & Linen Building |  | Medical Facilities |  | Narra Municapal Hospital | Narra | PEO | 2015 | DBP Loan | 2490085.72 | [7 empty] | 100% |  | By contract | Completed
137 | Construction of Isolation Building |  | Medical Facilities |  | Narra Municapal Hospital | Narra | PEO | 2015 | DBP Loan | 2402013.62 | [7 empty] | 100% |  | By contract | Completed
138 | Upgrading of Itangil Bailey Bridge to RCDG Bridge |  | Transportation Facilities |  | Bgy. Itangil | Dumaran | PEO | 2015 | PCF 2015 (DILG) | 7000000 | 6987806.15 | [6 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
139 | Construction of Dietary & Linen Building |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2015 | DBP Loan | 2500000 | [7 empty] | 100% |  | By contract | Completed
140 | Construction of Doctor's Quarter |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2015 | DBP Loan | 4500000 | [7 empty] | 100% |  | By contract | Completed
141 | Construction of Roxas Medicare Hospital (Main Building) Phaase II |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2015 | DOH | 6300000 | [7 empty] | 100% |  | By contract | Completed
142 | Construction of 3CL School Building in Mangsee Elementary School |  | Educational Facilities | 3 Classroom School Building | Bgy. Mangsee | Balabac | PEO | 2015 | Special Education Fund | 1905000 | [9 empty] | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
143 | Construction of 3CL School Building Paliisan Elementary School |  | Educational Facilities | 3 Classroom School Building | Bgy. Paliisan | Balabac | PEO | 2015 | Special Education Fund | 1905000 |  |  | 2018-01-10 |  | 2018-01-10 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
144 | Construction of Palawan People Technology Vocational University, Bgy. Plaridel |  | Educational Facilities |  | Bgy. Plaridel | Aborlan | PEO | 2015 | Locally Funded | 17762000 | [9 empty] | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
145 | Rehabilitation and Improvement of Gov. Office and mini conference room and Facilities |  | Other Facilities |  | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 1367300 | [9 empty] | By contract | Terminated
146 | Rehabilitation and Improvement of centenial pavillion and stage |  | Other Facilities |  | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 733500 | [9 empty] | By contract | Terminated
147 | Rehabilitation and Improvement of Gov. Conference Room and Facilities |  | Other Facilities |  | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 648574 | [9 empty] | By contract | Terminated
148 | Rehabilitation and Improvement of the 2nd Floor left wing , Capitol Bldg. |  | Other Facilities |  | Bgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2015 | Locally Funded | 2061970 | [9 empty] | By contract | Terminated
149 | Construction of Slaking & Storage Facilities |  | Medical Facilities |  |  | Quezon | PEO | 2015 | Locally Funded | 199900 | [7 empty] | 100% |  | By contract | Completed
150 | Renovation/Improvement of PNP Academic & Transient Bldg., Tiniguiban |  | Other Facilities |  | Bgy. Tiniguiban | Puerto Princesa City | PEO | 2015 | Locally Funded | 3620351 | 3620351 | [8 empty] | By contract | For Termination
151 | Construction of Southern Palawan Provincial Hospital |  | Medical Facilities |  | Bgy. Pangobilian, Brooke's Point, Palawan | Brooke's Point | PEO | 2015 | DBP Loan | 44410000 | [7 empty] | 100% |  | By contract | Completed
152 | Construction of Dietary & Linen Building |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 2490085.71 | [7 empty] | 100% |  | By contract | Completed
153 | Construction of Isolation Building |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 2402013.62 | [7 empty] | 100% |  | By contract | Completed
154 | Construction of Doctor's Quarter |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 4405153.15 | [7 empty] | 100% |  | By contract | Completed
155 | Construction of Material Recovery Facilities Building |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 586100.28 | [7 empty] | 100% |  | By contract | Completed
156 | Construction of Mortuary Building |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 778374.63 | [7 empty] | 100% |  | By contract | Completed
157 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 1507888.49 | [7 empty] | 100% |  | By contract | Completed
158 | Construction of Circular Elevated Water Tank |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2015 |  | 480869.63 | [7 empty] | 100% |  | By contract | Completed
159 | Upgrading of Villa Constancia Bailey Bridge to RCDG | ROAD 300-16-06-05893 | Transportation Facilities |  | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 7320000 | 7169578.6 | 210 | 2016-03-11 |  | 2016-10-07 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
160 | Upgrading of Ariman-an Bailey Bridge to RCDG | ROAD 300-16-06-05891 | Transportation Facilities |  | Bgy. Talog | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4553792.92 | 120 | 2016-11-18 |  | 2017-03-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
161 | Upgrading of Impatian Bailey Bridge I to RCDG | ROAD 300-16-06-05894 | Transportation Facilities |  | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4606459.03 | 120 | 2016-11-18 |  | 2017-03-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
162 | Upgrading of Impatian Bailey Bridge II to RCDG | ROAD 300-16-06-07511 | Transportation Facilities |  | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 6000000 | 5910060.61 | 120 | 2016-09-19 |  | 2017-01-17 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
163 | Upgrading of Tagumpay Bailey Bridge III to RCDG | ROAD 300-16-06-05890 | Transportation Facilities |  | Bgy. Sta. Maria | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4710678.74 | 120 | 2016-11-18 |  | 2017-03-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
164 | Upgrading of Sta. Maria Bailey Bridge 1 to RCDG (Length = 12.70lm) | B2 BFIP 300-16-11-15237 | Transportation Facilities |  | Bgy. Sta. Maria | Dumaran | PEO | 2016 | 20% Development Fund | 4800000 | 4721144.63 | 120 | 2017-03-07 |  | 2017-07-05 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
165 | Upgrading of Caruray Bailey Bridge to RCDG (Length = 15.24 lm) |  | Transportation Facilities |  |  | San Vicente | PEO | 2016 | 20% Development Fund | 6000000 | [9 empty] | By contract | For Validation | A.P. Consebido Construction & Trading | TIN 931-421-496
166 | Construction of Barangay Health Station in Sitio Lamud, Bgy. Luac | B2 BFIP 300-16-1-16176-166177 | Medical Facilities |  | Bgy. Luac | Culion | PEO | 2016 | 20% Development Fund | 1500000 | 1491336 | 150 | 2017-03-08 |  | 2017-08-05 |  | 2022-11-05 | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
167 | Construction of Multi-purpose Building in Bgy. Poblacion |  | Other Infrastructure |  | Bgy. Poblacion | El Nido | PEO | 2016 | 20% Development Fund | 2500000 | 2497989.47 | [8 empty] | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
168 | Repair of VEP Powerhouse |  | Power and Energy Development Program |  | Bisucay | Cuyo | PEO | 2016 | 20% Development Fund-Savings | 409504.09 | 407517.25 | 30 | [5 empty] | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
169 | Concreting of Malapandeg - Rancho Road (Intermittent Section) |  | Transportation Facilities |  |  | Rizal | PEO | 2016 | 20% Development Fund | 2800000 | 2793289.78 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
170 | Concreting of Critical Sections of Highway Junction - Taradungan Road | B2 BFIP 300-16-11-15239 | Transportation Facilities |  | Tumarbong and Taradungan, Roxas, Palawam | Roxas | PEO | 2016 | 20% Development Fund | 7047308.25 | 6949230.94 | 150 | 2017-08-11 |  | 2018-01-08 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
171 | Concreting of Highway Junction of New Guinlo Road (Intermittent Section) |  | Transportation Facilities |  | Bgy. New Guinlo | Taytay | PEO | 2016 | 20% Development Fund | 1880000 | 1876807.01 | 120 | 2017-03-08 |  | 2017-07-06 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
172 | Construction of Transformer Platform in Rizal Medicare Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2016 | 20% Development Fund | 227000 | 226313.49 | [6 empty] | 100% |  | By contract | Completed
173 | Rehabilitation of Hanging Bridge of San Juan |  | Transportation Facilities |  | Bgy. San Juan | Aborlan | PEO | 2016 | 20% Development Fund | 745000 | 743271.86 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
174 | Construction of RC Slide Slope Protection and Approach PCCP for Antonino RCBC | B2 BFIP 300-16-11-15240 | Other Infrastructure |  | Brgy. Antonino, Roxas, Palawan | Roxas | PEO | 2016 | 20% Development Fund | 1300000 | 1239259.58 | 40 | 2017-03-07 |  | 2017-04-16 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
175 | Concreting of Road network inside Aborlan Medicare Hospital Facilities |  | Transportation Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 2500000 | 2487509.99 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
176 | Concreting of Zabanal Road Phase 2 |  | Transportation Facilities |  |  | San Vicente | PEO | 2016 | 20% Development Fund | 5000000 | 4967139.44 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
177 | Construction of 4 barrels Reinforced Concrete Box Culvert in PSU Road (Ht. 4m) |  | Other Infrastructure |  |  | Bataraza | PEO | 2016 | 20% Development Fund | 3670000 | 3612204.01 | [6 empty] | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
178 | Construction of Multi-Purpose Pavement, Barangay Mendoza | B2 BFIP 300-16-11-16175 | Other Facilities |  | Bgy. Mendoza | Roxas | PEO | 2016 | 20% Development Fund | 664514.67 | 664196.41 | 15 | 2017-02-24 |  | 2017-03-11 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
179 | Construction of Multi-Purpose Bldg. in Alfonso XIII |  | Other Infrastructure |  | Bgy. Alfonso XIII | Quezon | PEO | 2016 | 20% Development Fund | 2500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
180 | Construction of Multi-Purpose Bldg. in Punta Baja |  | Other Infrastructure |  | Bgy. Punta Baja | Rizal | PEO | 2016 | 20% Development Fund | 2500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
181 | Construction of Multi-Purpose Bldg. in Pangobilian |  | Other Infrastructure |  | Bgy. Pangobilian | Brooke's Point | PEO | 2016 | 20% Development Fund | 2500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
182 | Construction of Perimeter Fence of Aborlan Medicare Hospital Phase 2 |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 650000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
183 | Construction of Transformer Platform in Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
184 | Construction of Transformer Platform in Roxas Medicare Hospital | B2 BFIP 300-16-11-15228 | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | 20% Development Fund | 227000 | 226313.49 | 27 | 2017-03-17 |  | 2017-04-13 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
185 | Construction of Transformer Platform in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
186 | Upgrading of Little Caramay Bailey Bridge to RCDG (Length= 19.00lm) |  | Transportation Facilities |  | San Vicente | San Vicente | PEO | 2016 | 20% Development Fund | 7400000 | 7363650.94 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
187 | Rehabilitation of Sagpangan - Pandacan Spillway |  | Other Infrastructure |  |  | Aborlan | PEO | 2016 | 20% Development Fund | 3000000 | 2919485.77 | [6 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
188 | Rehabilitation of Ipilan Spillway w/ riprap on riverbank |  | Other Infrastructure |  |  | Brooke's Point | PEO | 2016 | 20% Development Fund | 2500000 | 2425815.59 | [6 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
189 | Ipilan Slope Protection |  | Other Infrastructure |  |  | Brooke's Point | PEO | 2016 | 20% Development Fund | 1900000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
190 | Concreting of Panitian - Abokayan Road |  | Transportation Facilities |  | Bgy. Abokayan | Sofronio Española | PEO | 2016 | 20% Development Fund | 1500000 | 1439993.06 | [6 empty] | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
191 | Construction of Kalupisan Spillway, Punta Baja |  | Other Infrastructure |  | Bgy. Punta | Rizal | PEO | 2016 | 20% Development Fund | 1620000 | 1487895.23 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
192 | Construction of 1 Barrell RCBC - Antonino Road |  | Other Infrastructure |  | Bgy. Antonino | Roxas | PEO | 2016 | 20% Development Fund | 854012 | 850719.43 | [6 empty] | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
193 | Concreting of Bgy. Road, Minara (110m x 2.5m x 0.20m) |  | Transportation Facilities | (110m x 2.5m x 0.20m) | Bgy. Minara | Roxas | PEO | 2016 | 20% Development Fund | 400000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
194 | Construction of 4 Barrels Reinforced Concrete Box Culvert, Pamantolon |  | Other Infrastructure |  | Bgy. Pamantolon | Taytay | PEO | 2016 | 20% Development Fund | 3670000 | 3666585.05 | 120 | 2016-11-09 |  | 2017-03-09 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
195 | Construction of 4 Barrel Box Culvert, Dumarao |  | Other Infrastructure |  | Bgy. Dumarao | Roxas | PEO | 2016 | 20% Development Fund | 2330000 | 2319095.71 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
196 | Construction of San Nicolas Spillway |  | Other Infrastructure |  | Bgy. Nicolas, Coron | Coron | PEO | 2016 | 20% Development Fund | 3300000 | 3262614.04 | [6 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
197 | Construction of Motorpool |  | Other Facilities |  |  | Rizal | PEO | 2016 | 20% Development Fund | 6900000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
198 | Construction of Perimeter Fence of Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | 20% Development Fund | 3144388 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
199 | Construction of Perimeter Fence of Aborlan Medicare Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2016 | 20% Development Fund | 3100000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
200 | Construction of Pamantolon Dist. Pipeline (going to Pob.) |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Taytay | PEO | 2016 | 20% Development Fund | 18355612 | [7 empty] | 100% |  | By contract | Completed
201 | Concreting of Road Network Inside Southern Palawan Provincial Hospital Facilities with Gate |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 3500000 | 3490500.14 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
202 | Concreting of Road Network Inside Roxas Medicare Hospital |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2500000 | 2497858.36 | 120 | 2018-02-14 |  | 2018-06-14 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
203 | Concreting of Road Network inside Narra Municipal Hospital | B2 SB6 PEO17-300-18-03-01951 | Medical Facilities | (a) PCCP 360M (4M & 5M Width) - (b) 45m (L) x 6m(W) (C) 14LN.M | Narra Municipal Hospital | Narra | PEO | 2016 | SB No. 6 - Debt Servicing Under 20% DF (2014-2015-2016) | 3500000 | 3483428.65 | 60 | 2018-05-25 |  | 2018-07-24 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
204 | Concreting of Road Network Coron District Hospital |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2000000 | 1996206.34 | [6 empty] | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
205 | Construction of Cuyo Medicare Hospital Perimeter Fence with Gate Phase I, Cuyo, Palawan | B2 SB6 PEO 300-17-11-20076 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2016 | Supplemental Budget No. 6 | 2500000 | 2497556.65 | 120 | 2018-02-14 |  | 2018-06-14 |  |  |  |  | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
206 | Installation of Conversion of Single phase to Three Phase Line going to Roxas Medicare Hospital |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 148826.09 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
207 | Installation of Extension 3 Phase Line going to Rizal District Hospital |  | Medical Facilities |  | Rizal District Hospital | Rizal | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 904034.98 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
208 | Upgrading/Construction of RCDG Cabigaan Bridge 2 |  | Transportation Facilities |  |  | Aborlan | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 8000000 | 7848266.35 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
209 | Concreting of Road, Brgy Poblacion II |  | Transportation Facilities |  | Brgy Poblacion II | Balabac | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 300000 | 299280.19 | [6 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
210 | Completion of Multipurpose Hall for Bgy Poblacion II |  | Other Infrastructure |  | Brgy Poblacion II | Balabac | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 1400000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
211 | Construction of TB DOTS for SPPH |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 1242063.76 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
212 | Comstruction of Perimeter Fence in Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2500000 | [7 empty] | 100% |  | By contract | Completed
213 | Construction of Lamayo Processing Center Phase I, Sitio Yakal, New Guinlo, Taytay, Palawan |  | Other Facilities |  | Sitio Yakal, New Guinlo | Taytay | PEO | 2016 | Locally Funded | 3000000 |  |  | 2016-12-12 |  | 2016-12-12 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
214 | Construction of 30m reinforced Spillway, Bgy. Candawaga |  | Other Infrastructure |  | Bgy. Candawaga | Rizal | PEO | 2016 | Performance Challenge Fund | 2837038.87 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
215 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I) Busuanga |  | Medical Facilities |  | Bgy. Salvacion | Busuanga | PEO | 2016 | Trust Fund - DOH | 21800000 | 20927555.05 | 300 | 2018-09-21 |  | 2019-07-18 | 2023-12-09 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
216 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Sofronio Española |  | Medical Facilities |  | Sofronio Española | Sofronio Española | PEO | 2016 | Trust Fund - DOH | 19940000 | 19925093.35 | 210 | 2018-09-21 |  | 2019-04-19 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
217 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Bgy. Aporawan Phase 1 |  | Medical Facilities |  | Bgy. Aporawan | Aborlan | PEO | 2016 | Trust Fund - DOH | 11940000 | 11917517.14 | 300 | 2018-08-10 |  | 2019-06-06 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
218 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Bgy. Panalingaan Phase 1 |  | Medical Facilities |  | Bgy. Panalingaan | Rizal | PEO | 2016 | Trust Fund - DOH | 11940000 | 11916499.76 | 300 | 2018-08-10 |  | 2019-06-06 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
219 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Linapacan |  | Medical Facilities |  | Linapacan | Linapacan | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-11-26 |  | 2019-09-22 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
220 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Agutaya |  | Medical Facilities |  | Municipality of Agutaya | Agutaya | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-12-13 | 2 | 2019-10-09 | For approval | 2023-11-23 | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
221 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Magsaysay |  | Medical Facilities |  | Magsaysay | Magsaysay | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-12-13 |  | 2019-10-09 | 2020-12-15 |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
222 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Cagayancillo |  | Medical Facilities |  | Cagayancillo | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2019-11-28 |  | 2020-09-23 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
223 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Pancol |  | Medical Facilities |  | Bgy. Pancol | Taytay | PEO | 2016 | Trust Fund - DOH | 11940000 | 11915174.28 | 300 | 2018-11-15 |  | 2019-09-11 |  |  | 100% |  | By contract | Completed | High Riser Construction & Trading | TIN 928-603-901
224 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Northeast Taytay |  | Medical Facilities |  | Northeast Taytay | Taytay | PEO | 2016 | Trust Fund - DOH | 11940000 | 11915174.28 | 300 | 2018-11-15 |  | 2019-09-11 |  |  | 100% |  | By contract | Completed | High Riser Construction & Trading | TIN 928-603-901
225 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I), Bgy. Mangsee |  | Medical Facilities |  | Bgy. Mangsee | Balabac | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933162.4 | 300 | 2018-12-13 |  | 2019-10-09 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
226 | Construction Three (3) in One (1) Scale Rural Health Unit (Phase I) Bgy. Bancalaan |  | Medical Facilities |  | Bgy. Bancalaan | Balabac | PEO | 2016 | Trust Fund - DOH | 11940000 | 11933384.21 | 300 | 2018-12-14 |  | 2019-10-10 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
227 | Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2016 | Trust Fund - DOH | 49750000 | 49743376.32 | 364 | 2017-03-13 |  | 2018-03-12 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
228 | Construction of 4CL School Building in Magkalip ES, Bgy. Taburi |  | Educational Facilities | 4 Classroom School Building | Bgy. Taburi | Rizal | PEO | 2016 | Roads and Bridges Dev. Program-TF (2016) | 3000000 | 2991423.66 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
229 | Construction of Perimeter Fence of Narra Municipal Hospital |  | Medical Facilities |  |  | Narra | PEO | 2016 | Debt Servicing Under 20% DF (2014-2015-2016) | 2949649.54 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
230 | Casian Village Electrifcation Project |  | Power and Energy Development Program |  | Bgy. Casian | Taytay | PEO | 2016 | Energy Development Program | 5329561.03 | 5327093.43 | 210 | 2017-05-22 |  | 2017-12-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
231 | Procurement of Construction Materials for the Rehabilitation of Small Division DAM Rancho I |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Rancho | Rizal | PEO | 2016 | DILG - BUB / LGSF | 328925.25 | [9 empty] | By contract | Subject for Reversion | RAK Trading Construction & Supply
232 | Procurement of Construction Materials for the Construction of Irrigation Canal |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Malaca-laca Kampong Ulay, Rizal | Rizal | PEO | 2016 | DILG - BUB / LGSF | 425032.06 | [9 empty] | By contract | Subject for Reversion | RAK Trading Construction & Supply
233 | Construction of 2 Barrel RCBC, So. Singcab, Bgy Punang |  | Other Infrastructure |  | Bgy Punang | Sofronio Española | PEO | 2016 | Performance Challenge Fund | 1162644.4 | 1125555.37 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
234 | Construction of 30 m reinforced Spillway,Sitio Maruso, Bgy. Candawaga |  | Other Infrastructure |  | Bgy. Candawaga | Rizal | PEO | 2016 | Performance Challenge Fund | 2837038.87 | 2833978.07 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
235 | Concreting of Araceli- Dumaran Road "A" (Intermittent Section) |  | Transportation Facilities |  | Araceli | Araceli | PEO | 2016 | DILG -Kalasada Program | 55624667 | 40462906.79 | [6 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
236 | Concreting of Araceli- Dumaran Road "B" |  | Transportation Facilities |  | Araceli | Araceli | PEO | 2016 | DILG -Kalasada Program | 40495136.54 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
237 | Concreting of Latungay- Sta. Terisita Road (Intermittent Section) |  | Transportation Facilities |  |  | Dumaran | PEO | 2016 | DILG -Kalasada Program | 42397934.4 | 42358978.67 | 270 | [5 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
238 | Construction of Malambunga Spillway, Punta Baja |  | Other Infrastructure |  | Bgy. Punta Baja | Rizal | PEO | 2016 | 20% Development Fund | 2250000 | 2057472.07 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
239 | Construction of Slope Protection within the Roxas Medicare Hospital Area | B2 BFIP 300-16-11-15614 | Other Infrastructure |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | 20% Development Fund | 2000000 | 1994845.1 | 90 | 2017-03-22 |  | 2017-06-20 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
240 | Construction of Transformer Platform in Coron District Hospital |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
241 | Construction of Transformer Platform in Coron District Hospital | B2 BFIP 300-16-11-15232 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2016 | 20% Development Fund | 227000 | 226313.49 | 27 | 2017-03-03 |  | 2017-03-30 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
242 | Construction of Transformer Platform in Quezon Medicare Hospital |  | Medical Facilities |  | QuezonMedicare Hospital | Quezon | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
243 | Construction of Transformer Platform in Narra Medicare Hospital |  | Medical Facilities |  | Narra Medicare Hospital | Narra | PEO | 2016 | 20% Development Fund | 227000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
244 | Construction of Perimeter Fence of Roxas Medicare Hospital Phase 2 |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2016 | 20% Development Fund | 1726000 | [7 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
245 | Construction of Multi-purpose Building, Type II, in Sitio Balen |  | Other Infrastructure |  | Sitio Balen | Rizal | PEO | 2016 | 20% Development Fund | 950000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
246 | Construction of Multi-purpose Building, Type II, in Bgy. Salvacion | B2 BFIP 16 300-17-02-01581 | Other Infrastructure |  | Bgy. Salvacion | Roxas | PEO | 2016 | 20% Development Fund | 950000 | 937594.76 | 120 | 2018-01-10 |  | 2018-05-10 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
247 | Construction of Multi-purpose Building in Bgy. Pulot Center |  | Other Infrastructure |  | Bgy. Pulot | Sofronio Española | PEO | 2016 | 20% Development Fund | 2500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
248 | Construction of 4 Barrels Reinforced Concrete Box Culvert in Sta. 11+900, Alacalian |  | Other Infrastructure | Sta. 11+900, Alacalian (Ht. 4m) | Bgy. Alacalian | Taytay | PEO | 2016 | 20% Development Fund | 3670000 | 3612204.01 | 170 | 2017-03-17 |  | 2017-09-03 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
249 | Construction of Multi-purpose Building in Bgy. VI, Poblacion |  | Other Infrastructure |  | Bgy. VI, Poblacion | Balabac | PEO | 2016 | 20% Development Fund | 2500000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
250 | Construction of Multi-Purpose Building Type I |  | Other Infrastructure |  |  | Balabac | PEO | 2016 | 20% Development Fund | 2497986.48 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
251 | Rehabilitation of Bagumbayan- Latungay Road with Spillway |  | Other Infrastructure |  | Bgry. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 4200000 | 4159238.05 | 120 | 2017-03-07 |  | 2017-07-05 | 2017-05-07 |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
252 | Upgrading of Itangil Bridge 1 to RCDG |  | Transportation Facilities |  | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 6000000 | 5995492.35 | 180 | 2016-12-20 |  | 2017-06-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
253 | Upgrading of Layok Bridge Timber Bridge to RCDG (Bgy. Itangil) |  | Transportation Facilities |  | Bgy. Itangil | Dumaran | PEO | 2016 | 20% Development Fund | 6237588.54 | 6228973.74 | 185 | [7 empty] | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
254 | Upgrading of Lamoro Ibajay Bailey Bridge I to RCDG |  | Transportation Facilities |  |  | El Nido | PEO | 2016 | 20% Development Fund | 7100000 | 6892703.22 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
255 | Upgrading of Tumarbong Bailey Bridge to RCDG | B2 BFIP 300-16-12-17193 | Transportation Facilities | (Length = 18.90 lm) | Tumarbong, Roxas, Palawan | Roxas | PEO | 2016 | 20% Development Fund | 7320000 | 7015047.47 | 210 | 2017-10-13 |  | 2018-05-11 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
256 | Upgrading of Abokayan Bailey Bridge to RCDG |  | Transportation Facilities |  |  | Sofronio Española | PEO | 2016 | 20% Development Fund | 10600000 | 10572619.91 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
257 | Construction of Multi-purpose Pavement, Sitio Bubusawin, Aporawan |  | Other Facilities |  | Sitio Bubusawin, Aporawan | Aborlan | PEO | 2016 | 20% Development Fund | 486000 | 484062.83 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
258 | Upgrading of Tulduan Bridge I to RCDG |  | Transportation Facilities |  | Bgy. Tulduan | Taytay | PEO | 2016 | 20% Development Fund | 4800000 | 4381276.38 |  | 2016-11-18 |  | 2016-11-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
259 | Upgrading of Cataban Bailey Bridge I to RCDG | ROAD 300-16-06-05887 | Transportation Facilities |  | Bgy. Cataban | Taytay | PEO | 2016 | 20% Development Fund | 6000000 | 5995492.35 | 180 | 2016-09-19 |  | 2017-03-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
260 | Upgrading of Caniqui Bridge I to RCDG | ROAD 300-16-06-05889 | Transportation Facilities |  | Bgy. Caniqui | Taytay | PEO | 2016 | 20% Development Fund | 6000000 | 5995492.35 | 180 | 2016-09-19 |  | 2017-03-18 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
261 | Upgrading of Inalwayan Bailey Bridge to RCDG | B2 BFIP 300-16-11-15234 | Transportation Facilities |  | Bgy. Liminangcong | Taytay | PEO | 2016 | 20% Development Fund | 6237588.54 | 6228194 | 180 | 2017-03-07 |  | 2017-09-03 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
262 | Construction of Barangay Health Station in Bgy. Binudac |  | Medical Facilities |  | Bgy. Binudac | Culion | PEO | 2016 | 20% Development Fund | 1500000 | 1491336 | 150 | 2017-03-08 |  | 2017-08-05 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
263 | Construction of Barangay Health Station, Tagpait |  | Medical Facilities |  | Bgy. Tagpait | Aborlan | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
264 | Construction of Barangay Health Station, Madoldolon | Cluster: Construction of BHS (Bgy. Madoldolon - Bgy. Osmeña - Bgy. Balogo, Araceli, Palawan)B2 TF 416 DOH HFEP 17-021/022/024 (N-17-01) - Madoldolon (TF 416 DOH HFEP 17-021) | Medical Facilities | Dimension: 8.95m x 11.075m - Area: 99.12 sq.m | Bgy. Madoldolon | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1998979.25 | 120 | 2017-08-14 |  | 2017-12-12 |  |  | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
265 | Construction of Barangay Health Station, Osmeña | Cluster: Construction of BHS (Bgy. Madoldolon - Bgy. Osmeña - Bgy. Balogo, Araceli, Palawan)B2 TF 416 DOH HFEP 17-021/022/024 (N-17-01) - Osmeña (TF 416 DOH HFEP 17-022) | Medical Facilities | Dimension: 8.95m x 11.075m - Area: 99.12 sq.m | Bgy. Osmeña | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
266 | Construction of Barangay Health Station, Balogo | Cluster: Construction of BHS (Bgy. Madoldolon - Bgy. Osmeña - Bgy. Balogo, Araceli, Palawan)B2 TF 416 DOH HFEP 17-021/022/024 (N-17-01) - Balogo (TF 416 DOH HFEP 17-024) | Medical Facilities | Dimension: 8.95m x 11.075m - Area: 99.12 sq.m | Bgy.Balogo | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1988907.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  |  |  | By contract | Terminated | Lea & Sons Trading & Construction | TIN 134-897-002
267 | Construction of Barangay Health Station, Sto. Niño |  | Medical Facilities |  | Bgy. Sto. Niño | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1958925.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
268 | Construction of Barangay Health Station, San Jose De Oro | B2 TF 416 DOH HFEP 17-023-025-026-(N-17-02) | Medical Facilities |  | Bgy.San Jose De Oro | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989081.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  |  |  | By contract | Terminated | Lea & Sons Trading & Construction | TIN 134-897-002
269 | Construction of Barangay Health Station, Taloto | B2 TF 416 DOH HFEP 17-023-025-026 (N-17-02) | Medical Facilities |  | Bgy. Taloto | Araceli | PEO | 2016 | Trust Fund - DOH | 1990000 | 1988979.25 | 60 | 2017-08-14 |  | 2017-10-13 |  |  |  |  | By contract | Terminated | Lea & Sons Trading & Construction | TIN 134-897-002
270 | Construction of Barangay Health Station, Panitian, Bgy. Catagumpan |  | Medical Facilities |  | Sitio Panitian, Bgy. Catagumpan | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 240 | [5 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
271 | Construction of Barangay Health Station, Kambang Tuli, Melville | B2 TF 416-DOH HFEP 17-027-028-029 | Medical Facilities |  | Kambang Tuli, Bgry. Melville | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  |  |  | By contract | Order of Termination | Rhodamay Construction and Supply | 322-759-45
272 | Construction of Barangay Health Station, Catagupan Centro |  | Medical Facilities |  | Bgy. Catagupan Centro | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
273 | Construction of Barangay Health Station, Sitio Caguisan Bgy. Salang | B2 TF 416 DOH HFEP 17-030/031/032 (S-17-03) | Medical Facilities |  | Sitio Caguisan Bgy. Salang | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  |  |  | By contract | Order of Termination | Rhodamay Construction and Supply | 322-759-45
274 | Construction of Barangay Health Station, Maria Hangin | B2 TF 416 DOH HFEP 17-030-031-032 (S-17-03) | Medical Facilities |  | Bgy. Maria Hangin | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.55 | 240 | 2017-09-18 |  | 2018-05-16 |  |  |  |  | By contract | Order of Termination | Rhodamay Construction and Supply | 322-759-45
275 | Construction of Barangay Health Station, Sebaring |  | Medical Facilities |  | Bgy. Sebaring | Balabac | PEO | 2016 | Trust Fund - DOH | 1990000 | 1981649.65 | 240 | 2017-09-18 |  | 2018-05-16 |  |  | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
276 | Construction of Barangay Health Station, Puring |  | Medical Facilities |  | Bgy. Puring | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
277 | Construction of Barangay Health Station, Igang-igang |  | Medical Facilities |  | Bgy. Igang | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
278 | Construction of Barangay Health Station, Iwahig/Mampyu |  | Medical Facilities |  | Bgy.Iwahig | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
279 | Construction of Barangay Health Station, Tabud |  | Medical Facilities |  | Bgy. Tabud | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
280 | Construction of Barangay Health Station, Tagnato |  | Medical Facilities |  | Bgy. Tagnato | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
281 | Construction of Barangay Health Station, Taratak |  | Medical Facilities |  | Bgy. Taratak | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
282 | Construction of Barangay Health Station, Tagolango | TF 416-DOH HFEP 17-038-039-040-041- (S-17-015) | Medical Facilities |  | Bgy. Tagolango | Bataraza | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989328.03 | 300 | 2017-11-13 |  | 2018-09-09 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
283 | Construction of Barangay Health Station, Salogon |  | Medical Facilities |  | Bgy. Salogon | Brooke's Point | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
284 | Construction of Barangay Health Station, Bgy. Panlaitan | TF 416-DOH HFEP 17-033-034 | Medical Facilities |  | Bgy. Panlaitan | Busuanga | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989490.72 | 180 | 2017-12-29 |  | 2018-06-27 |  |  |  |  | By contract | Order of Termination | JFR Construction
285 | Construction of Barangay Health Station, Bgy. Quezon |  | Medical Facilities |  | Bgy. Quezon | Busuanga | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | JFR Construction
286 | Construction of Barangay Health Station, Santa Cruz |  | Medical Facilities |  | Bgy.Santa Cruz | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 300 | 2017-06-01 |  | 2018-03-28 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
287 | Construction of Barangay Health Station, Nusa | B2 TF 416 DOH HFEP 17-059-060-061-062 (N-17-04) | Medical Facilities |  | Bgy. Nusa | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 300 | 2017-06-01 |  | 2018-03-28 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
288 | Construction of Barangay Health Station, Talaga | B2 TF 416 DOH HFEP 17-059/060//061/062/(N-17-04) | Medical Facilities |  | Bgy. Talaga | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 300 | 2017-06-01 |  | 2018-03-28 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
289 | Construction of Barangay Health Station, Wahig |  | Medical Facilities |  | Bgy. Wahig | Cagayancillo | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
290 | Construction of Barangay Health Station, Bgy. Turda | B2 TF 416 DOH HFEP 17-057-058 (N-17-05) | Medical Facilities | Area: 99.12 sq.m | Bgy. Turda | Coron | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2018-02-05 |  | 2018-06-05 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
291 | Construction of Barangay Health Station, Bgy. Tagumpay | B2 TF 416 DOH HFEP 17-057-058 (N-17-05) | Medical Facilities | Area: 99.12 sq.m | Bgy. Tagumpay | Coron | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2018-02-05 |  | 2018-06-05 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
292 | Construction of Barangay Health Station, Bgy. Halsey | B2 TF 416 DOH HFEP 17-044-045 (N-17-06) | Medical Facilities |  | Bgy. Halsey | Culion | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-13 |  | 2017-12-10 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
293 | Construction of Barangay Health Station, So. Tampil, Bgy. Osmeña | B2 TF 416 DOH HFEP 17-044-045 (N-17-06) | Medical Facilities |  | So. Tampil, Bgy. Osmeña | Culion | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-13 |  | 2017-12-10 |  |  |  |  | By contract | Notice to Terminate | E.V Villaos Trading and Construction Supply | TIN 134-897-002
294 | Construction of Barangay Health Station, Bgy. Caburian | B2 TF 416-DOH-HFEP 17-015-017 (N-17-07) | Medical Facilities |  | Bgy. Caburian | Cuyo | PEO | 2016 | Trust Fund - DOH | 1990000 | 1990000 | 180 | 2018-03-05 |  | 2018-09-01 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Unreasonable price increase
295 | Construction of Barangay Health Station, So Malunlon, Bgy. Tanatanaen | TF 416-DOH HFEP 17-046-047 (N-17-08) | Medical Facilities |  | So Malunlon, Bgy. Tanatanaen | Dumaran | PEO | 2016 | Trust Fund - DOH | 1990000 | 3978738.42 | 180 | 2017-06-13 |  | 2017-12-10 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Insifficient budget
296 | Construction of Barangay Health Station, So. Nagtalula, Bgy. Catep | TF 416-DOH HFEP 17-046-047 (N-17-08) | Medical Facilities |  | So. Nagtalula, Bgy. Catep | Dumaran | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 180 | 2017-06-13 |  | 2017-12-10 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Insifficient budget
297 | Construction of Barangay Health Station, Manlag | TF 416-DOH HFEP 17-048-049 (N-17-09) | Medical Facilities |  | Bgy. Manlag, El Nido | El Nido | PEO | 2016 | Trust Fund - DOH | 1990000 | 1978738.42 |  | 2017-06-13 |  | 2017-06-13 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
298 | Construction of Barangay Health Station, Poblacion, Upper Quirino |  | Medical Facilities |  | Poblacion, Upper Quirino | Narra | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
299 | Construction of Barangay Health Station, Sowangan |  | Medical Facilities |  | Bgy. Sowangan | Quezon | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
300 | Construction of Barangay Health Station, Cocoro | B2 TF 416 DOH-HFEP 17-015-017 (N-17-07) | Medical Facilities |  | Bgy. Cocoro | Magsaysay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1990000 | 180 | 2018-03-05 |  | 2018-09-01 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Unreasonable price increase
301 | Construction of Barangay Health Station, Barangonan |  | Medical Facilities |  | Bgy. Barangonan | Linapacan | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-09 |  | 2017-12-06 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
302 | Construction of Barangay Health Station, Maroyogroyog | B2 TF 416 DOH HFEP 17-042-043 (N-17-10) | Medical Facilities |  | Bgy. Maroyogroyog | Linapacan | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 180 | 2017-06-09 |  | 2017-12-06 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Design not suitable to actual site condition
303 | Construction of Barangay Health Station, So. Ogis, Ransang |  | Medical Facilities |  | So. Ogis, Ransang | Rizal | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
304 | Construction of Barangay Health Station, Malotoc, Ransang |  | Medical Facilities |  | Malotoc, Ransang | Rizal | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
305 | Construction of Barangay Health Station, Green Island |  | Medical Facilities |  | Bgy. Green Island | Roxas | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
306 | Construction of Barangay Health Station, Caruray |  | Medical Facilities |  | Bgy. Caruray | San Vicente | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
307 | Construction of Barangay Health Station, Port Barton |  | Medical Facilities |  | Port Barton | San Vicente | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
308 | Construction of Barangay Health Station, Abo-abo |  | Medical Facilities |  | Bgy. Abo-abo | Sofronio Española | PEO | 2016 | Trust Fund - DOH | 1990000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
309 | Construction of Barangay Health Station, Bgy. Old Guinlo | B2 TF 416-DOH HFEP 17-050-054-056 (N-17-12) | Medical Facilities |  | Bgy. Old Guinlo | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 120 | 2018-01-02 |  | 2018-05-02 |  |  |  |  | By contract | Terminated | E.V Villaos Trading and Construction Supply | TIN 142-914-104
310 | Construction of Barangay Health Station, Baras | B2 TF 416-DOH HFEP 17-050-054-056 (N-17-12) | Medical Facilities | Building: 8.95m x 11.075m | Bgy. Baras | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 120 | 2018-01-02 |  | 2018-05-02 |  |  |  |  | By contract | Terminated
311 | Construction of Barangay Health Station, Tumbod | B2 TF 416-DOH HFEP 17-050-054-056 (N-17-12) | Medical Facilities | Building: 8.95m x 11.075m | Bgy. Tumbod | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 |  | 120 | 2018-01-02 |  | 2018-05-02 |  |  |  |  | By contract | Terminated
312 | Construction of Barangay Health Station, Biton | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | Building: 8.95m x 11.075m | Bgy. Biton | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  |  |  | By contract | Issued Notice to Terminate | E.V Villaos Trading and Construction Supply | TIN 142-914-104 | Design not suitable to actual site condition
313 | Construction of Barangay Health Station, Libertad | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | Building: 8.95m x 11.075m | Bgy. Libertad | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  | 100% |  | By contract | Completed
314 | Construction of Barangay Health Station, Meytegued | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | Building: 8.95m x 11.075m | Bgy. Meytegued | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  |  |  | By contract | Issued Notice to Terminate |  |  | Design not suitable to actual site condition
315 | Construction of Barangay Health Station, Poblacion | TF 416-DOH HFEP 17-051/053/055/052 - BITOON-LIBERTAD-MEYTEGUED-POBLACION Package: 7,957,476.85 | Medical Facilities | Building: 8.95m x 11.075m | Bgy. Poblacion | Taytay | PEO | 2016 | Trust Fund - DOH | 1990000 | 1989369.21 | 120 | 2017-08-11 |  | 2017-12-09 |  |  | 100% |  | By contract | Completed
316 | Construction of San Vicente District Hospital | B2 TF 416 DOH HFEP 16-506 | Medical Facilities | Building: 60.0m x 60.0m single storey | San Vicente District Hospital | San Vicente | PEO | 2016 | Trust Fund - DOH | 49750000 | 49743028.84 | 364 | 2017-05-15 |  | 2018-05-14 |  |  | 100% |  | By contract | Completed | MGB Construction and Trading
317 | Construction of Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2016 | Trust Fund - DOH | 49750000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
318 | Construction of El NidoCommunity Hospital |  | Medical Facilities |  | El NidoCommunity Hospital | El Nido | PEO | 2016 | Trust Fund - DOH | 49750000 | 49743710.84 |  | 2017-05-16 |  | 2017-05-16 |  |  | 100% |  | By contract | Completed | MGB Construction and Trading
319 | Construction of Bgy. Buluang Rescue Center |  | Other Infrastructure |  | Bgy. Buluang | Busuanga | PEO | 2016 | Trust Fund - DOH | 2487500 | [7 empty] | 100% |  | By contract | Completed | JFR Construction
320 | Construction of Bgy. Cheey Rescue Center |  | other Infrastructure |  | Bgy. Cheey | Busuanga | PEO | 2016 | Trust Fund - DOH | 2487500 | 2485845.67 | [6 empty] | 100% |  | By contract | Completed | JFR Construction
321 | Construction of Guadalupe Rescue Center |  | Other Infrastructure |  | Bgy. Guadalupe | Coron | PEO | 2016 | Trust Fund - DOH | 2487500 | [7 empty] | 100% |  | By contract | Completed | JFR Construction
322 | Construction of San Fernando Rescue Center |  | Other Infrastructure |  | El Nido | El Nido | PEO | 2016 | Trust Fund - DOH | 2487500 | [7 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
323 | Repair of KILN of Provincial Jail |  | Other Facilities |  |  | Puerto Princesa City | PEO | 2016 | Locally Funded | 75916 | [7 empty] | 100% |  | By contract | Completed
324 | Expansion of Southern Palawan Technical Vocational School |  | Educational Facilities |  | Southern Palawan Technical Vocational School | Aborlan | PEO | 2016 | Locally Funded | 35000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
325 | Construction of Northern Palawan Technical Vocational School (Phase I) |  | Educational Facilities |  | Northern Palawan Technical Vocational School | Taytay | PEO | 2016 | Locally Funded | 8254313.19 | 8250949.51 |  | 2021-02-05 |  | 2021-02-05 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
326 | Construction of PNP Crime Laboratory (Provincial Police Office) |  | Other Facilities |  |  | Puerto Princesa City | PEO | 2016 | Locally Funded | 3363671.8 | [7 empty] | 100% |  | By contract | Completed | UGM Construction | TIN 102-967-201
327 | Extension of 3 Phase line going to Aborlan Medicare Hospital |  | Medical Facilities |  |  | Aborlan | PEO | 2016 | Energy Development Program | 473929.12 |  | 121 | 2021-01-14 |  | 2021-05-15 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
328 | Installation of Cables, Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | Energy Development Program | 1865000 | [7 empty] | 100% |  | By contract | Completed
329 | Purchase of 75 KVA Transformer and Accessories for 2 Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2016 | Energy Development Program | 1762368.5 | [7 empty] | 100% |  | By contract | Completed
330 | Concreting of Cataban- Liminangcong Rd. (Intermittent Section) |  | Transportation Facilities |  |  | Taytay | PEO | 2017 | 20% Development Fund | 8888869.31 | 8837664.39 |  | 2018-10-11 |  | 2018-10-11 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
331 | Concreting of Circumferential Road Phase II |  | Transportation Facilities |  |  | Cagayancillo | PEO | 2017 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
332 | Concreting of Circumferential Road |  | Transportation Facilities |  | Linapacan | Linapacan | PEO | 2017 | 20% Development Fund | 1500000 | 1488875.51 | [6 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
333 | Concreting of Aramaywan Road (Extention), Bgy. Aramaywan |  | Transportation Facilities |  | Bgy. Aramaywan | Narra | PEO | 2017 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
334 | Construction of 3 Barrel RCBC, So. Nala, Sta Teresita |  | Other Infrastructure |  | So. Nala, Bgy. Sta Teresita | Dumaran | PEO | 2017 | 20% Development Fund | 1900000 | 1843310.04 | [6 empty] | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
335 | Construction of Alimoto Bridge RC Slope Protection, Sta. Teresita | B2 ROADS 300-17-07-11954 | Other Infrastructure |  | Bgy. Sta Teresita | Dumaran | PEO | 2017 | 20% Development Fund | 600000 | 598468.53 | 30 | 2018-01-10 |  | 2018-02-09 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
336 | Construction of Three (3) Barrel Reinforced Concrete Box Culvert with Detour Road (Re-bid) | B2 Roads 300-17-06-08439 | Other Infrastructure |  | Pamantolon - Pulariquen Road (Tagale Bridge), Taytay, Palawan | Taytay | PEO | 2017 | 20% Development Fund | 2000000 | 1996350.53 | 210 | 2017-10-24 |  | 2018-05-22 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
337 | Construction of Barake 4 Barrel RCBC, Bgy. Barake |  | Other Infrastructure |  |  | Aborlan | PEO | 2017 | 20% Development Fund | 3670000 | 3465963.05 | [6 empty] | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
338 | Construction of Jose Rizal Spillway (Box Type), Bgy. Jose Rizal |  | Other Infrastructure |  | Bgy. Jose Rizal | Aborlan | PEO | 2017 | 20% Development Fund | 1344000 | 1308041 | [6 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
339 | Construction of Tub-tub 3 Barrel RCBC w/ Slope Protection |  | Other Infrastructure |  |  | Brooke's Point | PEO | 2017 | 20% Development Fund | 1900000 | 1838690.15 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
340 | Construction of Amas 2 Barrel RCBC w/ Slope Protection |  | Other Infrastructure |  |  | Brooke's Point | PEO | 2017 | 20% Development Fund | 1300000 | 1195111.75 | [6 empty] | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
341 | Construction of Calvit Creek 3 Barrel RCBC w/ Slope Protection, Bunog |  | Other Infrastructure |  | Bgy. Bunog | Rizal | PEO | 2017 | 20% Development Fund | 1900000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
342 | Construction of Kalampinay BB (Lamoro Bridge II) to RCDG (Superstructure), Bgy. Pasadeña |  | Transportation Facilities |  | Bgy. Pasadeña | El Nido | PEO | 2017 | 20% Development Fund | 8000000 | 7969852.98 | [6 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
343 | Upgrading of Sta. Maria Bailey Bridge II to RCDG, Sta. Maria | B2 ROADS 300-17-06-08436 | Transportation Facilities |  | Bgy. Sta. Maria | Dumaran | PEO | 2017 | 20% Development Fund | 8000000 | 7691148.95 | 210 | 2016-09-19 |  | 2017-04-17 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
344 | Upgrading of Taradungan Bridge to RCDG, Bgy. Taradungan | B2 ROADS 300-17-06-08446 | Transportation Facilities |  | Bgy. Taradungan | Roxas | PEO | 2017 | 20% Development Fund | 5500000 | 5489999.65 | 210 | 2017-10-13 |  | 2018-05-11 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
345 | Upgrading of Iraan Bridge to RCDG, Bgy. Magara | B2 ROADS 300-17-06-08445 | Transportation Facilities |  | Bgy. Magara | Roxas | PEO | 2017 | 20% Development Fund | 8000000 | 7879325.37 | 135 | 2017-11-06 |  | 2018-03-21 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
346 | Upgrading of Maharlika Bridge I to RCDG, Bgy. Magara | B2 ROADS 300-17-06-08447 | Transportation Facilities |  | Bgy. Magara | Roxas | PEO | 2017 | 20% Development Fund | 5500000 | 5412281.88 | 120 | 2017-11-06 |  | 2018-03-06 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
347 | Upgrading of Burirao Timber Bridge to RCDG (Superstructure), Bgy. Burirao |  | Transportation Facilities |  | Bgy. Burirao | Narra | PEO | 2017 | 20% Development Fund | 6000000 | 5969311.36 | [6 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
348 | Upgrading of Barak-barakan Bridge to RCDG w/ Slope Protection |  | Transportation Facilities |  |  | Bataraza | PEO | 2017 | 20% Development Fund | 9600000 | 9595724.71 | [6 empty] | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
349 | Installation of RCCP and Const. of RCBC, Capayas - Salimbanog - Lamyang Road | B2 ROADS 300-17-08-12582 | Other Infrastructure |  | Bgy. Capayas | Dumaran | PEO | 2017 | 20% Development Fund | 10000000 | 9729175.83 | 120 | 2018-02-28 |  | 2018-06-28 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
350 | Installation of RCCP and Const. of RCBC, Cauban - Banbanan - Minapla Road | B2 ROADS 300-17-12-22014 | Other Infrastructure |  | Banbanan - Minapla Road | Taytay | PEO | 2017 | 20% Development Fund | 15344253 | 14700000.58 |  | 2018-03-21 |  | 2018-03-21 |  |  | 100% |  | By contract | Completed | LB Leoncio Trading and Construction | TIN 181-143-624
351 | Concreting of Barangay Road Galoc | B2 ROADS 300-17-06-08450 | Transportation Facilities |  | Bgy. Galoc | Culion | PEO | 2017 | 20% Development Fund | 1550000 | 1549444.93 | 76 | 2018-01-01 |  | 2018-03-18 |  |  |  |  | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
352 | Concreting of Agutaya Circumferential Road |  | Transportation Facilities |  | Municipality of Agutaya | Agutaya | PEO | 2017 | 20% Development Fund | 2000000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | TIN 944-093-894-001
353 | Construction of 1 Barrel RCBC, Latungay-Bagumbayan Road | B2 ROADS 300-17-06-08442 | Other Infrastructure |  | Dumaran | Dumaran | PEO | 2017 | 20% Development Fund | 800000 | 783919.14 | 120 | 2017-09-06 |  | 2018-01-04 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
354 | Concreting of Cataban-Liminangcong Road,(intermittent Section) |  | Transportation Facilities |  |  | Taytay | PEO | 2017 | 20% Development Fund | 8888869.31 | [7 empty] | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
355 | Upagrading of Pag-asa Bridge I to RCDG, So. Pag-asa, Little Caramay |  | Transportation Facilities |  |  | San Vicente | PEO | 2017 | 20% Development Fund | 7000000 | 6982887.32 | [6 empty] | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
356 | Cleaning of Solid Rocks & Boulders along Runway of Airstrip |  | Ports and Airports |  |  | Cagayancillo | PEO | 2017 | 20% Development Fund | 1800000 | 1798538.91 | [6 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
357 | Upgrading of Labog Bridge to RCDG w/ Slope Protection, Bgy. Labog |  | Transportation Facilities |  | Bgy. Labog | Sofronio Española | PEO | 2017 | 20% Development Fund | 8250000 | 8224810.78 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
358 | Rehabilitation/repair of Multi-Purpose Hall |  | Other Infrastructure |  |  | Narra | PEO | 2017 | 20% Development Fund | 1100000 | [7 empty] | 100% |  | By contract | Completed | Rhodamay Construction and Supply | 322-759-45
359 | Construction of Local Access Road |  | Transportation Facilities |  | Panaga, Rizal, Palawan | Rizal | PEO | 2017 | DILG - BUB/LGSF | 998442.34 | 998442.35 | [6 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
360 | Concreting of Balala- Malaking Patag Road | B2 TF 416 DILG CMGP 17-128 | Transportation Facilities |  | Culion, Palawan | Culion | PEO | 2017 | Kalsada | 169562217 | 169320307.53 | 279 | 2017-10-10 |  | 2018-07-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
361 | Concreting of Calasaguen Feeder Road |  | Transportation Facilities |  |  | Brooke's Point | PEO | 2017 | Kalsada | 62339864 | 54393934.43 | [6 empty] | 100% |  | By contract | Completed | Keilana Resources and DF Corporation
362 | Concreting of Magbabadil-Cabigaan Road | B2 TF 416 DILG CMGP 17-125 | Transportation Facilities |  | Aborlan, Palawan | Aborlan | PEO | 2017 | Kalsada | 116980113 | 105281882.25 | 250 | 2018-01-31 |  | 2018-10-08 |  |  | 100% |  | By contract | Completed | Werr Corporation International
363 | Concreting of Sandoval Feeder Road | B2 TF 416 DILG CMGP 17-122 | Transportation Facilities |  | Narra, Palawan | Narra | PEO | 2017 | Kalsada | 58155240 | 56916633.65 | 125 | 2017-12-19 |  | 2018-04-23 |  |  | 100% |  | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547
364 | Concreting of Ipilan-Linao Road |  | Transportation Facilities |  |  | Brooke's Point | PEO | 2017 | Kalsada | 80757611 | 79131323.98 | [6 empty] | 100% |  | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547
365 | Concreting of Paglaum-Itangil Road | B2 TF 416 DILG CMGP 17-127 | Transportation Facilities |  | Taytay & Dumaran, Palawan | Taytay | PEO | 2017 | Kalsada | 152478300 | 152323850.62 | 170 | 2017-10-10 |  | 2018-03-29 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
366 | Concreting of Tumarbong- Ilian Road (Intermittent Section) | B2 TF 416 DILG CMGP 17-126 | Transportation Facilities |  | Roxas, Palawan | Roxas | PEO | 2017 | Kalsada | 218855506 | 218593654.41 | 236 | 2017-10-10 |  | 2018-06-03 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
367 | Concreting of Lungsod-Igabas-Emilod Road "A" | B2 TF 416 DILG CMGP 17-124 | Transportation Facilities |  | Cuyo, Palawan | Cuyo | PEO | 2017 | Kalsada | 19731548 | 19704566.23 | 72 | 2017-10-10 |  | 2017-12-21 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
368 | Construction of ALS Learning Center | B2 SEF 300-17-10-17290 | Educational Facilities | Area: 36.00 sq.m | Balabac, Palawan | Balabac | PEO | 2017 | Special Education Fund | 650000 | 649077.52 | 90 | 2018-01-10 |  | 2018-04-10 |  |  |  |  | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
369 | Construction of ALS Learning Center | B2 SEF 300-17-10-17292 | Educational Facilities | Area: 36.00 sq.m | Rizal, Palawan | Rizal | PEO | 2017 | Special Education Fund | 650000 | 624851.11 | 90 | 2018-01-10 |  | 2018-04-10 |  |  |  |  | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
370 | Construction of ALS Learning Center | B2 SEF 300-17-10-19823 | Educational Facilities | Area: 36.00 sq.m | Taytay, Palawan | Taytay | PEO | 2017 | Special Education Fund | 650000 | 649077.51 | 90 | 2018-03-02 |  | 2018-05-31 |  |  |  |  | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
371 | Construction of ALS Learning Center | B2 SEF 300-17-10-17291 | Educational Facilities | Area: 36.00 sq.m | Roxas, Palawan | Roxas | PEO | 2017 | Special Education Fund | 650000 | 649077.52 | 90 | 2018-01-10 |  | 2018-04-10 |  |  |  |  | By contract | Order of Termination | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
372 | Equipping of Rural Health Unit |  | Medical Facilities |  |  | Araceli | PEO | 2017 | BUB/LGSF | 1200000 | [7 empty] | 100% |  | By contract | Completed
373 | Construction of Barangay Health Station with Birthing Facilities | B2 TF 416-DILG BUB 2016 | Medical Facilities |  | Bgy. Galoc, Culion, Palawan | Culion | PEO | 2017 | BUB/LGSF | 1525000 | 1523784.67 | [8 empty] | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
374 | Equipping of Rural Health Unit |  | Medical Facilities |  |  | Culion | PEO | 2017 | BUB/LGSF | 1200000 | [9 empty] | By contract | Subject for Reversion
375 | Rehabilitation of Barangay Health Station, Bgy. Poblacion |  | Medical Facilities |  | Bgy. Poblacion | Araceli | PEO | 2017 | BUB/LGSF | 500000 | 483664.2 |  | 2017-08-15 |  | 2017-08-15 |  |  | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
376 | Expansion of Rural Health Unit |  | Medical Facilities |  | Linapacan | Linapacan | PEO | 2017 | BUB/LGSF | 800000 | [9 empty] | By contract | Reverted | Reinastar Trading and Construction | TIN 944-093-894-001
377 | Construction of Faculty Rooms |  | Educational Facilities |  |  | Araceli | PEO | 2017 | BUB/LGSF | 1200000 | [7 empty] | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
378 | Construction of School Library |  | Educational Facilities |  |  | Araceli | PEO | 2017 | BUB/LGSF | 1200000 | [7 empty] | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
379 | Construction of School Fence |  | Educational Facilities |  |  | Araceli | PEO | 2016 | 2017-DILG - BUB/LGSF | 500000 | [9 empty] | By contract | For reversion | Lea & Sons Trading & Construction | TIN 134-897-002
380 | Flood Control Program |  | Other Infrastructure |  |  | Linapacan | PEO | 2017 | DILG - BUB / LGSF | 3500000 | [9 empty] | By contract | Reverted | Agency to Agency Agreement
381 | Provision of Potable Water System |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Linapacan | PEO | 2017 | 2016-DILG - BUB / LGSF | 1000000 | [9 empty] | By contract | Reverted | Agency to Agency Agreement
382 | Constuction of Irrigation Canal |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Rizal | PEO | 2017 | 2016-DILG - BUB / LGSF | 925000 | [9 empty] | By contract | Subject for Reversion | Agency to Agency Agreement
383 | Construction of Small Water Impounding Projects |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Rizal | PEO | 2017 | 2016-DILG - BUB / LGSF | 1000000 | [9 empty] | By contract | Subject for Reversion | Agency to Agency Agreement
384 | Establishment of Shallow Tube Well |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Rizal | PEO | 2017 | DILG - BUB / LGSF | 625000 | [9 empty] | By contract | Subject for Reversion | Agency to Agency Agreement
385 | Installation of Water Supply to Elementary Schools |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Rizal | PEO | 2017 | DILG - BUB / LGSF | 825000 | [9 empty] | By contract | Subject for Reversion | Agency to Agency Agreement
386 | Small Diversion Dam |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Rizal | PEO | 2017 | DILG - BUB / LGSF | 800000 | [9 empty] | By contract | Subject for Reversion | Agency to Agency Agreement
387 | Procurement of Construction Materials for the Construction of Irrigation Canal |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Rizal | PEO | 2017 | DILG - BUB / LGSF | 359359.33 | [9 empty] | By contract | Subject for Reversion | RAK Trading Construction & Supply
388 | Procurement of Construction Materials for the Construction of Irrigation Canal |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy Poblacion | Araceli | PEO | 2017 | DILG - BUB / LGSF | 3235000 | [7 empty] | 100% |  | By contract | Completed | Lea & Sons Trading & Construction | TIN 134-897-002
389 | Concreting of Local Core Road | B2 TF 416 DILG DSWD DBM BUB 17-096 | Transportation Facilities |  | Brgy. Poblacion, Dumaran , Palawan | Dumaran | PEO | 2017 | DILG - BUB / LGSF | 5000000 | 4995034.9 | 130 | 2017-12-11 |  | 2018-04-20 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
390 | Construction of School Library, Dumaran National High School | B2 TF 416 DILG DSWD DBM BUB 17-095 | Educational Facilities | 1 Unit Kindergarten Classroom | Dumaran National High School | Dumaran | PEO | 2017 | DILG - BUB/LGSF | 1200000 | 1197687.63 | 90 | 2017-10-19 |  | 2018-01-17 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
391 | Construction of 1 unit Kindergarten Classroom at Lamane ES, Quezon North District |  | Educational Facilities | 1 Unit Kindergarten Classroom | Lamane ES, Quezon North District | Quezon | PEO | 2017 | Special Education Fund | 916665 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
392 | Construction of 1 unit Kindergarten Classroom at Tara ES, Camanga Annex, Coron Inland |  | Educational Facilities | 1 Unit Kindergarten Classroom: Area: 63.00 sq.m | Tara ES, Camanga Annex, Coron Inland | Coron | PEO | 2017 | Special Education Fund | 1000000 | 997425.93 | 120 | [7 empty] | By contract | For Validation | Reinastar Trading and Construction | TIN 944-093-894-001
393 | Construction of 1 Unit of Kindergarten Classroom at Pamantolon ES | B2 SEF 300-17-10-16649 | Educational Facilities | 1 Unit Kindergarten Classroom | Kindergarten Classroom. ES | Taytay | PEO | 2017 | Special Education Fund | 916665 | 916237.39 | 120 | 2018-01-10 |  | 2018-05-10 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
394 | Construction of 1 unit Kindergarten Classroom at Culandanum | B2 SEF 300-17-10-16648 | Educational Facilities | 1 Unit Kindergarten Classroom | Culandanum Elementary School, Aborlan, Palawan | Aborlan | PEO | 2017 | Special Education Fund | 916665 |  |  | 2017-11-17 |  | 2017-11-17 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
395 | Construction of (3) Classroom of School Building Tara National Highschool |  | Educational Facilities | 3 Classroom School Building | Tara, Coron, Palawan | Coron | PEO | 2017 | Special Education Fund | 2400000 |  | 120 | 2018-03-09 |  | 2018-07-07 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
396 | Construction of 3 Classroom School Building in Camanga Elementary School, Bgy Tara | B2 SEF 300-17-12-22106 | Educational Facilities | 3 Classroom School Building | Camanga Elementary School | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2397041.4 | 120 | 2018-03-12 |  | 2018-07-10 |  |  |  |  | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
397 | Construction of 3 Classroom School Building in Sagrada Elementary School, Bgy Sagdrada | B2 SEF 300-17-12-2109 | Educational Facilities | 3 Classroom School Building | Bgy Sagrada | Busuanga | PEO | 2017 | Special Education Fund | 2250000 |  |  | 2018-03-12 |  | 2018-03-12 |  |  | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
398 | Construction of 3 Classroom School Building in Calauit Elementary School, Bgy Calauit |  | Educational Facilities | 3 Classroom School Building | Bgy Calauit | Busuanga | PEO | 2017 | Special Education Fund | 2250000 | [7 empty] | 100% |  | By contract | Completed | Reinastar Trading and Construction | TIN 944-093-894-001
399 | Construction of 3 Classroom School Building in San Nicolas National High School, Bgy. San Nicolas | B2 SEF 300-17-12-22107 | Educational Facilities | 3 Classroom School Building | San Nicolas National High School, Bgy. San Nicolas | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2244986.66 | 120 | 2018-03-12 |  | 2018-07-10 |  |  |  |  | By contract | Notice to Terminate | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
400 | Construction of 3 Classroom School Building in Capayas Elementary School, Bgy. VI | B2 SEF 300-17-12-22105 | Educational Facilities | 3 Classroom School Building | Bgy. VI, Coron, Palawan | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2245060.42 | 120 | 2018-03-12 |  | 2018-07-10 |  |  |  |  | By contract | Notice to Terminate | Reinastar Trading and Construction | TIN 944-093-894-001 | No accomplishment
401 | Construction of 4 Classroom School Building in Carlos M. Virrey National High School, Bgy. Saraza |  | Educational Facilities | 4 Classroom School Building | Bgy. Saraza | Brooke's Point | PEO | 2017 | Special Education Fund | 3000000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
402 | Construction of 2 Classroom School Building in Balen-balen Elementary School, Bgy. Ransang |  | Educational Facilities | 2 Classroom School Building | Bgy. Ransang | Rizal | PEO | 2017 | Special Education Fund | 1480721 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
403 | Construction of 4 CL Sch. Bldg. at Aramaywan ES, Bgy. Aramaywan |  | Educational Facilities | 4 Classroom School Building | Bgy. Aramaywan | Quezon | PEO | 2017 | Special Education Fund | 3000000 | [7 empty] | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
404 | Construction of 4 CL Sch. Bldg. at Marcelo Batuy NHS, Bgy. San Juan |  | Educational Facilities | 4 Classroom School Building | Bgy. San Juan | Aborlan | PEO | 2017 | Special Education Fund | 3000000 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
405 | Construction of Multi-Purpose Building Type II, Sitio Ogis, Rizal, Palawan |  | Other Infrastructure |  | Sitio Ogis | Rizal | PEO | 2017 |  | 950000 | 948416.55 |  | 2017-10-06 |  | 2017-10-06 |  |  | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
406 | Upgrading of Villa Constancia Bailey Bridge to RCDG | ROAD 300-16-06-05893 | Transportation Facilities |  | Villa Constancia | Dumaran | PEO | 2017 |  | 7320000 | 7306468.95 | 210 | 2017-03-07 |  | 2017-10-03 |  |  | 100% |  | By contract | Completed | E.V Villaos Trading and Construction Supply | TIN 142-914-104
407 | Construction of Road Network inside Quezon Medicare Hospital Facilities |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 5389000 | 5359489.63 | 120 | 2019-06-28 |  | 2019-10-26 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
408 | Const. of Bahay Tuluyan in Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | 20% Development Fund | 1800000 | [7 empty] | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
409 | Supply and Installation of 75 KVA Transformer and accessories in Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 1215433.49 | [7 empty] | 100% |  | By contract | Completed
410 | Const. of Multi Purpose Building in Narra, Palawan |  | Other Infrastructure |  | Narra Sports Complex | Narra | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3350000 | 3334388.82 |  | 2019-05-30 |  | 2019-05-30 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
411 | Upgrading of Tagumpay Bailey Bridge I to RCDG So. Tagumpay, Sta. Maria Dumaran | B2 SB6 PEO18 300-19-03-01980 | Transportation Facilities |  | Bgy. Sta. Maria | Dumaran | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 6620000 | 6280557.81 | 200 | 2019-06-28 |  | 2020-01-14 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
412 | Upgrading of Tagumpay Bailey Bridge II to RCDG So. Tagumpay, Sta. Maria Dumaran | B2 SB6 PEO18 300-19-03-01529 | Transportation Facilities |  | Bgy. Sta. Maria | Dumaran | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 5300000 | 4982200.66 | 140 | 2019-06-25 |  | 2019-11-12 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
413 | Construction of Distribution System, Paly, Taytay |  | Power and Energy Development Program |  | Bgy. Paly | Taytay | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 2984566.51 | [7 empty] | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
414 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 1900000 | 1853317.92 |  | 2019-10-08 |  | 2019-10-08 |  |  | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
415 | Construction. of Material Recovery Facilities |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 900000 | [7 empty] | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
416 | Construction of Mortuary Building |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 950000 | [7 empty] | 100% |  | By contract | Completed | GB Jade Construction and Trading | TIN 940-685-564
417 | Construction of Elevated Water Tank 300 CU.M Deepwell and Water Treatment Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 6592920 | 6631000 | [6 empty] | 100% |  | By contract | Completed | Hardrock Platinum Development Corporation | TIN 008-625-254
418 | Construction of Dietary/Linen Building |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3283679.49 | 3283265.52 | 230 | 2019-04-21 |  | 2019-12-07 |  |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
419 | Construction of Isolation Building |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3455339.91 | 3454681.86 |  | 2019-04-21 |  | 2019-04-21 |  |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
420 | Construction of Sewage Treatment Plant (Phase I) Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2018 | Locally Funded - Supplemental Budget No. 6 | 3600000 | 3491607.31 |  | 2019-09-09 |  | 2019-09-09 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
421 | Construction of Airstrip Perimeter Fence |  | Ports and Airports |  |  | Rizal | PEO | 2018 | Locally Funded | 6996542.93 | [9 empty] | By contract | For Termination | Johnstar Trading and Construction Supply | TIN 912-843-647
422 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 6613021.87 | 6279648.16 |  | 2018-08-15 |  | 2018-08-15 |  | 2020-11-03 | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
423 | Construction of Bahay Tuluyan in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 1800000 | 1794564.82 | 60 | 2021-08-24 |  | 2021-10-23 |  |  | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
424 | Construction of Three (3) - Storey Medical & Ward Building with Roof Deck for Helipad - Phase I in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 16943558 | 16935788.61 | [6 empty] | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
425 | Construction of Perimeter Fence Phase 2 in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | 20% Development Fund | 1055000 | [7 empty] | 100% |  | By contract | Completed | Eddmari Construction & Trading | TIN 141-763-814
426 | Construction of Doctor's Quarter in Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 5389000 | 5386970.89 |  | 2018-08-10 |  | 2018-08-10 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
427 | Construction of Motorpool/Powerhouse in Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 1700000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
428 | Construction of Mortuary Building in Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 810000 | 768396.54 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
429 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 6613021 | 6398568.58 | 90 | 2018-09-26 |  | 2018-12-25 | 2019-07-02 |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
430 | Supply & Installation of 3 Transformers/Accessories/Panel Board/ Main Cable in Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2018 | 20% Development Fund | 2566217 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
431 | Construction of Isolation Building in Dr Jose Rizal Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 2900000 | 2837760.6 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
432 | Construction of Material Recovery Facilities Building in Dr Jose Rizal Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 650000 | 646401.78 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
433 | Construction of Motorpool/Powerhouse in Dr Jose Rizal Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 1700000 | 1667428.99 | [6 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
434 | Concreting of Road inside Hospital Facilities in Dr Jose Rizal Hospital |  | Medical Facilities | (a) PCCP: 497m (4m and 5m width) (b) Veh gate: 6m (w) x 2m (h) x 2 sets (C) Ped gate: 1.8(w) x 2m (h) (d) 6" PVC: 60 ln.m | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 3500000 | 3496381.73 | 60 | [5 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
435 | Construction of Perimeter Fence Phase 2 in Dr Jose Rizal Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 2713000 | 2710750.96 | [8 empty] | By contract | Terminated | Maryknoll Builders and Supply | TIN 105-802-318
436 | Supply & Installation of 3 Transformers/Accessories/Panel Board/ Main Cable in Dr Jose Rizal Hospital |  | Medical Facilities |  | Dr Jose Rizal Hospital | Rizal | PEO | 2018 | 20% Development Fund | 2101217 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
437 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Dr Jose Rizal Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2018 | 20% Development Fund | 6613021 | 6263177.93 |  | 2018-11-16 |  | 2018-11-16 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
438 | Construction of Powerhouse Building in Roxas District Hospital | B2 PEO 300-18-05-07645 | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2018 | 20% Development Fund | 1700000 | 1693565.82 | 90 | 2018-08-09 |  | 2018-11-07 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
439 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities in Roxas District Hospital | B2 PEO 300-18-05-07644 | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2018 | 20% Development Fund |  | 6398568.58 | 90 | 2018-09-25 |  | 2018-12-24 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
440 | Purchase of 3 Transformer/Accessories/Panel Board/ Main Cable in Roxas District Hospital |  | Medical Facilities |  | Roxas District Hospital | Roxas | PEO | 2018 | 20% Development Fund | 2566217 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
441 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Banbanan | Covered Courts | Other Infrastructure |  | Bgy. Banbanan | Taytay | PEO | 2018 | Philippines Veterans Bank Loan | 3052155.48 | 3052127.77 | 150 | 2018-10-03 |  | 2019-03-02 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
442 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bato | Covered Courts | Other Infrastructure |  | Bgy. Bato | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2018-10-03 |  | 2019-03-02 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
443 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Beton (Island) | Covered Courts | Other Infrastructure |  | Bgy. Beton (Island) | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
444 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Busy Bees | Covered Courts | Other Infrastructure |  | Bgy. Busy Bees | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3760391.23 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
445 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calawag | Covered Courts | Other Infrastructure |  | Bgy. Calawag | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3241540.44 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
446 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Cataban | Covered Courts | Other Infrastructure |  | Bgy. Cataban | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3241540.43 |  | 2020-10-16 |  | 2020-10-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
447 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Depla (Island) | Covered Courts | Other Infrastructure |  | Bgy. Depla (Island) | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3502266.88 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
448 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Liminangcong (Roofing Only) | Covered Courts | Other Infrastructure |  | Bgy. Liminangcong | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 1997639.38 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | For Termination | Ivy Michelle Construction and Trading | TIN 009-492-339
449 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Guinlo | Covered Courts | Other Infrastructure |  | Bgy. New Guinlo | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
450 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Old Guinlo | Covered Courts | Other Infrastructure |  | Bgy. Old Guinlo | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
451 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pamantolon | Covered Courts | Other Infrastructure |  | Bgy. Pamantolon | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
452 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pancol | Covered Courts | Other Infrastructure |  | Bgy. Pancol | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 |  | 2019-11-12 |  | 2019-11-12 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
453 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Paly Island | Covered Courts | Other Infrastructure |  | Bgy. Paly Island | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
454 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pularaquen(Canique) | Covered Courts | Other Infrastructure |  | Bgy. Pularaquen(Canique) | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
455 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sandoval | Covered Courts | Other Infrastructure |  | Bgy. Sandoval | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3760391.23 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
456 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Silanga | Covered Courts | Other Infrastructure |  | Bgy. Silanga | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
457 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Libertad | Covered Courts | Other Infrastructure |  | Bgy. Libertad | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
458 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Minapla | Covered Courts | Other Infrastructure |  | Bgy. Minapla | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
459 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Talog | Covered Courts | Other Infrastructure |  | Bgy. Talog | Taytay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052155.48 | 3052127.77 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
460 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Maroyogroyog | Covered Courts | Other Infrastructure |  | Bgy. Maroyogroyog | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
461 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Culaylayan | Covered Courts | Other Infrastructure |  | Bgy. New Culaylayan | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | [6 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
462 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Nicolas | Covered Courts | Other Infrastructure |  | Bgy. San Nicolas | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223543.18 | 4223081.97 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
463 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calibangbangan | Covered Courts | Other Infrastructure |  | Bgy. Calibangbangan | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5028459.53 | 150 | 2019-12-26 |  | 2020-05-24 |  |  |  |  | By contract | For Termination | Kudz Trading and Construction | TIN 188-527-256
464 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Decabaitot | Covered Courts | Other Infrastructure |  | Bgy. Decabaitot | Linapacan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5028459.53 | 150 | 2019-12-26 |  | 2020-05-24 |  |  |  |  | By contract | For Termination | Kudz Trading and Construction | TIN 188-527-256
465 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sta. Cruz | B2 SB1 PEO 300-19-03-02426 | Other Infrastructure |  | Bgy. Sta. Cruz | Cagayancillo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5173349.53 | 150 | 2019-07-30 |  | 2019-12-27 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
466 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lipot South (Pob.) | B2 SB1 PEO 300-19-03-02428 | Other Infrastructure |  | Bgy. Lipot South (Pob.) | Cagayancillo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5173349.53 | 150 | 2019-07-30 |  | 2019-12-27 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
467 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Talaga | B2 SB1 PEO 300-19-03-02427 | Other Infrastructure |  | Bgy. Talaga | Cagayancillo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 5185509.01 | 5173349.53 | 150 | 2019-07-30 |  | 2019-12-27 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
468 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Dumarao | Covered Courts | Other Infrastructure |  | Bgy. Dumarao | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
469 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Antonino | Covered Courts | Other Infrastructure |  | Bgy. Antonino | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3052486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
470 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bagong Bayan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Bagong Bayan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053507.61 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
471 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Caramay | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Caramay | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
472 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Iraan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Iraan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
473 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Jolo | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Jolo | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
474 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malcampo | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Malcampo | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
475 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Barbacan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. New Barbacan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
476 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Cuyo | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. New Cuyo | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
477 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Barangay I (Poblacion) | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Barangay I (Poblacion) | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
478 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Rizal | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Rizal | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
479 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Salvacion | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Salvacion | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
480 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Isidro | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. San Isidro | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
481 | Construction of Covered Court/ Evacuation Center Phase 2 Bgy. San Jose | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. San Jose | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
482 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Miguel | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. San Miguel | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3054898.58 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
483 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Nicholas | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. San Nicholas | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
484 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sandoval, Roxas | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Sandoval, Roxas | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
485 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tagumpay | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Tagumpay | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3054898.58 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
486 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Taradungan | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Taradungan | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
487 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tinitian | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Tinitian | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3761846.12 | 3761846.12 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
488 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Nicanor Zabala | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Nicanor Zabala | Roxas | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3054898.58 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
489 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Mendoza | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Mendoza | Roxas | PEO | 2018 | NA | 3053507.61 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
490 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Minara | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. Minara | Roxas | PEO | 2018 | NA | 3053507.61 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
491 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. III (Poblacion) | B2 PEO Covered Court/evacuation Center Phase I Package 2 - Costruction and repair of 30 units covered court/evacuation center phase I (3 units in SE) (27 units in Roxas) | Other Infrastructure |  | Bgy. III (Poblacion) | Roxas | PEO | 2018 | NA | 3053507.61 | 3053486.67 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
492 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Iraray | B2 PEO Covered Court/evacuation Center Phase I Package 2 | Other Infrastructure |  | Bgy. Iraray | Sofronio Española | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3684653.76 | 3682930.15 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
493 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Labog | B2 PEO Covered Court/evacuation Center Phase I Package 2 | Other Infrastructure |  | Bgy. Labog | Sofronio Española | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.55 | 2974211.29 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
494 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Panitian | B2 PEO Covered Court/evacuation Center Phase I Package 2 | Other Infrastructure |  | Bgy. Panitian | Sofronio Española | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2974211.29 | 2974211.29 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
495 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Balogo | Covered Courts | Other Infrastructure |  | Bgy. Balogo | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4220052.28 | 4219451.21 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
496 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Dagman | Covered Courts | Other Infrastructure |  | Bgy. Dagman | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Termination
497 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Dalayawon | Covered Courts | Other Infrastructure |  | Bgy. Dalayawon | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3576544.12 | 3572790.65 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | For Termination
498 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lumacad | Covered Courts | Other Infrastructure |  | Bgy. Lumacad | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3393834.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
499 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Madoldolon (Expand 14.4x27.20) | Covered Courts | Other Infrastructure |  | Bgy. Madoldolon | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
500 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Mauringuen (15.8x29.20) | Covered Courts | Other Infrastructure |  | Bgy. Mauringuen | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
501 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Osmeña (Expand 15.15x31) | Covered Courts | Other Infrastructure |  | Bgy. Osmeña | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 |  | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  | 2022-11-13 | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
502 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Jose De Oro | Covered Courts | Other Infrastructure |  | Bgy. San Jose De Oro | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
503 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Santo Niño | Covered Courts | Other Infrastructure |  | Bgy. Santo Niño | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
504 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Taloto | Covered Courts | Other Infrastructure |  | Bgy. Taloto | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
505 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tudela (Calandagan) | Covered Courts | Other Infrastructure |  | Bgy. Tudela (Calandagan) | Araceli | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3400068.54 | 3394021.12 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
506 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bacao | Covered Courts | Other Infrastructure |  | Bgy. Bacao | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4220052.28 | 4219451.21 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
507 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calasag | Covered Courts | Other Infrastructure |  | Bgy. Calasag | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4220052.28 | 4219451.21 | 150 | 2019-01-17 |  | 2019-06-16 |  | 2022-11-13 | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
508 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Capayas | Covered Courts | Other Infrastructure |  | Bgy. Capayas | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756944.8 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
509 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Catep | Covered Courts | Other Infrastructure |  | Bgy. Catep | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3498581.69 | 3498086.07 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
510 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Culasian | Covered Courts | Other Infrastructure |  | Bgy. Culasian | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3048664.58 | 3048972.25 |  | 2019-11-12 |  | 2019-11-12 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
511 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Danleg | Covered Courts | Other Infrastructure |  | Bgy. Danleg | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3048664.58 | 3048972.24 |  | 2019-11-12 |  | 2019-11-12 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
512 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Ilian | Covered Courts | Other Infrastructure |  | Bgy. Ilian | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756943.58 |  | 2020-01-19 |  | 2020-01-19 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
513 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Juan | Covered Courts | Other Infrastructure |  | Bgy. San Juan | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3498581.69 | 3498086.07 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
514 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Santo Thomas | Covered Courts | Other Infrastructure |  | Bgy. Santo Thomas | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3498581.69 | 3498086.07 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
515 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tanatanaen | Covered Courts | Other Infrastructure |  | Bgy. Tanatanaen | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756943.58 |  | 2019-05-03 |  | 2019-05-03 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
516 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tanatanaen | Covered Courts | Other Infrastructure |  | Bgy. Santa Maria | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3756697.97 | 3756943.58 |  | 2019-05-03 |  | 2019-05-03 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
517 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Magsaysay | Covered Courts | Other Infrastructure |  | Bgy. Magsaysay | Dumaran | PEO | 2018 | Philippines Veterans Bank Loan 2019 | 3756697.97 | 3756944.8 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
518 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Banuang Daan | Covered Courts | Other Infrastructure |  | Bgy. Banuang Daan | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
519 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bintuan | Covered Courts | Other Infrastructure |  | Bgy. Bintuan | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
520 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Borac | Covered Courts | Other Infrastructure |  | Bgy. Borac | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
521 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Buenavista | Covered Courts | Other Infrastructure |  | Bgy. Buenavista | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
522 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bulalacao | Covered Courts | Other Infrastructure |  | Bgy. Bulalacao | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
523 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Decabobo | Covered Courts | Other Infrastructure |  | Bgy. Decabobo | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
524 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Decalachao | Covered Courts | Other Infrastructure |  | Bgy. Decalachao | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
525 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Guadalupe | Covered Courts | Other Infrastructure |  | Bgy. Guadalupe | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
526 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malawig | Covered Courts | Other Infrastructure |  | Bgy. Malawig | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 | 2022-07-07 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
527 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Marcilla | Covered Courts | Other Infrastructure |  | Bgy. Marcilla | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 | 2022-07-16 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
528 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. I (Poblacion) | Covered Courts | Other Infrastructure |  | Bgy. I (Poblacion) | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
529 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. IV (Poblacion) | B2 PEO Covered Court/Evacuation Center Phase I-Package 4 | Other Infrastructure | Court: 30(m) L x 118m (W) | Bgy. IV (Poblacion) | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  |  |  | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654
530 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. V (Poblacion), Coron | Covered Courts | Other Infrastructure |  | Bgy. V (Poblacion), Coron | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 | Subject for LD |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
531 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Jose | Covered Courts | Other Infrastructure |  | Bgy. San Jose | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 130 | 2020-06-01 |  | 2020-10-09 | 2022-07-14 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
532 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Nicholas, Coron | Covered Courts | Other Infrastructure |  | Bgy. San Nicholas, Coron | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
533 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tagumpay, Coron | Covered Courts | Other Infrastructure |  | Bgy. Tagumpay, Coron | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 | 2022-08-31 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
534 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tara | Covered Courts | Other Infrastructure |  | Bgy. Tara | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-03-09 |  | 2019-08-06 | 2019-09-21 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
535 | Construction of 4CL School Building in Tagpait Elementary School |  | Other Infrastructure | 4 Classroom School Building |  | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
536 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Barangay VI (Poblacion) | Covered Courts | Other Infrastructure |  | Bgy. Barangay VI (Poblacion) | Coron | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2018-10-09 |  | 2019-03-08 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
537 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bogtong | Covered Courts | Other Infrastructure |  | Bgy. Bogtong | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
538 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Buluang | Covered Courts | Other Infrastructure |  | Bgy. Buluang | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
539 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Cheey | Covered Courts | Other Infrastructure |  | Bgy. Cheey | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
540 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Concepcion | Covered Courts | Other Infrastructure |  | Bgy. Concepcion | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 | 2022-07-23 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
541 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Maglalambay (Island) | Covered Courts | Other Infrastructure |  | Bgy. Maglalambay (Island) | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 | Subject for LD |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
542 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Busuanga (Poblacion) | Covered Courts | Other Infrastructure |  | Bgy. New Busuanga (Poblacion) | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 | 2022-08-03 |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
543 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Old Busuanga | Covered Courts | Other Infrastructure |  | Bgy. Old Busuanga | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
544 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Panlaitan | Covered Courts | Other Infrastructure |  | Bgy. Panlaitan | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  |  |  | By contract | Cancelled | BCT Trading and Construction | TIN 102-698-654
545 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Quezon | Covered Courts | Other Infrastructure |  | Bgy. Quezon | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  |  |  | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654
546 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sagrada | Covered Courts | Other Infrastructure |  | Bgy. Sagrada | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 | 2022-07-24 |  |  |  | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654
547 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Isidro,Busuanga | Covered Courts | Other Infrastructure |  | Bgy. San Isidro,Busuanga | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 | 2022-08-26 |  |  |  | By contract | Notice to Terminate | BCT Trading and Construction | TIN 102-698-654
548 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Rafael | Covered Courts | Other Infrastructure |  | Bgy. San Rafael | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223995.52 | 150 | 2019-10-09 |  | 2020-03-07 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
549 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Santo Niño, Busuanga | Covered Courts | Other Infrastructure |  | Bgy. Santo Niño, Busuanga | Busuanga | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4223995.52 | 3400068.54 | 150 | 2019-10-09 |  | 2020-03-07 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
550 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Balading | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Brgy. Balading, Cuyo, Palawan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
551 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bangcal (Poblacion) | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Bangcal (Poblacion), Cuyo, Palawan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
552 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Cagigsing (Poblacion) | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Cagigsing (Poblacion) | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
553 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Caburian | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Caburian | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 |  | 2019-06-16 | Subject for LD |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
554 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Caponayan | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Caponayan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Project price escalation
555 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Catadman (Poblacion) | Covered Courts | Other Infrastructure |  | Bgy. Catadman | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 | Subject for LD |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
556 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lagaoriao (Poblacion) | B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Lagaoriao | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3501163.37 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Not moving
557 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lubid | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Lubid | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Not yet started
558 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lungsod (Poblacion) | Covered Courts | Other Infrastructure |  | Bgy. Lungsod (Poblacion) | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
559 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Pawa | Covered Courts | Other Infrastructure |  | Bgy. Pawa | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
560 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Carlos | Covered Courts | Other Infrastructure |  | Bgy. San Carlos | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  | 2023-05-01 | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
561 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tocadan | Covered Courts | Other Infrastructure |  | Bgy. Tocadan | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
562 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Alcoba | Covered Courts | Other Infrastructure |  | Bgy. Alcoba | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
563 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Balaguen | Covered Courts | Other Infrastructure |  | Bgy. Balaguen | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
564 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Canipo | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (13 Units in Cuyo - 11 Units in Magsaysay) Php 92,673,447.29 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 5 - B2 PEO Covered Court/Evacuation Center Phase I - Package 5 | Other Infrastructure |  | Bgy. Canipo | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339 | Not moving
565 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Danawan (Poblacion) | Covered Courts | Other Infrastructure |  | Bgy. Danawan (Poblacion) | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
566 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Emilod | Covered Courts | Other Infrastructure |  | Bgy. Emilod | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
567 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Igabas | Covered Courts | Other Infrastructure |  | Bgy. Igabas | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
568 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lacaren | Covered Courts | Other Infrastructure |  | Bgy. Lacaren | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
569 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Los Angeles | Covered Courts | Other Infrastructure |  | Bgy. Los Angeles | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
570 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Lucbuan | Covered Courts | Other Infrastructure |  | Bgy. Lucbuan | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
571 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Rizal, Magsaysay | Covered Courts | Other Infrastructure |  | Bgy. Rizal, Magsaysay | Magsaysay | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4222188.28 | 4221919.7 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
572 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bagong Bayan, Magsaysay | Covered Courts | Other Infrastructure |  | Bgy. Bagong Bayan, Magsaysay | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3053486.67 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
573 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Buena Suerte Poblacion | Covered Courts | Other Infrastructure |  | Bgy. Buena Suerte Poblacion | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 | 150 | 2018-10-19 |  | 2019-03-18 |  |  |  |  | By contract | Cancelled | BCT Trading and Construction | TIN 102-698-654
574 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Barotuan | Covered Courts | Other Infrastructure |  | Bgy. Barotuan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 |  | 2020-06-01 |  | 2020-06-01 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
575 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bebeladan | Covered Courts | Other Infrastructure |  | Bgy. Bebeladan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
576 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Corong-corong Poblacion | Covered Courts | Other Infrastructure |  | Bgy. Corong-corong Poblacion | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
577 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Mabini | Covered Courts | Other Infrastructure |  | Bgy. Mabini | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
578 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Manlag | Covered Courts | Other Infrastructure |  | Bgy. Manlag | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
579 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Masagana Poblacion | Covered Courts | Other Infrastructure |  | Bgy. Masagana Poblacion | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
580 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. New Ibajay | Covered Courts | Other Infrastructure |  | Bgy. New Ibajay | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3760806.92 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
581 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sibaltan | Covered Courts | Other Infrastructure |  | Bgy. Sibaltan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3760806.92 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
582 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Fernando | Covered Courts | Other Infrastructure |  | Bgy. San Fernando | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
583 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Villa Paz | Covered Courts | Other Infrastructure |  | Bgy. Villa Paz | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
584 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Teneguiban | Covered Courts | Other Infrastructure |  | Bgy. Teneguiban | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 |  | 2018-10-10 |  | 2018-10-10 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
585 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Bucana | Covered Courts | Other Infrastructure |  | Bgy. Bucana | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3760933.55 | 3760806.92 |  | 2018-10-10 |  | 2018-10-10 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
586 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Aberawan | Covered Courts | Other Infrastructure |  | Bgy. Aberawan | El Nido | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3052900.16 | 3052703.72 |  | 2018-10-10 |  | 2018-10-10 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
587 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Gogognan | Covered Courts | Other Infrastructure |  | Bgy. Gogognan | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3682655.34 | 3683332.62 | 150 | 2019-08-06 |  | 2020-01-03 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
588 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Iraan, Aborlan | Covered Courts | Other Infrastructure |  | Bgy. Iraan, Aborlan | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3682655.34 | 3683332.62 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
589 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Magbabadil | Covered Courts | Other Infrastructure |  | Bgy. Magbabadil | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3683332.62 | 3683332.62 | 150 | 2018-10-19 |  | 2019-03-18 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
590 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. San Juan (pavement only) | Covered Courts | Other Infrastructure |  | Bgy. San Juan | Aborlan | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 651557.84 | 650251.85 |  | 2018-10-19 |  | 2018-10-19 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
591 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Binudac | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Binudac | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
592 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Galoc | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Galoc | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 |  |  |  |  | By contract | Notice to Terminate | Ivy Michelle Construction and Trading | TIN 009-492-339
593 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Luac | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Luac | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
594 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malaking Patag | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Malaking Patag | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
595 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Burabod | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Burabod | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
596 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Halsey | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Halsey | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 | 2022-03-20 |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
597 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Baldat | Construction and repiar of twenty four (24) units Covered Court/Evacuation Center Phase I (11 Units in Quezon - 13 Units in Culion) Php 91,518,740.78 - Phase I - Package No. 7 - B2 PEO COVERED/EVACUATION CENTER PHASE I - PACKAGE 7 | Other Infrastructure |  | Bgy. Baldat | Culion | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 4226286.28 | 4223608.28 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
598 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Aramaywan | Covered Courts | Other Infrastructure |  | Bgy. Aramaywan | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2973942.37 | 2972186.71 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
599 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calumpang | Covered Courts | Other Infrastructure |  | Bgy. Calumpang | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.37 | 2973942.37 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
600 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Isugod | Covered Courts | Other Infrastructure |  | Bgy. Isugod | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3684653.76 | 3681975.76 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
601 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Quinlogan | Covered Courts | Other Infrastructure |  | Bgy. Quinlogan | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.37 | 2973942.37 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
602 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Maasin | Covered Courts | Other Infrastructure |  | Bgy. Maasin | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
603 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Sowangan | Covered Courts | Other Infrastructure |  | Bgy. Sowangan | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 2976620.37 | 2973942.37 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
604 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tabon | Covered Courts | Other Infrastructure |  | Bgy. Tabon | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
605 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Calatagbak | Covered Courts | Other Infrastructure |  | Bgy. Calatagbak | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
606 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Malatgao | Covered Courts | Other Infrastructure |  | Bgy. Malatgao | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
607 | Construction of Covered Court/ Evacuation Center Phase 1 Bgy. Tagusao | Covered Courts | Other Infrastructure |  | Bgy. Tagusao | Quezon | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3681975.76 | 3681975.76 | 150 | 2019-07-17 |  | 2019-12-14 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
608 | Construction and Repair of Covered Court Evacuation Center Phase 1 |  | Other Infrastructure |  | Bgy. Bancal | Cuyo | PEO | 2018 | Philippines Veterans Bank Loan 2018 | 3504815.69 | 3500986.64 | 150 | 2019-01-17 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
609 | Repair and Upgrading of Mangsee Village Electrification Project |  | Power and Energy Development Program |  | Bgy. Mangsee | Balabac | PEO | 2018 | Trust Fund - (OCD FUNDS) | 3960878.13 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
610 | Construction of One School Building Melville Elementary School |  | Educational Facilities | 1 Classroom School Building | Bgy. Melville | Balabac | PEO | 2018 | Trust Fund - (OCD FUNDS) | 1372825.3 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
611 | Construction of One School Building Melville National High School |  | Educational Facilities | 1 Classroom School Building | Bgy. Melville | Balabac | PEO | 2018 | Trust Fund - (OCD FUNDS) | 1372826.3 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
612 | Construction of Balabac District Hospital Building Phase I |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2018 | DOH-Trust Fund | 7900000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
613 | Construction of Dietary /Linen Building (NPPH) |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2018 | DOH-Trust Fund | 1776000 | 1760796.53 | 160 | 2019-01-07 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ian and Jayson Construction | TIN 182-291-537
614 | Construction of Doctors/Nurses Quarter | B2 TF DUE TO NGAS 18-129 | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2018 | DOH-Trust Fund | 5550000 | 5381624.42 | 160 | 2019-01-07 |  | 2019-06-16 |  |  | 100% |  | By contract | Completed | Ian and Jayson Construction | TIN 182-291-537
615 | Construction of Three (3) Storey Medical Ward Building with Roof Deck for Helipad Phase 2 |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Brooke's Point | PEO | 2018 | DOH-Trust Fund | 8058600 | 8056808.23 |  | 2019-12-13 |  | 2019-12-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
616 | Construction of Mini-Port Phase I | B2 TF DUE TO NGAS 18-174 | Ports and Airports |  | Bgry. Mangsee, Balabac, Palawan | Balabac | PEO | 2018 | Trust Fund - DOTr |  | 9844495.6 | 240 | 2019-03-15 |  | 2019-11-10 |  |  |  |  | By contract | Terminated | Johnstar Trading and Construction Supply | TIN 912-843-647
617 | Construction of Sheltered Port Phase I Bgy. Pag-asa, Municipality of Kalayaan, Palawan | B2 TF DOTR BGY. PAG-ASA SHELTERED PORT DEVELOPMENT PROJECT 18-042 | Ports and Airports |  | Bgy. Pag-asa, Municipality of Kalayaan, Palawan | Kalayaan | PEO | 2018 | Trust Fund - DOTr | 450000000 | 416709467.72 | 510 | 2018-06-24 |  | 2019-11-16 |  |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
618 | Construction of 3 Classroom School Building in Ipilan National High School, Bgy Ipilan |  | Educational Facilities | 3 Classroom School Building | Bgy Ipilan | Brooke's Point | PEO | 2018 | Special Education Fund | 2250000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
619 | Construction of 2 Classroom School Building in Mendoza Elemenatry School, Bgy. Mendoza |  | Educational Facilities | 2 Classroom School Building | Bgy. Mendoza | Roxas | PEO | 2018 | Special Education Fund | 1500000 | [7 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
620 | Construction of 2 Classroom School Building at Narra ES, Bgy. Minara |  | Educational Facilities | 2 Classroom School Building | Bgy. Minara | Roxas | PEO | 2018 | Special Education Fund | 1500000 | 1493726.07 | [6 empty] | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
621 | Construction of 2 Classroom School Building in Burrirao National High School, Bgy. Burirao |  | Educational Facilities | 2 Classroom School Building | Bgy. Burirao | Narra | PEO | 2018 | Special Education Fund | 1500000 | 1492714.09 | 70 | 2018-09-26 |  | 2018-12-05 | 2018-12-26 |  | 100% |  | By contract | Completed | Nale Construction
622 | Construction of 2 Classroom School Building in Tobo Elementary School, Bgy Punta Baja |  | Educational Facilities | 2 Classroom School Building |  | Rizal | PEO | 2018 | Special Education Fund | 1500000 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
623 | Construction of 3 classroom School Building in Balingasag Elem. School, Bgy. Culasian |  | Educational Facilities | 3 Classroom School Building | Bgy. Culasian | Taytay | PEO | 2018 | Special Education Fund | 2250000 | 2245934.03 |  | 2018-09-12 |  | 2018-09-12 |  |  | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
624 | Construction 3-Classroom School Building, Bantulan Elementary School | B2 SEF 300-18-02-01124 | Educational Facilities | 3 Classroom School Building | Bantulan Elementary School | Taytay | PEO | 2018 | Special Education Fund | 2250000 | 2248739.33 | 100 | 2018-08-23 |  | 2018-12-01 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
625 | Construction 2-Classroom School Building Amoguez Elementary School | B2 SEF 300-18-02-01122 | Educational Facilities | 2 Classroom School Building | Amoguez Elementary School | Taytay | PEO | 2018 | Special Education Fund | 1500000 | 1496106.73 | 70 | 2018-08-23 |  | 2018-11-01 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
626 | Concreting of Cataban-Liminangcong Road | B2 TF CMGP 2018 18-11 | Transportation Facilities |  | Municipality of Taytay, Palawan | Taytay | PEO | 2018 | Kalsada | 77853114 | 77745024.91 | 334 | 2018-10-10 |  | 2019-09-09 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
627 | Concreting of Highway Junction Tumarbong Road | B2 TF CMGP 2018 18-075 | Transportation Facilities |  | Roxas, Palawan | Roxas | PEO | 2018 | Kalsada | 31151057 | 29923726.45 | 189 | 2018-08-14 |  | 2019-02-19 |  |  | 100% |  | By contract | Completed | Seven Digit Construction and Supplies | TIN 183-661-696
628 | Concreting of Latungay-Sta Teresita Road, Ph 2 |  | Transportation Facilities |  |  | Dumaran | PEO | 2018 | Kalsada | 40134637 | 38889231.12 | [6 empty] | 100% |  | By contract | Completed | Seven Digit Construction and Supplies | TIN 183-661-696
629 | Concreting of Araceli Road A Ph 2 |  | Transportation Facilities |  | Araceli | Araceli | PEO | 2018 | Kalsada | 40882842 | 40065185.03 | [6 empty] | 100% |  | By contract | Completed | Premium Megastructures Inc.
630 | Concreting of Lungsod-Igabas-Emilod Road (A) Ph 2 | B2 TF CMGP 2018 18-074 | Transportation Facilities |  | Bgy. Lungsod Igabas, Cuyo, Palawan | Cuyo | PEO | 2018 | Kalsada | 15034559 | 14733866.49 | 92 | 2018-10-09 |  | 2019-01-09 | 2019-12-31 |  | 100% |  | By contract | Completed | Octagon Concrete Solution | TIN 901-128-486
631 | Concreting of Lungsod-Balaguen Road B |  | Transportation Facilities |  | Bgy. Lungsod Igabas, Cuyo, Palawan | Magsaysay | PEO | 2018 | Kalsada | 15317722 | 15011366.36 | 113 | 2018-10-09 |  | 2019-01-30 |  |  | 100% |  | By contract | Completed | Octagon Concrete Solution | TIN 901-128-486
632 | Concreting of Magbabadil-Barake Road |  | Transportation Facilities |  |  | Aborlan | PEO | 2018 | Kalsada | 25171607 | 25004567.72 | 130 | [5 empty] | 100% |  | By contract | Completed | Werr Corporation International
633 | Concreting of Taritien Road | B2 TF CMGP 2018 18-078 | Transportation Facilities |  | Narra | Narra | PEO | 2018 | Kalsada | 24798543 | 20732610.22 | 170 | 2018-09-24 |  | 2019-03-13 |  |  | 100% |  | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547
634 | Elnido Water System Project Phase 1 |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | El Nido | PEO | 2018 |  | 46294665.62 | 46294665.62 |  | 2018-02-19 |  | 2018-02-19 |  |  | 100% |  | By contract | Completed
635 | Concreting of Cataban-Liminangcong Road (Intermittent Section) |  | Transportation Facilities |  |  | Taytay | PEO | 2018 |  | 8900000 | 8840406.05 |  | 2018-10-10 |  | 2018-10-10 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
636 | Construction of IP Village, Bunog |  | Other Facilities |  | Bgy. Bunog, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 2998634.31 | 2998634.31 | 180 | 2020-01-31 |  | 2020-07-29 |  |  | 100% |  | By contract | Completed | RAK Trading Construction & Supply
637 | Construction of Mortuary Building in Dr. Rizal District Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1135000 | 1129873.53 | 60 | 2019-12-16 |  | 2020-02-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
638 | Construction of Distribution System of Bancalaan 1 Village Electrifiction Project |  | Power and Energy Development Program |  | Bgy. Bancalaan I | Balabac | PEO | 2019 | 20% Development Fund | 12613597.66 | 11041248.36 |  | 2020-01-23 |  | 2020-01-23 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
639 | Installation of Communication System/Security Monitoring Devices (PBX, INTERCOM, CCTV) |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1090000 | [7 empty] | 100% |  | By contract | Completed | Western Fortune
640 | Construction of Sewage Treatment Plant in Dr. Jose Rizal District Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 3200000 | 3124809.97 | 60 | 2019-07-30 |  | 2019-09-28 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
641 | Construction of Sewage Treatment Plant | B2 SB1 PEO 300-19-03-02430 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3200000 | 3194884.2 | 60 | 2019-08-19 |  | 2019-10-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
642 | Construction of Dietary/Linen Building | B2 SB1 PEO 300-19-03-02442 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3416000 | 3395201.94 | 90 | 2019-06-28 |  | 2019-09-26 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
643 | Construction of Isolation Building | B2 SB1 PEO 300-19-03-02441 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3740000 | 3719074.68 | 120 | 2019-06-28 |  | 2019-10-26 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
644 | Construction of Motorpool/Powerhouse Building | B2 SB1 PEO 300-19-03-02505 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 2029000 | 2007506.45 | 150 | 2019-06-28 |  | 2019-11-25 | Subject for LD |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
645 | Construction of Material Recovery Facilities | B2 SB1 PEO 300-10-03-02440 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 1073000 | 1054041.98 | 30 | 2019-06-28 |  | 2019-07-28 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
646 | Construction of Perimeter Fence Phase 1 | B2 SB1 PEO 300-19--06-08777 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 3500000 | 3498790.87 | 120 | 2019-08-15 |  | 2019-12-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
647 | Construction of Doctors/Nurses Quarter, Coron District Hospital | B2 SB1 PEO 300-119-03-02419 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 5555000 | 5553227.08 | 150 | 2019-08-15 |  | 2020-01-12 |  |  |  |  | By contract | Order of Termination | Johnstar Trading and Construction Supply | TIN 912-843-647 | Inacceible site
648 | Rehabilitation/Improvement of Facilities at Coron District Hospital | B2 TF 416 DPWH DOH HFEP 17-154 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2017 | Trust Fund | 4000000 | 3999494.93 | 180 | 2017-10-27 |  | 2018-04-25 |  |  |  |  | By contract | For Termination | E.V Villaos Trading and Construction Supply | TIN 142-914-104
649 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities | B2 SB1 PEO 300-19-06-13183 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 7300000 | 7276730 | 90 | 2019-10-21 |  | 2020-01-19 |  |  |  |  | By contract | For Termination | Hardrock Platinum Development Corporation | TIN 008-625-254
650 | Construction of Mortuary Building | B2 SB1 PEO 300-19-03-02439 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 1135000 | 1113507.62 | 60 | 2019-06-28 |  | 2019-08-27 | Subject for LD |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
651 | Improvement of Hospital Landscaping and Fcilities | B2 SB1 PEO19-300-20-08-09854 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 2790554.75 | 2781729.24 | 120 | 2020-10-07 |  | 2021-02-04 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
652 | Supply and Installation of Airconditioning Unit |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 3980442 | [7 empty] | 100% |  | By contract | Completed | Nand Trading
653 | Construction of Doctors/Nurses' Quarter, Araceli/Dumaran District Hospital | B2 SB1 PEO 300-19-03-024 | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2019 | 20% Development Fund | 5800000 | 5553227.08 | 150 | 2019-10-15 |  | 2020-03-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
654 | Concreting of San Vicente District Hospital Road Network and Access Road |  | Medical Facilities | (a) PCCP (Road Network)=97.35m(l) x 5m(w) x 0.20m(l) - 356m(l) x 4m(w) x 0.20m(t) (b) PCCP (Access Road)=0.560 km x 5m(w) x 0.20m (t) - 1m shoulder both side - STA. 0+000 to STA. 0+560 | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 10500000 | 9540335.41 | 120 | 2019-10-22 |  | 2020-02-19 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
655 | Construction of Sewage Treatment Plant, San Vicente District Hospital |  | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 3200000 | 3068141.82 |  | 2019-07-31 |  | 2019-07-31 |  |  | 100% |  | By contract | Completed | IKM Builders & Construction Supply
656 | Construction of Bahay Tuluyan |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1800000 | 1797986.31 | 90 | 2019-08-15 |  | 2019-11-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
657 | Distribution System of Concepcion Village Elctrification Project | B2 SB4 PEO 300-19-11-21287 | Power and Energy Development Program |  | Bgy. Concepcion | Agutaya | PEO | 2019 | Supplemental Budget No. 4 | 8210705.55 | 8195898.89 | 105 | 2020-01-23 |  | 2020-05-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
658 | Construction of Road Network Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 6500000 | 6486107.1 |  | 2020-01-31 |  | 2020-01-31 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
659 | Construction of Dietary/Linen Building in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 3412192.76 | 3412192.76 | 180 | 2020-02-14 |  | 2020-08-12 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
660 | Construction of Motorpool/Powerhouse Building in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 2026258.99 | 2000565.43 | 90 | 2020-02-24 |  | 2020-05-24 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
661 | Construction of Perimeter Fence in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 1669993.6 | 1669576.86 | 120 | 2020-01-20 |  | 2020-05-19 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
662 | Construction of Multipurpose Building Type II, Mangsee Elementary School |  | Other Infrastructure |  | Mangsee Elementary School | Balabac | PEO | 2019 | 20% Development Fund | 3598655.44 | 3598655.44 | 150 | 2020-02-05 |  | 2020-07-04 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
663 | Construction of Multipurpose Building Type II, Paliisan Elementary School |  | Other Infrastructure |  | Paliisan Elementary School | Balabac | PEO | 2019 | 20% Development Fund | 3598655.44 | 3598655.44 | 150 | 2020-02-05 |  | 2020-07-04 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
664 | Construction of 3rd Floor OPD Building, Coron District Hospital | B2 SB4 PEO 300-19-11-21279 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2019 | 20% Development Fund | 5346192.81 | 5346051.19 | 120 | 2020-02-20 |  | 2020-06-19 | Subject for LD |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
665 | Construction of Distribution System of Bancalaan 2 Village Electrifiction Project |  | Power and Energy Development Program |  | Bgy. Bancalaan | Balabac | PEO | 2019 | 20% Development Fund | 11162045.48 | 11162045.48 | 120 | 2020-01-23 |  | 2020-05-22 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
666 | Evacuation/ Covered Court in Cabunlawan, Linapacan | SB 1 300-15-12-20589-20590 | Other Infrastructure |  | Cabunlawan, Linapacan | Linapacan | PEO | 2019 | 20% Development Fund | 5185509 |  | 150 | [5 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
667 | Construction of Transformer Platform in Bataraza District Hospital and Extension of 3 Phase Line from Highway to Transformer |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2019 | Supplemental Budget No. 4 | 1259946 | 1256727.22 | 60 | 2020-05-22 |  | 2020-07-21 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
668 | Construction of Three (3) Barrel RCBC, Kalawiton, Bgy. Canipaan |  | Other Infrastructure |  | Bgy. Canipaan | Rizal | PEO | 2019 | 20% Development Fund | 2851835 | 2849356.57 | 180 | 2019-07-11 |  | 2020-01-07 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
669 | Upgrading of Kaybulusan Bailey Bridge to RCDG, Purok Masigla, Bgy. Magara |  | Transportation Facilities |  | Bgy. Magara | Roxas | PEO | 2019 | 20% Development Fund | 7315000 | 7275366.56 |  | 2019-08-22 |  | 2019-08-22 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
670 | Upgrading of Malebeb Bailey Bridge to RCDG, Magara-Caruray Road, |  | Transportation Facilities |  |  | Roxas | PEO | 2019 | 20% Development Fund | 4920000 | 4918994.3 | 177 | 2019-05-17 |  | 2019-11-10 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
671 | Upgrading of Salban Bailey Bridge to RCDG, Dumaran | B2 SB4 PEO 300-19-11-21273 | Transportation Facilities |  | Bgy. Danleg | Dumaran | PEO | 2019 | 20% Development Fund | 6045200 | 5514577.04 | 180 | 2020-01-21 |  | 2020-07-19 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
672 | Upgrading of Ibalod Bailey Bridge to RCDG Sta. Maria, Dumaran |  | Transportation Facilities |  | Brgy. Ilian, Dumaran | Dumaran | PEO | 2019 | 20% Development Fund | 8125000 | 7970837.68 | 181 | 2020-02-13 |  | 2020-08-12 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
673 | Upgrading of Ibalod Bailey Bridge to RCDG Bgy. Ilian, Dumaran |  | Transportation Facilities |  |  | Dumaran | PEO | 2019 | 20% Development Fund | 7970837.68 | 7970837.68 |  | 2020-02-12 |  | 2020-02-12 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
674 | Upgrading of Kinabuyukan Bailey Bridge to RCDG Phase I |  | Transportation Facilities |  | Brgy. Caruray, San Vicente, Palawan | San Vicente | PEO | 2019 | 20% Development Fund | 7445000 | 6578371.87 | 182 | 2019-11-28 |  | 2020-05-28 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
675 | Distribution System of Tara Village Elctrification Project | BS SB4 PEO 300-19-11-21290 | Power and Energy Development Program |  | Bgry. Tara, Coron, Palawan | Coron | PEO | 2019 | 20% Development Fund | 9798841.16 | 9780949.66 |  | 2020-01-23 |  | 2020-01-23 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
676 | Upgrading of Kinabuyukan Bailey Bridge to RCDG, Phase II |  | Transportation Facilities |  |  | San Vicente | PEO | 2019 | 20% Development Fund | 1783556.74 | 1708065.39 |  | 2020-02-11 |  | 2020-02-11 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
677 | Construction of BHS Tumarbong, Roxas | BS SB4 PEO 300-19-11-21281 | Medical Facilities |  | Bgy. Tumarbong | Roxas | PEO | 2019 | Supplemental Budget No. 4 | 1500000 | 1498705.81 | 120 | 2020-01-20 |  | 2020-05-19 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
678 | Construction of BHS Caramay, Roxas |  | Medical Facilities |  | Bgy. Caramay | Roxas | PEO | 2019 | 20% Development Fund | 1500000 | 1498705.81 | 120 | 2020-01-20 |  | 2020-05-19 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
679 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities | Modern Tropical Garden | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 2790554.75 | 2784585.91 | 120 | 2020-03-06 |  | 2020-07-04 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
680 | Upgrading of Caponayan Barangay Road, Bgy. Caponayan, Cuyo, Palawan | B2 SB1 PEO 300-19-03-02425 | Transportation Facilities | Roads: PCCP: 1.180km x 1.8m (w) x 0.15m(t) - 0.92 km x 1.8m (w) x 0.15m (t) - Limits: Sta.0+000 - Sta. 0+180 - Sta.0+000 - Sta. 0+920 | Bgy. Caponayan | Cuyo | PEO | 2019 | Supplemental Budget No. 1 | 7854206.1 | 7617456.45 | 104 | 2019-06-26 |  | 2019-10-08 | 2020-06-24 |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
681 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 2844298.35 | 2842239.81 | 90 | 2019-08-20 |  | 2019-11-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
682 | Installation of Communication System/Security Monitoring Devices (PABX, INTERCOM,CCTV) |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2019 | 20% Development Fund | 1100000 |  |  | 2019-06-27 |  | 2019-06-27 |  |  | 100% |  | By contract | Completed
683 | Supply and Installation of Electrical Cables and Metering Accessories |  | Medical Facilities |  | Rizal District Hospital | Rizal | PEO | 2019 | 20% Development Fund | 1145166 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
684 | Construction of Perimeter Fence Phase III and Concrete Grease Filter in SPPH |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2019 | 20% Development Fund | 1645189.2 |  |  | 2020-02-06 |  | 2020-02-06 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
685 | Construction of Perimeter Fence | B2 SB1 PEO 300-19-06-08778 | Medical Facilities | Semi concrete fence=158.03m:53 span - Concrete fence=135m; 2.4m(h) x 3.0m(l) x 45.0 span | San Vicente District Hospital | San Vicente | PEO | 2019 | Supplemental Budget No. 1 | 2844298.35 | 2842652.87 | 120 | 2019-08-15 |  | 2019-12-13 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
686 | Supply & Installation of (47) Air Conditioning units (1.5hp,36/2hp,5/1hp,6) |  | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2019 | 20% Development Fund | 3069159.31 | [7 empty] | 100% |  | By contract | Completed | Nand Trading
687 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2019 | 20% Development Fund | 2695067.91 | 2693688.17 | 60 | 2019-08-19 |  | 2019-10-18 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
688 | Construction of Sewage Treatment Plant |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2019 | 20% Development Fund | 3200000 | 3194886 | 60 | 2019-08-16 |  | 2019-10-15 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
689 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2019 | 20% Development Fund | 2790554.75 | 2789042.41 | 90 | 2019-08-16 |  | 2019-11-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
690 | Supply and Installation of Electrical Cables and Metering Accessories |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2019 | 20% Development Fund | 2120085.3 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
691 | Improvement of Hospital Landscaping and Facilities |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 2713889.6 | 2711998.32 | 90 | 2019-08-16 |  | 2019-11-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
692 | Supply & Installation of 12 Units Air Conditioning units |  | Medical Facilities | Air-condition: 12 Units | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 719274 | [7 empty] | 100% |  | By contract | Completed
693 | Construction of Sewage Treatment Plant |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 3200000 | 3194888 | 60 | 2019-08-16 |  | 2019-10-15 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
694 | Supply and Installation of Electrical Cables and Metering Accessories |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2019 | 20% Development Fund | 1617907.24 | 1617907.24 | 10 | 2019-06-27 |  | 2019-07-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
695 | Const of Three (3) Barrel RCBC with Slope Protection and Pavement at Bgy. Busybees, Taytay |  | Other Infrastructure |  | Bgy. Busybees | Taytay | PEO | 2019 | 20% Development Fund | 5148622.47 | 4993683.1 | [6 empty] | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
696 | Construction of Multi-purpose Pavement |  | Other Facilities |  | Bgy. Burirao | Narra | PEO | 2019 | ROADS 15 300-19-10-18749 | 515000 | 509846.6 | 30 | 2020-02-23 |  | 2020-03-24 |  |  | 100% |  | By contract | Completed | VJ Builders
697 | Tubbataha Reef Ranger Station (Main Module, Research Module and Transportation Module) Phase 1 |  | Other Facilities |  | Tubbataha Reef, Cagayancillo, Palawan | Cagayancillo | PEO | 2019 | Trust Fund - TIEZA | 40000000 | 39899535.7 | 365 | 2020-01-14 |  | 2021-01-13 |  |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
698 | Construction of Caramay Hanging Bridge |  | Transportation Facilities |  | Bgy. Caramay | Roxas | PEO | 2019 | LGSF- DILG CMGP | 4300000 | 4248791.65 |  | 2020-01-07 |  | 2020-01-07 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
699 | Concreting of Highway Junction - Tumarbong Road (Intermittent Section) | B2 TF Due to NGAS-DILG/DBM CMGP 2019-19-137 | Transportation Facilities |  | Roxas, Palawan | Roxas | PEO | 2019 | CMGP | 41442579 | 36319060.55 | 184 | 2019-09-11 |  | 2020-03-13 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
700 | Concreting of Ilian - Bagumbayan - Latungay Road | B2 TF Due to NGAS-DILG/DBM CMGP 2019-19-138 | Transportation Facilities | 2.092 km | Roxas and Dumaran, Palawan | Roxas | PEO | 2019 | CMGP | 36303969 | 33113435.37 | 155 | 2019-09-25 |  | 2020-02-27 |  |  | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
701 | Concreting of Pulot III-Tabud Road |  | Transportation Facilities |  | Sofronio Española, Palawan | Sofronio Española | PEO | 2019 | CMGP | 25968806.92 | 25968806.92 | 160 | 2019-09-12 |  | 2020-02-19 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
702 | Concreting of Tubtub - Amas Road |  | Transportation Facilities |  |  | Brooke's Point | PEO | 2019 | CMGP | 29269302 | 26693338.96 |  | 2019-08-31 |  | 2019-08-31 |  |  | 100% |  | By contract | Completed | Chad Lourence Trading & Construction Services | TIN 919-616-230
703 | Concreting of Abongan - Alacalian - Binga - Banbanan Road | B2 TF DUE TO NGAS DILG CMGP 2019 19-184 | Transportation Facilities |  | Taytay, Palawan | Taytay | PEO | 2019 | CMGP | 51594656 | 51320890.34 | 184 | 2019-12-17 |  | 2020-06-18 |  |  | 100% |  | By contract | Completed | A.C. Rivero Development Corp | TIN 001-355-547
704 | Construction of Bids and Awards Committee Office Capitol Compound |  | Other Facilities |  | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2019 | Locally Funded | 2410530.58 | 2460407.64 | 120 | 2019-06-29 |  | 2019-10-27 |  |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
705 | Renovation of Capitol Commercial Complex, Capitol Compound, PPC |  | Other Facilities |  | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 5250000 | 5197482.2 | 180 | 2019-10-07 |  | 2020-04-04 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
706 | Renovation of Accounting Office |  | Other Facilities |  | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 999942.1 | 998552.27 | 150 | 2019-10-17 |  | 2020-03-15 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
707 | Construction of Warehouse for Disaster Relief Goods/Stockpile (Phase I) |  | Other Facilities |  | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 3799000.5 | 3779000.5 |  | 2019-10-22 |  | 2019-10-22 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
708 | Construction of Perimeter Fence, Lualhati Women Center of Palawan Situated at Provincial Agricultural Center, Bgy. Irawan, Puerto Princesa City |  | Other Facilities |  | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 1000000 | 919695.15 | 90 | 2020-01-08 |  | 2020-04-07 |  |  | 100% |  | By contract | Completed | Jas Trading and Construction
709 | Construction of Giraffe Coral Pen | B2 CSP18 300-19-03-02634 | Other Facilities |  | Calauit Safari Park | Busuanga | PEO | 2019 | General Fund | 549654 | 539384.67 | 60 | 2019-06-27 |  | 2019-08-26 |  |  |  |  | By contract | For Termination | RDF Trading and Construction | CTC 097-331-47
710 | Construction of Zebra Coral Pen | B2 CSP18 300-19-03-02634 | Other Facilities |  | Calauit Safari Park | Busuanga | PEO | 2019 | General Fund | 549654 | 539384.67 | 60 | 2019-06-27 |  | 2019-08-26 |  |  |  |  | By contract | For Termination | RDF Trading and Construction | CTC 097-331-47
711 | Construction of Animal Shed, Construction of Restroom, Rehabilitation of Dormitory Building and Renovation of Information Building, Calauit Safari Park, Busuanga, Palawan |  | Other Facilities |  | Calauit Safari Park | Busuanga | PEO | 2019 | General Fund | 5270018.92 | 5247930.02 | 315 | 2019-06-27 |  | 2020-05-07 |  |  |  |  | By contract | For Termination | Samurai Construction | TIN 919-621-019
712 | Construction of Covered Walk & Rehabilitation of Flagpole, Hall of Justice, Sta. Monica Heights, PPC. |  | Other Facilities |  | Sta. Monica Heights, Puerto Princesa City | Puerto Princesa City | PEO | 2019 | Locally Funded | 459000 | 457981.86 |  | 2019-12-17 |  | 2019-12-17 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
713 | Construction of One (1) Units Proposed New Banua Institute for Resiliency & Green Growth Center |  | Other Facilities |  | Bgy. Pangobilian, Brooke's Point | Bataraza | PEO | 2019 | General Fund | 2366077.52 | 2287036.27 | 120 | 2019-11-29 |  | 2020-03-28 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
714 | Construction of Isolation Building |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 3740000 | 3142459.67 | 200 | 2020-02-05 |  | 2020-08-23 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
715 | Construction of Dietary Building | B2 SB4 PEO 300-19-11-21494 | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 3416000 | 3244588.44 | 90 | 2020-02-05 |  | 2020-05-05 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
716 | Construction of Motorpool Building |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 2029000 | 2017036.46 | 150 | 2020-06-02 |  | 2020-10-30 |  |  | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
717 | Construction of Material Recovery Facilities Building |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1073000 | 1064515.62 | 30 | 2020-06-03 |  | 2020-07-03 |  |  | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
718 | Construction of Doctors Quarter Building | B2 SB4 PEO19 300-20-02-00681 | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 5555000 | 5448235.2 | 180 | 2020-06-02 |  | 2020-11-29 |  | 4526600% | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
719 | Construction of Transformer Platform in El Nido District Hospital and Extension of 3 Phase Line |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1299279 | 1289739.41 | 60 | 2020-01-23 |  | 2020-03-23 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
720 | Construction of Elevated Water Tank 300 m^3 with Deepwell/ Water Treatment Plant | B2 SB4 PEO 300-19-11-21499 | Medical Facilities | Transmission Lines - Deepwell and Pumping Station - Dual Filter Tube and Chlorination System - Chlorination Housing - 300m^3 Spherical Steel Elevated Tank | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 7300000 | 7295796 | 180 | 2020-01-21 |  | 2020-07-19 | Subject for LD |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
721 | Construction of Mortuary Building, El Nido Community Hospital |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1135000 | 1125634.27 |  | 2020-07-29 |  | 2020-07-29 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
722 | Installation of Fire Protection and Alarm System, El Nido Community Hospital | B2 SB4 PEO19 300-20-02-00677 | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 3418000 | 2800000 | 64 | 2020-02-24 |  | 2020-04-28 |  |  | 100% |  | By contract | Completed | Warlen Industrial and Sales Corporation
723 | Installation of Communication System/Security Monitoring Devices (PABX, Intercom & CCTV) | B2 SB4 PEO19 300-20-02-00678 | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2019 | DBP Loan | 1090000 | 1081326.15 |  | 2020-11-18 |  | 2020-11-18 |  |  | 100% |  | By contract | Completed
724 | Construction of Elevated Water Tank, Bgy. San Isidro | B2 SB4 PEO 300-19-11-21491 | Medical Facilities | Transmission Lines - Deepwell and Pumping System - Dual Filter Tube and Chlorination System - Chlorination Housing - 300m^3 Spherical Steel Elevated Tank | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 7300000 | 7295318 | 180 | 2020-07-18 |  | 2021-01-14 |  |  |  |  | By contract | For Termination | Kudz Trading and Construction | TIN 188-527-256 | For Legal Endorsement
725 | Construction of Transformer Platform in San Vicente District Hospital and Extension of 3 Phase Line from Highway to Transformer |  | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1299279 | 1287932.98 |  | 2020-01-24 |  | 2020-01-24 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
726 | Construction of Mortuary Building |  | Medical Facilities | 1 storey: 6.0m x 6.0m - steel trusses | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1135000 | 1063839.94 | 60 | 2021-02-12 |  | 2021-04-13 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
727 | Construction of Material Recovery Facilities |  | Medical Facilities | Buildings: 24.00 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1073000 | 1069798.04 | 30 | 2020-01-30 |  | 2020-02-29 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
728 | Construction of Dietary/Linen Building |  | Medical Facilities | Buildings: 200 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 3416000 | 3402587.7 | 90 | 2020-02-07 |  | 2020-05-07 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
729 | Construction Isolation Building |  | Medical Facilities | 1 storey: 20.0m(L) x 8.0m(W) - Steel Truss | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 3730033.72 | 3543291.67 | 90 | 2019-11-28 |  | 2020-02-26 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
730 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities | Buildings: 126 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 2029000 | 1848611.11 | 90 | 2020-04-27 |  | 2020-07-26 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
731 | Construction of Doctors/Nurses Quarter |  | Medical Facilities | Buildings: 560 sq.m | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 5555000 | 5381624.42 | 150 | 2020-01-31 |  | 2020-06-29 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
732 | San Vicente District Hospital - Installation of Fire Protection and Alarm System |  | Medical Facilities | Sprinkler heads: 389 sets - Smoke detector: 50 sets | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 3418000 | 2800000 | 64 | 2020-02-24 |  | 2020-04-28 |  |  | 100% |  | By contract | Completed | Warlen Industrial and Sales Corporation
733 | Installation of Communication System/Security Monitoring Devices (PABX, Intercom & CCTV) |  | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2019 | DBP Loan | 1090000 | 1081326.15 |  | 2020-11-17 |  | 2020-11-17 |  |  | 100% |  | By contract | Completed
734 | Construction of Motorpool Powerhouse Building |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2019 | DBP Loan | 2025246.02 | 2023304.42 |  | 2020-06-20 |  | 2020-06-20 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
735 | Construction of Dietary-Linen Building, Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2019 | DBP Loan | 3414563.6 | 3411525.72 | 230 | 2021-09-10 |  | 2022-04-28 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
736 | Construction of Roxas Water System Phase 2-2 |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Roxas | PEO | 2019 |  | 106000000 | 93339955.29 |  | 2020-05-22 |  | 2020-05-22 |  |  | 100% |  | By contract | Completed
737 | Construction of Poblacion Water Pipeline |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Balabac, Palawan | Balabac | PEO | 2019 |  | 8859000 | 8706200.69 |  | 2019-10-17 |  | 2019-10-17 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
738 | Improvement of Landscaping for Sofronio Española District Hopsital |  | Medical Facilities |  | Bgy. Pulot Center, Sofronio Española, Palawan | Sofronio Española | PEO | 2019 | Supplemental Budget | 900000 | 899029.67 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
739 | Construction of Lamayo Processing Center Phase II |  | Other Facilities |  | Sitio Yakal, New Guinlo | Taytay | PEO | 2019 | GAD Fund | 1500000 | 1438997.74 | 60 | 2019-12-16 |  | 2020-02-14 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
740 | Construction of Roxas Water System Phase 2-1 |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Roxas, Palawan | Roxas | PEO | 2019 |  | 135000000 | 134352788.88 |  | 2019-05-18 |  | 2019-05-18 |  |  | 100% |  | By contract | Completed
741 | Renovation/Rehabilitation of Existing Rural Agricultural Center Building and Perimeter Fence |  | Other Facilities |  | Sitio Igang, Poblacion | Taytay | PEO | 2020 |  | 3000000 | 2,675,106..49 |  | 2020-12-17 |  | 2020-12-17 |  |  | 100% |  | By contract | Completed
742 | Construction of Northern Palawan Provincial Hospital (Phase II) |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2020 | Supplemental Budget No. 12 | 30000000 | 29940281.89 | 210 | 2021-07-15 |  | 2022-02-10 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
743 | Construction of Balabac District Hospital Building Phase II |  | Medical Facilities |  | Balabac District Hospita | Balabac | PEO | 2020 | Supplemental Budget No. 12 | 30000000 | 29992169.47 | 180 | 2021-04-06 |  | 2021-10-03 | 2022-01-25 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
744 | Construction of Southern Palawan Provincial Hospital (Construction of Medical Workers Dormitory) |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2020 | 20% Development Fund | 10500000 | 8924986.55 | 135 | 2021-01-11 | 1 | 2021-05-26 | Subject for LD |  | 95.17% |  | By contract | On going | BCL Construction | TIN 308-390-430
745 | Construction of Bataraza District Hospital Perimeter Fence Phase II |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | 20% Development Fund | 3950000 | 3407331.82 |  | 2020-10-01 |  | 2020-10-01 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
746 | Installation of Transformer with Metering Accessories and Main Cable | B2 PEO 300-20-06-07368 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2020 | 20% Development Fund | 2868181.16 | 2861250.46 | 90 | 2020-07-29 |  | 2020-10-27 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
747 | Construction of Narra Municipal Hospital (Additional Ceiling Works inside Main Building) | B2 PEO 300-20-11-16949 | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2020 | 20% Development Fund | 1667256.34 | 1665187.73 | 120 | 2021-01-15 |  | 2021-05-15 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
748 | Construction of Multi-purpose Building with Perimeter Fence, |  | Other Infrastructure |  | Bgy. Bunog, Buliluyan, Bataraza | Bataraza | PEO | 2020 | 20% Development Fund | 6294996.21 | 6292990.05 |  | 2020-08-21 |  | 2020-08-21 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
749 | Construction of Sewage Treatment Plant |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | 20% Development Fund | 3200000 |  |  | 2020-08-10 |  | 2020-08-10 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
750 | Construction of Barangay Health Station |  | Medical Facilities |  | Brgy. Bunog, Municipality of Rizal, Palawan | Rizal | PEO | 2020 | 20% Development Fund | 2300000 | 2068031.4 | 120 | 2020-10-07 |  | 2021-02-04 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
751 | Construction/Rehabilitation of Maasin Bailey Bridge |  | Transportation Facilities |  | Bgy. Maasin | Quezon | PEO | 2020 | 20% Development Fund | 6378906.45 | 6378906.45 | 182 | 2020-05-09 |  | 2020-11-07 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
752 | Upgrading of Cataban Bailey Bridge II to RCDG | B2 PEO 300-20-07-08703 | Transportation Facilities |  | Bgry. Cataban, Taytay | Taytay | PEO | 2020 | 20% Development Fund | 16200000 | 14497276.33 | 197 | 2020-10-06 |  | 2021-04-21 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
753 | Construction/Extension of New Guinlo Boat Landing Phase II | B2 PEO 300-20-08-10035 | Ports and Airports |  | Municipality of Taytay, Palawan | Taytay | PEO | 2020 | 20% Development Fund | 2500000 | 2491169.78 | 90 | 2020-10-05 |  | 2021-01-03 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
754 | Construction of Barangay Health Station, Lagaoriao | B2 PEO 300-20-06-07373 | Medical Facilities |  | Bgy. Lagaoriao | Cuyo | PEO | 2020 | 20% Development Fund | 2300000 | 2294294.55 | 120 | 2020-07-28 |  | 2020-11-25 |  | 2022-10-15 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
755 | Construction of Barangay Health Station, Los Angeles |  | Medical Facilities |  | Bgy.Los Angeles | Magsaysay | PEO | 2020 | 20% Development Fund | 2294294.55 | 2294294.55 | 120 | 2020-07-28 |  | 2020-11-25 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
756 | Construction of Sewage Treatment Plant |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2020 | 20% Development Fund | 3200000 | 3196665.89 | 60 | 2020-08-10 |  | 2020-10-09 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
757 | Construction of Perimeter Fence in Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 4198409.61 | 4198409.61 | 120 | 2020-08-07 |  | 2020-12-05 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
758 | Construction/Rehabilitation of Hospital Buildings and Facilities Quezon Medicare Hospital, Phase III |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 26320104 | 26303910 |  | 2020-08-08 |  | 2020-08-08 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
759 | Final Completion Works of Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 17701415.93 | 17157910.52 | 180 | 2020-11-17 |  | 2021-05-16 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
760 | Construction of Doctors/Nurses' Quarter |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | 20% Development Fund | 5800000 | 5761269.01 |  | 2020-10-07 |  | 2020-10-07 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
761 | Construction of Evacuation Center/Multi-Purpose Bldg., Suba ,Cuyo Palawan | B2 PEO 300-20-09-12724 | Other Infrastructure | Floor Area: 9m x 6m = 54 sqm (Two-storey building) | Bgy. Suba, Cuyo, Palawan | Cuyo | PEO | 2020 | 20% Development Fund | 2800000 | 2798739.06 | 150 | 2021-01-04 |  | 2021-06-03 | 2021-07-23 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
762 | Construction of Evacuation Center/Multi-Purpose Building , Bunog, Rizal |  | Other Infrastructure |  | Rizal | Rizal | PEO | 2020 | 20% Development Fund | 1532067.65 | 1532067.65 | 120 | 2020-10-07 |  | 2021-02-04 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
763 | Concreting of Narra Municipal Hospital (Concreting of Roads Leading to Facilities) |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2020 | 20% Development Fund | 1332743.66 | 1330246.98 |  | 2021-04-06 |  | 2021-04-06 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
764 | Construction of Bataraza Distict Hospital (Installation of Airconditioning Units) |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | 20% Development Fund | 3454659 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
765 | Concreting of El Nido Community Hospital Road Network | B2 PEO 300-20-06-07385 | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 5921673.6 | 5908042.26 | 120 | 2020-09-03 |  | 2021-01-01 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
766 | Construction of El Nido Community Hospital (Installation of Airconditioning Units) |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 3454659 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
767 | Construction of Sewage Treatment Plan in El Nido Community Hospital |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 3196665.89 | 3150728.39 | 60 | 2019-08-10 |  | 2019-10-09 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
768 | Construction of Two (2) Additional rooms in Doctors Quarter Building | B2 PEO20 300-21-02-00390 | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2020 | 20% Development Fund | 1100000 | 1084825.82 | 120 | 2021-04-08 |  | 2021-08-06 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
769 | Final Completion Works of Coron District Hospital Building | B2 PEO20 300-21-00389 | Medical Facilities |  | Coron District Hospital Building | Coron | PEO | 2020 | 20% Development Fund | 11100000 | 11098723.94 | 180 | 2021-04-16 |  | 2021-10-13 |  |  |  |  | By contract | For Termination | Smmiley Builders and Trading | TIN 936-564-958
770 | Construction of Coron District Hospital (Installation of Distribution Panel Board, Main Cable and Other Electrical Material for the Main Building and Other Facilities) |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2020 | 20% Development Fund | 2702601 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
771 | Construction of San Juan hanging Bridge |  | Transportation Facilities | (A) Hanging Bridge: 60m (l) x 2.10m (w) | San Juan, Aborlan | Aborlan | PEO | 2020 | 20% Development Fund | 3502950.19 | 3498698.24 | 120 | 2020-08-14 |  | 2020-12-12 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
772 | Rehabilitation of Magbabadil Bridge I | B2 PEO 300-20-06-07376 | Transportation Facilities |  | Bgy. Mabini | Aborlan | PEO | 2020 | 20% Development Fund | 3196665.89 | 3136392.17 | 177 | 2020-08-12 |  | 2021-02-05 |  |  | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
773 | Construction/Rehabilitation of RCBC with Slope Protection in National High way-Tabud Road |  | Other Infrastructure |  | Bgy. Panitian | Quezon | PEO | 2020 | 20% Development Fund | 2320000 | 2315541.32 |  | 2020-08-13 |  | 2020-08-13 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
774 | Construction of Candis RCDG Bridge | B2 PEO 300-20-11-16447 | Transportation Facilities | Approach:6m x 6m (both sides) - Bridge: 14ln.m - RC Slope: 6m x 4 sides - PCCP: 30ln.m | Dumaran, Palawan | Dumaran | PEO | 2020 | 20% Development Fund | 10342148.11 | 8583616.78 | 182 | 2021-01-18 |  | 2021-07-19 | Subject for LD |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
775 | Construction of two (2) Barrel RCBC with concrete slope protection |  | Other Infrastructure |  | Magsaysay, Dumaran | Dumaran | PEO | 2020 | 20% Development Fund | 3729963.8 | 3721400.59 | 300 | 2020-08-15 |  | 2021-06-11 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
776 | Upgrading of Cataban Bailey Bridge II to RCDG |  | Transportation Facilities |  | Brgy. Cataban, Taytay, Palawan | Taytay | PEO | 2020 | 20% Development Fund | 16200000 | 14497276.33 | 197 | 2020-10-06 |  | 2021-04-21 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
777 | Concreting of Pulot Shore Provincial Road |  | Transportation Facilities |  |  | Sofronio Española | PEO | 2020 | 20% Development Fund | 10215663.47 | 10214282.32 |  | 2020-11-09 |  | 2020-11-09 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
778 | Concreting of Magara Bgy. Road, Phase II |  | Transportation Facilities |  |  | Roxas | PEO | 2020 | 20% Development Fund | 3211933.56 | 3206891.39 | 60 | 2020-08-14 |  | 2020-10-13 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
779 | Concreting of Suba-Pawa-San Carlos Road (Half Lane) | B2 PEO 300-20-06-07379 | Transportation Facilities |  | Cuyo, Palawan | Cuyo | PEO | 2020 | 20% Development Fund | 5353777.15 | 5345514.9 | 90 | 2020-08-14 |  | 2020-11-12 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
780 | Construction of Spillway |  | Other Infrastructure |  | Sto. Kalampinay, Pasadena, El Nido | El Nido | PEO | 2020 | 20% Development Fund | 1799450.6 | 1793152.64 | 60 | 2020-08-07 |  | 2020-10-06 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
781 | Construction of Three (3) Barrel RCBC |  | Other Infrastructure |  | Minara, Roxas | Roxas | PEO | 2020 | 20% Development Fund | 4513564.88 | 4505210.5 |  | 2020-08-17 |  | 2020-08-17 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
782 | Construction of One (1) Barrel RCBC Leading to Borac Port | B2 PEO 300-20-06-07383 | Other Infrastructure |  | Bgry. Borac, Coron, Palawan | Coron | PEO | 2020 | 20% Development Fund | 3700000 | 3698950.01 | 120 | 2020-09-22 |  | 2021-01-20 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
783 | Construction of Evacuation Center/Multi-purpose Building |  | Other Infrastructure |  | Kalatagbak, Quezon | Quezon | PEO | 2020 | 20% Development Fund | 850000 | 837906.05 |  | 2020-10-01 |  | 2020-10-01 |  |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
784 | Construction of Covered Court/Evacuation Center Phase I | B2 PEO 300-20-06-07374 | Other Infrastructure |  | Macaranao, Agutaya | Agutaya | PEO | 2020 | 20% Development Fund | 5270214.07 | 5259935.48 | 150 | 2021-01-21 |  | 2021-06-20 | 2022-05-09 |  |  |  | By contract | Terminated | RAK Trading Construction & Supply |  | Due to: (-) 10% slippage
785 | Concreting of Barangay Road |  | Transportation Facilities |  | Bunog, Rizal | Rizal | PEO | 2020 | 20% Development Fund | 5161995.31 | 5161995.3 | 86 | 2020-10-07 |  | 2021-01-01 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
786 | Construction of Covered Court/Evacuation Center Phase I |  | Other Infrastructure | Court: 30m(l) x 18m(w) | Sitio Gawid, San Vicente | San Vicente | PEO | 2020 | 20% Development Fund | 5109576.74 | 5073169.82 | 150 | 2020-12-02 |  | 2021-05-01 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
787 | Construction of Sewage Treatment Plant in Cuyo District Hospital | B2 PEO 300-20-08-10036 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2020 | 20% Development Fund | 3200000 | 3198008.58 | 60 | 2020-09-29 |  | 2020-11-28 | 2021-08-12 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
788 | Expansion of SPS Government Center Bancao-Bancao |  | Other Facilities |  | Bgy. Bancao-Bancao | Puerto Princesa City | PEO | 2020 | Supplemental Budget No. 9 | 3411457.86 | [7 empty] | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
789 | Construction/Improvement of SPS Government Center Bancao-Bancao |  | Other Facilities |  | Bgy. Bancao-Bancao | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 9 | 10330261.87 | 10329196.97 | 360 | 2021-09-23 | 1 | 2022-09-18 | 2022-11-16 |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
790 | Improvement of Hospital Landscaping,Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2020 | Supplemental Budget No. 12 | 2757096.4 | 2757096.4 |  | 2021-03-30 |  | 2021-03-30 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
791 | Improvement of Hospital Landscaping, El Nido Community Hospital |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2020 | Supplemental Budget No. 12 | 2769899.3 | 2769899.3 |  | 2021-04-08 |  | 2021-04-08 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
792 | Improvement of Hospital Landscaping, Quezon Medicare Hospital |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | Supplemental Budget No. 12 | 2764220.9 | 2764220.9 |  | 2021-03-30 |  | 2021-03-30 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
793 | Concreting of Parking Area and access leading to Facilities |  | Medical Facilities | Parking Area=280.60 sq.m - Access Road=270.14 sq.m | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 12 | 1160954.26 | 1159987 | 45 | 2021-04-07 |  | 2021-05-22 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
794 | Construction of Hazardous Waste Vault and Additional Ceiling Works |  | Medical Facilities | Septic Vault=2m(l) x 2m(w) x 2.5m(h) - Ceiling=697.32 sq.m | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 12 | 550000 | 549935.39 | 60 | 2021-01-13 |  | 2021-03-14 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
795 | Supply and Delivery of Transformer Units ( CT/PT) |  | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 12 | 624810 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
796 | Supply and Delivery of 3 - 50 KVA and Line Hardware of Calandagan Village Electrification Project |  | Power and Energy Development Program |  | Calandagan, Araceli | Araceli | PEO | 2020 | Supplemental Budget No. 12 | 877675.05 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
797 | Construction of Transformer Platform with Distribution of Three (3) Phase Line at Motorpool Irawan |  | Medical Facilities |  | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2020 | Supplemental Budget No. 12 | 1627651.97 | 1626057.03 |  | 2021-04-06 |  | 2021-04-06 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
798 | Supply and Installation of Fire Protection for Roxas Medicare Hospital |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2020 | Supplemental Budget No. 12 | 3400000 | 3390808.37 | 64 | 2021-04-22 |  | 2021-06-25 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
799 | Supply and Installation of Airconditioning Units for Quezon Medicare Hospital |  | Medical Facilities |  | Quezon, Palawan | Quezon | PEO | 2020 | Supplemental Budget No. 12 | 3454659 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
800 | Supply and Installation of Hospital Billboards and Markers |  | Medical Facilities |  | *San Vicente District Hospital *El Nido Community Hospital *Bataraza District Hospital |  | PEO | 2020 | Supplemental Budget No. 12 | 1500000 | [7 empty] | 100% |  | By contract | Completed | Megaprint
801 | Repair of Powerhouse of Calandagan Village Electrification Project |  | Power and Energy Development Program |  | Calandagan, Araceli | Araceli | PEO | 2020 | Supplemental Budget No. 12 | 499866.12 | 489732.75 | 45 | 2021-01-11 |  | 2021-02-25 |  |  |  |  | By contract | For Termination | Carina Electrical Construction Supply | TIN 188-374-116
802 | Renovation of Provincial Health Office |  | Other Facilities |  | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2020 | Supplemental Budget No. 14 | 6443263.19 | 6443753.42 |  | 2021-06-23 |  | 2021-06-23 |  |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
803 | Construction of San Vicente District Hospital Perimeter Fence, Phase II |  | Medical Facilities | CHB Fence=420ln.m - 2m (height) | San Vicente District Hospital | San Vicente | PEO | 2020 | Supplemental Budget No. 14 | 4100000 | 4058723.74 | 120 | 2021-04-13 |  | 2021-08-11 |  |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
804 | Construction of Quezon Medicare Hospital STP Tank Phase II |  | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2020 | Supplemental Budget No. 14 | 895627.22 | 895627.22 | 90 | 2021-03-22 |  | 2021-06-20 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
805 | Construction of Multi-Purpose Building |  | Other Infrastructure |  |  | Roxas | PEO | 2020 | Supplemental Budget No. 14 | 1487840.75 | 1487815.75 |  | 2021-06-07 |  | 2021-06-07 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
806 | Construction of Evacuation Center/ Multi-Purpose Building |  | Other Infrastructure |  | Tenga-Tenga | Cuyo | PEO | 2020 | Supplemental Budget No. 14 | 1500000 | 1499164.73 | 120 | 2021-03-20 |  | 2021-07-18 | 2021-11-06 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
808 | Construction of Perimeter Fence in El Nido Community Hospital |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2020 | 20% Development Fund | 6820933.67 | 6404833 | 180 | 2020-08-14 |  | 2021-02-10 |  |  | 100% |  | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176
809 | Concreting of Panitian - Abokayan Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | 1.98 KM | Sofronio Española | Sofronio Española | PEO | 2020 | CMGP | 34173455 | 33650753.97 | 131 | 2021-01-22 |  | 2021-06-02 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
810 | Concreting of Panitian - Tabud Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | 2.10 KM | Quezon | Quezon | PEO | 2020 | CMGP | 41126334 | 40497286.05 | 205 | 2021-01-22 |  | 2021-08-15 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
811 | Concreting of Teresa - Batang Batang Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | 1.504 KM | Narra | Narra | PEO | 2020 | CMGP | 26332019 | 26155597.41 | 136 | 2021-01-22 |  | 2021-06-07 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
812 | Concreting of Junction Highway - Burirao Road | B2 TF DUE TO NGAS DILG-CMGP 20-036 - Package:Php 126,081,623.27 - Concreting of Various Roads in Southern Palawan Funded under conditional matching grant for provinces (CMGP) | Transportation Facilities | 1.484 KM | Narra | Narra | PEO | 2020 | CMGP | 26437914 | 25777985.84 | 113 | 2021-01-22 |  | 2021-05-15 | 2021-06-05 |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
813 | Expansion of Isolation Building and Construction of Hazardous Waste Vault | SB3 HDMP 300-20-06-07206 | Medical Facilities | No. 1 storey - Floor area: 20.0m(l) x 8.0m(w) - steel truss | Roxas Medicare Hospital | Roxas | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3880000 | 3839182.15 | 150 | 2020-07-13 |  | 2020-12-10 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
814 | Expansion of Isolation Building and Construction of Hazardous Waste Vault (Narra Municipal Hospital) |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3850000 | 3838801.72 | 150 | 2020-07-11 |  | 2020-12-08 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
815 | Construction of TB DOTS, Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2020 | Supplemental Budget No. 3 HDMP | 1637141.17 | 1637141.17 | 120 | 2020-07-29 |  | 2020-11-26 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
816 | Expansion of Isolation Building and Construction of Hazardous Waste Vault | SB3 HDMP 300-20-06-07207 | Medical Facilities | 1 Storey: Floor Area: 20.00m (l) x 8.00m (w) - Steel Truss | Aborlan Medicare Hospital | Aborlan | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3848742.93 | 3848742.93 | 150 | 2020-07-15 |  | 2020-12-12 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
817 | Construction of TB Dots | SB3 HDMP 300-20-07-08059 | Medical Facilities | 10.00m x 8.00m TB DOTS Building | Aborlan Medicare Hospital | Aborlan | PEO | 2020 | Supplemental Budget No. 3 HDMP | 1500000 | 1498529.47 | 120 | 2020-09-16 |  | 2021-01-14 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
818 | Expansion of Isolation Building and Construction of Hazardous Waste Vault (Southern Palawan Provincial Hospital) |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2020 | Supplemental Budget No. 3 HDMP | 3817957.71 | 3808198.5 | 150 | 2020-07-10 |  | 2020-12-07 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
819 | Expansion of Isolation Building and Construction of Hazardous Waste Vault (Southern Palawan Provincial Hospital) | SB3 HDMP 300-20-07-08057 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2020 | Supplemental Budget No. 3 HDMP | 1785000 | 1784000 | 180 | 2020-07-30 |  | 2021-01-26 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
820 | Construction and Upgrading of Junction Salban-Culasian-Magsaysay FMR | PRDP-IB-R04B-PAL-005-000-000-2014-AF | Transportation Facilities |  | Bgy. Danleg, Culasian, Magsaysay, Dumaran, Palawan | Dumaran | PEO | 2020 | D.A FUND | 218599855.41 | 197209134.68 | 369 | 2020-02-27 |  | 2021-03-02 | 2022-06-15 |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
821 | Construction of Kapangyan Water System Retaining Wall |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bataraza, Palawan | Bataraza | PEO | 2020 |  | 1059995.84 | 1059995.84 |  | 2020-12-19 |  | 2020-12-19 |  |  | 100% |  | By contract | Completed
822 | Provincial Engineering Office Renovation |  | Other Facilities |  | Capitol Building, Bgy. Tanglaw | Puerto Princesa City | PEO | 2020 | MOOE PEO | 684993.05 | 684576.77 |  | 2021-01-13 |  | 2021-01-13 |  |  | 100% |  | By contract | Completed
823 | Improvement of Capitol Park (Capitol Ground) |  | Other Facilities |  | Capitol Building, Bgy. Tanglaw | Puerto Princesa City | PEO | 2020 | MOOE PEO | 12000000 | 11952584.52 |  | 2021-06-10 |  | 2021-06-10 |  |  | 100% |  | By contract | Completed
824 | Construction of Araceli/Dumaran District Hospital Phase II |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2020 |  | 21001275.07 |  |  | 2021-06-11 |  | 2021-06-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
825 | Constrcution of Free Standing COVID-19 Testing Laboratory with Comfort Rooms and Hazardous Waste Vault | SB3 HDMP 300-20-07-08060 | Medical Facilities | Single Storey: (a) Laboratory: 12.00m x 10.50m - (b) CR: 6.00m x 3.00m - © Vault: 2.00m x 2.00m | Bgy. Irawan | Puerto Princesa City | PEO | 2020 | HDMP - Supplemental Budget No. 3 | 4273835 | 4272957.06 | 150 | 2020-11-12 |  | 2021-04-11 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction
826 | Construction of Provincial Disaster Operation Center of Palawan Phase II |  | Other Facilities |  | Bgy. Irawan | Puerto Princesa City | PEO | 2020 |  | 12657400 | 11380944.78 |  | 2021-02-01 |  | 2021-02-01 |  |  | 100% |  | By contract | Completed
827 | Construction of Roxas Waterworks Office Perimeter Fence and Waterhouse |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Roxas | PEO | 2021 |  | 1399000 | 1397754.67 | 150 | 2021-11-08 |  | 2022-04-07 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
828 | Construction of Elevated Water Tank 300m³/Deepwell/Water Treatment Facilities | B2 PEO15 300-18-06-09394 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 6613020.87 | 6476855.512 | 90 | 2019-01-08 |  | 2019-04-08 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
829 | Supply and Installation of Fire Protection & Alarm System | B2 PEO15 300-20-08-11261 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 3417513.7 | 3414039.04 | 64 | 2020-11-16 |  | 2021-01-19 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
830 | Installation of Communication System/Security Monitoring Devices (PABX,Intercom & CCTV) |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 1095783 | 1084830.35 |  | 2020-12-17 |  | 2020-12-17 |  |  | 100% |  | By contract | Completed
831 | Concreting of Ramp and Parking Area |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 979315.43 | [7 empty] | 100% |  | By contract | Completed | Conte Builders and Construction Supply | TIN 923-929-215
832 | Installation of Additional Ceiling (Ward Nursing Station and Const of Canopy from Main Building to Dietary & MHB to Isolation |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Aborlan Medicare Hospital | 412795.58 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
833 | Construction/Supply and Installation of STP Equipment and Facilities |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 1 | 2165056.74 |  | 60 | [5 empty] | 100% |  | By contract | Completed
834 | Improvement of Northern Palawan Provincial Hospital (Installation of Airconditioning Units) |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | 20% Development Fund | 3400000 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
835 | Improvement of Bataraza District Hospital (Installation of Communication System/Security Monitoring Devices (Paging System, PABX,Intercom & CCTV)) |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 1100000 | 1095000 | 75 | 2021-12-06 |  | 2022-02-19 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
836 | Improvement of Bataraza District Hospital (Installation of Fire Protection and Alarm System) |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 3300000 | 3289676.71 | 64 | 2021-06-24 |  | 2021-08-27 | 2022-01-09 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
837 | Construction of Isolation Building in Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 3740000 | 3736267.23 | 200 | 2021-09-22 |  | 2022-04-10 | For approval |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
838 | Construction of Material Recovery Facilities Building in Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 1068780.72 | 1068777.26 |  | 2021-06-21 |  | 2021-06-21 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
839 | Improvement of Araceli/Dumaran District Hospital (Installation of Fire Protection and Alarm System) |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 3296239.21 | 3296239.21 |  | 2021-08-05 |  | 2021-08-05 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
840 | Construction of Isolation Building in Cuyo District Hospital | B2 PEO 300-21-04-03046 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 4200341.76 | 4200281.64 | 200 | 2021-06-07 | 2 | 2021-12-24 | For approval |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
841 | Construction of Material Recovery Facilities Building in Cuyo District Hospital |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 1126956.44 | 1126941.84 | 120 | 2021-06-07 |  | 2021-10-05 | 2022-09-21 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
842 | Construction of Doctors/Nurses Quarter Building in Cuyo District Hospital |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 6074917.7 | 6014846.48 | 240 | 2021-06-07 | 2 | 2022-02-02 | Subject for LD |  | 70% |  | By contract | On going | Julriz Trading and Construction | TIN 495-740-401
843 | Construction of Dietary/Linen Building in Cuyo District Hospital |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 4300000 | 4297123.18 | 180 | 2021-09-16 | 2 | 2022-03-15 | For approval |  |  |  | By contract | For Termination | Julriz Trading and Construction | TIN 495-740-401
844 | Construction of Mortuary Building in Cuyo District Hospital |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 1195000 | 1193531.64 | 90 | 2021-09-16 | 2 | 2021-12-15 | For approval | 2023-10-11 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
845 | Improvement of Cuyo District Hospital (Installation of Fire Protection and Alarm System) |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 3500000 | 3497903.33 | 85 | 2021-08-05 |  | 2021-10-29 | 2022-01-12 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
846 | Improvement of Cuyo District Hospital (Installation of Airconditioning Units) |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 3400000 | [7 empty] | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
847 | Improvement of Hospital Landscaping in Old Narra Municipal Hospital |  | Medical Facilities |  | Old Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 488585.9 | 488585.9 | 90 | 2021-07-12 |  | 2021-10-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
848 | Improvement of Hospital Landscaping in Cuyo District Hospital |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 2798022.47 |  | 120 | 2021-09-16 |  | 2022-01-14 | 2022-09-25 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
849 | Improvement of Hospital Landscaping in Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 2800000 | 2794861.5 | 120 | 2021-10-28 |  | 2022-02-25 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
850 | Construction of Perimeter Fence in Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 2544672 | 2542436.1 | 120 | 2021-09-16 |  | 2022-01-14 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
851 | Construction of Perimeter Fence Phase III in Dr Jose Rizal District Hospital | B2 PEO 300-21-11-15795 | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2021 | 20% Development Fund | 270000 | 269750 | 93 | 2021-12-17 |  | 2022-03-20 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
852 | Construction of Perimeter Fence in Roxas Medicare Hospital, Phase 3 |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2021 | 20% Development Fund | 2000000 | 1998231.64 | 120 | 2021-12-13 |  | 2022-04-12 | 2022-06-12 |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
853 | Concreting of Road Network Phase II in Dr Jose Rizal District Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2021 | 20% Development Fund | 1230000 | 1229971.51 | 60 | 2021-10-06 |  | 2021-12-05 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
854 | Concreting of Road Network Phase II in El Nido Community Hospital | B2 PEO 300-21-05-04027 | Transportation Facilities | Roads: PCCP (Road Network): 342.109 sq.m x 0.15m (t) - 236m(l) x 4m(w) x 0.020m(t) - 1m shoulder both side | El Nido Community Hospital | El Nido | PEO | 2021 | 20% Development Fund | 2000000 | 1999230.77 | 120 | 2021-06-21 |  | 2021-10-19 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
855 | Construction of One (1) Barrel RCBC |  | Other Infrastructure |  | Bgy. Labog, Sofronio Española, Palawan | Sofronio Española | PEO | 2021 | 20% Development Fund | 2000000 | 1998601.44 | 180 | 2021-07-02 |  | 2021-12-29 |  |  | 100% |  | By contract | Completed | R. Narrazid Trading and Construction | TIN 330-975-725
856 | Construction of Bridge Slope Protection |  | Other Infrastructure |  | Pulot Shore | Sofronio Española | PEO | 2021 | 20% Development Fund | 302551.38 | 302551.38 |  | 2021-05-21 |  | 2021-05-21 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
857 | Repair of Slope Protection in Saraza Bridge |  | Other Infrastructure |  | Saraza | Brooke's Point | PEO | 2021 | 20% Development Fund | 843042.7 | 841716.59 | 90 | 2021-06-07 |  | 2021-09-05 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
858 | Construction of 2-units of One (1) Barrel RCBC with PCCP approach and Slope Protection |  | Other Infrastructure | RCBC/RC Slope Protection: (a) RCBC 1-3m(h) x 3m(w) x 6.0(l) x 0.30m thk. (b) approach" 2-10m(l) x 6.0m(w) x 0.20m thk x 2 sides ( c) Detour Road 2-12m(l) x 5m(w) with 24'' RCPC (d) Slope Protection 5m (l) x 2m (h) x 0.30m thk x 4 sides | Bgry. Magsaysay, Dumaran, Palawan | Dumaran | PEO | 2021 | 20% Development Fund | 4000000 | 3998116.65 | 300 | 2022-12-23 |  | 2023-10-19 | 2023-07-31 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
859 | Concreting of Cataban - Liminangcong Road (Intermitent Section) |  | Transportation Facilities | 1.0 km |  | Taytay | PEO | 2021 | 20% Development Fund | 10485742.24 | 10484696.85 |  | 2021-07-31 |  | 2021-07-31 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
860 | Concreting of Abongan - Alacalian - Binga Road (Intermitent Section) |  | Transportation Facilities | 1.0 km | Alacalian - Binga | Taytay | PEO | 2021 | 20% Development Fund | 10500000 | 10492669.72 |  | 2021-07-29 |  | 2021-07-29 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
861 | Concreting of Road from Highway Junction Leading to NPPH Facilities | B2 PEO 300-01-05-05582 | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | 20% Development Fund | 5000000 | 4999088 | 60 | 2021-08-02 |  | 2021-10-01 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
862 | Construction of Powerhouse/ Motorpool Building in Cuyo District Hospital |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 2700170.25 | 2698173.92 | 90 | 2021-09-16 | 2 | 2021-12-15 | For approval | 2023-09-01 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
863 | Construction of Powerhouse for Bancalaan 1 VEP |  | Other Infrastructure |  | Bgy. Bancalaan I | Balabac | PEO | 2021 | 20% Development Fund | 1332158.2 | 1330146.46 | 270 | 2021-06-10 |  | 2022-03-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
864 | Construction of Powerhouse for Bancalaan 2 VEP |  | Other Infrastructure |  | Bgy. Bancalaan 2 | Balabac | PEO | 2021 | 20% Development Fund | 1335815.99 |  | 270 | 2021-06-10 |  | 2022-03-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
865 | Construction of Powerhouse for Concepcion VEP |  | Other Infrastructure |  | Bgy. Concepcion | Agutaya | PEO | 2021 | 20% Development Fund | 1335815.99 | 1331162.16 | 270 | 2021-06-10 |  | 2022-03-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
866 | Construction of Powerhouse for Tara VEP | B2 PEO 300-21-04-03109 | Other Infrastructure |  | Bgry. Tara, Coron, Palawan | Coron | PEO | 2021 | 20% Development Fund | 1874043.14 | 1330162.22 | 270 | 2021-06-10 |  | 2022-03-07 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
867 | Construction of Transformer Platform and Installation of 3 Phase Extension Line from Highway to Transformer in Northern Palawan Provincial Hospital | B2 PEO 300-21-04-033110 | Medical Facilities | Construction of 3.30 meters x 2.80 meters platform, 0.497 kms 3 phase | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | 20% Development Fund | 1874879.12 | 1874039.44 | 60 | 2021-08-17 |  | 2021-10-16 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
868 | Construction of Transformer Platform and Installation of 3 Phase Extension Line from Highway to Transformer in Araceli/Dumaran District Hospital | B2 PEO 300-21-08-09459 | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 1259946 | 1246956.73 | 75 | 2021-09-23 |  | 2021-12-07 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
869 | Upgrading of Caruray Bridge IV (Aluningan) to RCDG, Caruray |  | Transportation Facilities | 36 m | Caruray, San Vicente, Palawan | San Vicente | PEO | 2021 | 20% Development Fund | 8549250.06 | 8549231.39 | 184 | 2021-10-06 |  | 2022-04-08 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
870 | Concreting of Road Network in Araceli/Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 2594980.91 | 2594977.94 | 120 | 2021-06-21 |  | 2021-10-19 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
871 | Construction of Araceli/Dumaran District Hospital Phase III |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | 20% Development Fund | 19053067.47 | 18999413.9 | 270 | 2021-11-10 |  | 2022-08-07 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
872 | Construction of Mortuary Building in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 1135000 | 1128568.14 |  | 2021-07-23 |  | 2021-07-23 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
873 | Construction of Material Recovery Facilities in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 1073000 | 1055395.29 |  | 2021-06-04 |  | 2021-06-04 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
874 | Construction of Doctors's/Nurse's Quarter Building in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 5800000 | 5798531.76 | 240 | 2021-06-07 |  | 2022-02-02 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
875 | Construction of Isolation Building in Bataraza District Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | 20% Development Fund | 3740000 | 3739459.65 | 120 | 2021-06-07 |  | 2021-10-05 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
876 | Improvement of Aborlan Medicare Hospital (Canopy, Wash Area, Concreting of Access Road and Drainage Canal) | B2 PEO 300-21-05-04018 | Medical Facilities | Canopy: 14.60m x 4.60m - Wash Area: 5.90m x 1.8m - Drainage: 0.40m x 0.40m (14units) - Access Roads: 38.50 cu.m - Pavement with ramp: 2.072 cu.m | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | 20% Development Fund | 1048805.07 | 1045012.78 | 90 | 2021-06-29 |  | 2021-09-27 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
877 | Improvement of Aborlan Medicare Hospital (Construction of Waiting Area) |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | 20% Development Fund | 1803941.03 | 1802302.65 | 60 | 2021-11-08 |  | 2022-01-07 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
878 | Construction of Narra Municipal Hospital Perimeter Fence, Phase II | B2 PEO 300-21-05-05585 | Medical Facilities | 317.80 ln.m - Concrete fence: 106 span | Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 2544672 | 2543632.2 | 90 | 2021-09-15 |  | 2021-12-14 |  |  |  |  | By contract | Suspended | Mazon Engineering and Construction | TIN 273-819-199 | Due to informal settler
879 | Concreting of Parking Area in Old Narra Municipal Hospital | B2 PEO 300-21-05-04019 | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 300000 | 295035.28 | 30 | 2021-06-07 |  | 2021-07-07 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
880 | Concreting of Road Network in Old Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2021 | 20% Development Fund | 1200000 | 1199083.16 | 60 | 2021-07-15 |  | 2021-09-13 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
881 | Rehabilitation of Old Narra Municipal Hospital (for Mental Health/PADAC) | B2 PEO 300-21-05-04020 | Medical Facilities | 42X12.5m Building - 4.15mx1.66m septic tank | Narra Municipal Hospital (for. PADAC) | Narra | PEO | 2021 | 20% Development Fund | 3620000 | 3617003.33 | 120 | 2021-06-29 |  | 2021-10-27 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
882 | Construction of Water Supply System (Calauit Safari Park) | B2 CSP 300-21-00692 | Artesian Wells, Reservoir, Pumping and Conduits |  | Calauit Island, Busuanga, Palawan | Busuanga | PEO | 2021 |  | 600000 | 598646.31 | 150 | 2021-07-12 |  | 2021-12-09 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
883 | Construction of Hospital Building and Facilities at Northern Palawan Provincial Hospital | B2 SB12 PEO20 300-21-02-00393 | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 12 | 30000000 | 24990789.21 |  | 2020-11-16 |  | 2020-11-16 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
884 | Construction of Three (3) Storey Medical Ward Building with Roof Deck for Helipad Phase 2 |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2021 | Supplemental Budget No. 3 | 20000000 | 19994054.3 | 100 | 2021-09-16 |  | 2021-12-25 |  |  | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
885 | Construction of Three (3) Storey Medical Ward Building with Roof Deck for Helipad Phase 2 |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 1799897.13 | 1799897.13 | 150 | 2021-08-24 |  | 2022-01-21 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
886 | Construction of Oxygen Building in SPPH |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 1799893.15 | 1797226.37 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
887 | Construction of Perimeter Fence in Palawan Technical Vocational School Phase I |  | Medical Facilities |  | Bgy. Poblacion, Taytay, Palawan | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 2700000 | 2699000.5 |  | 2021-08-27 |  | 2021-08-27 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
888 | Construction of Cory Park Covered Event Center |  | Other Facilities |  | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 139901440.31 | 139901440.31 | 333 | 2021-08-28 |  | 2022-07-27 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
889 | Vice Governor Francisco F. Ponce de Leon Memorial Hospital: Construction of New Building | B2 SB3 PEO 300-21-07-08628 | Medical Facilities | Construction limits: Construction of 42 meters x 33.50 meters single storey building with electrical and plumbing system and concreting of 438.34 sq.m road area | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 3 | 25000000 | 24949565.775 | 150 | 2021-10-05 |  | 2022-03-04 | Subject for LD |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
890 | Completion of Three (3) Storey Medical Arts Building Southern Palawan Provincial Hospital, Brooke’s Point, Palawan |  | Medical Facilities |  | Southern Palawan Provincial Hospital, Brooke. Palawan | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 11000000 | 10941402.64 | 180 | 2021-10-06 | 1 | 2022-04-04 | Subject for LD |  | 99.22% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
891 | Construction of Three (3) - Storey Medical Arts Building with Roof Deck for Helipad, Phase 1, Aborlan Medicare Hospital | B2 SB3 PEO 300-21-07-08630 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 3 | 20000000 | 19668318.22 | 100 | 2021-09-16 |  | 2021-12-25 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
892 | Completion of Three in One Large Scale Rural Health Unit, Bgy. Panalingaan, Rizal, Palawan |  | Medical Facilities |  | Bgy. Panalingaan, Rizal, Palawan | Rizal | PEO | 2021 | Supplemental Budget No. 3 | 8000000 | 7383444.79 | 120 | 2021-10-27 |  | 2022-02-24 |  |  |  |  | By contract | For Termination | Nab Construction & Enterprises | TIN 445-503-720
893 | Completion of Three in One Large Scale Rural Health Unit, Bgy. Pancol, Taytay, Palawan | B2 SB3 PEO 300-21-08-09454 | Medical Facilities |  | Bgy. Pancol, Taytay, Palawan | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 8000000 | 7393850.06 | 120 | 2021-10-27 | 1 | 2022-02-24 | 2022-04-27 |  | 63% |  | By contract | For Termination | Nab Construction & Enterprises | TIN 445-503-720
894 | Expansion of Three in One Large Scale Rural Health Unit, Bgy. Pulot Center, Sofronio Española, Palawan |  | Medical Facilities |  | Bgy. Pulot Center. Palawan | Sofronio Española | PEO | 2021 | Supplemental Budget No. 3 | 8000000 | 5597498.31 |  | 2021-09-16 |  | 2021-09-16 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
895 | Construction of Northern Palawan Technical Vocational School Phase 2, Taytay, Palawan |  | Educational Facilities |  | Northern Palawan Technical Vocational School | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 12000000 | 11994320.26 |  | 2021-09-15 |  | 2021-09-15 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
896 | Construction of Perimeter Fence in Northern Palawan Provincial Hospital, Taytay, Palawan |  | Medical Facilities |  | Northern Palawan Provincial Hospita | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 3398547.28 | 2699000.5 |  | 2021-08-27 |  | 2021-08-27 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
897 | Repair and Rehabilitation of Capitol Building |  | Other Facilities |  | Capitol Bldg., Puerto Princesa City | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 25000000 | 24926014.87 |  | 2021-12-28 |  | 2021-12-28 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
898 | Construction of Bahay Tuluyan Building, Aborlan Medicare Hospital | B2 SB3 PEO 300-21-07-07263 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 3 | 1800000 | 1797898.92 | 120 | 2021-08-24 |  | 2021-12-22 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
899 | Construction of Bahay Tuluyan Building Annex, Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 1794571 | 1794564.82 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
900 | Centralize Oxygen Plant, Southern Palawan Provincial Hospital | SB3 PEO 300-21-07-08565 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 3 | 30000000 | 30000000 |  | 2021-10-25 |  | 2021-10-25 |  |  | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
901 | Centralize Oxygen Plant, Northern Palawan Provincial Hospital |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 3 | 30000000 | 30000000 |  | 2021-10-25 |  | 2021-10-25 |  |  | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
902 | Operation of El Nido Sewage & Solid Waste Treatment Plant |  | Artesian Wells, Reservoir, Pumping and Conduits |  | El Nido | El Nido | PEO | 2021 | Supplemental Budget No. 4 | 20000000 |  | 150 | 2021-09-29 |  | 2022-02-26 |  |  | 100% |  | By contract | Completed | Hardrock Platinum Development Corporation | TIN 008-625-254
903 | Operation of Roxas Water System |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Roxas, Palawan | Roxas | PEO | 2021 | Supplemental Budget No. 4 | 10000000 | 8779866.21 | 150 | 2021-10-21 |  | 2022-03-20 |  |  | 100% |  | By contract | Completed | Hardrock Platinum Development Corporation | TIN 008-625-254
904 | Supply and Installation of Hospital Billboards and Markers in San Vicente District Hospital, El Nido Community Hospital and Bataraza District Hospital |  | Medical Facilities |  | El Nido Community Hospital and Bataraza District Hospital |  | PEO | 2021 | Supplemental Budget No.12 | 1500000 | [7 empty] | 100% |  | By contract | Completed
905 | Construction of Dietary/Linen Building Phase II |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1819580 | 17929341.27 |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
906 | Construction of Isolation Building |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 3710000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
907 | Construction of Material Recovery Facilities |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1073000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
908 | Construction of Mortuary Building |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1135000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
909 | Construction of Motorpool/Powerhouse Building |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 2029000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
910 | Concreting of Road Networks |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 5089141 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
911 | Construction of Sewage Treatment Plant |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 3100000 |  |  | 2021-11-19 |  | 2021-11-19 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
912 | Construction of Doctor's/Nurses Quarter | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 6016000 | 6014518.38 | 160 | 2021-11-29 | 1 |  | 2022-06-07 | 2024-01-26 | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
913 | Construction of Dietary/Linen Building Phase | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3610000 | 3608090.05 | 190 | 2021-11-29 | 1 |  | 2022-07-07 | 2023-12-08 | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
914 | Construction of Isolation Building | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3740000 | 3737758.85 | 120 | 2021-11-29 | 1 |  | 2022-05-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
915 | Construction of Mortuary Building | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1195000 | 1192252.82 | 90 | 2021-11-29 | 1 |  | 2022-04-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
916 | Construction of Powerhouse/Motorpool Building | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 2156000 | 2153353.85 | 90 | 2021-11-29 | 1 |  | 2022-04-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
917 | Construction of Road Network | Cluster: Construction of BDH (DNQ-DLB-IB-MB-PMB-Concreting of Road NetworkB2 SB5 PEO 300-21-09-12141-12145/12165 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 5000000 | 4998207.45 | 90 | 2021-11-29 |  |  |  |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
918 | Construction of Transformer Platform |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 327279 | 325840 | 60 | 2021-12-18 | 1 | 2022-02-16 | 2022-06-15 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
919 | Installation of Fire Protection and Alarm System |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 3300000 | 3281840.63 | 60 | 2021-11-10 |  | 2022-01-09 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
920 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) | B2 SB5 PEO 200-21-09-12140 | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095000 | 50 | 2021-12-15 |  | 2022-02-03 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
921 | Construction of Elevated Water Tank 300 cu.m/ Water Treatment Facilities |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 7300000 | 7296574.07 | 180 | 2021-11-29 |  | 2022-05-28 | 2023-01-20 |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
922 | Construction of Perimeter Fence Phase II |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1651945.51 | 1638333.21 | 90 | 2021-12-20 |  | 2022-03-20 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
923 | Improvement of Hospital Landscaping |  | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 2800000 | 2797495.93 |  | 2021-11-12 |  | 2021-11-12 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
924 | Concreting of Road from Highway Junction Leading to NPPH Facilities Phase II | B2 SB5 PEO 300-21-09-12167 | Medical Facilities | Sta. 0+260 to Sta. 0+370 - 1m shoulder both side | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 1063000 | 1061747 | 60 | 2022-05-26 |  | 2022-07-25 |  |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
925 | Construction of Balabac District Hospital, Phase III |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 18025337.58 | 18020270.86 | 120 | 2021-11-29 | 1 | 2022-03-29 | 2022-05-28 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
926 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095098.48 | 45 | 2021-12-01 |  | 2022-01-15 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
927 | Construction of Material Recovery Facilities |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1051421.68 | 1050283.84 | 60 | 2021-11-15 | 1 | 2022-01-14 | 2022-03-15 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
928 | Construction of Sewage Treatment Plant | B2 SB5 PEO 300-21-09-12153 | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3100000 | 3094987.66 | 60 | 2021-12-07 |  | 2022-02-05 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
929 | Construction of Perimeter Fence Phase I |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 3400000 | 3399086.45 | 120 | 2021-11-15 | 1 | 2022-03-15 | 2022-05-14 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
930 | Improvement of Hospital Landscaping | B2 SB5 PEO 300-21-09 | Medical Facilities | Modern Tropical Garden | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 2800000 | 2799499.88 | 60 | 2021-11-22 | 1 | 2022-01-21 | 2022-06-24 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
931 | Concreting of Road Network Phase II | B2 SB5 PEO 300-21-09-12169 | Transportation Facilities | Roads: PCCP (Road Network): 110m(l) x 6m(w) x 0.20m(t) | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 2200000 | 2199787.14 | 60 | 2021-11-22 | 1 | 2022-01-21 | 2022-07-21 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
932 | Installation of 3 Phase Extension Line from Highway to Transformer |  | Medical Facilities |  | Balabac District Hospital | Balabac | PEO | 2021 | Supplemental Budget No. 5 | 1072830.6 | 1067974.94 | 20 | 2021-12-07 |  | 2021-12-27 |  | 2023-06-21 | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
933 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095000 |  | 2021-12-14 |  | 2021-12-14 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
934 | Installation of Communication System/Securing Monitoring Devices (PABX,Intercom & CCTV) | B2 SB5 PEO 300-21-09-12136 | Medical Facilities | Installation: Communication system intercom: Intercom station with Monitor=4 pcs; intercom handset=35 pcs; UPS=1 PC - Securing Monitoring Device (CCTV): 16 channels DVR=1 pc; CCTV Camera=16 pcs; 32'' LED Monitor=1 pc; UPS=1 pc - Communication System (PABX): Telephone Set=30 sets Main control Unit= 1 set; AVR=1 set | Cuyo District Hospital | Cuyo | PEO | 2021 | Supplemental Budget No. 5 | 1100000 | 1095000 | 45 | 2021-12-17 |  | 2022-01-31 |  |  | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
935 | Completion of Perimeter Fence |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | Supplemental Budget No. 5 | 909000 | 908006.88 | 60 | 2021-10-27 |  | 2021-12-26 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
936 | Improvement of Hospital Landscaping (Facilities Area) Narra Municipal Hospital |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2021 | Supplemental Budget No. 5 | 1000000 | 999817.5 |  | 2021-10-27 |  | 2021-10-27 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
937 | Construction of Perimeter Fence Phase I |  | Medical Facilities |  | Sofronio Española Rural Health Unit | Sofronio Española | PEO | 2021 | Supplemental Budget No. 5 | 804000 | 803469.32 | 60 | 2021-11-03 |  | 2022-01-02 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
938 | Concreting of Road with Parking Area |  | Medical Facilities |  | Sofronio Española Rural Health Unit | Sofronio Española | PEO | 2021 | Supplemental Budget No. 5 | 1817270 | 1814868.88 |  | 2021-11-12 |  | 2021-11-12 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
939 | Improvement of Landscaping |  | Other Facilities |  | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 900000 | 899113.23 |  | 2021-10-27 |  | 2021-10-27 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
940 | Concreting of Road Network with Parking Area (Molecular Diagnostic Lab) |  | Other Facilities |  | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 5500000 | 5479831.8 | 90 | 2021-11-15 |  | 2022-02-13 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
941 | Extension of 3-Phase Line from Irawan Motorpool to Molecular Diagnostic Laboratory (Covid 19 Testing Center) | B2 SB5 PEO 300-21-09-12155 | Other Facilities |  | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 1550000 | 1547958.44 |  | 2021-11-30 |  | 2021-11-30 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
942 | Installation of 25 Airconditioning Units |  | Other Facilities |  | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 713259.63 | [7 empty] | 100% |  | By contract | Completed
943 | Improvement of Araceli/Dumaran District Hospital (Installation of 25 Units Airconditioning Units) |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 5 | 1641935 | [7 empty] | 100% |  | By contract | Completed
944 | Concreting of Highway Junction to Barangay Poblacion (Intermittent Section) with Drainage |  | Transportation Facilities |  | Salvacion, Roxas, Palawan | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 8000000 | 7990469.35 |  | 2021-12-01 |  | 2021-12-01 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
945 | El Nido Sewage and Solid Waste Treatment Plant |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 3370421 | 3366360.33 | 90 | 2021-12-28 |  | 2022-03-28 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
946 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Bgy. Bato | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-27 |  | 2022-02-10 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
947 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Bgy. New Guinlo | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
948 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Bgy. Old Guinlo | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
949 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Pancol | Taytay | PEO | 2021 | Supplemental Budget No. 5 | 872687.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
950 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Malcampo | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
951 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Mendoza | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
952 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Near Barbacan (Retac) | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
953 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Rizal | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
954 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Salvacion | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
955 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | San Isidro | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
956 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | San Jose | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
957 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Tagumpay | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
958 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | Nicanor Zabala | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
959 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure |  | Corong-Corong (Barangay 4) | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
960 | Improvement of Covered Court/Evacuation Center (Flooring only) |  | Other Infrastructure |  | Mabini | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
961 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure |  | Manlag | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
962 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure |  | San Fernando | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
963 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB NO. 5 - 2021 - PEO 300-21-10-13316 | Other Infrastructure |  | Villa Paz | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  |  |  | By contract | Terminated | One Hundred Percent and Development Corp. | TIN 168-154-730 | Termination for convenience: LGU initiated provision of flooring
964 | Improvement of Covered Court/Evacuation Center (Flooring only) |  | Other Infrastructure |  | Aberawan | El Nido | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
965 | Improvement of Covered Court/Evacuation Center (Flooring only) | B2 SB5 PEO 300-21-10-13316 | Other Infrastructure |  | San Miguel | Roxas | PEO | 2021 | Supplemental Budget No. 5 | 872684.19 | 872408.47 | 45 | 2021-12-28 |  | 2022-02-11 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
966 | Completion of 2-Storey Barangay Hall of Ipilan |  | Other Facilities |  | Bgy. Ipilan | Brooke's Point | PEO | 2021 | Supplemental Budget No. 5 | 3323150.34 | 3313181.35 | 150 | 2021-12-27 |  | 2022-05-26 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
967 | Repair of Capitol Building and Provision of Door and Window Grills |  | Other Facilities |  | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 5 | 4223153.86 | 4220152.71 | 180 | 2021-12-27 |  | 2022-06-25 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
968 | Upgrading of Omao Bridge |  | Transportation Facilities | 21 m | Bgy. Bagong Bayan, El Nido,Palawan | El Nido | PEO | 2021 | Supplemental Budget No. 6 | 9000000 | 8999582.12 | 184 | 2021-12-10 |  | 2022-06-12 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
969 | Construction of Powerhouse/Motorpool Building, NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 2156000 | 2126703.18 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-04 |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
970 | Construction of Doctor's/Nurses Quarter, NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities | Net length: 31m x 24m (744 sq.m) One Storey Building | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 6016000 | 6012640.25 | 80 | 2021-12-14 |  | 2022-03-04 | Subject for LD |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
971 | Construction of Dietary/Linen Building, NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 3610000 | 3596228.53 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-03 | 2023-08-10 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
972 | Construction of Isolation Building , NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 3740000 | 3730769.95 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-03 | 2023-06-11 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
973 | Construction of Material Recovery Facilities , NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 1128000 | 1087724.2 | 30 | 2021-12-14 |  | 2022-01-13 | 2022-09-03 | 2023-07-15 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
974 | Construction of Mortuary Building , NVGPDLMH | B2 SB6 PEO 300-21-10-12849/12851-12855 (Cluster: Mortuary/Dietary/Isolation/MRF/DNQ/Powerhouse) | Medical Facilities |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 6 | 1195000 | 1190355.14 | 60 | 2021-12-14 |  | 2022-02-12 | 2022-09-03 | 2023-08-10 | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
975 | Centralize Oxygen Plant |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2021 | Supplemental Budget No. 6 | 16000000 | 15691385 |  | 2022-06-28 |  | 2022-06-28 |  |  | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
976 | Construction of Linapacan Water Supply Systems |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Linapacan | PEO | 2021 | Supplemental Budget No. 8 | 265510000 | 262401315.21 | 510 | 2021-12-29 |  | 2023-05-23 |  |  |  |  | By contract | On going | Ivy Michelle Construction and Trading | TIN 009-492-339 | PEEDO Validate
977 | Installations of 3 Lines 36" Diameter RCPC with Headwall, Pulot Interior | B2 GF PEO 22-02-063 | Other Infrastructure |  | Provincial Road Pulot Interior | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 329561.05 | 30 | 2022-03-16 |  | 2022-04-15 | 2022-06-01 |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
978 | Installations of 15 Lines 36" Diameter RCPC with Headwall, Provincial Road Labog, Naltep | B2 GF PEO 22-02-055 | Other Infrastructure |  | Provincial Road Labog, Naltap | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 1650000 | 1542671.28 | 90 | 2022-05-11 |  | 2022-08-09 |  |  |  |  | By contract | Notice to Terminate | R. Narrazid Trading and Construction | TIN 330-975-725 | Waiting for Contractor to received the Notice to Terminate: Unresponsive Contractor
979 | Construction of 3-Barrel Box Culvert with Slope Protection, Provincial Road Isaub | B2 GF PEO 22-02-051 | Other Infrastructure |  | Bgy. Isaub | Aborlan | PEO | 2021 | Supplemental Budget No. 9 | 4000000 | 3997972.29 | 90 | 2022-05-11 |  | 2022-08-09 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
980 | Installations of 3 Lines 36" Diameter RCPC with Headwall, Bgy. Aramaywan | B2 GF PEO 22-02-060 | Other Infrastructure |  | Bgy. Aramaywan | Quezon | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 328979.73 | 30 | 2022-03-21 |  | 2022-04-20 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
981 | Installations of 3 Lines 36" Diameter RCPC with Headwall, Bgy. Panitian | B2 GF PEO 22-02-059 | Other Infrastructure |  | Bgy. Panitian | Quezon | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 328979.73 | 30 | 2022-03-21 |  | 2022-04-20 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
982 | Installations of 7 Lines 36" Diameter RCPC with Headwall, Provincial Road Itangil-Sta. Teresita Road | B2 GF PEO 22-02-064 | Other Infrastructure | Construction Limits:Seven (7) 1-L 36" Diameter RCPC x 8.00 Length with Headwall bothsides in different stations | Itangil-Sta.Teresita | Dumaran | PEO | 2021 | Supplemental Budget No. 9 | 730000 | 724491.42 | 45 | 2022-03-15 |  | 2022-04-29 | Subject for LD |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
983 | Installation of 2 Lines 36" Diameter RCPC with Headwall, Abaroan FMR | B2 GF PEO 22-02-062 | Other Infrastructure |  | Abaroan FMR | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 220000 | 219907.52 | 30 | 2022-03-21 |  | 2022-04-20 | 2022-03-21 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
984 | Installation of 3 Lines 36" Diameter RCPC with Headwall,Dumarao FMR | B2 GF PEO 22-02-066 | Other Infrastructure |  | Dumarao FMR, Roxas | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 324951.69 | 30 | 2022-03-15 | 1 | 2022-04-14 | 2023-01-05 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
985 | Installation of 3 Lines 36" Diameter RCPC with Headwall, Nicanor Zabala | B2 GF PEO 22-02-061 | Other Infrastructure |  | Nicanor Zabala, Roxas | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 325698.57 | 30 | 2022-03-15 | 1 | 2022-04-14 | 2022-06-24 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
986 | Installation of 2 Lines 36" Diameter RCPC with Headwall, Malaking Patag-Canimango Road | B2 GF PEO 22-02-058 | Other Infrastructure |  | Provincial Road Malaking Patag-Canimango Road | Culion | PEO | 2021 | Supplemental Budget No. 9 | 220000 | 214948.46 | 30 | 2022-03-15 |  | 2022-04-14 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
987 | Installation of 2 Lines 36" Diameter RCPC with Headwall,Magara-Caruray Road | B2 GF PEO 22-02-065 | Other Infrastructure |  | Magara-Caruray Road | Roxas | PEO | 2021 | Supplemental Budget No. 9 | 220000 | 215030.87 | 30 | 2022-03-15 | 1 | 2022-04-14 | 2022-06-24 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
988 | Construction of One (1) Barrel Box Culvert Sitio Marimek, Bgy. Aramaywan | B2 GF PEO 22-02-054 | Other Infrastructure |  | Sitio Marimek, Bgy. Aramaywan | Quezon | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1777488.54 | 90 | 2022-05-11 |  | 2022-08-09 |  |  |  |  | By contract | For Termination | R. Narrazid Trading and Construction | TIN 330-975-725 | For Legal Endorsement
989 | Construction of One (1) Barrel Box Culvert Sitio Diapla, Bgy. Teneguiban, El Nido | B2 GF PEO 22-02-050 | Other Infrastructure |  | Bgy. Teneguiban, El Nido | El Nido | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1992229.85 | 90 | 2022-05-11 |  | 2022-08-09 |  |  | 100% |  | By contract | Completed | F.F Galang Construction | TIN 188-519-198
990 | Construction of PWD Ramp, Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 4300000 | [10 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 3 - 2022
991 | Construction of Bahay Tuluyan |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1996599.15 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
992 | Construction of Perimeter Fence Phase IV | B2 GF PEO 22-02-053 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 1500000 | 1494748.2 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
993 | Improvement of Landscaping for Temporary and Treatment Monitoring Facilities | B2 GF PEO 22-02-079 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Supplemental Budget No. 9 | 370000 | 369256.78 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
994 | Improvement of Landscaping for Three Storey Medical Arts Building, Aborlan Medicare Hospital | B2 GF PEO 22-03-084 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 9 | 330000 | 329209.44 | 60 | 2022-07-26 |  | 2022-09-24 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
995 | Construction of Oxygen Building for Aborlan Medicare Hospital | B2 GF PEO 22-02-057 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | Supplemental Budget No. 9 | 1800000 | 1795559.6 | 150 | 2022-05-11 |  | 2022-10-08 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
996 | Improvement of Landscaping for Sofronio Espanola District Hospital | B2 GF PEO 22-02-080 | Medical Facilities |  | Sofronio Espanola District Hospital | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 900000 | 899029.67 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
997 | Concreting of Road Network Ph 2, Araceli-Dumaran District Hospital | B2 GF PEO 22-02-051 | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2021 | Supplemental Budget No. 9 | 2110000 | 2108233.38 | 120 | 2022-05-11 |  | 2022-09-08 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
998 | Concreting Of Cataban-Liminangcong Road (STA. 9+700 TO Sta. 9+987, Sta. 10+550 to Sta. 11+100 and Sta. 18+400 to Sta. 19+000) | B2 GF PEO 22-02-048 | Transportation Facilities |  | Cataban-Liminangcong | Taytay | PEO | 2021 | Supplemental Budget No. 9 | 10000000 | 9374893.39 | 90 | 2022-07-19 | 1 | 2022-10-17 | 2022-11-16 |  |  |  | By contract | For Termination | L.M John Construction Supplies Trading | TIN 422-936-808
999 | Construction of Three (3) Storey Medical Arts Building with Roofdeck for Helipad Phase I - Coron District Hospital | B2 GF PEO 22-02-046 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2021 | Supplemental Budget No. 9 | 18300000 | 18299211.23 | 180 | 2022-07-19 | 1 | 2023-01-15 | 2023-09-30 |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
1000 | Operation of El Nido Sewage Treatment Plant |  | Artesian Wells, Reservoir, Pumping and Conduits |  | El Nido Community Hospital | El Nido | PEO | 2021 | Supplemental Budget No. 9 | 1496227 | [9 empty] | By contract | On going |  |  | PEEDO Validate
1001 | Construction of Molecular Laboratory and Swabbing Facilities - Northern Palawan Provincial Hospital | B2 GF PEO 22-02-068 | Medical Facilities |  | Northern Palawan Provincial Hospital | Taytay | PEO | 2021 | Supplemental Budget No. 9 | 6000000 | 5996626.6 | 260 | 2022-05-27 | 1 | 2023-02-11 | 2022-02-24 |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1002 | Extension of Four Bays at the Existing Motorpool Building, Irawan | B2 GF PEO 22-02-067 | Other Facilities |  | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 9 | 2000000 | 1976569.56 | 90 | 2022-05-19 |  | 2022-08-17 | 2022-10-31 |  | 100% |  | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662
1003 | Sandoval Water System Staff House and Pipeline Appurtenance |  | Artesian Wells, Reservoir, Pumping and Conduits |  |  | Roxas | PEO | 2021 |  | 1235992.9 | 1235992.9 |  | 2021-04-19 |  | 2021-04-19 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1004 | Concreting Of Farm To Market Road (Sitio Tagpirara II From National Highway To Sea Shore) |  | Transportation Facilities |  | Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 16000000 | 15998583.16 | 60 | 2022-01-14 |  | 2022-03-15 | 2022-08-31 |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1005 | Water System At Sitio Kelwe |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Sitio Kelwe Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 992979.84 | 90 | 2022-01-25 |  | 2022-04-25 | 2022-06-10 |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
1006 | Renovation Of Barangay Hall Two (2) Storey Building |  | Other Facilities |  | Sitio Proper, Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 3000000 | 2999477.03 | 150 | 2022-01-14 |  | 2022-06-13 | 2022-09-02 |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1007 | Construction Of Level II Potable Water Supply 50cu.M Elevated Water Tank, 2km (PPE) Pipe Distribution Line 20 Communal Faucets |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 4000000 | 3998421.34 | 90 | 2022-04-25 |  | 2022-07-24 | 2022-06-10 |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
1008 | Construction Of (3) Units Multi-Purpose Drying Pavement |  | Other Facilities |  | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1500000 | 1499400.28 | 75 | 2022-01-14 |  | 2022-03-30 | 2022-05-15 |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1009 | Construction Of One (1) Storey School Building |  | Educational Facilities | 1 Classroom School Building | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2000000 | 1999812.49 | 90 | 2022-01-14 |  | 2022-04-14 | 2022-07-04 |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1010 | Construction Of Health Care Center With Perimeter Fence |  | Medical Facilities |  | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2500000 | 2498317.07 | 120 | 2022-01-14 |  | 2022-05-14 | 2022-06-29 |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1011 | Upgrading & Improvement Of Barangay Road |  | Transportation Facilities |  | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 10000000 | 9999985.71 | 90 | 2022-01-14 |  | 2022-04-14 |  |  | 100% |  | By contract | Completed | NRNS Trading And Construction Supply | TIN 922-390-708
1012 | Construction Of Health Center Sitio Cabangaan And Proper Two (2) Units Health Center |  | Medical Facilities |  | Sitio Cabangaan And Sitio Proper, Bgy. Samariñana, Brooke's Point | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 4000000 | 3993206 | 120 | 2022-01-15 |  | 2022-05-15 | 2022-08-03 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1013 | Construction Of (3) Units Multi-Purpose Drying Pavement For Sitio Cabangaan And Proper |  | Other Facilities |  | Sitio Cabangaan And Sitio Proper, Bgy.Samarinaña, Brooke's Point | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1500000 | 1498504.19 |  | 2022-01-15 |  | 2022-01-15 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1014 | Spring Development In Sitio Cabangaan |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Sitio Cabangaan, Bgy. Samariñana, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2000000 | 1993002.18 | 90 | 2022-01-25 |  | 2022-04-25 | 2022-06-10 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1015 | Concreting Of Access Road Proper 1 And Proper 2 |  | Transportation Facilities |  | Sitio Proper I And Sitio Proper, Bgy. Samarinaña, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 12500000 | 12498074.57 | 90 | 2022-01-14 |  | 2022-04-14 | 2022-12-17 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1016 | Concreting Of Farm To Market Road From National Highway To Sitio Proper |  | Transportation Facilities |  | National Highway To Sitio Proper, Brgy, Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 16000000 | 15998025.86 | 90 | 2022-01-14 |  | 2022-04-14 | 2022-08-05 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1017 | Two (2) Unit Multi-Purpose Drying Pavement at Sitio Proper and Sitio Rabok (15mx10m) Each Project |  | Other Facilities |  | Sitio Proper And Sitio Rabok, Bgy. Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 498854.05 | 45 | 2022-01-14 |  | 2022-02-28 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1018 | One (1) School Building Sitio Proper |  | Educational Facilities | 1 Classroom School Building | Sitio Proper, Bgy. Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 998340.77 | 60 | 2022-01-14 |  | 2022-03-15 | 2022-05-25 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1019 | One (1) Unit Multi-Purpose Drying Pavement at Sitio Tagpinasao (20mx30m) |  | Other Facilities |  | Sitio Tagpinasao, Bgry. Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 496683.42 | 45 | 2022-01-14 |  | 2022-02-28 | 2022-06-10 |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1020 | Rehabilitation Of Multi-Purpose Hall At Sitio Proper |  | Other Infrastructure |  | Sitio Proper,Brgy Salogon, Brooke's Point, Palawan | Brooke's Point | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 496052.8 | 60 | 2022-01-14 |  | 2022-03-15 |  |  | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1021 | Rural Electrification Project From Purok Pag-Asa (Capalan) To Purok Masigla (Kaibulusan) |  | Power and Energy Development Program |  | Purok Pag-Asa (Capalan) To Purok Masigla (Kaibulusan) | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 6000000 | 5999169.55 | 90 | 2021-12-31 |  | 2022-03-31 | 2022-12-22 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1022 | Rural Electrification Project From National Highway, Sitio Arasan To Sitio Tara-Tara Both In Purok Magtulungan |  | Power and Energy Development Program |  | Sitio Arasan To Sitio Tara-Tara Both In Purok Magtulungan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999419.71 | 30 | 2021-12-31 |  | 2022-01-30 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1023 | Concreting Of Farm To Market Road (FMR) From National Highway To Purok Matiyaga (Malatgao Falls) |  | Transportation Facilities |  | Magara | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 6500000 | 5671259.42 | 60 | 2022-03-01 |  | 2022-04-30 | 2022-05-31 |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
1024 | Concreting Of Farm To Market Road (Fmr) From Junction Bagong Silang Elementary School To Sitio Upper Iraan (Interior Iraan) |  | Transportation Facilities |  | Magara | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 5500000 | 4784494.05 | 60 | 2022-03-01 |  | 2022-04-30 | 2022-05-31 |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
1025 | Rural Electrification Project From National Highway To Purok Rancheria |  | Power and Energy Development Program |  | Magara | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999587.99 | 30 | 2021-12-31 |  | 2022-01-30 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1026 | Concreting Of Farm To Market Road From Barangay Proper/Poblacion To Sitio Linapawan, Barangay Abaroan |  | Transportation Facilities |  | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 13500000 | 13496644.22 |  | 2021-12-31 |  | 2021-12-31 | 2022-05-16 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1027 | Rural Electrification Project From Purok Mabuhay To Purok Maagap, Barangay Abaroan |  | Power and Energy Development Program |  | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999516.3 | 45 | 2021-12-31 |  | 2022-02-14 | 2022-07-07 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1028 | Rural Electrification Project From Sitio Ibangan, Purok Maunlad To Sitio Linapawan, Purok Nagkakaisa, Barangay Abaroan |  | Power and Energy Development Program |  | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 3000000 | 2999620.02 | 60 | 2021-12-31 |  | 2022-03-01 | 2022-08-06 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1029 | Construction Of Birthing Clinic With Complete Facilities And Equipment In Purok Bagong Silang (Barangay Proper), Barangay Abaroan |  | Medical Facilities |  | Bgy. Abaroan | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 2000000 | 1994628.3 | 120 | 2021-12-31 |  | 2022-04-30 | 2022-12-09 | 2022-12-26 | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1030 | Water System For Sitio Matalangaw |  | Artesian Wells, Reservoir, Pumping and Conduits |  | Sitio Matalangaw | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 500000 | 499354.96 | 30 | 2022-04-25 |  | 2022-05-25 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
1031 | Concreting Of Farm To Market Road From National Highway (Daval Road) Going, Bgy. Poblacion To Purok Ilian-Ilian (Portion Only) |  | Transportation Facilities |  |  | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 12500000 | 12496581.46 | 90 | 2022-04-14 |  | 2022-07-13 | 2022-07-29 |  | 100% |  | By contract | Completed | Bicol Goldrock Construction Corporation | TIN 006-098-920
1032 | Rural Electrification Project From Sitio Ilian-Ilian |  | Power and Energy Development Program |  | Bgy. Dumarao | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999382.43 | 30 | 2021-12-31 |  | 2022-01-30 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1033 | Rural Electrification Project At Sitio Lower Subingao |  | Power and Energy Development Program |  | Sitio Lower Subingao | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1000000 | 999442.73 | 30 | 2021-12-31 |  | 2022-01-30 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1034 | Rural Electrification Project From Sitio Itabiak To Sitio Salvador |  | Power and Energy Development Program |  | Sitio Itabiak To Sitio Salvador | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 4000000 | 3999529.88 | 75 | 2021-12-31 |  | 2022-03-16 | 2022-11-20 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1035 | Construction Of 1-Storey 1-Cl School Building At Dumarao National High School |  | Educational Facilities | 1 Classroom School Building |  | Roxas | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 1500000 | 1496520.39 | 60 | 2022-04-14 |  | 2022-06-13 | 2022-07-10 |  | 100% |  | By contract | Completed | Bicol Goldrock Construction Corporation | TIN 006-098-920
1036 | Road Concreting Of 820 Meters From Purok Bagong Silang To Purok Ugnayan | B2 TF DUE TO NGAS ELCAC 2021 21-050 | Transportation Facilities |  | Villa Fria (Kemdeng) | San Vicente | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 16400000 | 16393004.74 | 90 | 2022-04-14 |  | 2022-07-13 | 2022-07-29 |  |  |  | By contract | Terminated | Bicol Goldrock Construction Corporation | TIN 006-098-920 | Termination for convenience: Transfer of location
1037 | Road Concreting Of 180 Meters At Labrador St. | B2 TF DUE TO NGAS ELCAC 2021 21-050 | Transportation Facilities |  | Villa Fria (Kemdeng) | San Vicente | PEO | 2021 | SBDP-NTF-ELCAC 2021 | 3600000 | 3596835.09 | 90 | 2022-01-14 |  | 2022-04-14 | 2022-07-29 |  | 100% |  | By contract | Completed | Bicol Goldrock Construction Corporation | TIN 006-098-920
1038 | PR of Materials for the Repair and Maintenance of PGP Hospital Roofing |  | Medical Facilities |  | Dr. Jose Rizal District Hospital, SPPH, Narra Municipal Hospital, Aborlan Medicare Hospital, Roxas Medicare Hospital, San Vicente District Hospital, El Nido Community Hospital |  | PEO | 2021 | MOOE | 2098492.48 | [7 empty] | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1039 | Repair/Renovation of Registry of Deeds |  | Other Facilities |  | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2021 | MOOE | 1500000 | 1498806.5 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
1040 | Rehabilitation and Repair of PGP Property Perimeter Fence |  | Other Facilities |  | Bgy. Irawan, PPC | Puerto Princesa City | PEO | 2021 | MOOE | 1938402 | 1929390.23 |  | 2021-09-08 |  | 2021-09-08 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1041 | Provincial Engineering Office Renovation (Quality Division) |  | Other Facilities |  | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2021 | MOOE | 146100.94 | 145276 |  | 2021-08-10 |  | 2021-08-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1042 | Repair/Renovation of Aborlan Medicare Hospital (Ceiling Works) | B2 PEO 200-21-06-07177 | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2021 | MOOE | 968141.15 | 955202.03 | 90 | 2021-08-10 |  | 2021-11-08 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1043 | Repair/Renovation of Southern Palawan Provincial Hospital (Ceiling and Tiles) |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | MOOE | 703320.41 | 698373.4 |  | 2021-08-10 |  | 2021-08-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1044 | Repair/Renovation of Roxas Medicare Hospital (Ceiling and Tiles) |  | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2021 | MOOE | 1334346.07 | 1332958.61 |  | 2021-08-24 |  | 2021-08-24 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1045 | Repair/Renovation of Bataraza Distirct Hospital (Ceiling) |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2021 | MOOE | 353552.07 | 352508 |  | 2021-08-10 |  | 2021-08-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1046 | Repair/Renovation Dr. Jose Rizal District Hospital (Ceiling) |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2021 | MOOE | 916625.48 | 942662.45 |  | 2021-08-13 |  | 2021-08-13 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1047 | Repair/Renovation of PGP Facilities (DILG-SGLG Compliance) |  | Other Facilities |  |  | Puerto Princesa City | PEO | 2021 | MOOE | 770441 | [7 empty] | 100% |  | By contract | Completed
1048 | Repair and Maintenance of Power Take Off of Bisucay Power Plant |  | Power and Energy Development Program |  | Bisucay | Cuyo | PEO | 2021 | MOOE | 70000 | [7 empty] | 100% |  | By contract | Completed
1049 | Supply and Installation of Hospital Billboards and Markers |  | Medical Facilities |  |  |  | PEO | 2021 | MOOE | 1500000 | [7 empty] | 100% |  | By contract | Completed | Megaprint
1050 | Construction of Molecular Laboratory and Swabbing Facilities, Coron District Hospital | B2 TF DUE TO NGAS DOH 21-007 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2021 | DOH Fund | 5000000 | 4989044.9 | 230 | 2021-06-28 |  | 2022-02-13 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1051 | Construction of Molecular Laboratory and Swabbing Facilities, El Nido Community Hospital |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2021 | DOH Fund | 6000000 | 5999488.45 | 260 | 2021-06-29 |  | 2022-03-16 |  |  | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
1052 | Construction of Temporary and Treatment and Monitoring Facilities, Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | DOH Fund | 10000000 | 9896366.18 | 180 | 2021-06-30 |  | 2021-12-27 |  |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1053 | Medical Equipment for Molecular Laboratory and Swabbing Facilities, Coron District Hospital |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2021 | DOH Fund | 5000000 | [7 empty] | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1054 | Medical Equipment for Molecular Laboratory and Swabbing Facilities, El Nido Community Hospital |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2021 | DOH Fund | 5000000 | [7 empty] | 100% |  | By contract | Completed | Smmiley Builders and Trading | TIN 936-564-958
1055 | Construction of Sheltered Port Phase II Bgy. Pag-asa, Municipality of Kalayaan, Palawan | B2 TF DUE TO NGAS - DOTR 21- 006 | Ports and Airports |  | Bgy. Pag-asa, Municipality of Kalayaan, Palawan | Kalayaan | PEO | 2021 | Trust Fund - DOTr | 220673124.57 | 220569081.3 | 390 | 2021-06-11 |  | 2022-07-06 | 2023-04-11 |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1056 | Construction of El Nido Sewage and Solid Waste Treatment Plant Project Phase 2-2 | B2 SB3 PEO 300-21-07-08567 | Artesian Wells, Reservoir, Pumping and Conduits |  |  | El Nido | PEO | 2021 | Supplemental Budget No. 3 | 72000000 | 71950000 |  | 2021-09-22 |  | 2021-09-22 |  |  | 100% |  | By contract | Completed | Ivy Michelle Construction and Trading | TIN 009-492-339
1057 | Concreting of Antonio-Maragok-Tanatanaen Road (Intermittent Section) | B2 GF PEO 22-01-001 | Transportation Facilities | Section No. 1: 1000 ln.m - Section No. 2: 240ln.m - Section No. 3: 960 ln.m - Total Length: 2.2 km | Dumaran | Dumaran | PEO | 2022 | 20% Development Fund | 23100000 | 19148894.25 | 120 | 2022-05-12 | 3 | 2022-09-09 | 2023-12-03 |  | 86% |  | By contract | No movement | Leon John Great Builders Construction Corp. | TIN 009-924-271 | No activity on site: Subject for LD
1058 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-037 | Other Infrastructure |  | Sto. Tomas, Dumaran | Dumaran | PEO | 2022 | 20% Development Fund | 3700000 | 3690707.21 | 120 | 2022-05-16 | 1 | 2022-09-13 | 2022-11-12 | 2023-05-11 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1059 | Upgrading of Caruray Bailey Bridge II (Pag-Asa 2) to RCDG | B2 GF PEO 22-01-002 | Transportation Facilities | 25 m | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 9000000 | 7554570.43 | 184 | 2022-07-01 | 1 | 2023-01-01 | 2023-08-31 | 2024-03-18 | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
1060 | Upgrading of Caruray New Site Bailey Bridge to RCDG | B2 GF PEO 22-01-014 | Transportation Facilities | 32 m | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 18150000 | 15408362.58 | 197 | 2022-07-01 | 1 | 2023-01-14 | 2023-04-30 | 2024-07-12 | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
1061 | Concreting of Magara-Caruray Road (Intermittent Section) | B2 GF PEO 22-01-003 | Transportation Facilities | 2.202 km | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 23100000 | 18281985.6 | 120 | 2022-05-20 | 1 | 2022-09-17 | 2023-04-03 |  | 86.2% |  | By contract | Suspended | A.P. Consebido Construction & Trading | TIN 931-421-496 | Limited supply of aggregates
1062 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-029 | Other Infrastructure |  | New Agutaya ,San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 3700000 | 3647836.57 | 120 | 2022-03-17 | 1 | 2022-07-15 | 2023-05-29 |  | 100% |  | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271
1063 | Construction of Hanging Bridge | B2 GF PEO 22-01-004 | Transportation Facilities | 36 m | New Agutaya ,San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 6000000 | 5924964.76 | 90 | 2022-03-17 | 1 | 2022-06-15 | 2023-05-26 |  | 100% |  | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271
1064 | Construction of Hanging Bridge | B2 GF PEO 22-08-141 | Transportation Facilities | 36 m | Alimanguan, San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 4500000 | 4002540.76 | 90 | 2022-11-21 | 1 | 2023-02-19 | 2023-06-26 |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1065 | Construction of Three (3) Barrel Box Culvert - Construction of Spillway |  | Other Infrastructure |  | Alimanguan, San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 6145521.47 | [10 empty] | Re-aligned
1066 | Construction of 3-Barrel Box Culvert | B2 GF PEO 22-01-039 | Other Infrastructure |  | New Agutaya ,San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 4500000 | 4449952.28 | 90 | 2022-03-17 | 1 | 2022-06-15 | 2022-11-25 |  | 100% |  | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271
1067 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-038 | Other Infrastructure |  | San Isidro, San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 3700000 | 3325959.99 | 120 | 2022-07-18 | 1 | 2022-11-15 | 2023-07-14 |  | 100% |  | By contract | Completed | Furosam Incorporated | TIN 009-062-221
1068 | Concreting of Benga - Calapa Road (Intermittent Section) | B2 GF PEO 22-01-026 | Transportation Facilities | 1.0 km | San Vicente | San Vicente | PEO | 2022 | 20% Development Fund | 35805000 | 35698490.36 | 150 | 2022-05-12 | 1 | 2022-10-09 | 2023-01-22 |  | 90% |  | By contract | Suspended | Leon John Great Builders Construction Corp. | TIN 009-924-271 | Limited supply of aggregates
1069 | Construction of New Guinlo RCDG Bridge | B2 GF PEO 22-01-027 | Transportation Facilities | 30 m | Bgy. New Guinlo, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 30000000 | 29971024.82 | 180 | 2022-03-10 |  | 2022-09-06 | 2022-12-05 |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
1070 | Upgrading of Talugon Bailey Bridge I to RCDG | B2 GF PEO 22-01-005 | Transportation Facilities | 15 m | Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 9000000 | 7638561.98 | 184 | 2022-07-01 | 1 | 2023-01-01 | 2023-04-06 |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
1071 | Upgrading of Talugon Bailey Bridge II to RCDG | B2 GF PEO 22-01-023 | Transportation Facilities | 15 m | Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 7500000 | 6366515.79 | 182 | 2022-07-01 | 1 | 2022-12-30 | 2023-04-04 | 2023-09-26 | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
1072 | Upgrading of Talugon Bailey Bridge III to RCDG | B2 GF PEO 22-02-047 | Transportation Facilities | 15 m | Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 7500000 | 7499774.11 | 182 | 2022-12-09 | 1 | 2023-06-09 | 2023-10-17 |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1073 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-036 | Other Infrastructure |  | Sto. Talugon, Bagumbayan, El Nido | El Nido | PEO | 2022 | 20% Development Fund | 3700000 | 3690706.71 | 120 | 2022-05-16 |  | 2022-09-13 |  |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1074 | Upgrading of Orol Bailey Bridge I to RCDG | B2 GF PEO 22-01-006 | Transportation Facilities | 21 m | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 7500000 | 6044191.6 | 182 | 2022-05-11 | 1 | 2022-11-09 | Subject for LD |  | 98% |  | By contract | On going | Louiese Trading & Construction | TIN 940-685-564
1075 | Upgrading of Orol Bailey Bridge II to RCDG | B2 GF PEO 22-01-008 | Transportation Facilities | 21 m | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 7500000 | 6044191.6 | 182 | 2022-05-11 | 1 | 2022-11-09 | Subject for LD |  | 97% |  | By contract | On going | Louiese Trading & Construction | TIN 940-685-564
1076 | Upgrading of Orol Bailey Bridge III to RCDG | B2 GF PEO 22-01-007 | Transportation Facilities | 21 m | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 7150000 | 5702491.3 | 182 | 2022-05-17 | 1 | 2022-11-15 | 2023-02-13 |  | 100% |  | By contract | Completed | Louiese Trading & Construction | TIN 940-685-564
1077 | Construction of 2-Barrel Box Culvert | B2 GF PEO 22-01-034 | Other Infrastructure |  | Caniqui, Taytay | Taytay | PEO | 2022 | 20% Development Fund | 3700000 | 3690664.21 | 90 | 2022-05-16 |  | 2022-08-14 |  | 2022-08-05 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1078 | Concreting of Linapacan Road | B2 GF PEO 22-01-022 | Transportation Facilities | 1.50 km | Linapacan, Palawan | Linapacan | PEO | 2022 | 20% Development Fund | 15750000 | 15749098.26 | 90 | 2022-05-16 |  | 2022-08-14 | Subject for LD |  | 95% |  | By contract | On going | Julriz Trading and Construction | TIN 495-740-401
1079 | Concreting of Abaroan Road (Intermittent Section) | B2 GF PEO 22-01-015 | Transportation Facilities | 1.098 km | Bgy. Abaroan | Roxas | PEO | 2022 | 20% Development Fund | 11550000 | 11548516.56 | 90 | 2022-03-10 |  | 2022-06-08 | 2022-10-22 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1080 | Concreting of Lucbuan-Emilod Road | B2 GF PEO 22-01-009 | Transportation Facilities | 1.403 km | Magsaysay | Magsaysay | PEO | 2022 | 20% Development Fund | 16800000 | 16799532.15 | 120 | 2022-03-16 |  | 2022-07-14 |  |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
1081 | Concreting of Plaridel-Apis-Cabigaan Road | B2 GF PEO 22-01-016 | Transportation Facilities | 1.0 km | Aborlan | Aborlan | PEO | 2022 | 20% Development Fund | 10500000 | 9197925.23 | 90 | 2022-06-09 |  | 2022-09-07 | 2023-01-05 |  | 100% |  | By contract | Completed | Chad Lourence Trading & Construction Services | TIN 919-616-230
1082 | Rehabilitation of Sagpangan Spillway |  | Other Infrastructure | Spillway=16m(l) x 15m(w) x 1.55m(h) | Sagpangan - Barake Road, Aborlan | Aborlan | PEO | 2022 | 20% Development Fund | 2000000 |  | 80 | [8 empty] | Re-aligned
1083 | Concreting of Cataban - Liminangcong Critical Road (Intermittent Section) | B2 GF PEO 22-01-010 | Transportation Facilities | 1.905 km | Taytay | Taytay | PEO | 2022 | 20% Development Fund | 20000000 | 18021396.03 | 120 | 2022-05-18 | 1 | 2022-09-15 | 2023-02-12 |  | 100% |  | By contract | Completed | L.M John Construction Supplies Trading | TIN 422-936-808
1084 | Concreting of Paglaum Itangil to Sta. Teresita | B2 GF PEO 22-01-011 | Transportation Facilities | 1.906 km | Dumaran | Dumaran | PEO | 2022 | 20% Development Fund | 20000000 | 17967926.62 | 120 | 2022-05-18 |  | 2022-09-15 | Subject for LD |  | 100% |  | By contract | Completed | L.M John Construction Supplies Trading | TIN 422-936-808
1085 | Concreting of 1 km Barotuan to Bucana | B2 GF PEO 22-01-012 | Transportation Facilities | 1.0 km | El Nido | El Nido | PEO | 2022 | 20% Development Fund | 10500000 | 10488328.82 | 90 | 2022-05-11 |  | 2022-08-09 | 2022-12-13 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1086 | Concreting of 1 km Highway to Teneguiban | B2 GF PEO 22-01-017 | Transportation Facilities | 1.0 km | El Nido | El Nido | PEO | 2022 | 20% Development Fund | 10500000 | 8521495.96 | 90 | 2022-05-16 | 1 | 2022-08-14 | 2023-01-16 |  | 100% |  | By contract | Completed | A.P. Consebido Construction & Trading | TIN 931-421-496
1087 | Concreting of 1 km Pulot Sea Road | B2 GF PEO 22-01-018 | Transportation Facilities | 1.0 km | Sofronio Española | Sofronio Española | PEO | 2022 | 20% Development Fund | 10500000 | 8596286.23 | 90 | 2022-07-18 | 1 | 2022-10-16 | 2023-05-04 | 2023-07-03 | 100% |  | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176
1088 | Concreting of 1 km Labog to Naltep Road | B2 GF PEO 22-01-013 | Transportation Facilities | 1.0 km | Sofronio Española | Sofronio Española | PEO | 2022 | 20% Development Fund | 10500000 | 8596286.23 | 90 | 2022-07-18 | 1 | 2022-10-16 | 2023-09-21 |  | 100% |  | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176
1089 | Construction of One (1) Barrel RCBC | B2 GF PEO 22-01-031 | Other Infrastructure | RCBC: 1-3m(h) X 3m(w) X 6(l) X 0.30m(thick) Approach: 6m(l) X 0.60m(w) X 0.20m(Thick) X 2 Sides Detour Road: 2-12m(l) 5m(w) w/ 24'' RCPC | Apo-Aporawan, Aborlan | Aborlan | PEO | 2022 | 20% Development Fund | 2000000 | 1862000 | 90 | 2022-06-27 |  | 2022-09-25 | 2022-11-09 |  | 100% |  | By contract | Completed | Palbic Construction and Supply | TIN 128-066-252
1090 | Construction of 3-Barrel Box Cuvert | B2 GF PEO 22-01-024 | Other Infrastructure |  | Sowangan, Quezon | Quezon | PEO | 2022 | 20% Development Fund | 6000000 | 4717681.25 | 120 | 2022-07-08 |  | 2022-11-05 |  |  | 100% |  | By contract | Completed | Maintin Construction and Supply | TIN 488-730-176
1091 | Construction of Cacarigan Spillway | B2 GF PEO 22-01-020 | Other Infrastructure | (A) Spillway: 30m(l) x 9.73m (w) x 3.05m (h) - (B) Approach: 6m (l) x 6m (w) x 0.2 (h) - © Slope protection 5M (L) x 4 sides | Aramaywan, Narra | Narra | PEO | 2022 | 20% Development Fund | 6145521.47 | 5156938.33 | 120 | 2022-05-11 | 1 | 2022-09-08 | 2022-08-17 |  |  |  | By contract | Terminated | N.Sales Construction | TIN 174-694-454 | Please see Notice of Termination
1092 | Concreting of Caguesan Road | B2 GF PEO 22-01-021 | Transportation Facilities | 0.8 km | Caguesan, Narra | Narra | PEO | 2022 | 20% Development Fund | 8000000 | 7979873.47 | 90 | 2022-07-08 |  | 2022-10-06 |  | 2022-09-29 | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1093 | Construction of Raang Spillway | B2 GF PEO 22-01-025 | Other Infrastructure |  | Mainit, Brooke's Point | Brooke's Point | PEO | 2022 | 20% Development Fund | 8600000 | 7215051.97 | 120 | 2022-05-11 |  | 2022-09-08 |  |  |  |  | By contract | Terminated | N.Sales Construction | TIN 174-694-454 | Termination for convenience: Duplication of project
1094 | Construction of Ugnisan 1 Spillway | B2 GF PEO 22-01-028 | Other Infrastructure |  | Culion | Culion | PEO | 2022 | 20% Development Fund | 3000000 | 2999218.64 | 90 | 2022-05-16 |  | 2022-08-14 | 2022-11-17 | 2023-03-15 | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1095 | Construction of Ugnisan 2 Spillway | B2 GF PEO 22-01-032 | Other Infrastructure |  | Culion | Culion | PEO | 2022 | 20% Development Fund | 3000000 | 2999218.64 | 90 | 2022-05-16 |  | 2022-08-14 | 2022-11-17 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1096 | Construction of Sowangan Hanging Bridge | B2 GF PEO 22-01-033 | Transportation Facilities | 60 m | Sowangan, Quezon | Quezon | PEO | 2022 | 20% Development Fund | 4512687.53 | 4507518.61 | 90 | 2022-03-15 |  | 2022-06-13 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1097 | Construction of Tagasag Hanging Bridge | B2 GF PEO 22-01-035 | Transportation Facilities | 22 m | Canipaan, Rizal | Rizal | PEO | 2022 | 20% Development Fund | 4512687.53 | 4510105.46 | 90 | 2022-03-22 |  | 2022-06-20 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1098 | Construction of Provincial Health Office | B2 GF PHO 22-11-207 | Other Facilities | Floor area (3 storey): 43m x 15m - Porch with ramp: 15.575m x 5.1m - Road Network: 477.44m^2 - Parking Area: 300.84m^2 - Perimeter Fence: 400m | Bgy. Bancao-Bancao | Puerto Princesa City | PEO | 2022 | Capital outlay | 48000000 | 47974854 | 260 | 2023-03-02 |  | 2023-11-17 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1099 | Construction of Three (3) Storey Medical Ward Building, Phase II in Aborlan Medicare Hospital | B2 GF PEO 22-02-070 | Medical Facilities |  | Aborlan, Palawan | Aborlan | PEO | 2022 | Capital outlay | 20000000 | 19427448.22 | 120 | 2022-06-27 |  | 2022-10-25 | 2022-12-14 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1100 | Completion of Bahay Tuluyan and Additional Hazardous Waste Vault Treatment Facilities in Aborlan Medicare Hospital | B2 GF AMH 22-02-072 | Medical Facilities |  | Aborlan, Palawan | Aborlan | PEO | 2022 | Capital outlay | 4100000 | 4098575.72 | 120 | 2022-06-27 |  | 2022-10-25 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1101 | Centralized Oxygen Generator System |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2022 | Capital outlay | 16000000 | [7 empty] | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
1102 | Construction of Four-Storey Medical Arts Building A Phase II in Southern Palawan Provincial Hospital | B1 GF SPPH 22-02-078 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | Capital outlay | 20000000 |  | 120 | [8 empty] | Reverted
1103 | Construction of Southern Palawan Provincial Hospital (Completion of Medical Workers Dormitory) | B2 GF SPPH 22-02-071 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | Capital outlay | 5000000 | 4997529.45 | 90 | 2022-05-11 |  | 2022-08-09 | Subject for LD |  | 40.2% |  | By contract | On going | RD Abacial Construction | TIN 327-679-690
1104 | Improvement of Coron District Hospital (Concreting of Access Road to Mortuary & Motorpool Parking Area, Construction of Hazardous Waste Vault, Manifold & Perimeter Fence, Additional Works in Molecular Laboratory) | B2 GF CODH 22-08-142 | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2022 | Capital outlay | 6100000 | 5960147.47 | 90 | 2023-03-02 |  | 2023-05-31 |  | 2023-12-28 | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1105 | Construction of Oxygen Building |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2022 | Capital outlay | 1800000 | 1774809.77 | 150 | 2023-02-27 |  | 2023-07-27 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1106 | Completion of Three (3) Storey Medical & Ward Building in Narra Municipal Hospital | B2 GF NMH 22-03-083 | Medical Facilities | (a) Floor area: 43m x 15m - (b) Ramp up: 24m x 6m - © Oxygen Building: 45.14 sq.m (d) Walkway: 126 ln.m | Narra Municipal Hospital | Narra | PEO | 2022 | Capital outlay | 35000000 | 34984209.43 | 120 | 2022-05-18 | 1 | 2022-09-15 | 2022-12-20 | 2022-12-21 | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
1107 | Centralized Oxygen Generator System |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2022 | Capital outlay | 16000000 | [7 empty] | 100% |  | By contract | Completed | Brilliant Metal Industrial Corp. | TIN 143-754-742-000
1108 | Construction of Medical Record and Pharmacy Storage in Roxas Medicare Hospital | B2 GF RMH 22-02-073 | Medical Facilities |  | Roxas Medicare Hospital | Roxas | PEO | 2022 | Capital outlay | 1910000 | 1757426.18 | 90 | 2022-07-11 |  | 2022-10-09 | 2022-12-07 |  | 100% |  | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662
1109 | Centralized Oxygen Generator System |  | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2022 | Capital outlay | 16000000 | [10 empty] | Failure of bidding
1110 | Construction of Manifold, Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan | Aborlan | PEO | 2022 | Supplemental Budget No. 2 | 250000 | [10 empty] | Re-aligned
1111 | Construction of Manifold, Southern Palawan Provincial Hospital |  | Medical Facilities |  | Brooke's Point | Brooke's Point | PEO | 2022 | Supplemental Budget No. 2 | 250000 | [10 empty] | Re-aligned
1112 | Construction of Manifold, Northern Palawan Provincial Hospital |  | Medical Facilities |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 250000 | [10 empty] | Re-aligned
1113 | Construction of Multi-Purpose Building, Aborlan Medicare Hospital | B2 GF SB2 INFRA 22-08-100 | Medical Facilities |  | Aborlan | Aborlan | PEO | 2022 | Supplemental Budget No. 2 | 2400000 | 1990784.03 | 120 | 2023-01-24 |  | 2023-05-24 |  | 2023-12-30 | 100% |  | By contract | Completed | F.B Murillo Construction | TIN 772-152-432
1114 | Construction of One (1) Box Culvert | B2 GF SB2 INFRA 22-08-117 | Other Infrastructure | RCBC/RC Slope Protection: (a) 1-3m(h) x 3m(w) x 6.0m(l) x 0.30m thk (b) 6m(l) x 6.0m(w) x 0.20m (thk) x 2 sides (c ) Detour road 2-12m(l) x 5m(w) w/ 24'' RCPC (d) Slope protection 5m(l) x 2m(h) x 0.30m thk x 4 sides | Sitio Tabud, Panitian, Quezon | Quezon | PEO | 2022 | Supplemental Budget No. 2 | 2000000 | 1997693.49 | 60 | 2023-02-06 |  | 2023-04-07 |  |  | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1115 | Rehabilitation of Bridge Slope Protection at Abutment "A-B" in Tiondunan Bridge | B2 GF INFRA 22-08-099 | Other Infrastructure | Slope protection: 103.89 cu.m | Tiondunan Bridge, Bgy.Mendoza, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 2 | 1477166.85 | 1473973.18 | 60 | 2023-01-12 | 1 | 2023-03-13 | 2023-08-11 |  | 100% |  | By contract | Completed | MKB Builders and Supply | TIN 262-511-948
1116 | Improvement of Molecular Laboratory and Swabbing Facilities (Mechanical Layout) |  | Medical Facilities |  | Irawan, PPC | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 2 | 1000000 | [9 empty] | By contract | For Termination
1117 | Construction of Transformer Platform in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB2 INFRA 22-09-129 | Medical Facilities |  | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 2 | 327000 | 326764.24 | 30 | 2023-01-17 |  | 2023-02-16 |  |  | 100% |  | By contract | Completed | New Space Trading and Construction | TIN 010-545-401
1118 | Construction of Transformer Platform in Sofronio Española District Hospital |  | Medical Facilities |  | S. Española | Sofronio Española | PEO | 2022 | Supplemental Budget No. 2 | 327000 | [10 empty] | Re-aligned
1119 | Improvement of Molecular Laboratory and Swabbing Facilities in El Nido Community Hospital (Mechanical Layout) |  | Medical Facilities |  | El Nido Community Hospital | El Nido | PEO | 2022 | Supplemental Budget No. 2 | 550000 | [10 empty] | Re-aligned |  |  | Fund Re-aligned
1120 | Improvement of Molecular Laboratory and Swabbing Facilities in San Vicente District Hospital (Mechanical Layout) |  | Medical Facilities |  | San Vicente | San Vicente | PEO | 2022 | Supplemental Budget No. 2 | 550000 | [10 empty] | Re-aligned |  |  | Fund Re-aligned
1121 | Construction of Molecular Laboratory and Swabbing Facilities in Northern Palawan Provincial Hospital (Mechanical Layout) |  | Medical Facilities |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 550000 | [10 empty] | Re-aligned |  |  | Fund Re-aligned
1122 | Concreting from National Highway to El Nido STP | B2 GF INFRA 22-08-127 | Transportation Facilities | Road length: 1140.00 l.m - Drainage-RCPC=2pcs-1Lx8m RCPC with End Protection - RC Box culvert=2 barrel Ht. 2.0m W=3m | El Nido | El Nido | PEO | 2022 | Supplemental Budget No. 2 | 12642822.16 | 10665425.22 | 90 | 2022-01-16 | 2 | 2022-04-16 | 2023-12-17 |  | 100% |  | By contract | Completed | Diane Construction and Enterprises | TIN 140-882-282
1123 | Construction of Northern Palawan Technical Vocational School Phase 3 |  | Educational Facilities |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 5810000 | [10 empty] | Re-aligned
1124 | Construction of Perimeter Fence in Palawan Technical Vocational School Phase II |  | Educational Facilities |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 2700000 | [10 empty] | Re-aligned
1125 | Construction of Multi-purpose Drying Pavement |  | Other Facilities |  | Dumangueña, Narra | Narra | PEO | 2022 | Supplemental Budget No. 2 | 2250000 | [10 empty] | Re-aligned
1126 | Construction of Multi-purpose Hall Building |  | Other Infrastructure |  | Dumangueña, Narra | Narra | PEO | 2022 | Supplemental Budget No. 2 | 2800000 | [10 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 3 - 2022
1127 | Upgrading from 75 KVA to 250 KVA Transformer and accessories in Southern Palawan Provincial Hospital | B2 GF SB2 INFRA 22-10-157 | Medical Facilities |  | Brooke's Point | Brooke's Point | PEO | 2022 | Supplemental Budget No. 2 | 10826953.06 | 10770998.78 | 60 | 2023-03-27 |  | 2023-05-26 | 2023-08-14 | 2024-02-03 | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1128 | Supply and Installation of 1 - 500 KVA Generator Set with ATS in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Brooke's Point | Brooke's Point | PEO | 2022 | Supplemental Budget No. 2 | 4200000 | 4193000 | 60 | 2023-02-15 |  | 2023-04-16 |  |  |  |  | By contract | Order of Termination | N-Gines Technology Inc.
1129 | Upgrading from 75 KVA to 250 KVA Transformer and accessories in Northern Palawan Provincial Hospital | B2 GF SB2 INFRA 22-08-156 | Medical Facilities |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 10826953.06 | 10770998.78 | 60 | 2023-03-27 | 1 | 2023-05-26 | 2023-07-30 | 2023-11-27 | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1130 | Supply and Installation of 1 - 500 KVA Generator Set with ATS in Northern Palawan Provincial Hospital |  | Medical Facilities |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 4200000 | 3823000 | 60 | 2023-02-15 |  | 2023-04-16 |  |  |  |  | By contract | Order of Termination | N-Gines Technology Inc.
1131 | Supply and Installation of 1 - 500 KVA Generator Set with ATS in Cory Park Covered Event Center |  | Other Facilities |  | Capitol Compound, Tanglaw, PPC | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 2 | 4200000 | 3823000 | [8 empty] | By contract | For Termination | N-Gines Technology Inc. |  | For Legal Endorsement
1132 | Construction of Powerhouse in Paly VEP |  | Power and Energy Development Program |  | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 2 | 1400000 | [10 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 3 - 2022
1133 | Construction of Sewage Treatment Plant, Aborlan Medicare Hospital |  | Medical Facilities |  | Aborlan Medicare Hospital | Aborlan | PEO | 2022 | Supplemental Budget No. 1 | 822000 | [10 empty] | Re-aligned |  |  | Re-aligned for Supplemental Budge No. 5
1134 | Construction of Material Recovery Facilities, Sofronio Española Hopsital | B2 GF SB1 PEO22 24-05-086 | Medical Facilities | One Storey Building: 24 sq.m | Bgy. Pulot Center | Sofronio Española | PEO | 2022 | Supplemental Budget No. 1 | 1128000 | 1126610.75 | 45 | 2024-07-29 |  | 2024-09-12 | 2024-10-02 |  | 100% |  | By contract | Completed | JD Golez Construction Services | TIN 181-147-186
1135 | Installation of Fire Protection and Alarm System, Quezon Medicare Hospital | B2 GF SB1 PEO 22-11-187 | Medical Facilities |  | Quezon Medicare Hospital | Quezon | PEO | 2022 | Supplemental Budget No. 1 | 3300000 | 3294749.006 | 60 | 2023-02-16 |  | 2023-04-17 |  | 2023-06-09 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1136 | Installation of Fire Protection and Alarm System, Dr. Jose Rizal Medicare Hospital |  | Medical Facilities |  | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2022 | Supplemental Budget No. 1 | 3300000 | [10 empty] | Re-aligned
1137 | Construction of Hazardous Waste Vault in Bataraza Medicare Hospital |  | Medical Facilities |  | Bataraza Distirct Hospital | Bataraza | PEO | 2022 | Supplemental Budget No. 1 | 56000 | [10 empty] | For Re-bid
1138 | Construction of 100 cu.m Elevated Water Tank with Deepwell and Chlorination System in Balabac District Hospital | B2 GF SB1 PEO22 24-09-106 | Medical Facilities | 100 cu.m Elevated Water Tank with Deepwell and Chlorination System | Bgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2022 | Supplemental Budget No. 1 | 5000000 | 4994952.68 | [9 empty] | For Award |  |  | NTP on process
1139 | Installation of Fire Protection and Alarm System, Balabac District Hospital | B2 GF SB1 PEO 22-08-135 | Medical Facilities |  | Bgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2022 | Supplemental Budget No. 1 | 3500000 | 3497307.19 | 64 | 2023-01-23 |  | 2023-03-28 |  | 2023-05-02 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1140 | Construction of Three (3) Storey Building Medical Worker's Dormitory, Northern Palawan Provincial Hospital |  | Medical Facilities | Dimension: 21mx11.10m = 233.10 sqm | Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 12600000 |  | 115 | [8 empty] | Re-aligned |  |  | Re-aligned to 2-Storey Building (SB NO. 4)
1141 | Construction of Bahay Tuluyan in Northern Palawan Provincial Hospital | B2 GF SB1 PEO22-23-11-147 | Medical Facilities | Floor area: 27m x 6m - Septic Vault: 3.610m(h) x 1.50m(w) x 1.50m (d) | Sitio Arado, Brgy. Poblacion, Taytay, Palawan | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 3800000 | 3798638.06 | 90 | 2024-02-22 |  | 2024-05-22 |  | 2024-05-14 | 100% |  | By contract | Completed | Cjetzu Lumber & Construction Supply | TIN 920-28-159
1142 | Construction of Additional Two (2) -Rooms in Isolation Building for Northern Palawan Provincial Hospital |  | Medical Facilities |  |  | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 1598389.97 | [10 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 5
1143 | Construction of Bahay Tuluyan Building in El Nido Community Hospital | B2 GF SB1 PEO 22-23-11-148 | Medical Facilities | Floor area: 27m x 6m - Septic Vault: 3.610m(h) x 1.50m(w) x 1.50m (d) | El Nido Community Hospital | El Nido | PEO | 2022 | Supplemental Budget No. 1 | 3800000 | 3798638.06 | 90 | 2024-02-05 |  | 2024-05-05 |  | 2024-05-05 | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1144 | Construction of 100 cu.m Water Tank with Deepwell and Chlorination System in Cuyo District Hospital | B2 GF SB3 PEO 22-12-213 | Medical Facilities | 100 cu.m Capacity Tank | Cuyo District Hospital | Cuyo | PEO | 2022 | Supplemental Budget No. 1 | 5500000 | 5489800.07 | 120 | 2023-03-28 | 2 | 2023-07-26 | 2023-10-25 |  | 100% |  | By contract | Completed | M. Luengo Construction | TIN 257-013-134
1145 | Construction of Sewage Treatment Plant in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB1 PEO 22-12-225 | Medical Facilities | Sewage Treatment Plant | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 3200000 | 3140269.25 | 60 | 2023-03-29 | 1 | 2023-07-27 |  |  |  |  | By contract | No movement | M. Luengo Construction | TIN 010-545-401 | Septic vault is not yet completed - with Suspension No. 1
1146 | Concreting of Road & Parking Area in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB1 PEO 22-09-138 | Medical Facilities | Road Network: 389.00 sq.m - Parking Area: 140.00 sq.m - Pathwalk: 150.14 sq.m | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1000000 | 999108.91 | 45 | 2023-01-17 |  | 2023-03-03 | Subject for LD |  | 75.56% |  | By contract | On going | New Space Trading and Construction | TIN 010-545-401
1147 | Concreting of Perimeter Fence in New Vice Gov Ponce De Leon Memorial Hospital | B2 GF SB1 PEO 22-09-149 | Medical Facilities | Construction limits : (a) Semi concrete=59.70 ln.m - Fence=20.00 Span (b) Concrete fence=33.00 ln.m - 11.00 span | Bgy. Danleg, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1000000 | 998585.44 | 60 | 2023-01-17 |  | 2023-03-18 |  |  | 100% |  | By contract | Completed | New Space Trading and Construction | TIN 010-545-401
1148 | Construction of Sewage Treatment Plant in Araceli-Dumaran District Hospital | B2 GF SB1 PEO 22-09-152 | Medical Facilities | STP | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 3200000 | 3187275.95 | 60 | 2023-02-03 |  | 2023-04-04 |  |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1149 | Construction of 100 cu.m water tank with Deepwell and Chlorination System in Araceli-Dumaran District Hospital |  | Medical Facilities |  | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 3500000 | [10 empty] | Re-aligned
1150 | Construction of Mortuary Building in Araceli/Dumaran District Hospital | B2 GF SB1 PEO 22-08-139 | Medical Facilities | 1 Storey - Floor area: 6.0m x 6.0m - Steel truss | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1135000 | 1067829.52 | 50 | 2023-01-06 |  | 2023-02-25 |  |  | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496
1151 | Construction of Barangay Health Station | B2 GF SB1 PEO 22-08-126 | Medical Facilities | Floor Area: 8.95m x 11.075m | Pulot Interior | Sofronio Española | PEO | 2022 | Supplemental Budget No. 1 | 2300000 | 2292181.86 | 120 | 2022-11-21 | 1 | 2023-03-21 | 2023-04-21 |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1152 | Improvement of Molecular Laboratory and Swabbing Facility in Southern Palawan Provincial Hospital (Supply and Installation of Mechanical Equipment) |  | Medical Facilities |  |  | Brooke's Point | PEO | 2022 | Supplemental Budget No. 1 | 550000 | [10 empty] | For Re-alignment
1153 | Construction of Three In One Large Scale Rural Health Unit Phase II |  | Medical Facilities |  |  | Magsaysay | PEO | 2022 | Supplemental Budget No. 1 | 8000000 |  | 180 | [8 empty] | Re-aligned |  |  | Re-aligned to Supplemental Budget No. 4
1154 | Construction of Three In One Large Scale Rural Health Unit Phase II |  | Medical Facilities |  | Cagayancillo | Cagayancillo | PEO | 2022 | Supplemental Budget No. 1 | 8000000 | [10 empty] | Re-aligned |  |  | Same project Re-aligned to Supplemental Budget No. 4
1155 | Completion of Drainage System in Northern Palawan Provincial Hospital |  | Medical Facilities |  |  | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 2000000 | [10 empty] | Re-aligned
1156 | Construction of Cabinbin River RCDG Bridge |  | Transportation Facilities |  | Bgy. Imulnod | Brooke's Point | PEO | 2022 | Supplemental Budget No. 1 | 8000000 | [10 empty] | Re-aligned
1157 | Construction of Perimeter Fence of the Halfway House for Former Rebel & Militia ng Bayan | B2 GF SB1 PEO 22-08-134 | Other Facilities | Net length: 75.5 lm CHB Perimeter fence - 75 lm Tubular Perimeter fence | Bgy. Irawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 1 | 1500000 | 1497880.18 | 90 | 2022-12-09 |  | 2023-03-09 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1158 | Improvement of Evacuation Center/ Covered Court (Flooring only) | B2 GF SB1 PEO 22-08-120 | Other Infrastructure | Court= 30m(L) x 18m(W) | Bgy. Labog | Sofronio Española | PEO | 2022 | Supplemental Budget No. 1 | 872687.19 | 860977.02 | 45 | 2022-11-28 |  | 2023-01-12 |  |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1159 | Repair/Restoration of Infrastructure Damaged by Typhoon Odette |  | Other Infrastructure |  | Various barangay in Northern Palawan (Roxas/El Nido/Araceli/Dumaran/Taytay) |  | PEO | 2022 | Supplemental Budget No. 1 | 8418965 | 8367374.69 | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1160 | Construction of Power Distribution Lines of Maracanao Village Electrification Project | B2 GF SB1 PEO22-24-05-085 | Power and Energy Development Program | CL: 1 PHASE LINE=0.290 KM - U.B LINES=0.290 KM - O.S LINES=0.630 KM | Bgy. Macaranao, Agutaya | Agutaya | PEO | 2022 | Supplemental Budget No. 1 | 1802238.82 | 1797213.67 | 30 | 2024-08-16 |  | 2024-09-15 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266
1161 | Construction of Power Distribution Lines of Batas Village Electrification Project | B2 GF SB1 PEO 22-10-162 | Power and Energy Development Program |  | Bgy. Batas, Taytay, Palawan | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 3869919.08 | 2853437.41 | 55 | 2023-02-22 |  | 2023-04-18 |  |  | 100% |  | By contract | Completed | One Badajos Construction & Trading Corporation | TIN 010-590-630
1162 | Construction of Power Distribution Lines of Debangan Village Electrification Project | B2 GF SB1 PEO 22-08-146 | Power and Energy Development Program |  | Bgy. Debangan, Taytay, Palawan | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 3681098.4 | 3481969.82 | 80 | 2023-02-15 |  | 2023-05-06 | 2023-05-03 |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1163 | Construction of Power Distribution Lines of Galoc Village Electrification Project | B2 GF SB1 PEO 22-08-147 | Power and Energy Development Program | 3 Phase Line=0.884 km - 1 Phase=0.867 km - U.B Lines=1.606 kms O.S lines= 0.617 km | Bgy. Galoc, Culion, Palawan | Culion | PEO | 2022 | Supplemental Budget No. 1 | 4330608.61 | 3642978.53 | 60 | 2023-02-15 |  | 2023-04-16 | 2023-06-29 |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1164 | Construction of Power Distribution Lines of Maglalambay Village Electrification Project | B2 GF SB1 PEO 22-09-155 | Power and Energy Development Program |  | Bgy. Maglalambay, Busuanga, Palawan | Busuanga | PEO | 2022 | Supplemental Budget No. 1 | 5312904.21 | 3939049.36 | 90 | 2023-01-06 |  | 2023-04-06 | 2023-05-20 |  | 100% |  | By contract | Completed | Carina Electrical Construction Supply | TIN 188-374-116
1165 | Construction of Power Distribution Lines of Ramos Village Electrification Project (Re-bid) | B2 GF SB1 PEO 22-08-148 | Power and Energy Development Program |  | Bgy. Ramos, Balabac, Palawan | Balabac | PEO | 2022 | Supplemental Budget No. 1 | 5312904.21 | 5303523.47 | 110 | 2023-02-13 |  | 2023-06-03 |  |  | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496
1166 | Concreting of 1.2 km Farm to Market Road with box culvert/ cross drainage |  | Transportation Facilities |  | Bgy. Malitub | Bataraza | PEO | 2022 | Local Fund (Support to Muslim Communities) | 12000000 | 10499199.69 | 120 | 2022-05-11 |  | 2022-09-08 |  |  |  |  | By contract | For Termination | R. Narrazid Trading and Construction | TIN 330-975-725
1167 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-02-044 | Other Infrastructure |  | Sitio Sumbiling Proper, Bgy. Sumbiling | Bataraza | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3467728.18 | 90 | 2022-05-13 |  | 2022-08-11 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
1168 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-02-043 | Other Infrastructure |  | Sitio Culandanum, Bgy. Canipaan | Rizal | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3467728.18 | 90 | 2022-05-14 |  | 2022-08-12 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
1169 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-02-042 | Other Infrastructure |  | Sitio Banise, Bgy. Iraan | Rizal | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3467728.18 | 90 | 2022-05-14 |  | 2022-08-12 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
1170 | Construction of Multi-Purpose Building with Perimeter Fence & Elevated Water Tank | B2 GF SMC 22-08-140 | Other Infrastructure |  | Sitio Sayab 1, Bgy. Tagnato | Bataraza | PEO | 2022 | Local Fund (Support to Muslim Communities) | 3500000 | 3496738.18 | 90 | 2023-02-15 |  | 2023-05-16 |  |  | 100% |  | By contract | Completed | E.C Timbancaya Enterprises | TIN 142-914-153
1171 | Construction of Molecular Laboratory and Swabbing Facility, Southern Palawan Provincial Hospital, Brooke's Point, Palawan | B2 TF PDRRMO 22-001 | Medical Facilities |  | Southern Palawan Provincial Hospital, Brooke's Point, Palawan | Brooke's Point | PEO | 2022 | TF LDRRMF 2021-PO 2615-A | 6000000 | 5988215.19 | 120 | 2022-03-10 |  | 2022-07-08 |  |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
1172 | Construction of Molecular Laboratory and Swabbing Facility, San Vicente District Hospital, San Vicente, Palawan | B2 TF PDRRMO 22-002 | Medical Facilities |  | San Vicente District Hospital | San Vicente | PEO | 2022 | TF LDRRMF 2021-PO 2615-A | 6000000 | 5997742.5 | 260 | 2022-03-18 | 1 | 2022-12-03 | 2023-01-17 |  | 73% |  | By contract | No movement | MG Tan Construction | TIN 113-310-056 | No manpower on site
1173 | Construction of Bahay Tuluyan, Southern Palawan Provincial Hospital | B2 GF PEO 22-02-049 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | 300-22-02-00670 | 2000000 | 1996599.15 | 60 | 2022-05-18 |  | 2022-07-17 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1174 | Construction of Warehouse Rizal, Palawan | B1 GF DRAC21 22-02-074 | Other Facilities |  | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 5000000 | 4321071.23 | 180 | 2022-07-19 |  | 2023-01-15 | For approval |  | 36.7% |  | By contract | Slow movement | Furosam Incorporated | TIN 009-062-221 | No materials and man power on site
1175 | Concreting of Road Network Rizal, Palawan | B1 GF DRAC21 22-02-075 | Transportation Facilities |  | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 1500000 | 1262526.62 | 75 | 2022-07-19 |  | 2022-10-02 |  |  | 10% |  | By contract | Notice to Terminate | Furosam Incorporated | TIN 009-062-221
1176 | Construction of Perimeter Fence Rizal, Palawan | B1 GF DRAC21 22-02-076 | Other Infrastructure |  | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 2000000 | 1681841.95 | 120 | 2022-07-19 |  | 2022-11-16 |  |  | 100% |  | By contract | Completed | Furosam Incorporated | TIN 009-062-221
1177 | Construction of Rizal Agricultural Center (RAC) Office | B1 GF DRAC21 22-02-077 | Other Facilities |  | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2022 | General Fund | 5000000 | 4037572.85 | 120 | 2022-06-27 |  | 2022-10-25 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1178 | Construction of Sheltered Port,Phase III, Bgy. Pag-asa, Municipality of Kalayaan, Palawan | B2 TF PEO 22-04-085 | Ports and Airports |  | Bgy. Pag-asa, Municipality of Kalayaan, Palawan | Kalayaan | PEO | 2022 | Trust Fund - DOTr | 470687046.57 | 465973152.12 | 540 | 2022-06-30 | 1 | 2023-12-22 | For approval |  | 95.1% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1179 | Improvement/Construction of New Narra Municipal Hospital | B2 TF Due to NGAS-DPWH 20-001 | Medical Facilities |  | Bgry. Antipuluan, Narra Municiapl Hospital | Narra | PEO | 2020 | DPWH | 3418000 | 3284409.19 | 102 | 2020-06-22 | 1 | 2020-10-02 | 2021-05-15 | 2022-07-27 | 100% |  | By contract | Completed | CRMMD Trading and Construction | TIN 183-461-224
1180 | Construction of 3 Barrel Box Culvert, Labog to Naltep road |  | Other Infrastructure |  | Bgy. Labog Naltep, Sofronio Española, Palawan | Sofronio Española | PEO | 2021 | Supplemental Budget No. 9 | 4000000 | 3447989.52 | 90 | 2022-08-15 | 1 | 2022-11-13 | 2022-11-13 |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1181 | Construction of 3 Barrel Box Culvert |  | Other Infrastructure |  | Aporawan,Aborlan | Aborlan | PEO | 2021 |  | 2785001.66 |  | 150 | 2021-03-01 |  | 2021-07-29 | 2022-07-02 |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
1182 | Construction/Rehabilitation of Hospital Building and Facilities | B2 SB3 INFRA 15 300-20-11-17054 | Medical Facilities |  | Brgy. Catadman, Cuyo, Palawan | Cuyo | PEO | 2020 | Supplemental Budget No. 3 | 16000000 | 15972520.31 | 210 | 2021-01-19 | 2 | 2021-08-17 | Subject for LD |  | 95% |  | By contract | On going | Julriz Trading and Construction | TIN 495-740-401
1183 | Construction of Seaweeds Solar Dryer |  | Other Facilities | Farm facilities: Floor area: 6m x 12m=72 sqm (Concrete and Bamboo) - 12mx6.0mx1.2m Solar Dryer | Dumaran Nursery Area | Dumaran | PEO | 2015 |  | 150000 | 149464.73 | 40 | [5 empty] | 100% |  | By contract | Completed | Jas Trading and Construction
1184 | Construction of Salt Processing Center |  | Other Facilities | One Storey Building: 110.37 sqm (14.15M x 7.80m) | Bgry. Danleg, Dumaran, Palawan | Dumaran | PEO | 2020 |  | 2000000 | 1998631.16 | 180 | [5 empty] | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1185 | Construction of Three Storey Building | B2 SB3 PEO 300-21-08-09676 | Other Facilities |  | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 20000000 | 19980869.57 | 360 | 2021-10-14 |  | 2022-10-09 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1186 | Construction of Warehouse for Disaster Relief Goods/Stockpile (Phase II) |  | Other Facilities |  | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2021 | PDRRMO Fund | 10000000 | 9185703.75 | 120 | 2021-11-09 | 1 | 2022-03-09 | For approval |  | 99.2% |  | By contract | On going | JB & Sons Trading & Construction | TIN 166-376-497
1187 | Construction of Road Network Around Cory Park | B2 SB3 PEO 300-21-07-081007 | Other Facilities |  | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 3 | 7488331.75 | 7474996.86 | 90 | 2021-11-26 |  | 2022-02-24 | 2021-06-04 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1188 | Construction of Lualhati Women Center Phase II | B2 SB8 LWC202 300-21-09-12041 | Other Facilities |  | Bgry. Irawan, PPC | Puerto Princesa City | PEO | 2021 | Supplemental Budget No. 8 - LWC | 2500000 | 2497817.8 | 150 | 2021-12-16 |  | 2022-05-15 | 2022-07-29 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1189 | Construction of Highway-Junction Tumarbong Road (Intermittent Section) |  | Transportation Facilities | 2.42 km | Bgry. Tumarbong, Roxas, Palawan | Roxas | PEO | 2018 | B2 ROADS17 300-21-11-15968 | 8000000 | 7947995.79 | 90 | 2022-01-01 |  | 2022-04-01 | 2022-03-31 |  | 100% |  | By contract | Completed | Leon John Great Builders Construction Corp. | TIN 009-924-271
1190 | Construction of Dried Fruit Processing Center and Innovation Center |  | Other Facilities |  | Bgry. Marangas, Bataraza, Palawan | Bataraza | PEO | 2021 | Livelihood Fund | 2000000 | 1993167.01 | 120 | 2021-07-28 |  | 2021-11-25 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1191 | Proposed New Banua Institute for Resiliency & Green Growth Center | 30-00-11-9940(2) B CRGGP (Cluster San Vicente and Roxas) | Other Infrastructure |  | Bgry. Kemdeng, San Vicente, Palawan | San Vicente | PEO | 2021 | CRGGP Fund | 2366077.52 | 2245692.82 | 120 | 2021-05-06 | 1 | 2021-09-03 |  |  | 53% |  | By contract | No movement | BCL Construction | TIN 308-390-430
1192 | Proposed New Banua Institute for Resiliency & Green Growth Center | 30-00-11-9940(2) B CRGGP (Cluster San Vicente and Roxas) | Other Infrastructure |  | Bgry. Tumarbong, Roxas, Palawan | Roxas | PEO | 2021 | CRGGP Fund | 2366077.52 | 2245692.82 | 120 | 2021-01-05 | 1 | 2021-05-05 | 2021-06-05 |  |  |  | By contract | Suspended | BCL Construction | TIN 308-390-430 | Propose for Termination end user cannot provide location
1193 | Construction of Four-Storey Medical Arts Building A Phase I in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | Capital outlay | 20000000 | 19391780.9 | 120 | 2021-12-14 | 1 | 2022-04-13 | Subject for LD |  | 99.27% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1194 | Construction of Three (3) Classroom of School Building. Turda National High School | B2 SEF 300-17-09-14162 | Educational Facilities | 3 Classroom School Building | Bgy. Turda, Coron, Palawan | Coron | PEO | 2017 | Special Education Fund | 2250000 | 2247629.97 | 100 | 2017-11-17 |  | 2018-02-25 |  |  |  |  | By contract | For Termination | Reinastar Trading and Construction | TIN 944-093-894-001
1195 | Concreting of National Highway - Igang Road | B2 GF PEO 22-01-019 | Transportation Facilities | 1000 lm | Bgy. Iwahig | Bataraza | PEO | 2022 | 20% Development Fund | 10500000 | 9225486.71 | 90 | 2022-07-28 | 1 | 2022-10-26 | 2024-02-09 |  | 100% |  | By contract | Completed | N.Sales Construction | TIN 174-694-454
1196 | Construction of Three (3) - Storey Medical & Ward Building with Roof Deck for Helipad - Phase II in Southern Palawan Provincial Hospital |  | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2021 | DOH Fund | 8058600 | 8057475.66 | 150 | 2019-12-13 |  | 2020-05-11 |  |  | 100% |  | By contract | Completed | Johnstar Trading and Construction Supply | TIN 912-843-647
1197 | Construction of 3 Classroom School Building in San Jose Elementary School | B2 SEF17 300-19-05-07132 | Educational Facilities | 3 Classroom School Building | San Jose,Coron, Palawan | Coron | PEO | 2017 | Special Education Fund - 2017 | 2250000 | 2247629.97 | 100 | 2017-11-29 |  | 2018-03-09 |  |  | 100% |  | By contract | Completed | Kudz Trading and Construction | TIN 188-527-256
1198 | Installation of Water and Lights with Plumbing Works |  | Other Facilities |  | RAC, Bono-bono, Bataraza, Palawan | Bataraza | PEO | 2021 | PEEDO Fund | 500000 | 497661.52 | 90 | 2021-12-06 |  | 2022-03-06 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1199 | Improvement of Cuyo District Hospital (Installation of Fire Protection and Alarm System) | B2 PEO 300-21-05-04025 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 |  | 3500000 | 3497903.33 | 85 | 2021-08-05 |  | 2021-10-29 | 2022-01-12 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1200 | Bahay Pag-Asa Renovation/Repair | B2 GF BPYV 22-05-086 | Other Facilities |  | Bgy. Irawan, Puerto Pincesa City, Palawan | Puerto Princesa City | PEO | 2022 | BPYC | 328696.71 | 327590.54 | 75 | 2022-11-15 |  | 2023-01-29 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1201 | Completion of Cuyo District Hospital | B2 GF PEO 22-09-150 | Medical Facilities |  | Cuyo District Hospital | Cuyo | PEO | 2021 | 20% Development Fund | 10000000 | 8671749.53 | 180 | 2022-12-16 | 3 | 2023-06-14 | 2023-11-25 |  | 95% |  | By contract | Stop construction | Bacs Construction and Engineering Consultancy | TIN 920-630-716 | No workers and materials on site/upvc supplier delivery delay
1202 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Dumarao, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 73912.27 | 8367374.69 | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1203 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Salvacion, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 187317.27 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1204 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. 1, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 1474010.39 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1205 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. San Miguel, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 268738.68 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1206 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Iraan, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 1242718.56 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1207 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. New Barbacan, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 242201 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1208 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Mendoza, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 151847.04 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1209 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Malcampo, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 84174.33 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1210 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Sandoval, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 80442.67 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1211 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Minara, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 1002581.79 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1212 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. San Isidro, Roxas | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 52455.25 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1213 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. New Guinlo, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 364527.16 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1214 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Old Guinlo, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 569504.96 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1215 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Libertad, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 386027.98 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1216 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Talog, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 335650.61 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1217 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Pamantolon, Taytay | Taytay | PEO | 2022 | Supplemental Budget No. 1 | 52455.25 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1218 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Magsaysay, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 182652.7 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1219 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Ilian, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 41260.28 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1220 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Sta. Maria, Dumaran | Dumaran | PEO | 2022 | Supplemental Budget No. 1 | 1043119.71 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1221 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Catep, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 133993.39 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1222 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Bacao, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 83440.58 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1223 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. San Juan, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 62458.48 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1224 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Lumacad, Araceli | Araceli | PEO | 2022 | Supplemental Budget No. 1 | 254751 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1225 | Repair/restoration of infrastructure damaged by Typhoon Odette |  | Other Infrastructure |  | Brgy. Bebeladan, El Nido | El Nido | PEO | 2022 | Supplemental Budget No. 1 | 48723.59 |  | 90 | 2023-03-02 |  | 2023-05-31 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1226 | Construction of Covered Court/Evacuation Center | B2 GF SB1 PEO 22-12-214 | Other Infrastructure |  | Brgy. Tinitian, Roxas, Palawan | Roxas | PEO | 2022 | Supplemental Budget No. 1 | 5525303 | 5500426.25 | 130 | 2023-02-22 | 1 | 2023-07-02 | 2023-07-14 | 2023-07-14 | 100% |  | By contract | Completed | I. Marcelo Builders Incorporated | TIN 008-755-657
1227 | Rehabilitation of Legislative Building | B2 GF SB4 INFRA 22-11-184 | Other Facilities |  | Capitol, PPC | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 10000000 | 9993597.78 | 60 | 2023-01-24 |  | 2023-03-25 |  |  |  |  | By contract | Terminated | Panaad Construction | TIN 938-375-592 | Termination for convenience: Change scope of work
1228 | Improvement of Capitol Complex Additional Works in Three Storey Building (Tileworks & Electrical) | B2 GF SB4 INFRA 22-11-216 | Other Facilities |  | Provincial Capitol Complex | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 3000000 | 2992970.09 | 75 | 2023-03-02 |  | 2023-05-16 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1229 | Improvement of Capitol Complex Establishment of Five (5) Offices in Three Storey Building | B2 GF SB4 INFRA 22-12-217 | Other Facilities | Net length: 3-storey building Interior Improvement (22.85m x 17.080 m) | Provincial Capitol Complex | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 6000000 | 5933247.74 | 90 | 2023-04-17 |  | 2023-07-16 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1230 | Improvement of Prov'l Government of Palawan Convention Center (Supply, Installation, Testing and Commissioning of Transformer, Panel Boards, LEDs and Sound) |  | Other Facilities |  | Provincial Capitol Complex | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 22756713.94 | [10 empty] | For Bidding
1231 | Construction of Transformer Platform with Genset Room for Electrical Material (PGP Convention Center) | B2 GF SB4 INFRA 22-12-208 | Other Facilities |  | PGP Convention Center | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 7380407.22 | 7275532.31 | 60 | 2023-02-26 |  | 2023-04-27 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1232 | Supply and Installation of Air Conditioning Unit for VIP Room and Dressing Room of the PGP Convention Center |  | Other Facilities |  | PGP Convention Center | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 4 | 538954.84 | [7 empty] | 100% |  | By contract | Completed
1233 | Restoration and Rehabilitation of Governor's Residence | B2 GF SB5 INFRA22 23-02-053 | Other Facilities | Three storey Building | M. Quezon, Barangay Matiyaga, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 8000000 | 7938086.78 | 180 | 2023-06-13 |  | 2023-12-10 |  |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1234 | Construction of Multi-Purpose Room, PGP Event Center | B2 GF SB5 INFRA 22 23-02-053 | Other Facilities |  | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 1500000 | 1496127.97 | 60 | 2023-07-25 |  | 2023-09-23 |  | 2023-09-22 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1235 | Construction of Day Care Center, PGP Event Center | B2 GF SB5 INFRA22 23-09-118 | Other Facilities | 12M X 0.6M Construction | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 1200000 | 1189982.77 | 60 | 2023-12-11 |  | 2024-02-09 |  | 2024-04-03 | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services
1236 | Improvement of the Office of the Vice Governor & SP Session Hall | B2 GF SB5 INFRA 22-23-02-052 | Other Facilities |  | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 2750000 | 2749051.25 | 100 | 2023-08-11 |  | 2023-11-19 |  | 2024-10-11 | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1237 | Renovation/Repair of Provincial Human Respurce Management Office | B2 GF PEO 23-03-052 | Other Facilities |  | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Supplemental Budget No. 5 | 1780000 | 1776314.78 | 90 | 2023-08-03 |  | 2023-11-01 |  | 2024-04-26 | 100% |  | By contract | Completed | RD Abacial Construction
1238 | Repair / Rehabilitation of Paly VEP |  | Power and Energy Development Program |  | Paly | Taytay | PEO | 2022 | MOOE 2022 | 312859 | [7 empty] | 100% |  |  | Completed
1239 | Repair / Rehabilitation of GSO Building | B2 GF PEO 22-11-197 | Other Facilities |  | Bgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 1042320.84 | 1039700.89 | 75 | 2023-01-24 |  | 2023-04-09 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1240 | Repair / Rehabilitation of Ground Floor Capitol Commercial Complex Building | B2 GF PEO 22-11-196 | Other Facilities |  | Bgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 1500000 | 1498532.62 | 90 | 2023-01-25 |  | 2023-04-25 |  |  | 100% |  | By contract | Completed | F.B Murillo Construction | TIN 327-679-690
1241 | Repair / Rehabilitation of PJMP Annex Building Kitchen Area | B2 GF PEO 22-11-208 | Other Facilities |  | Bancao-bancao | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 440000 | 439796.33 | 45 | 2023-01-24 |  | 2023-03-10 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1242 | Repair / Rehabiitation of Interior Walls of Capitol Complex |  | Other Facilities |  | Capitol | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 4079129.39 | [10 empty] | Re-aligned |  |  | Re-aligned: SB No. 2 - 2023
1243 | Procument of Signages in PDRRMO Building |  | Other Facilities |  | Irawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 606173.19 | [10 empty] | Re-aligned
1244 | Repair and Maintenance of Hospitals (PWD FACILITIES) | PO-PEO 2023-11-1273 | Other Facilities | PWD Facilities | ADDH,CODH ,NMH,RMH,SEDH |  | PEO | 2022 | MOOE 2022 | 144689.13 | 143920 | 14 | 2024-02-12 |  | 2024-02-26 | For approval |  |  |  | By contract | On going | E.C Timbancaya Enterprises
1245 | Repair/Rehabilitation of PEO (Installation of Glass Wall Partition) |  | Other Facilities |  | Capitol | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 104742.3 | [7 empty] | 100% |  | By contract | Completed
1246 | Repair of COVID-19 Laboratory (Staff Quarters Ceiling) | B2 GF PEO 22-11-209 | Medical Facilities |  | Irawan | Puerto Princesa City | PEO | 2022 | MOOE 2022 | 140588.15 | 140520 | 45 | 2023-02-13 |  | 2023-03-30 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1247 | Construction of Dietary/Linen Building in Sofronio Española District Hospital |  | Medical Facilities |  | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2022 | SFVIP 2022 | 4300000 | 4293301.72 | 90 | 2022-08-24 | 1 | 2022-11-22 | 2023-04-22 |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1248 | Construction of Mortuary Building in Sofronio Española District Hospital | B2 GF SFVIP22 24-05-084 | Medical Facilities | Net Length: Single Storey: 6.0m x 6.0m (36 sq.m) | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2022 | SFVIP 2022 | 1195000 | 1183455.92 | 60 | 2024-08-28 |  | 2024-10-27 | For approval |  | 95% |  | By contract | On going | Maximmus Construction
1249 | Construction of Sewage Treatment Plant in Sofronio Española District Hospital | B2 GF SFVIP 22-11-206 | Medical Facilities | Sewage Treatment Plant | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2022 | SFVIP 2022 | 3200000 | 3195278.33 | 60 | 2023-02-22 |  | 2023-04-23 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1250 | Improvement of Cory Park Covered Event Center (Installation of Air-conditioning Units) |  | Other Facilities |  | Capitol Building, PPC | Puerto Princesa City | PEO | 2022 | SFVIP 2022 | 13366500 | [10 empty] | Re-aligned
1251 | Construction of Two (2) Units Multipurpose Building |  | Other Infrastructure |  | Sito Bagto, Bgy. Sandoval, Roxas | Roxas | PEO | 2022 | SFVIP 2022 | 4000000 | [9 empty] | By contract | For Termination
1252 | Construction of Two (2) Storey Dormitory in Aborlan Medicare Hospital | B2 GF SFVIP 22-08-145 | Medical Facilities | CL: 20m(L) x 10m(W) x 9.4m(H) | Aborlan | Aborlan | PEO | 2022 | SFVIP 2022 | 4000000 | 3981380.54 | 180 | 2023-02-15 |  | 2023-08-14 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1253 | Renovation of Provincial Jail Management Division Records Office with Cabinets |  | Other Facilities |  | Bgy. Bancao-, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2020 | PJMD Fund | 350000 | 349129.83 | 60 | 2020-12-30 |  | 2021-02-28 |  |  | 100% |  | By contract | Completed | Maryknoll Builders and Supply | TIN 105-802-318
1254 | Construction of Three (3) - Storey Medical & Ward Building with Roof Deck for Helipad - Phase I |  | Medical Facilities |  | Narra Municipal Hospital | Narra | PEO | 2018 | DOH Fund | 7326000 | [7 empty] | 100% |  | By contract | Completed | Samurai Construction | TIN 919-621-019
1255 | Construction of Barangay Health Station, Maligaya |  | Medical Facilities |  | Bgy. Maligaya, El Nido | El Nido | PEO | 2016 | Trust Fund - DOH | 1990000 | [9 empty] | By contract | Cancelled | E.V Villaos Trading and Construction Supply | TIN 142-914-104
1256 | Construction of 2nd and 3rd Floor of Main Building, Phase 3 |  | Medical Facilities |  | Coron District Hospital | Coron | PEO | 2018 | Trust Fund - DOH | 18135810 | [7 empty] | 100% |  | By contract | Completed | BCT Trading and Construction | TIN 102-698-654
1257 | Construction of Rural Agricultural Center | B2 GF DRAC 22-07-154 | Other Facilities |  | Bgy. Sta. Teresita | Dumaran | PEO | 2022 | RAC Fund | 3500000 | 2968937.64 | 180 | 2023-01-24 |  | 2023-07-23 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1258 | Repair and Maitenance of Palawan Cooperative Center | B2 GF PCDP 22-09-151 | Other Facilities |  | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | PCDP Fund | 1300492.5 | 1078123.59 | 75 | 2022-12-27 |  | 2023-03-12 |  |  | 100% |  | By contract | Completed | Luis YC Builders & Supply | TIN 120-420-502-006
1259 | Repair and Covid-19 Laboratory and Staff Quarters | B2 GF PEO 22-11-209 | Medical Facilities |  | Bgy. Irawan. Puerto Princesa City | Puerto Princesa City | PEO | 2022 | General Fund | 140588.15 | 140520 | 45 | 2023-02-22 |  | 2023-04-08 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1260 | Renovation of PJMD Main Building | B2 GF JMFDP 22-11-170 | Other Facilities |  | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | PJMD Fund | 1156000 | 1154321.3 | 75 | 2023-01-23 |  | 2023-04-08 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1261 | Construction of PGP Solid Waste Management Central Material Recovery Facility | B2 GF SWM 22-11-171 | Other Facilities |  | Bgy. Iraawan, Puerto Princesa City | Puerto Princesa City | PEO | 2022 | General Fund | 400000 | 398972.71 | 45 | 2023-02-16 |  | 2023-04-02 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1262 | Repair/Rehabilitation of Main Building & Facilities (Iso Bldg. Medical Annex Bldg. and Extension of Iso Bldg.) in SPPH | B2 GF SPPH 22-10-165/166/167/168 | Medical Facilities |  | Southern Palawan Provincial Hospital | Brooke's Point | PEO | 2022 | Capital outlay | 2247629.97 | 1990364.45 | 180 | 2023-01-23 | 2 | 2023-07-22 | For approval |  | 94.43% |  | By contract | On going | F.B Murillo Construction | TIN 772-152-432
1263 | Repair and Maintenance of Aborlan Medicare Hospital, Aborlan, Palawan |  | Medical Facilities | Road Network: 112m(l) x 4m(w) x 0.15m (t) - Main Building: 60m x 60m - E.R Complex: 2.5m x 19m - Isolation Building: 8m x 20m - Dietary Building: 10m x 20m | Aborlan Medicare Hospital | Aborlan | PEO | 2022 | Aborlan Medical Hospital Fund | 5000000 | 4775580.89 | 120 | 2023-01-17 |  | 2023-05-17 | 2023-07-16 | 2023-09-01 | 100% |  | By contract | Completed | VCH Construction and Trading | TIN 924-818-554
1264 | Construction of Proposed 11m x 12.5m Bunk House | B2 SB2 POP19 300-20-03-02965 | Other Facilities |  | Bgy. Apurawan, Aborlan, Palawan | Aborlan | PEO | 2020 | Supplemental Budget No. 2 POP | 2999999.24 | 2631826.62 | 150 | 2020-10-02 |  | 2021-03-01 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
1265 | Construction of Proposed 11m x 12.5m Bunk House | B2 SB2 POP19 300-20-03-02966 | Other Facilities |  | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2020 | POP Fund | 2999999.24 | 2631826.62 | 150 | 2020-10-02 |  | 2021-03-01 |  |  | 100% |  | By contract | Completed | Beta-J Construction | 159-232-934
1266 | Concreting of Road Network in Cuyo District Hospital | B2 PEO 300-21-08-09452 | Medical Facilities |  | Cuyo, Palawan | Cuyo | PEO | 2021 | 20% Development Fund | 2000000 | 1999504.21 | 90 | 2021-10-06 | 2 | 2022-01-04 | 2022-02-03 |  | 100% |  | By contract | Completed | Julriz Trading and Construction | TIN 495-740-401
1267 | Improvement of Intesive Juvenile Intervention Support Center (IJSC) | B2 GF BPTC 22-05-089 | Other Facilities | Floor Area: Construction of Multi-purpose hall=175.64 sqm. - Floor Area: Construction of Perimater Fence=24.3 - Length=Renovation of Main Building=144.87 sq.m | Barangay Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2022 | Other fund | 5500000 | 5169583.32 | 180 | 2023-03-29 |  | 2023-09-25 | 2023-12-09 | 2024-02-07 | 100% |  | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662
1268 | Construction of Tubbataha Reef Ranger Station (Main Module) (Research Module) (Transportation Module) Phase II | B2 TF PEO 23-01-005 | Other Facilities | Construction of structural concrete, installation of structural metal, fabricated metal and decking including metal painting works for Ranger Station Building | Tubbataha Reef, Cagayancillo, Palawan | Cagayancillo | PEO | 2022 | DENR - TIEZA (Trust Fund 2022) | 58375080 | 58234005.51 | 365 | 2023-04-18 |  | 2024-04-17 | 2025-01-10 |  | 93.56% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1269 | Construction of Covered Court with Stage at Lualhati Women Center | B1 GF LWC21 22-09-133 | Other Facilities | Net length: 9.0m x 15.0m Covered court - 4.20m x 6.30m stage | Bgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Trust Fund | 1497000 | 1489722.6 | 120 | 2023-01-25 |  | 2023-05-25 |  |  |  |  | By contract | Terminated | HNT Builders & Enterprises | TIN 909-572-814 | Termination for convenience: RA 11361
1270 | Rehabilitation Of Magbabadil Bridge (Approach, PCCP & Slope Protection) | B2 GF PEO 23-02-030 | Other Infrastructure | 7 M X 6 M | Bgy. Mabini | Aborlan | PEO | 2023 | 20% Development Fund | 1500000 | 1477901 | 90 | 2023-05-05 |  | 2023-08-03 |  |  | 100% |  | By contract | Completed | AMLC Builders Construction and Supply | TIN 428-298-201
1271 | Repair Of Road From National Highway - Jose Rizal | B2 GF PEO 23-02-025 | Transportation Facilities | 2 Pccp Blocks: L=4.5 M; W=2.0 M, T=0.20, With 1-L-36'' Diameter X 7 Rcpc With Headwall B.S | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 220000 | 219180.99 | 45 | 2023-05-26 |  | 2023-07-10 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1272 | Repair & Rehabilitation Of Bridge Slope Protection In Saraza Bridge | B2 GF PEO 23-04-079 | Other Infrastructure | 10m(L),6.10m(W),0.20m(T) | Bgy. Saraza | Brooke's Point | PEO | 2023 | 20% Development Fund | 5400000 | 5391830.43 | 205 | 2023-08-30 |  | 2024-03-22 | Subject for LD |  | 99.65% |  | By contract | On going | MVP Construction and Trdaing Inc. | TIN 616-777-887
1273 | Construction Of Riverbank Protection/Flood Control At Tamlang Bridge |  | Other Infrastructure | Sp:236.88 Cu.M - 15m (L) X 0.30m (T)-30 Gabions | Bgy. Saraza | Brooke's Point | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 5 | 5000000 |  | 120 | [8 empty] | Re-aligned |  |  | Re-aligned to 2023 Supplemental Budget No. 5
1274 | Construction Of Cabinbin River Flat Slab Bridge |  | Transportation Facilities | 6m X 4m (Bothsides) - Bridge (4.40mx30ln.M) Rc Slope (68.24) Riprap (237.44 Cu.M) Pccp 30 Ln.M | Bgy. Imulnod | Brooke's Point | PEO | 2023 | 20% Development Fund | 18000000 |  | 182 | [8 empty] | Re-aligned |  |  | Re-aligned to 2023 Supplemental Budget No. 3
1275 | Rehabilitation Of Pulot Shore Bridge Slope Protection | B2 GF PEO 23-04-078 | Other Infrastructure | 156.58 Cu.M; 28 Gabions (1mx1mx2m) | S. Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 3000000 | 2986642.2 | 115 | 2023-09-09 |  | 2024-01-02 |  | 2023-12-29 | 100% |  | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887
1276 | Rehabilitation Of Panitian Bridge Slope Protection | B2 GF PEO 23-04-059 | Other Infrastructure | 273.42 Cu.M; 38 Gabions (1mx1mx2m) | S. Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 5000000 | 4046838.42 | 115 | 2023-06-19 | 1 | 2023-10-12 | 2023-12-11 |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1277 | Restoration/Repair of Tagumpay RCDG Bridge 2 (Approach) | B2 GF PEO 23-02-022 | Transportation Facilities | 1 Side - 6m X 6.1 M | Bgy. Tagumpay, Dumaran, Palawan | Dumaran | PEO | 2023 | 20% Development Fund | 300000 | 298884.7 | 60 | 2023-06-05 |  | 2023-08-04 |  | 2023-08-04 | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
1278 | Rehabilitation Of Bridge Slope Protection At Abutment "A-B" In Latungay Bridge | B2 GF PEO 23-02-044 | Other Infrastructure | Bridge Slope Protection: Volume (cu.m): 124.7352 - Approach Slope Protection: 4.7m both sides of upstream | Bgy. Ilian, Dumaran, Palawan | Dumaran | PEO | 2023 | 20% Development Fund | 2500000 | 2490641.44 | 113 | 2023-05-29 |  | 2023-09-19 | 2023-12-07 | 2024-03-11 | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1279 | Rehabilitation Of Bridge Slope Protection At Abutment "A-B" In Sta. Maria Bridge II | B2 GF PEO 23-02-046 | Other Infrastructure | Bridge Slope Protection: Volume (cu.m): 124.74 - 12.8m Both Sides Of Upstream | Bgy. Sta. Maria, Dumaran, Palawan | Dumaran | PEO | 2023 | 20% Development Fund | 3000000 | 2520934.12 | 113 | 2023-05-30 |  | 2023-09-20 | 2023-12-07 | 2024-03-11 | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1280 | Rehabilitation Of Caramay Hanging Bridge | B2 GF PEO 23-04-058 | Transportation Facilities | 101.10 Ln.M | Bgy. Caramay, Roxas, Palawan | Roxas | PEO | 2023 | 20% Development Fund | 2000000 | 1989843.27 | 60 | 2023-07-19 |  | 2023-09-17 | For approval |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1281 | Installation Of 5 Lines - 36" Diameter Rcpc With Headwall In Tigman Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 5 Units Of 5 Lines - 36" Diameter Rcpc With Headwall In Tigman Road | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 600000 |  | 45 | 2023-06-15 |  |  | For approval |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1282 | Construction Of Spillway | B2 GF PEO 23-05-093 | Other Infrastructure | Spillway: 15mlx9.70mwx3.05mh | Isaub | Aborlan | PEO | 2023 | 20% Development Fund | 3000000 | 2994333.15 | 115 | 2023-07-10 |  | 2023-11-02 |  | 2023-10-18 | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1283 | Installation Of 1 Line - 36" Diameter Rcpc With Headwall In Linamen - Batang Batang Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 1-L 36'' Diameter Rcpc X 8.00 Length With Headawall Bothsides In Different Stations | Municipality Of Narra | Narra | PEO | 2023 | 20% Development Fund | 120000 | 119804.55 | 30 | 2023-06-15 |  |  | Subject for LD |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1284 | Installation Of 2 Lines - 36" Diameter Rcpc With Headwall In Aramaywan Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 2 (Two) 1-L 36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Municipality Of Narra | Narra | PEO | 2023 | 20% Development Fund | 240000 | 239004.35 | 45 | 2023-06-15 |  |  | Subject for LD |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1285 | Rehabilitation Of 2-Barrel Box Culvert, Aramaywan Road | B2 GF PEO 23-04-085 | Other Infrastructure | 2.8m(H) X 5.60m(W) X 8m(L) X 0.30m Thk With Slope Protection And Approach | Narra, Palawan | Narra | PEO | 2023 | 20% Development Fund | 3550000 | 2981117.03 | 113 | 2023-06-30 | 1 | 2023-10-21 | 2024-01-24 |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1286 | Installation Of 5 Lines - 36" Diameter Rcpc With Headwall In Agis Agis Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 5 Units 1l-36'' Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 600000 |  | 45 | 2023-06-15 |  |  | 2023-09-28 |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1287 | Installation Of 6 Lines - 36" Diameter Rcpc With Headwall In Abokayan Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 6 Units 1l-36''diameter Rcpc With Headwall Bothsides In Different Station | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 720000 |  | 75 | 2023-06-15 | 1 |  | 2023-09-28 |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1288 | Installation Of 4 Lines - 36" Diameter Rcpc With Headwall In Iraray Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 4 Units 1-L36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 480000 |  | 45 | 2023-06-15 |  |  | 2023-09-28 |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1289 | Installation Of 10 Lines - 36" Diameter Rcpc With Headwall In Panitian Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 10 Units 1l-36''diameter Rcpc With Headwall Bothsides In Different Station | Quezon, Palawan | Quezon | PEO | 2023 | 20% Development Fund | 1200000 | 1199269.65 | 75 | 2023-06-15 |  | 2023-08-29 |  |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1290 | Installation Of 2 Lines - 36" Diameter Rcpc With Headwall In Inogbong Feeder Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 2 (Two) 1-L 36 Diamteter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Municipality Of Bataraza | Bataraza | PEO | 2023 | 20% Development Fund | 240000 | 239004.37 | 45 | 2023-06-15 | 1 |  | For approval |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1291 | Installation Of 4 Lines - 36" Diameter Rcpc With Headwall In Iwahig - Igang Igang - Sarong Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 4 Units 1l-36''diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Station | Bataraza, Palawan | Bataraza | PEO | 2023 | 20% Development Fund | 480000 | 478714.67 | 45 | 2023-06-15 |  |  | For approval |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1292 | Construction Of RCDG Bridge | B2 GF PEO 23-04-068 | Transportation Facilities | Approach: 4m X 6m (Bothsides) - Bridge: 15ln.m - RC Slope (cu.m) 97.35 | Sandoval | Bataraza | PEO | 2023 | 20% Development Fund | 8652821.98 | 7311536 | 180 | 2023-07-06 |  | 2024-01-02 |  |  | 100% |  | By contract | Completed | KIR Konstructicon Builders and Supply | TIN 010-605-480
1293 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) | B2 GF PEO 23-03-057 | Other Infrastructure | 1-3m (H) - 3.56m (W) - 6.6(L) - 0.30m Thick With Approach And Slope Prtotection | Bunog, Rizal, Palawan | Rizal | PEO | 2023 | 20% Development Fund | 2000000 | 1682824.11 | 115 | 2023-06-30 |  | 2023-10-23 |  | 2023-09-10 | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1294 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) | B2 GF PEO 23-04-086 | Other Infrastructure | 1-3m (H) - 3.56m (W) - 6.6(L) - 0.30m Thick With Approach And Slope Prtotection | TDC, Port Barton | San Vicente | PEO | 2023 | 20% Development Fund | 2000000 | 1765317.29 | 115 | 2023-06-30 |  | 2023-10-23 |  |  | 100% |  | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887
1295 | Construction Of Spillway | B2 GF PEO 23-05-091 | Other Infrastructure | 10m(L) X 9.60m (W) X 3.05m (H) | Tinitian, Roxas, Palawan | Roxas | PEO | 2023 | 20% Development Fund | 2000000 | 1991735.49 | 115 | 2023-07-17 |  | 2023-11-09 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1296 | Installation Of 6 Lines - 36" Diameter Rcpc With Headwall In Barotuan - Bucana Road | Installation of 45 Lines - 36" Diameter RCPC with Headwall at Various Provincial Roads (CONTRACT PACKAGE Php 5,389,416.65) - B2 GF PEO 23-02-017/021/023/027/029/038/045 | Other Infrastructure | 6 Units 1l-36''diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Station | El Nido, Palawan | El Nido | PEO | 2023 | 20% Development Fund | 720000 |  | 60 | 2023-06-15 |  |  | For approval |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1297 | Replacement Of Timber Bridge To Two (2) Barrel RCBC - (2 Units), National Highway - Old Guinlo Road | B2 GF PEO 23-03-069 | Other Infrastructure | 2 Units In Different Location/Station 3m(H)X6.9m(W)X8.5(L)X0.30m Thick | So. Pagkakaisa & So.Campo, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 8000000 | 7990227.82 | 144 | 2023-06-29 |  | 2023-11-20 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1298 | Construction Of Two (2) Barrel RCBC And Installation Of 4-Lines 36" Dia RCPC | B2 GF PEO 23-03-059 | Other Infrastructure | 1 Unit -3m (H) X 6.9m (W)X8.5m(L)X0.30m(Thick) With Slope Protection And Approach | Brgy. Guadalupe, Coron, Palawan | Coron | PEO | 2023 | 20% Development Fund | 5800000 | 5795648.4 | 144 | 2023-06-29 |  | 2023-11-20 |  | 2024-01-12 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1299 | Concreting Of Road Network In Capitol Ville Subdivision |  | Other Facilities |  | Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 11100000 | [10 empty] | Re-aligned |  |  | Re-aligned to 2023 Supplemental Budget No. 3
1300 | Concreting Of Slab & Road Network In Warehouse For Disaster Relief Goods/Stockpile | B2 GF PEO 23-02-028 | Other Facilities | (A) Road Network: 78m x 5m - (B) Concrete Slab: 75m x 20m x 0.1m - (C) 36'' RCPC: 4 Lines - 7 ln.m - (D) Grouted Riprap: 91 ln.m | Bgy. Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 4600000 | 3175553.72 | 120 | 2023-05-12 | 1 | 2023-09-09 | For approval |  | 100% |  | By contract | Completed | West Blue Builders
1301 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Magara | Roxas | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  |  |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1302 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Liminangcong | Taytay | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  |  | 2024-04-28 | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1303 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 (B2 TF PEO 23-08-109) | Other Infrastructure | 30 m (l) x 18m (w) | Poblacion | Araceli | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  | For approval |  | 80% |  | By contract | On going | St.Timothy Construction Corporation | TIN 008-813-669-000
1304 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Brgy. 3 | Coron | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 | 1 |  | 2023-12-30 | 2024-01-13 | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1305 | Construction Of Evacuation Center/ Covered Court Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Bgy. Cocoro | Magsaysay | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  | Subject for LD |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1306 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Panlaitan | Busuanga | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  | 2024-08-01 |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1307 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Tagumpay | Roxas | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  |  | 2024-05-02 | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1308 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Jolo | Roxas | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  |  | 2024-05-01 | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1309 | Construction Of Evacuation Center/ Covered Court, Phase I | Construction of Evacuation Center/Covered Court Phase I at Various Barangay in Northern Palawan - B2 PEO 23-02 015/016/031/032/033/034/039/040/041 | Other Infrastructure | 30 m (l) x 18m (w) | Culasian | Dumaran | PEO | 2023 | 20% Development Fund | 7300000 | 7295426.79 | 150 | 2023-05-04 |  |  |  |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1310 | Construction Of Multi-Purpose Building (Livelihood Center) | B2 GF PEO 23-04-083 | Other Infrastructure | 320 Sqm | Roxas | Roxas | PEO | 2023 | 20% Development Fund | 8000000 | 6951109.51 | 210 | 2023-07-10 | 1 | 2024-02-05 | 2024-04-04 |  | 100% |  | By contract | Completed | Hardshell Design and Construction | TIN 211-391-300-001
1311 | Construction Of Multi-Purpose Building (Livelihood Center) | B2 GF PEO 23-04-055 | Other Infrastructure | 320 Sqm | Taytay | Taytay | PEO | 2023 | 20% Development Fund | 8000000 | 7114928.25 | 210 | 2023-09-26 | 1 | 2024-04-23 | For approval |  | 85% |  | By contract | On going | Jaica Construction Services
1312 | Construction Of Multi-Purpose Building (Livelihood Center) | B2 GF PEO 23-04-054 | Other Infrastructure | 320 Sqm | El Nido | El Nido | PEO | 2023 | 20% Development Fund | 8000000 | 6799453.44 | 210 | 2023-07-24 |  | 2024-02-19 | Subject for LD |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1313 | Construction Of Four (4) Model Unit In Capitol Ville |  | Other Facilities |  | Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 7200000 | [10 empty] | Re-aligned |  |  | Re-aligned to 2023 Supplemental Budget No. 3
1314 | Construction Of Multi-Purpose Building, Phase II | B2 GF PEO 23-02-024 | Other Infrastructure | 6.5m X 11 M Two-Storey Building Second Floor | Tenga-Tenga | Cuyo | PEO | 2023 | 20% Development Fund | 2000000 | 1880491.65 | 90 | 2023-05-12 | 2 | 2023-08-10 | For approval |  | 100% |  | By contract | Completed | Bat's Construction Services | TIN 491-731-278
1315 | Construction Of Two (2) Storey Dormitory Phase II, Aborlan Medicare Hospital | B2 GF PEO 23-34-03-076 | Medical Facilities | 20m(l) X 10m(w) X 9.4m(h) | Municipality Of Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 6000000 | 5982386.64 | 210 | 2024-07-16 |  | 2025-02-11 |  |  | 86.2% |  | By contract | On going | ZYK Construction
1316 | Construction Of PWD Ramp For Three (3) Storey Medical Arts Building, Aborlan Medicare Hospital | B2 GF PEO 23-04-086 | Medical Facilities | 24m x 6m | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 4950000 | 4896891.5 | 150 | 2023-07-06 | 1 | 2023-12-03 | Subject for LD |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1317 | Supply And Installation Of Fire Protection System For Three (3) Storey Medical Arts Building, Aborlan Medicare Hospital | B2 GF PEO 23-05-092 | Medical Facilities | n/a | Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 3450000 | 3441716.25 | 75 | 2023-07-17 |  | 2023-09-30 | Subject for LD | 2024-07-31 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1318 | Construction Of Three (3) Storey Medical Arts Building Phase III | B2 GF PEO 23-04-084 | Medical Facilities | 43m x 15m | Municipality Of Aborlan, Palawan | Aborlan | PEO | 2023 | 20% Development Fund | 10000000 | 9904303.69 | 150 | 2023-07-06 | 1 | 2023-12-03 | Subject for LD |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1319 | Improvement Of Landscaping For Medical Arts Building | B2 GF PEO-28-02-051 | Medical Facilities | Modern Tropical Garden | Municipality Of Narra | Narra | PEO | 2023 | 20% Development Fund | 350000 | 346663.63 | 45 | 2023-05-17 |  | 2023-07-01 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1320 | Supply And Installation Of 1-125 Kva Generator Set With Automatic Transfer Switch (Ats), Sofronio Española District Hospital | Hospital Facilities | Medical Facilities | Supply and Installation | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 1375000 | [7 empty] | 100% |  | By contract | Completed
1321 | Supply And Installation Of 200 Mm² Copper Wire Power Cable, Sofronio Española District Hospital |  | Medical Facilities | Supply and Installation | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 654000 | [10 empty] | Failure of bidding |  |  | Failure of Bidding: For re-construction of Financial Documents of Procurement - Insufficient Fund
1322 | Supply And Installation Of Four (4) Units Of Air Conditioned, Sofronio Española District Hospital |  | Medical Facilities | Aircon: 4 Units | Pulot Center, Sofronio Española | Sofronio Española | PEO | 2023 | 20% Development Fund | 254080.49 | [7 empty] | 100% |  |  | Completed
1323 | Construction Of Two (2) Storey Dormitory Phase II, Sofronio Española District Hospital | Hospital Facilities | Medical Facilities | 12.0 X 10.50M Building concrete laundry and patio | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 2500000 |  | 210 | [8 empty] | Re-aligned |  |  | Re-aligned to 2023 Supplemental Budget No. 3
1324 | Construction Of Retaining Wall, Sofronio Española District Hospital | B2 GF PEO 23-02-047 | Other Infrastructure | 69.58 m (l) | Municipality Of Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund | 5000000 | 4988002.69 | 90 | 2023-05-10 | 1 | 2023-08-08 | 2023-11-21 |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1325 | Supply And Installation Of Automatic Voltage Regulator For The Generator Set, Bataraza District Hospital |  | Medical Facilities | Supply and Installation | Bataraza Distirct Hospital | Bataraza | PEO | 2023 | 20% Development Fund | 52500 | [10 empty] | Failure of bidding |  |  | Failure of Bidding: For re-construction of Financial Documents of Procurement - Insufficient Fund
1326 | Supply And Installation Of Twenty Five (25) Units Of Air Conditioned, Balabac District Hospital | Hospital Facilities | Medical Facilities | Supply and Installation | Catagupan | Balabac | PEO | 2023 | 20% Development Fund | 1576511.53 | [7 empty] | 100% |  |  | Completed
1327 | Construction Of Perimeter Fence Phase II, Balabac District Hospital | B2 GF PEO 23-02-050 | Medical Facilities | 273 l.m X 91 Span | Catagupan | Balabac | PEO | 2023 | 20% Development Fund | 2800000 | 2741746.82 | 120 | 2023-06-13 |  | 2023-10-11 | 2024-01-09 |  | 100% |  | By contract | Completed | Breis Construction | TIN 010-590-630
1328 | Construction Of Drainage Structure In Northern Palawan Technical Vocational School, Phase II | B2 GF PEO 23-04-056 | Other Infrastructure | 67.50 Ln.m | Arado, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 900000 | 899323.55 | 75 | 2023-05-29 | 1 | 2023-08-12 | 2023-08-13 |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1329 | Construction Of Three In One Large Scale Rural Health Unit, Phase II | B2 GF PEO 23-04-077 | Medical Facilities | 981 Sq.M | Aporawan | Aborlan | PEO | 2023 | 20% Development Fund | 9500000 | 9138883.9 | 150 | 2023-08-29 | 2 | 2024-01-26 | 2024-03-26 |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1330 | Construction Of Perimeter Fence Phase I, Panalingaan Rural Health Unit | B2 GF PEO 23-02-043 | Medical Facilities | 120 Ln. M - 40.00 Span | Panalingaan, Rizal, Palawan | Rizal | PEO | 2023 | 20% Development Fund | 1500000 | 1499006.75 | 120 | 2023-08-30 |  | 2023-12-28 |  | 2024-02-05 | 100% |  | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887
1331 | Concreting Of Road With Parking Area, Panalingaan Rural Health Unit | B2 GF PEO 23-02-035 | Medical Facilities | L=109 M; W=5.0m; T=0.15m | Panalingaan, Rizal, Palawan | Rizal | PEO | 2023 | 20% Development Fund | 2000000 | 1995469.45 | 90 | 2023-07-17 |  | 2023-10-15 |  |  | 100% |  | By contract | Completed | Mazon Engineering and Construction | TIN 273-819-199
1332 | Construction Of Three In One Large Scale Rural Health Unit, Phase II | B2 GF PEO 23-04-076 | Medical Facilities | 981 Sqm | Municipality Of Agutaya | Agutaya | PEO | 2023 | 20% Development Fund | 9500000 | 9494438.33 | 180 | 2023-07-10 | 2 | 2024-09-02 | For approval |  | 92% |  | By contract | On going | Maryjonica Construction | TIN 350-458-389
1333 | Construction Of Three In One Large Scale Rural Health Unit, Phase II | B2 GF PEO 23-04-081 | Medical Facilities | 981 Sqm | Linapacan | Linapacan | PEO | 2023 | 20% Development Fund | 9500000 | 9450000 | 180 | 2023-08-04 |  | 2024-01-31 | For approval |  | 85% |  | By contract | On going | JBS Abia Construction | TIN 428-617-369
1334 | Concreting Of Access Road With RCPC & Parking Area In Busuanga Rural Health Unit | B2 GF PEO 23-02-026 | Medical Facilities | L=135 M; W=5.0m; T=0.15m | Busuanga | Busuanga | PEO | 2023 | 20% Development Fund | 3000000 | 2998119.82 | 90 | 2023-06-13 |  | 2023-09-11 |  |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1335 | Construction Of Barangay Health Station |  | Medical Facilities | 8.95m X 11.075m | Green Island | Roxas | PEO | 2023 | 20% Development Fund | 2500000 |  | 120 | [8 empty] | Re-aligned |  |  | Re-aligned: to Imulnod Bridge - Re-aligned: Supplemental Budget No. 3 - 2023
1336 | Repair And Upgrading Of Calandagan VEP Power Distribution | B2 GF PEO 23-02-048 | Power and Energy Development Program | 3 Phase Line = 960 Mts - Ub Lines=960 Mts | Calandagan | Araceli | PEO | 2023 | 20% Development Fund | 2500000 | 2498766.63 | 60 | 2023-06-05 | 1 | 2023-08-04 | 2023-09-03 | 2023-08-14 | 100% |  | By contract | Completed | One Badajos Construction & Trading Corporation | TIN 010-590-630
1337 | Construction Of Power Distribution Lines Of Biton VEP, Phase II | B2 GFPEO 23-02-037 | Power and Energy Development Program | 1 Phase Line = 360 Mts - Ub Lines=360 Mts - Os Lines=1,120 Mts | Bgy. Biton, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 1800000 | 1798596.36 | 60 | 2023-09-15 |  | 2023-11-14 |  | 2024-02-02 | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496
1338 | Completion Of Powerhouse In Biton Vep | B2 GF PEO 23-04-060 | Power and Energy Development Program | 30mx20m Co0mpletion/Repair | Biton | Taytay | PEO | 2023 | 20% Development Fund | 1200000 | 1160350.11 | 75 | 2023-08-09 |  | 2023-10-23 |  |  | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1339 | Construction Of Power Distribution Lines, Phase II In Casian Vep | B2 GF PEO 23-02-036 | Power and Energy Development Program | 3 Phase Line=1275 Mts - 1 Phase Line=726 Mts - Up Lines=2001 Mts - Os Lines=337 Mts | Bgy. Casian, Taytay, Palawan | Taytay | PEO | 2023 | 20% Development Fund | 3300000 | 3052145.85 | 85 | 2024-02-28 |  | 2024-05-23 | 2024-06-22 |  | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services | TIN 931-421-496
1340 | Repair Of Bisucay Island Village Electrification Project | B2 GF PEO 23-02-049 | Power and Energy Development Program | 3 Phase Line =2760 Mts - 1 Phase Line=2741 Mts - Ub Lines=5501 Mts - Os Lines=1962 Mts | Bisucay Island, Cuyo, Palawan | Cuyo | PEO | 2023 | 20% Development Fund | 1300000 | 1261785.47 | 30 | 2023-05-29 |  | 2023-06-28 |  | 2023-06-28 | 100% |  | By contract | Completed | Synchros Power Solutions | TIN 134-545-266-000
1341 | Construction Of Perimeter Fence Of The Halfway House For Former Rebel & Militia Ng Bayan, Phase II | B2 GF PEO 23-02-042 | Other Facilities | Painting Masonry (557.33 Sqm) - Painting Metal (136.33 Sqm) - Cemwnt Plaster (165 Sqm) | Bgy. Irawan | Puerto Princesa City | PEO | 2023 | 20% Development Fund | 300000 | 299495.35 | 30 | 2023-05-29 |  | 2023-06-28 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1342 | Construction Of 2-Classroom School Building, Diapila National Highschool | B2 GF SEF 23-05-096 | Educational Facilities | 2 CL - 22.5 M (L) X 7 M (W) | El Nido Del Norte District, El Nido, Palawan | El Nido | PEO | 2023 | Special Education Fund - 2022 | 5666000 | 5600000 | 155 | 2023-08-04 |  | 2024-01-06 | For Approval |  | 100% |  | By contract | Completed | JBS Abia Construction | TIN 428-617-369
1343 | Construction Of 2-Classroom School Building,Buliluyan National Highschool | B2 GF SEF 23-05-095 | Educational Facilities | 2 CL - 22.5 M (L) X 7 M (W) | Bataraza District, Bataraza, Palawan | Bataraza | PEO | 2023 | Special Education Fund - 2022 | 5666000 | 5647876.35 | 155 | 2023-08-09 |  | 2024-01-11 | For Approval |  | 46.01% |  | By contract | No movement | F.B Murillo Construction | TIN 772-152-432 | No presence of manpower on site. No materials were stored on site
1344 | Construction Of 2-Classroom School Building,Maringian Elementary School | B2 GF SEF 23-05-095 | Educational Facilities | 2 CL - 22.5 M (L) X 7 M (W) | Cuyo District, Cuyo | Cuyo | PEO | 2023 | Special Education Fund - 2022 | 5666000 | 5665458.08 | 155 | 2023-09-26 |  | 2024-02-28 | Subject for LD |  | 100% |  | By contract | Completed | M. Luengo Construction | TIN 257-013-134
1345 | Construction Of 2-Classroom School Building,Decalachao Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Decalachao | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1346 | Construction Of 2-Classroom School Building,Sta. Monica Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Guadalupe | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1347 | Construction Of 2-Classroom School Building,Bulalacao Integrated School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Bulalacao | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5485260.73 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1348 | Construction Of 2-Classroom School Building,Bintuan Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Bintuan | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1349 | Construction Of 2-Classroom School Building,Borac Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Borac | Coron | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 | 2024-01-08 | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1350 | Construction Of 2-Classroom School Building,Concepcion Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Concepcion | Busuanga | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5446572.78 | 140 | 2023-07-10 | 1 | 2023-11-27 | For approval |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1351 | Construction Of 2-Classroom School Building,Bogtong Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Bogtong | Busuanga | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5457405.08 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-02-10 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1352 | Construction Of 2-Classroom School Building,New Culaylayan Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. New Culaylayan | Linapacan | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5485260.73 | 140 | 2023-07-10 |  | 2023-11-27 | For approval |  | 50% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730
1353 | Construction Of 2-Classroom School Building, Sandoval Elementary School | B2 GF SB2 SEF22 -23-04-058/061/071-075 - Construction of Nine (9) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Taytay | Taytay | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5466687.58 | 140 | 2023-07-10 | 1 | 2023-11-27 | 2024-01-17 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1354 | Construction Of 2-Classroom School Building, Jose Rizal Apoc-Apoc National Highschool | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Apoc-Apoc | Aborlan | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5410798.05 | 140 | 2023-07-24 | 1 | 2023-12-11 | 2024-05-10 | 2024-03-17 | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1355 | Construction Of 2-Classroom School Building, Panacan Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Narra | Narra | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5418026 | 140 | 2023-07-24 | 1 | 2023-12-11 | 2024-01-22 |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1356 | Construction Of 2-Classroom School Building, Cacarigan Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Narra, Palawan | Narra | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5418026 | 140 | 2023-07-24 |  | 2023-12-11 |  | 2023-12-29 | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1357 | Construction Of 2-Classroom School Building, Busay Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Taburi, Rizal, Palawan | Rizal | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5509839.05 | 140 | 2023-07-24 | 1 | 2023-12-11 |  | 2023-12-29 | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1358 | Construction Of 2-Classroom School Building, Rizal Central School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Punta Baja, Rizal, Palawan | Rizal | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5509839.05 | 140 | 2023-07-24 |  | 2023-12-11 |  | 2023-11-27 | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1359 | Construction Of 2-Classroom School Building, Bulalacao Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bataraza | Bataraza | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5509839.05 | 140 | 2023-07-24 |  | 2023-12-11 | For Approval |  | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1360 | Construction Of 2-Classroom School Building, Luntab Elementary School | B2 GF SB2 SEF22 -23-04-057/062/065/070/080 - Construction of Seven (7) Units of 2-Classroom School Building, Various Municipalities in Northern Palawan | Educational Facilities | 2 Classroom School Building: 22.5 M (L) X 7 M (W) | Bgy. Pulot Shore | Sofronio Española | PEO | 2023 | Special Education Fund - 2022 | 5512000 | 5418026 | 140 | 2023-07-24 |  | 2023-12-11 |  | 2024-03-17 | 100% |  | By contract | Completed | One Hundred Percent and Development Corp. | TIN 168-154-730
1361 | Restoration / Repair Of Northern Palawan Provincial Hospital And Facilities | B2 TF PEO 23-07-101 | Medical Facilities | Main Building - 1,090.20 Sqm; Ceiling: Dietary-132 Sqm - Ceiling Oxygen -222 Ln M - Motorpool 6 Ln.M | Sitio Arado, Bgy. Poblacion, Taytay, Palawan | Taytay | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 2602202.98 | 2596793.65 | 90 | 2023-11-06 |  | 2024-02-04 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
1362 | Restoration/Renovation Of Roxas Medicare Hospital | B2 TF PEO 23-07-106 | Medical Facilities | Main Building 3600 M2 - New Isolation Building 160m2 - Old Isolation 160m2 - Dietary Building 200m2 - Motorpool Building 243.5m2 - Dq - 464 M2 | Roxas Medicare Hospital | Roxas | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 4527738.54 | 3984249.25 | 120 | 2023-09-26 |  | 2024-01-24 | 2024-02-23 |  | 100% |  | By contract | Completed | Apollo Construction & Enterprises | TIN 181-140-662
1363 | Restoration/Repair Of San Vicente District Hospital And Facilities | B2 TF PEO 23-07-107 | Medical Facilities | Main Building - 606.53 Sqm, Dietary/Linen Building - 36.0 Sqm, Isolation Building - 54.34 Sqm | San Vicente, Palawan | San Vicente | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 1872951.35 | 1856547.55 | 90 | 2023-11-05 |  | 2024-02-03 |  |  | 100% |  | By contract | Completed | Kayano Trading and Construction | TIN 497-273-240
1364 | Restoration/Repair Of Cuyo District Hospital | B2 TF PEO 23-07-104 | Medical Facilities | Single Storey 60m X 60m Hospital Building | Municipality Of Cuyo, Palawan | Cuyo | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 561123.17 | 546483.36 | 30 | 2023-11-06 |  | 2023-12-06 |  |  | 100% |  | By contract | Completed | M. Luengo Construction | TIN 257-013-134
1365 | Restoration/Repair Of Araceli-Dumaran District Hospital | B2 TF PEO 23-07-102 | Medical Facilities | 60m X 60m | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 1104052.3 | 1102998.48 | 78 | 2023-09-26 |  | 2023-12-13 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1366 | Restoration/Repair Of El Nido Community Hospital And Facilities | B2 GF PEO 23-04-103 | Medical Facilities | 60m X 60m | El Nido | El Nido | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 1710672.2 | 1587322 | 120 | 2023-09-25 |  | 2024-01-23 |  |  | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1367 | Repair/Rehabilitation Of Coron District Hospital & Facilities | B2 TF PEO 23-07-105 | Medical Facilities | 360 Square Meters 151.20 Square Meter Chb 168 Square Meter Roofing | Coron | Coron | PEO | 2023 | DOH Fund (Typhoon Odette) - 2021 | 2621259.36 | 2600216.03 | 90 | 2023-09-26 |  | 2023-12-25 |  |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1368 | Concreting Of Road From Highway Junction - Brgy. Mendoza | B2 GF SFVIP 23-04-090 | Transportation Facilities | 687 Lm | Roxas, Palawan | Roxas | PEO | 2023 | SFVIP | 12000000 | 11819999.2 | 120 | 2023-07-19 |  | 2023-11-16 |  |  | 100% |  | By contract | Completed | Seven Digit Construction and Supplies | TIN 183-661-696
1369 | Concreting Of Balala-Malaking Patag Road (Sta. 5+913.80-Sta. 6+071.80) | B2 GF SFVIP 23-04-089 | Transportation Facilities | Road Network=158 Ln.M - W=6.10m - T=0.20m - Shoulder 1m B.S | Culion, Palawan | Culion | PEO | 2023 | SFVIP | 4000000 | 3956976.52 | 90 | 2023-08-29 |  | 2023-11-27 |  |  |  |  | By contract | Not yet started | Maximmus Construction | TIN 925-322-134
1370 | Concreting Of New Busuanga-Quezon-Cheey | B2 GF SFVIP 23-09-117 | Transportation Facilities | 620 Ln.M - W=6.10, Thick=0.20m, Shoulder=1m B.S | Municipality Of Busuanga | Busuanga | PEO | 2023 | SFVIP | 12000000 | 11993006.64 | 120 | 2024-01-15 |  | 2024-05-14 | 2024-06-03 |  | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1371 | Concreting Of Labog-Naltep Road, Phase II | B2 GF SFVIP 23-09-119 | Transportation Facilities | Road Network: 405 Lm - W=6.10m - Thk=0.20m - Shoulder=1m - B.S: Slope Protection Lm=8m - Ht=2.2m | Municipality Of Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | SFVIP | 8000000 | 7976821.91 | 155 | 2023-12-12 |  | 2024-05-15 |  | 2024-05-14 | 100% |  | By contract | Completed | MVP Construction and Trdaing Inc. | TIN 616-777-887
1372 | Concreting/Upgrading Of Aramaywan-Cacarigan FMR (PGP Counterpart) |  | Transportation Facilities |  | Narra, Palawan | Narra | PEO | 2023 | Supplemental Budget No. 2 | 12910000 | [10 empty] | For preparation (POW and DED)
1373 | Improvement Of Capitol Building (Rehab Of Interior Walls) |  | Other Facilities | 4,902.22 Square Meter: Removal Of Interioir Marble Stone Bricks Wall - Plastering And Painting On Interior Wall - Repaint Of Genset Room Exterioir Wall - Repaint Of Pavillion Column | Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 2 | 4079130 |  | 210 | [8 empty] | Re-aligned
1374 | Renovation Of Palawan Provincial Crime Laboratory Office In Brgy. Tiniguiban, Puerto Princesa City | B2 GF SB2 PEO 23-07-098 | Other Facilities | 22.10m X 12.00m Renovation/Improvement | Brgy. Tiniguiban, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 2 | 2016000 | 2010648.96 | 90 | 2023-12-11 |  | 2024-03-10 |  | 2024-03-10 | 100% |  | By contract | Completed | One Badajos Construction & Trading Corporation | TIN 010-590-630
1375 | Concreting of Road Network Phase II, Sofronio Española,Palawan | B2 GF SB3 PDP 23-11-141 | Medical Facilities | Road Network: 4700075 lm (w=4,t=0.20m) - Drainage: 24" diameter RCPC x 8m - Line canal = 20.14m | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 800000 | 789452.4 | 45 | 2024-01-29 |  | 2024-03-14 |  |  | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1376 | Construction of STP Vault and Drainage Structure Phase I, Capitol Ville Subdivision | B2 GF SB3 PDP 23-11-140 | Other Facilities | Construction Limits: Stp Vault=9.6(L) X 4.6(W) - Catch Basins:43 Pcs - 610mm Dia. Rcpc: 829 Lm - 910mm Rcpc: 417 L.M - 1220mm Dia Rcpc: 165 L.M | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 11000000 | 10996710.08 | 205 | 2024-04-01 |  | 2024-10-23 | For approval |  | 70% |  | By contract | On going | FSD Construction
1377 | Concreting of Road Network and Parking Area Phase I, Provincial Health Office | B2 GF SB3 PDP23 24-06-093 | Other Facilities | Acess Road: 737.64 Sqm - Parking 204.25 Sq.M - Sidewalk 93.18sq.M | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 3000000 | 2984327.39 | 59 | 2024-10-02 |  | 2024-11-30 | For approval |  | 60% |  | By contract | On going | Luis YC Builders & Supply | TIN 120-420-502-00006
1378 | Improvement of Provincial Health Office Landscaping | B2 GF SB3 PDP 23-10-124 | Other Facilities | Modern tropical garden | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 500000 | 469656.85 | 45 | 2024-01-23 |  | 2024-03-08 | For approval |  |  |  | By contract | Suspended | RD Abacial Construction | TIN 327-679-690
1379 | Repair and Rehabilitation of Coron District Hospital | B2 GFSB3 PDP 23-11-146 | Medical Facilities | Area: 24m(w) x 60m(l) Three Storey | Coron, Palawan | Coron | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 2400000 | 2398120.74 | 120 | 2024-02-19 |  | 2024-06-18 | For Approval |  | 100% |  | By contract | Completed | E.M Abin Trading & Construction | CTC 936-562-132-000
1380 | Repair and Rehabilitation of El Nido Community Hospital | B2 GF SB3 PDP 23-10-125 | Medical Facilities | Main Building: 60m x 60m | El Nido Community Hospital | El Nido | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 4700000 | 4686055.78 | 90 | 2023-12-29 |  | 2024-03-28 | For Approval | 2024-03-28 | 100% |  | By contract | Completed | Maximmus Construction | TIN 497-273-240
1381 | Improvement of PGP Event Center (Supply and Installation of Acoustic Treatment Noise Management) |  | Other Facilities |  | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 5300000 | [10 empty] | For Re-alignment
1382 | Construction of Elevated Water Tank/Water Treatment Facilities, Bataraza District Hospital | B2 GF SB3 PDP23 24-06-092 | Medical Facilities | 100 cu.m Capacity Tank | Bataraza Distirct Hospital | Bataraza | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 6000000 | 5996737.48 | 120 | 2024-11-29 |  | 2025-03-29 |  |  | 0% |  | By contract | Not yet started | Lea and Sons Trading and Construction
1383 | Construction of Sewage Treatment Plant Equipment and Facilities, PJMD | B2 GF SB3 PDP 23-11-145 | Other Facilities | Sewage Treatment Plant | Bancao-Bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 4000000 | 3999999.98 | 90 | 2024-04-26 |  | 2024-07-25 | For approval |  | 100% |  | By contract | Completed | Gth Builders and Developers
1384 | Constructrion of Septic Vault | B2 GF SB3 PDP 23-10-123 | Other Facilities | Septic Vault= 6m x 2m x 2.5m | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 400000 | 399999.59 | 60 | 2024-01-23 |  | 2024-03-23 |  | 2024-03-23 | 100% |  | By contract | Completed | JD Golez Construction Services | TIN 340-084-699
1385 | Improvement of Provincial Health Office (Supply and Installation of Fire Protection and Alarm System) |  | Other Facilities | Supply,Installation Testing And Commissioning Of Fire Protection Alarm System | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | 20% Development Fund 2023 - Realigned to SB No. 3 | 3200000 | [10 empty] | Failure of bidding |  |  | Failure of Bidding: For re-construction of Financial Documents of Procurement
1386 | Improvement of Governor's Residence | B2 GF CADP 23-05-097 | Other Facilities | Coffee shop - 203 sq.m - Landscape - 1,596.8 sq.m - Perimeter Fence - 191.86 ln.m | Brgy. Matiyaga, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PGO Fund | 10000000 | 9931452.76 | 240 | 2023-08-10 |  | 2024-04-06 | For approval |  | 98% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730
1387 | Restoration/Repair Of Lamayo Processing Center | B2 GF SB4 INFRA 23-11-137 | Other Facilities | 18m x 23.25m building | Brgy. New Guinlo, Municipality Of Taytay Palawan | Taytay | PEO | 2023 | Supplemental Budget No. 4 | 500000 | 498037.45 | 30 | 2024-01-29 |  | 2024-02-28 |  | 2024-02-25 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1388 | Renovation Of Provincial Budget Office | B2 GF SB4 INFRA 23-11-135 | Other Facilities | Construction of floor extension, circular stair, and 2 - additional exit doors | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 950000 | 948450.21 | 75 | 2024-01-29 |  | 2024-04-13 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1389 | Improvement Of Capitol Building (Rehab Of Interior Walls) | B2 GF SB24 INFRA 23-11-139 | Other Facilities | Removal of interior marble stone bricks wall - plastering and painting of inetrior wall - repaint of genset room exterior wall - repaint of pavillon column | Capitol Compound, Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 4079130 | 4075412.74 | 210 | 2024-02-19 |  | 2024-09-16 | For approval |  | 73% |  | By contract | On going | RC Gadiano Construction | TIN 342-792-217
1390 | Improvement Of Governor's Residence (Landscaping Enhancement) | B2 GF SB4 INFRA 23 24 08 099 | Other Facilities | Landscape | M. Quezon, Bgy. Matiyaga, PPC | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 1100000 | 1092800.3 | 90 | 2024-10-16 |  | 2025-01-14 |  |  | 80% |  | By contract | On going | RD Abacial Construction | TIN 327-679-690
1391 | Improvement Of Capitol Complex - Improvement Of Landscaping | B2 GF SB4 INFRA 23-11-138 | Other Facilities | Modern tropical garden | Pgp Event Center, Bgy. Tanglaw, PPC | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 900000 | 898936.71 | 45 | 2024-01-29 |  | 2024-03-14 |  | 2024-04-14 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1392 | Expansion Of Provincial Accounting Office | B2 GF SB4 23-11-136 | Other Facilities | 15mx16m - repair and repaint of mezzanine floor, walls and ceiling | Capitol Compound, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 3000000 | 2950314.99 | 60 | 2024-03-05 |  | 2024-05-04 |  | 2024-07-10 | 100% |  | By contract | Completed | Maryjonica Construction | TIN 350-458-389
1393 | Enhancement Of Three Storey Building | B2 GF SB4 INFRA 24-03-073 | Other Facilities | n/a | Capitol Compound, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 | 950000 | 948786.68 | 90 | 2024-06-04 |  | 2024-09-02 |  |  | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1394 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-131 | Medical Facilities | Area: 981 sq.m | So. Tabudniayo, Brgy. Bancalaan, Balabac | Balabac | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7988698.33 | 180 | 2024-01-29 |  | 2024-07-27 | For approval |  | 67% |  | By contract | On going | Hadiyah Construction | TIN 324-356-720
1395 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-132 | Medical Facilities | Area: 981 sq.m | Brgy. Mangsee, Balabac | Balabac | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7992569.97 | 180 | 2024-02-12 |  | 2024-08-10 | 2025-02-07 |  | 70% |  | By contract | On going | Breis Construction | TIN 010-590-630
1396 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-130 | Medical Facilities | Area: 801 sqm | Cagayancillo | Cagayancillo | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7995037.24 | 180 | 2024-03-18 |  | 2024-09-14 | For approval |  | 95% |  | By contract | On going | J.JH Construction Supplies Trading
1397 | Construction Of Three In One Large Scale Rural Health Unit Phase II | B2 GF SB4 INFRA 23-11-133 | Medical Facilities | Area: 981 sq.m | Magsaysay | Magsaysay | PEO | 2023 | Supplemental Budget No. 4 | 8000000 | 7988124.79 | 180 | 2024-02-14 |  | 2024-08-12 | 2024-10-11 |  | 100% |  | By contract | Completed | Bat's Construction Services | TIN 491-731-278
1398 | Construction Of Two (2) Storey Building Medical Worker's Dormitory | B2 GF SB4 INFRA 23-11-134 | Medical Facilities | Dimension: 21mx11.10m = 233.10 sqm | Sitio Arado, Taytay | Taytay | PEO | 2023 | Supplemental Budget No. 4 | 12600000 | 12595349.02 | 115 | 2024-03-18 |  | 2024-07-11 | 2024-10-09 |  | 100% |  | By contract | Completed | J.JH Construction Supplies Trading
1399 | Construction of Evacuation Center/ Covered Court with Bleachers | B2 TF PEO 23-08-115 | Other Infrastructure | Covered Court: 540 sq.m - Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Talaga | Cagayancillo | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 17062500 | 17007253.74 | 280 | 2023-12-11 |  | 2024-09-16 | For approval |  | 95% |  | By contract | On going | J.JH Construction Supplies Trading
1400 | Construction of Evacuation Center/ Covered Court with Bleachers | B2 TF PEO 23-08-116 | Other Infrastructure | Covered Court: 540 sq.m - Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Abaroan | Roxas | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 17062500 | 17034102.69 | 280 | 2024-01-19 | 1 | 2024-10-25 | 2024-12-24 |  | 95.3% |  | By contract | On going | HNT Builders & Enterprises | TIN 909-572-814
1401 | Construction of Evacuation Center/ Covered Court with Bleachers | B2 TF PEO 23-08-114 | Other Infrastructure | Covered Court: 540 sq.m - Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. New Agutaya | San Vicente | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 17062500 | 17055628.75 | 280 | 2023-11-24 |  | 2024-08-30 | 2024-12-15 |  | 70% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730
1402 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-112 | Other Infrastructure | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Culasian | Dumaran | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9759392.95 | 130 | 2023-11-06 |  | 2024-03-15 | 2024-04-29 |  | 100% |  | By contract | Completed | Triplestone Construction and Development Corporation | TIN 009-149-175
1403 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-111 | Other Infrastructure | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Tinitian | Roxas | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9758126.68 | 130 | 2023-11-24 | 1 | 2024-04-02 | For approval |  | 90.2% |  | By contract | On going | HNT Builders & Enterprises | TIN 909-572-814
1404 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-109 | Other Infrastructure | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Poblacion | Araceli | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9759592.98 | 130 | 2024-03-20 |  | 2024-07-28 | For approval |  | 94.25% |  | By contract | On going | Cjetzu Lumber & Construction Supply
1405 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-110 | Other Infrastructure | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Sto. Tomas | Dumaran | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9674458.78 | 130 | 2023-11-25 |  | 2024-04-03 | For approval |  | 98% |  | By contract | On going | F.F Galang Construction | TIN 188-519-198
1406 | Construction of Evacuation Center/ Covered Phase II | B2 TF PEO 23-08-113 | Other Infrastructure | Stage: 65.61 sqm - Bleachers: 120 sq.m - Messhall 84 sq.m - Kitchen: 84.00 sq.m | Brgy. Sandoval | Taytay | PEO | 2023 | Typhoon Odette Financial Assistance (Office of the President) - 100M | 9762500 | 9752298.49 | 130 | 2023-10-23 |  | 2024-03-01 | For approval | 2024-03-01 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1407 | Construction Of Slope Protection In Latungay-Sta. Teresita Road | B2 TF PDRRMO 24-04-079 | Other Infrastructure | Slope Protection: Volume (Cu/M)=72.12 - Length 25.90 M | Dumaran, Palawan | Dumaran | PEO | 2023 | PDRRMO Fund | 1500000 | 1496944.74 | 93 | 2024-09-26 |  | 2024-12-28 |  |  | 100% |  | By contract | Completed | RL Abia Construction | TIN 274-260-467
1408 | Construction Of Slope Protection, Malague Elementary School | B2 GF DPF 23-09-120 | Other Infrastructure | Slope Protection: Volume (Cu/M)=7422.15 - Length (1 Side) 46.20 M | Brgy. Sta. Teresita, Dumaran, Palawan | Dumaran | PEO | 2023 | PDRRMO Fund | 7500000 | 7449998.76 | 128 | 2024-01-20 |  | 2024-05-27 |  | 2024-05-10 | 100% |  | By contract | Completed | Seven Digit Construction and Supplies | TIN 008-664-275
1409 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection, Panitian - Abokayan Road | B2 TF PDRRMO 24-05-089 | Other Infrastructure | Rcbc: 1-2m (H) X 3.56m (W) X 8.30(L) X 0.28m Thnk With Approach And Slope Protection | Sofronio Española, Palawan | Sofronio Española | PEO | 2023 | PDRRMO Fund | 3000000 | 2976044.19 | 115 | 2024-08-01 |  | 2024-11-24 |  | 2024-10-18 | 100% |  | By contract | Completed | Maximmus Construction
1410 | Installation Of 6 Lines - 36" Diameter RCPC With Headwall, Latongay - Bagumbayan Road | B2 GF DPF 23-11-153 | Other Infrastructure | Cl: 6 Units 1l-36'' Diameter Rcpc X 8.00 Length With Headwall Bothsides In Differrent Stations | Dumaran, Palawan | Dumaran | PEO | 2023 | PDRRMO Fund | 900000 | 890247.42 | 60 | 2024-01-19 |  | 2024-03-19 | For approval | 2024-03-01 | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1411 | Installation Of 11 Lines - 36" Diameter RCPC With Headwall, Dumarao FMR (Phase 2) | B2 GF DPF 23-11-155 | Other Infrastructure | Cl: 11 Units 1l-36'' Diameter Rcpc X 8.00 Length With Headwall Bothsides In Differrent Stations | Roxas, Palawan | Roxas | PEO | 2023 | PDRRMO Fund | 1600000 | 1599325.76 | 90 | 2024-01-29 |  | 2024-04-28 |  | 2024-03-25 | 100% |  | By contract | Completed | Azarraga Construction | TIN 418-292-176
1412 | Installation Of 7 Lines - 36" Diameter RCPC With Headwall, Abongan -Alacalian-Kawakayan-Binga Road | B2 GF DPF 23-11-152 | Other Infrastructure | Cl: 7 Units 1l-36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Taytay, Palawan | Taytay | PEO | 2023 | PDRRMO Fund | 1050000 | 1049456.91 | 90 | 2024-01-29 |  | 2024-04-28 |  | 2024-03-21 | 100% |  | By contract | Completed | Azarraga Construction | TIN 418-292-176
1413 | Installation Of 5 Lines - 36" Diameter RCPC With Headwall, Comalibongbong-Calawag Road | B2 GF DPF 23-11-157 | Other Infrastructure | Cl: 5 Units 1l-36" Diameter Rcpc X 8.00 Length With Headwall Bothsides In Different Stations | Taytay, Palawan | Taytay | PEO | 2023 | PDRRMO Fund | 750000 | 690155.32 | 60 | 2024-01-19 | 1 | 2024-03-19 | For approval | 2024-03-03 | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1414 | Construction Of 3-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection , Dumarao - Ilian Ilian Road | B2 GF DPF 23-11-160 | Other Infrastructure | Rcbc: 1-3m (H) X 3.56m(W) X 8.30(L) X 0.30m Thick With Approach And Slope Protection And Slope Protection | Roxas, Palawan | Roxas | PEO | 2023 | PDRRMO Fund | 6700000 | 6683961.47 | 202 | 2024-02-05 |  | 2024-08-25 |  | 2024-06-28 | 100% |  | By contract | Completed | Hadiyah Construction | TIN 324-356-720
1415 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) With Pccp Approach And Slope Protection Dumarao-Subingao Road | B2 GF DPF 23-11-151 | Other Infrastructure | Rcbc 1-2.5m(H) X 3.56m(W) X 8.30(L) X 0.30m Thk With Approach Annd Slope | Roxas, Palawan | Roxas | PEO | 2023 | PDRRMO Fund | 4500000 | 4493833.32 | 144 | 2024-02-12 |  | 2024-07-05 |  | 2024-06-28 | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1416 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) With Pccp Approach And Slope Protection, Sibaltan - Siwangwang Road | B2 GF DPF 23-11-156 | Other Infrastructure | Rcbc- 1-3m(H) X 3.56m (W) X 8.30(L) X 0.28m Thk. With Approach And Slope Protection | El Nido, Palawan | El Nido | PEO | 2023 | PDRRMO Fund | 4500000 | 4489450.11 | 115 | 2024-02-12 |  | 2024-06-06 |  | 2024-05-13 | 100% |  | By contract | Completed | HNT Builders & Enterprises | TIN 909-572-814
1417 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) With Pccp Approach And Slope Protection | B2 GF DPF 23-11-154 | Other Infrastructure | 1-3m(H) X 3.56m(W) X 8.30(L) X 0.30m Thk With Approach And Slope Protection | Highway Jct. Tagumpay - Maliko Road | Roxas | PEO | 2023 | PDRRMO Fund | 4500000 | 4464014.51 | 144 | 2024-01-29 |  | 2024-06-21 |  | 2024-06-18 | 100% |  | By contract | Completed | Hadiyah Construction | TIN 324-356-720
1418 | Construction Of PDRRMO Warehouse Phase III | B2 TF PDRRMO 24-01-002 | Other Facilities | Pavement Road - 177.53m (L) X 6.10m(W) - Grouted Rip Rap - 4.24m (W) X 88.50m (L) - Concrete Culvert 24'' Diameter - 7 Mtrs | Barangay Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PDRRMO Fund | 7122529.21 | 7083101.28 | 150 | 2024-05-27 |  | 2024-10-24 | For approval |  | 50% |  | By contract | On going | Luis YC Builders & Supply
1419 | Construction Of Seacraft Motorpool |  | Other Facilities | 18m X 10m Motorpool | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PDRRMO Fund | 3500000 |  | 150 | [8 empty] | For Bidding
1420 | Construction of IT Room (Command Center) | B2 TF PDRRMO 24-03-025 | Other Facilities | Buildings: Net Length: 17.60m X 9.20m - Addition Of Emergency Operation Center Office(It Room) | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PDRRMO Fund | 3500000 | 3312409.51 | 95 | 2024-08-20 |  | 2024-11-23 | For approval |  | 60% |  | By contract | On going | RC Gadiano Construction | TIN 342-792-217
1421 | Construction Of Seacraft Operation Base With Slipway | B2 TF PDRRMO 24-03-024 | Other Facilities | Building: 18mx6m - Spillway: 6.50mx7.50m | Buliluyan, Batarza, Palawan | Bataraza | PEO | 2023 | PDRRMO Fund | 2500000 | 2494994.82 | 141 | 2024-05-31 |  | 2024-10-19 | 2024-12-31 |  | 61.04% |  | By contract | On going | Global Teleconstruction Specialist Inc.
1422 | Construction Of Seacraft Operation Base With Slipway | B2 TF PDRRMO 24-03-026 | Other Facilities | Building: 18mx6m - Spillway: 6.50mx7.50m | Dipnay, El Nido | El Nido | PEO | 2023 | PDRRMO Fund | 2500000 | 2496259.43 | 201 | 2024-06-28 |  | 2025-01-15 |  |  | 53% |  | By contract | On going | Global Teleconstruction Specialist Inc. | TIN 218-601-693-00000
1423 | Renovation of Provincial Administrator's Office | B2 GF SB5 PGO 23-10-121 | Other Facilities | Renovation | Capitol Building, Brgy. Tanglaw, PPC | Puerto Princesa City | PEO | 2023 | Admin Fund | 536378.96 | 536169.43 | 60 | 2023-12-13 |  | 2024-02-11 |  |  | 100% |  | By contract | Completed | Gth Builders and Developers
1424 | Construction of Calauit Safari Park Improvement Works, Brgy. Buluang, Busuanga, Palawan | B2 GF SB4 CSPMP 23-11-150 | Other Infrastructure | Net length as plan | Brgy. Buluang, Busuanga, Palawan | Busuanga | PEO | 2023 | Supplmental Budget No. 4 (CSPMP) | 6050000 | 6022332.85 | 200 | 2024-02-21 |  | 2024-09-08 | For approval |  | 92% |  | By contract | On going | Rabb Construction & Supply | TIN 325-261-868
1425 | Renovation/Repair of Provincial Cooperative Development Office | B2 GF SB4 PCDO 23-11-158 | Other Facilities | Arc Length: 10.50m x 6.20m (w) with mezanine floor | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 4 (PCDO) | 500000 | 497678.01 | 90 | 2024-01-02 |  | 2024-04-01 |  | 2024-04-29 | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1426 | Renovation of Coron Bay Development Project Phase I, Luwalhati, Coron, Palawan | B2 GF CBDP 23-11-149 | Other Infrastructure | 2-Storey Building | Luwalhati, Coron, Palawan | Coron | PEO | 2023 | Supplemental Budget No. 2 | 6604484 | 6602769.52 | 200 | 2024-01-29 |  | 2024-08-16 | For approval |  | 81.23% |  | By contract | On going | Triplestone Construction and Development Corporation | TIN 009-149-175
1427 | Repair and Maintenance Building and Other Structures, Bgy. Bancao-Bancao, PPC | B2 GF PJMD 23-11-162 | Other Facilities | Net length: 16m x 16m Building Renovation New Tileworks, Partition wall, ceiling, renovation of comfort rooms & canopy roofing | Bgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | PJMD Fund | 500000 | 497207.74 | 60 | 2024-01-19 |  | 2024-03-19 |  | 2024-04-29 | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1428 | Repair of Commission on Audit (Repainting of Wall and Ceiling) | B2 GF SB2 PGO 23-11-158 | Other Facilities | COA Office and stockrooms: 11m x 8.5m, 15m x 3.1m, 10m x 6.5m - Repainting of wall and ceiling | Capitol Compound, Brgy. Tanglaw & PEO compound, Bancao-bancao, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | PGO Fund - Supplemental Budget No. 2 | 200000 | 148123.4 | 45 | 2024-02-12 |  | 2024-03-28 |  | 2024-05-13 | 100% |  | By contract | Completed | JD Golez Construction Services | TIN 340-084-699
1429 | Repair and Rehabilitation of Southern Palawan Provincial Hospital, Bgy. Tub-tub, Brooke's Point, Palawan | B2 GF SPPH 23-10-129 | Medical Facilities | Area: 60m (w) x 60m (l) | Bgy. Tub-tub, Brooke's Point, Palawan | Brooke's Point | PEO | 2023 | SPPH | 3172472.55 | 3170715.3 | 120 | 2024-01-17 |  | 2024-05-16 | Subject for LD |  | 100% |  | By contract | Completed | FSD Construction
1430 | Completoin of New Provincial Economic Enterprise Development Office, Capitol Complex, Puerto Princesa City | B2 GF WDP22 23-10-122 | Other Facilities | 8.80m x 20.85m - 1 storey building | Capitol Complex, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | PEEDO Fund | 700000 | 644754 | 45 | 2023-12-29 |  | 2024-02-12 |  |  | 100% |  | By contract | Completed | Rabb Construction & Supply | TIN 325-261-868
1431 | Replacement of BPYC Main Building and Multi-purpose Hall Roofing, Bgy. Irawan, PPC | B2 GF SB1 BPYC 23-07-108 | Other Facilities | Roof Area: 378.20 sqm - 1 Storey Building | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City | PEO | 2023 | BPYC | 700000 | 689813.5 | 60 | 2023-10-04 |  | 2023-12-03 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-001
1432 | Upgrading of Timber Bridge to RCDG Bridge, Tanatanaen - Maragok Road | B2 GF PEO 24-02-009 | Transportation Facilities | Bridge: Net Length Approach: 9.2mx4m (Both Sides) - Bridge: 9.52m X 30.60 Ln.M - Rc Slope (Cu.M) 159.40 - Pccp: 8 Ln.M | Dumaran | Dumaran | PEO | 2024 | 20% Development Fund 2024 | 30000000 | 28946467 | 214 | 2024-06-29 |  | 2025-01-29 |  |  | 30% |  | By contract | On going | Global Teleconstruction Specialist Inc.
1433 | Concreting of Highway Junction-Tumarbong, Phase 2 | B2 GF PEO 24-02-006 | Transportation Facilities | Road Length: 1,260m(L) X 0.20m(T) X 6.10m(W) - 1 Line Rcpc 36" Dia - Existing Half Lane Pccp Left Side - Sta. 0+000 - Sta.0+060 | Roxas | Roxas | PEO | 2024 | 20% Development Fund 2024 | 25000000 | 24875000 | 178 | 2024-05-22 |  | 2024-11-16 | For approval |  | 98.6% |  | By contract | On going | Seven Digit Construction and Supplies | TIN 183-661-696
1434 | Concreting of Access Road going to San Fernando Port | B2 GF PEO 24-02-007 | Transportation Facilities | Net Length (Cu.M) Pccp Road A -367m X 6.70m X 0.25m Thk. Shoulder Width 1.00m B.S Road B-31.16m X 8.00m X 0.25m Thk - V-Shaped Lined Canal - 140m On R.S | El Nido | El Nido | PEO | 2024 | 20% Development Fund 2024 | 12641215 | 12634124.84 | 120 | 2024-05-22 |  | 2024-09-19 |  |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation
1435 | Concreting of Access Road going to Pier - Marikit Road | B2 GF PEO 24-02-019 (Re-bid) | Transportation Facilities | Road Length:900m(L) X 0.25m(T) X 6.10m(W) - 2 Rcbc H=1.41m X 6m - Seawall L=80m | Aborlan | Aborlan | PEO | 2024 | 20% Development Fund 2024 | 18000000 | 15770700 | 121 | 2024-08-05 |  | 2024-12-04 |  |  | 65% |  | By contract | On going | Palbic Construction and Supply
1436 | Construction of Evacuation Center/ Covered Court, Phase I | B2 GF PEO 24-02-004 | Other Infrastructure | Court: 30m(L) X 18m(W) | Nicanor Zabala | Roxas | PEO | 2024 | 20% Development Fund 2024 | 7300000 | 7267765.51 | 150 | 2024-05-02 |  | 2024-09-29 |  |  | 100% |  | By contract | Completed | Maximmus Construction
1437 | Construction of Evacuation Center/ Covered Court, Phase I | B2 GF PEO 24-02-011 | Other Infrastructure | Court: 30m(L) X 18m(W) | Lajala | Coron | PEO | 2024 | 20% Development Fund 2024 | 7300000 | 7292134.71 | 150 | 2024-05-15 |  | 2024-10-12 | For approval |  | 71.11% |  | By contract | On going | Maximmus Construction
1438 | Construction of Evacuation Center/ Covered Court, Phase I | B2 GF PEO 24-02-010 (Re-bid) | Other Infrastructure | Court: 30m(L) X 18m(W) | Brgy. Tumbod | Taytay | PEO | 2024 | 20% Development Fund 2024 | 7300000 | 7285118.06 | 150 | 2024-08-15 |  | 2025-01-12 |  |  | 65% |  | By contract | On going | RD Abacial Construction
1439 | Construction of Drainage System,Aborlan Medicare Hospital | B2 GF PEO 24-02-016 (Re-bid) | Other Infrastructure | Length Of Rc Canal: 118m - Earthen Canal: 400m - Length Of 1 Line: 12'' - 8m | Municipality of Aborlan, Palawan | Aborlan | PEO | 2024 | 20% Development Fund 2024 | 2000000 | 1650000 | 96 | 2024-07-29 |  | 2024-11-02 |  |  | 100% |  | By contract | Completed | Mark Dennis Deniel Trading and Construction
1440 | Construction of Three Phase Line Power Supply, Balabac District Hospital | B2 GF PEO 24-02-008 | Medical Facilities | 3 Phase Line = 7.50kms - Transformer Banking - Cl: Power Cable Installation And Termination | Brgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2024 | 20% Development Fund 2024 | 16500000 | 16454913.37 | 150 | 2024-06-18 |  | 2024-11-15 | For approval |  | 95% |  | By contract | On going | TCC Powerserve Trading and Engineering Services
1441 | Construction of Oxygen Building with Centralized Oxygen Generator System, Balabac District Hospital | B2 GF PEO 24-03-22 | Medical Facilities | Net Length: 9.50m (L) X 9.00m (W) | Brgy. Catagupan, Balabac, Palawan | Balabac | PEO | 2024 | 20% Development Fund 2024 | 21500000 | 21495048.38 | 180 | 2024-07-22 |  | 2025-01-18 | 2025-04-19 |  | 87% |  | By contract | On going | Lea and Sons Trading and Construction
1442 | Construction of Drainage System,Roxas Medicare Hospital | B2 GF PEO 24-02-015 | Other Infrastructure | Length of RC Canal: 340.92M - Length of 1 LINE: 12'' - 53m | Municipality of Roxas, Palawan | Roxas | PEO | 2024 | 20% Development Fund 2024 | 3000000 | 2947022.62 | 102 | 2024-04-06 |  | 2024-07-17 |  |  | 100% |  | By contract | Completed | Maximmus Construction
1443 | Construction of Drainage System, Dr. Jose Rizal District Hospital | B2 GF PEO 24-02-005 | Other Infrastructure | Drainage: Length Of 362.52m - Length Of 1 Line: 12" - 37.0m | Municipality of Rizal, Palawan | Rizal | PEO | 2024 | 20% Development Fund 2024 | 3000000 | 2984456.53 | 102 | 2024-05-29 |  | 2024-09-08 |  |  | 100% |  | By contract | Completed | Luis YC Builders & Supply
1444 | Construction of Three (3) - Storey Medical Arts Building with Roof Deck for Helipad, Northern Palawan Provincial Hospital | B2 GF PEO 24-05-083 | Medical Facilities | Buildings: Floor Area:43m x 15m - Porch:5mx4m - Ramp up: 24mx6m- Water Tank: 5,249 liters x 3 sets - Others: Fire Pro, Fire tank, Oxygen Piping, CCTV and PABX and accessories | Northern Palawan Provincial Hospital | Taytay | PEO | 2024 | 20% Development Fund 2024 | 80000000 | 79997834.99 | 283 | 2024-08-16 |  | 2025-05-26 |  |  | 30% |  | By contract | On going | One Hundred Percent and Development Corp.
1445 | Construction of Three (3) - Storey Medical Arts Building with Roof Deck for Helipad phase II, Coron District Hospital | B2 GF PEO 24-05-087 | Medical Facilities | Building: Floor area: 43m x x15m - Ramp Up: 24m x 6m - Water tank: 5,259 liters x 3 sets - Others: Fire pro, fire tank, Oxygen Piping, CCTV and PABX, and accessories | Coron District Hospital | Coron | PEO | 2024 | 20% Development Fund 2024 | 60000000 | 59989673.59 | 258 | 2024-08-16 |  | 2025-05-01 |  |  | 55% |  | By contract | On going | St. Timothy Construction Corporation | TIN 008-813-669-000
1446 | Supply and Installation of 30 KW Hybrid Solar System, Araceli-Dumaran District Hospital |  | Medical Facilities | Supply and Installation of 2-30 KW Hybrid Solar System | Bgy. Poblacion, Dumaran | Dumaran | PEO | 2024 | 20% Development Fund 2024 | 17500000 |  | 120 | [8 empty] | Re-aligned |  |  | Re-aligned to 3 projects
1447 | Construction of Three In One Large Scale Rural Health Unit Phase III | B2 GF PEO 24-02-017 | Medical Facilities | Area: 981 sq.m | So. Tabudniayo, Brgy. Bancalaan, Balabac | Balabac | PEO | 2024 | 20% Development Fund 2024 | 4100000 | 4097793.64 | 150 | 2024-05-06 |  | 2024-10-03 | For approval |  | 70% |  | By contract | On going | Hadiyah Construction | TIN 324-356-720
1448 | Construction of Three In One Large Scale Rural Health Unit Phase III | B2 GF PEO 24-02-013 | Medical Facilities | Area: 981 sq.m | Brgy. Mangsee, Balabac | Balabac | PEO | 2024 | 20% Development Fund 2024 | 4100000 | 4098229.98 | 150 | 2024-08-02 |  | 2024-12-30 | 2025-03-31 |  | 70% |  | By contract | On going | Breis Construction
1449 | Construction of Power Plant and Distribution Lines of Green Island VEP |  | Power and Energy Development Program |  | Green Island | Roxas | PEO | 2024 | 20% Development Fund 2024 | 5630000 | [10 empty] | Re-aligned |  |  | Re-aligned to 2 projects
1450 | Improvement Of Legislative Building | B2 GF SFVIP 24-03-023 | Other Facilities | Legislative 76M(L) - 26.50M(W) - 14.47M(H) - Building - 2 Storey | Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | SFVIP | 20000000 | 19966832.32 | 225 | 2024-05-27 |  | 2025-01-07 |  |  | 83.5% |  | By contract | On going | One Hundred Percent and Development Corp.
1451 | Construction Of PEO Sub-Office Building | B2 GF SFVIP 24-02-021 | Other Facilities | Net Length: Two-Storey Office Building (26.29m X 7.20m) | San Jose, Roxas, Palawan | Roxas | PEO | 2024 | SFVIP | 7000000 | 6990216.86 | 165 | 2024-06-24 |  | 2024-12-06 |  |  | 65.2% |  | By contract | On going | M. Luengo Construction
1452 | Improvement Of Motorpool Building (Expansion Of Office Area) | B2 GF PEO 24-02-012 | Other Facilities | 126 Sq.M | Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | SFVIP | 2200000 | 2192113.38 | 120 | 2024-07-03 |  | 2024-10-31 | For approval |  | 75% |  | By contract | On going | RL Abia Construction
1453 | Extension Of Drainage Structure In Northern Palawan Technical Vocational School | B2 GF PEO 24-02-014 | Other Infrastructure | Open Line Canal: 112 Lm - Ushape Line Canal With Steel Cover: 160 Lm | Taytay, Palawan | Taytay | PEO | 2024 | SFVIP | 2500000 | 2495641.81 | 90 | 2024-05-06 |  | 2024-08-04 |  | 2024-08-25 | 100% |  | By contract | Completed | Yurich Builders & Construction Supply
1454 | Improvement Of Provincial Capitol Building (Lactation Station And Nutrition Clinic) |  | Other Facilities | Net Length: 3.12m X 2.77m - Renovation | Tanglaw, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | SFVIP | 200000 |  | 45 | [8 empty] | Re-aligned
1455 | Repair Of Taradungan Spillway | B2 GF PEO 24-02-015 | Other Infrastructure | Rc Slope (Cu.M) - 29.38 Cu.M | Roxas, Palawan | Roxas | PEO | 2024 | SFVIP | 500000 | 496502.2 | 113 | 2024-04-06 |  | 2024-07-28 |  | 2024-05-10 | 100% |  | By contract | Completed | Maximmus Construction
1456 | Rehabilitation Of Cabigsing Bridge | B2 GF SFVIP 24-08-098 | Transportation Facilities | Pccp Approach: 7.80m X 4.50m (Right Side Inly) - Bridge: 6.7m X 6 Ln.M - Rc Slope: 19.70 Cu.M | Cuyo, Palawan | Cuyo | PEO | 2024 | SFVIP | 3600000 | 3595528.9 | 177 | 2024-10-11 |  | 2025-04-06 |  |  | 35% |  | By contract | On going | EG Batiancilla Construction
1457 | Construction Of Riverbank Protection/Flood Control At Tamlang Bridge | B2 GF SB5 PDP23 24-03-075 (Re-bid) | Other Infrastructure | Slope Ptotection: 244.30 cu.m - (4) sides: 13m(l) x 0.30m(t) - 26 Gabions | Sitio Tamlang, Bgy. Saraza, Brooke's Point | Brooke's Point | PEO | 2023 | Supplemental Budget No. 5 | 5000000 | 4974854.7 | 120 | 2024-08-14 |  | 2024-12-12 | For approval |  | 48.92% |  | By contract | On going | KIR Konstructicon Builders and Supply
1458 | Information and Communication Technology Equipment |  | Supply | Supply | PEO, Puerto Princesa City | Puerto Princesa City | PEO | 2023 | Supplemental Budget No. 6 | 731576 | [7 empty] | 100% |  |  | Completed
1459 | Construction of Evacuation Center/Covered Court, Suba, Cuyo | B2 GF SB6 INFRA 23 24 -04-077 | Other Infrastructure | 30m (L) X 18m (W) | Cuyo, Palawan | Cuyo | PEO | 2023 | Supplemental Budget No. 6 | 7300000 | 7136684.87 | 170 | 2024-08-05 |  | 2025-01-22 |  |  | 65% |  | By contract | On going | J.JH Construction Supplies Trading
1460 | Construction/Supply and Installation of STP Equipment & Facilities, Aborlan Medicare Hospital, Aborlan | B2 GF SB6 INFRA 23-24-24-078 | Medical Facilities | Installation and Termination of Power Cable = 133 Meters | Aborlan, Palawan | Aborlan | PEO | 2023 | Supplemental Budget No. 6 | 4000000 | 3999999.97 | 30 | 2024-08-01 |  | 2024-08-31 | For approval |  | 15.56% |  | By contract | On going | Gth Builders and Developers
1461 | Installation of Fire Protection and Alarm System, Dr. Jose Rizal District Hospital, Rizal | B2 GF SB6 INFRA23 24-03-074 (Re-bid) | Medical Facilities | Sprinkler Heads = 256 Stes - Smoke Detector = 67 Sets | DJRDH, Bgy. Punta Baja, Rizal | Rizal | PEO | 2023 | Supplemental Budget No. 6 | 4500000 | 4491319.14 | 120 | 2024-08-15 |  | 2024-12-13 | 2025-01-12 |  | 90% |  | By contract | On going | RD Abacial Construction
1462 | Supply and Installation of Main Cable of Fire Protection, Aborlan Medicare Hospital, Aborlan | B2 GF SB6 INFRA23-24-04-081 | Medical Facilities | Installation and Termination of Power Cable = 133 Meters | Aborlan, Palawan | Aborlan | PEO | 2023 | Supplemental Budget No. 6 | 500000 | 479600 | 30 | 2024-07-04 |  | 2024-08-03 |  | 2024-07-31 | 100% |  | By contract | Completed | TCC Powerserve Trading and Engineering Services
1463 | Concreting Of Plaridel-Apis-Cabigaan Road Phase II | B2 GF SB1 INFRA 24-03-028 | Transportation Facilities | Road Length: Pccp: 1,000m (L) X 0.20m (T) X 6.10m (W) - Drainage: 1 Line Rcpc 36" Dia. | Plaridel, Aborlan, Palawan | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 15000000 | 13331968.07 | 123 | 2024-09-05 |  | 2025-01-06 |  |  |  |  | By contract | Recently Awarded | St. Timothy Construction Corporation | TIN 008-813-669-000
1464 | Concreting Of Aporawan-Daan-Cabigaan Road | B2 GF SB1 INFRA 24-03-027 | Transportation Facilities | Road: Net Volume Road Length: 4.750m(L) X 0.20m (T) X 6.10m (W) - 6 Lines Rcpc 36" Diameter | Brgy. Cabigaan, Aborlan, Palawan | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 85500000 | 85380611.71 | 280 | 2024-10-11 |  | 2025-07-18 |  |  | 21.02% |  | By contract | On going | Mamsar Construction & Industrial Corporation
1465 | Concreting Of Panacan Sea Road | B2 GF SB1 INFRA 24-03-057 | Transportation Facilities | Road: Net Volume (Cu.M): Pccp 1.310mx5.00mx0.20m Thk Shoulder Width 1.00b.S - 29 Lm 24" Dia Rcpcw/ Shw On L.S - 490m Concrete Slope Protection | Panacan, Narra, Palawan | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 27000000 | 25621153.38 | 180 | 2024-07-29 |  | 2025-01-25 |  |  |  |  | By contract | Not yet started | St.Timothy Construction Corporation | TIN 008-813-669-000
1466 | Concreting Of Suring - Lada Road | B2 GF SB1 INFRA 24-03-036 | Transportation Facilities | Road Length: 1890m (L) X 6.10 (W) X 0.20m (T) | Pangobilian, Brooke's Point | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 28350000 | 26904762.92 | 190 | 2024-07-29 |  | 2025-02-04 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply
1467 | Concreting Of Sandoval - Igang Igang - Sarong Road |  | Transportation Facilities | Road Length: 5954.71m (L)X6.1m(W) X 0.20m(T) No. Of Rcpc: 10 Lines Rcpc 36: Dia | Sandoval & Iwahig, Bataraza, Palawan | Bataraza | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 90000000 |  | 299 | [8 empty] | For Bidding
1468 | Concreting Of Ocayan Road | B2 GF SB1 INFRA 24-03-046 | Transportation Facilities | Pccp: 3,330m (L) X 0.20m(T) X 6.10m(W) - Line Canal: 470.82m (L) 0.40m(W) X 0.70m (H) - 9 Lines Rcpc 36" Diameter | Ocayan, Bataraza | Bataraza | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 49950000 | 46274408.02 | 222 | 2024-08-19 |  | 2025-03-29 |  |  | 15% |  | By contract | On going | Goldrock Construction & Development Corp.
1469 | Concreting Of Panitian - Tabud Road Phase II | B2 GF PEO SB1 INFRA 24-03-033 | Transportation Facilities | Net Volume: Pccp-4,820m X 6.10m X 0.20mthk., Shoulder Wdth 1.00 B.S - 103 Lm 36" Dia. Rcpc With 216lm Concrete Slope Protection And 70m Line Canal | Brgy. Panitian, Quezon, Palawan | Quezon | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 74899526.39 | 226 | 2024-08-16 |  | 2025-03-30 |  |  | 22% |  | By contract | On going | Ivy Michelle Construction and Trading | TIN 008-664-275
1470 | Concreting Of Pulot I - Pulot III Road |  | Transportation Facilities | Pccp: Sta. 0+000.00-Sta. 1+860 - 5260m(L) X 6.10m: Sta. 1+960-Sta.3+480 - (W) X0.20m Thck Sta.4+700 - Sta 6+531.225 - Rcpc 101 Lm (36''diameter) - Stone Masonry H-1mxl-3m | Pulot I - Pulot III, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 84450000 |  | 299 | [8 empty] | For Bidding
1471 | Concreting Of Pulot Sea Road | B2 GF SB1 INFRA 24-03-056 | Transportation Facilities | Total Length: 2,679 M - Stone Masonry: 486 Cu.M - Rcpc:36" Diameter: 65m | Pulot Shore, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 47250000 | 47232174.89 | 216 | 2024-07-29 |  | 2025-03-02 |  |  | 30% |  | By contract | On going | Yurich Builders & Construction Supply | TIN 258-921-757-00001
1472 | Concreting Of Tanatanaen - Maragok Road | B2 GF SB1 INFRA 24-03-060 | Transportation Facilities | Net Volume: Pccp-3,500mx6.10mx0.20m Thk., Shoulder Width 1.00 B.S - 18lm - 36" Dia Rcpc W/ S.H.W. On B.S -160 Lm Stone Masonsry Slope Protection - Road | Tanatanaen, Dumaran, Palawan | Dumaran | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 66000000 | 65800000 | 255 | 2024-08-02 |  | 2025-04-14 |  |  | 20.45% |  | By contract | No movement | Seven Digit Construction and Supplies
1473 | Concreting Of Magsaysay - Itangil Road (Critical Section) | B2 GF SB1 INFRA 24-03-055 | Transportation Facilities | Road Length: 2000m(L) X 0.20m (T) X 5.00m(W) - Drainage: 9 Lines Rcpc 36' Dia | Magsaysay,Dumaran, Palawan | Dumaran | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 30000000 | 29959595.93 | 190 | 2024-09-09 |  | 2025-03-18 |  |  | 30.45% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 009-446-039
1474 | Concreting Of Itangil-Layok Road | B2 GF SB1 INFRA 24-03-058 | Transportation Facilities | Road Length: 1,590m(L) X 0.20m(T) X 6.10m(W) - Drainage: 5 Lines Rcpc 36" Dia(Length Varies) - 45.00lm | Itangil, Dumaran, Palawan | Dumaran | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 30000000 | 29700011.64 | 185 | 2024-08-19 |  | 2025-02-20 |  |  | 30.54% |  | By contract | On going | F.F Galang Construction
1475 | Concreting Of Tumarbong - Antonino Road | B2 GF SB1 INFRA 24-03-072 | Transportation Facilities | Road: 3,900m(L) X 0.20m(T) X 6.10m(W) - Drainage: 2 Lines Rcpc 36" Dia. | Bgy. Antonino, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 61903822.78 | 266 | 2024-08-19 |  | 2025-05-12 |  |  | 15% |  | By contract | On going | One Hundred Percent and Development Corp.
1476 | Concreting Of Highway Junction Little Caramay - Caruray Road B | B2 GF SB1 INFRA 24-03-071 | Transportation Facilities | Road: Net Volume: Road Length: 5,100m X 0.20m(T) X 6.10m(W) - Drainage:7 Lines Rcpc 36"Dia. | Brgy. Magara,Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 105000000 | 104977978.39 | 300 | 2024-08-19 |  | 2025-06-15 |  |  | 9% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 009-446-039
1477 | Concreting Of Highway Junction New Cuyo - Rizal Road | B2 GF SB1 INFRA 24-03-061 | Transportation Facilities | Total Length: 3,971m(L) X 6.1m(W) X 0.2m (T) - Rccp: 26ln.M Rcpc 36" Dia. | New Cuyo, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 74800000 | 278 | 2024-08-22 |  | 2025-05-27 |  |  | 8% |  | By contract | On going | Seven Digit Construction and Supplies | TIN 183-661-696
1478 | Concreting Of Highway Junction Calawag Road | B2 GF SB1 INFRA 24-03-038 | Transportation Facilities | Road : Road Length: 3.940m(L) X 0.20m(T)X6.10m(W) - 58.09 Cu.M Stone Masonry - Drainage: 7 Lines Rcpc 36" Dia | Calawag,Taytay, Palawan | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 75000000 | 74974286.89 | 280 | 2024-09-09 |  | 2025-06-16 |  |  | 20% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 009-446-039
1479 | Concreting Of Sto. Niño - New Canipo - Binga Road | B2 GF SB1 INFRA 24 - 03- 062 | Transportation Facilities | Road Length: 4970m(L) X 0.20m(T) X 6.10m(W) - Drainage: 9 Lines Rcpc 36" Diameter | New Canipo, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 105000000 | 104982513.5 | 310 | 2024-08-16 |  | 2025-06-22 |  |  | 62% |  | By contract | On going | Yurich Builders & Construction Supply | TIN 258-921-757-00001
1480 | Concreting Of Highway Junction Little Caramay - Caruray Road A | B2 GF SB1 INFRA 24-03-063 | Transportation Facilities | Road Length: 4100m(L) X 0.20m(T) X 6.10m (W) - Remove And Replace 2 Units Of 1-L Rcpc 36" Diameter | Caruray,San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 90000000 | 89975752 | 286 | 2024-08-19 |  | 2025-06-01 |  |  |  |  | By contract | Not yet started | One Hundred Percent and Development Corp. | TIN 009-446-039
1481 | Concreting Of Canadcan - Alimanguan Road | B2 GF SB1 INFRA 24-03-068 | Transportation Facilities | Road Length: 900m (L) X 6.10(W) X 0.20m(T) | Alimanguan, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 17850000 | 17468919.39 | 143 | 2024-07-29 |  | 2024-12-19 |  |  | 100% |  | By contract | Completed | Yurich Builders & Construction Supply | TIN 258-921-757-00001
1482 | Concreting Of Alimanguan - Sto. Niño Road | B2 GF SB1 INFRA 24 - 03- 067 | Transportation Facilities | Road Length: 4.740m (L) X 0.20m(T) X 6.10m (W) - 38.05 Cu.M Stone Masonry - Drainage: 6 Lines Rcpc 36" Dia | Alimanguan & Sto. Niño, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 88500000 | 88489305.39 | 280 | 2024-08-16 |  | 2025-05-23 |  |  | 70% |  | By contract | On going | Yurich Builders & Construction Supply | TIN 258-921-757-00001
1483 | Concreting Of Araceli-Dumaran Road A | B2 GF SB1 INFRA 24-03-064 | Transportation Facilities | Road Concreting: 2860m(L) X 6.1m(W) X 0.2m(T) | Mauringen, Araceli, Palawan | Araceli | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 58830000 | 49962469.74 | 247 | 2024-08-30 |  | 2025-05-04 |  |  | 38.61% |  | By contract | On going | Maryknoll Construction and Supply
1484 | Concreting Of Cuyo - Suba - San Carlos Road | B2 GF SB1 INFRA 24-03-032 | Transportation Facilities | Road Length: 640m (L) X 6.10(W) X 0.20 (T) | Pawa & San Carlos, Cuyo, Palawan | Cuyo | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 13155000 | 12497142.11 | 125 | 2024-08-12 |  | 2024-12-15 | For approval |  | 15% |  | By contract | On going | Crishelle Construction | TIN 133-967-996-00000
1485 | Concreting Of New Busuanga - New Quezon Rd | B2 GF SB1 INFRA 24-03-069 | Transportation Facilities | Net Volume(Cu.M): Pccp 1,470m X 6.10m X0.20m Thl - Shoulder Width 1.00m (B.S) - 2l 36" Dia. Rcpc X 8m W/ Shw On B.S | Brgy. New Quezon, Busuanga, Palawan | Busuanga | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 30300000 | 25738892.41 | 185 | 2024-08-08 |  | 2025-02-09 |  |  | 92.42% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730
1486 | Concreting Of New Quezon - Cheey Road | B2 GF SB1 INFRA 24-03-066 | Transportation Facilities | Road Concreting: 1840m (L) X 6.10m(W) X 0.2m(T) | Cheey, Busuanga, Palawan | Busuanga | PEO | 2024 | 2024 - DBP Loan Projects (Concreting) | 37865000 | 37849431.08 | 233 | 2024-07-29 |  | 2025-03-19 |  |  | 10% |  | By contract | On going | One Hundred Percent and Development Corp. | TIN 168-154-730
1487 | Installlation Of 2-Lines 36" Rcpc With Headwall, Plaridel - Apis - Cabigaan Road |  | Transportation Facilities | 2 Lines 36" Diameter Rcpc X 8.00 Length With F. Headwall And Riprap B.S | Brgy. Plaridel | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 400000 |  | 45 | [8 empty] | For Bidding
1488 | Construction Of 40m(L)X3(M) Height Retaining Wall At San Jose Cojamco Sr. Road | B2 GF SB1 INFRA 24-03-049 | Transportation Facilities | Rw: 230.73 - Length: 1 Side: 40m(L) 2m(H) | Brgy. Magbabadil | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1000000 | 995566 | 113 | 2024-06-03 |  | 2024-09-24 |  | 2024-07-31 | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1489 | Removal And Construction Of 60m(L) X6m Height Of Slope Protection Along Jose Cojamco Sr. Road | B2 GF SB1 INFRA 24-03-048 | Transportation Facilities | Slope Protection - (Cu.M) - 156.60 - Length I Side - 601m (L) X 6m (H) | Brgy. Magbabadil | Aborlan | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 2500000 | 2444702.86 | 113 | 2024-07-22 |  | 2024-11-12 |  |  | 100% |  | By contract | Completed | Maximmus Construction | TIN 925-322-134
1490 | Rehabilitation Of Slope Protection Structures In Teresa - Batang Batang Road | B2 GF SB1 INFRA 24-03-050 (Re-bid) | Transportation Facilities | Slope Protection: 76.28 Cu.M - Length Sp Approach: 2 Sides=10m - Abutment A=11.5m - Abutmebt B=8.00m | Brgy. Batang Batang | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1700000 | 1689828.38 | 94 | 2024-07-30 |  | 2024-11-01 | For approval |  | 94.85% |  | By contract | On going | R.R Leoncio Construction
1491 | Rehabilitation Of Drainage And Slope Protection Structures In Highway Junction - Burirao Road | B2 GF SB1 INFRA 24-03-070 | Transportation Facilities | Sp: 248.21 Cu.M - Length Sp: 211.6 M - Length Shoulder: 211.6 M | Brgy. Burirao | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 6250000 | 6020143.26 | 121 | 2024-08-16 |  | 2024-12-15 |  |  |  |  | By contract | Not yet started | Mamsar Construction & Industrial Corporation
1492 | Construction Of Slope Protection, Caguisan Feeder Road | B2 GF SB1 INFRA 24-03-052 | Transportation Facilities | Net Length: 114 Ln.M - 57 Ln.M Both Sides | Brgy. Caguisan | Narra | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 2000000 | 1997936.71 | 113 | 2024-07-22 |  | 2024-11-12 |  |  | 100% |  | By contract | Completed | Maryjonica Construction
1493 | Construction Of Seawall Protection | B2 GF SB1 INFRA 24-03-31 | Transportation Facilities | Seawall: Net Length: 806 Ln.M - H=1.70m | Brgy. Pangobilian, Brooke's Point, Palawan | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 35900000 | 35889368.03 | 240 | 2024-08-16 |  | 2025-04-13 |  |  | 85% |  | By contract | On going | St.Timothy Construction Corporation
1494 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) With PCCP Approach Slope And Protection | B2 GF SB1 INFRA 24-03-043 | Transportation Facilities | (A) Rcbc = 1 Unit - 2.2m(H) - 3.06m(W) X 7.0m(L) X 0.25m (Thck) With Slope Protection And Approach | Bgy. Amas, Brooke's Point, Palawan | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 5000000 | 4404685.8 | 113 | 2024-05-31 |  | 2024-09-21 |  |  | 100% |  | By contract | Completed | Hadiyah Construction
1495 | Construction Of Riverbank Protection/ Flood Control, Mainit Spillway | B2 GF SB1 INFRA 24-03-30 | Transportation Facilities | Slope Protection: 1426.52 Cu.M - 565 M (L) - 0.30m (T) - 283 Gabions - 1m X 1m X 2m | Bgy. Mainit, Brooke's Point | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 30000000 | 29995508.97 | 213 | 2024-08-16 |  | 2025-03-17 | For approval |  | 80% |  | By contract | On going | St.Timothy Construction Corporation
1496 | Construction Of Riverbank Protection/Flood Control, Imulnod Bridge |  | Transportation Facilities | Riverbank: Slope Protection: 736.32 Cu.M - 207.20m(L) X 0.30m (T) - 104 Gabions - 1mx1mx2m | Imulnod, Brooke's Point | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 15000000 |  | 158 | [8 empty] | For Bidding
1497 | Construction Of Riverbank Protection/Flood Control At Tamlang Bridge, Phase 2 |  | Transportation Facilities | Sp: 497.35 Cu.M - 4 Sides: 31 M(L) X 0.30 M(T) - 62 Gabions - 1m X 1m X 2m | Bgy. Saraza, Brooke's Point, Palawan | Brooke's Point | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 10000000 |  | 145 | [8 empty] | For Bidding
1498 | Construction Of Riverbank Protection/Flood Control |  | Transportation Facilities | Slope Protection: 996.65 Cu.M - 305.20m(L) X 0.30m (T) - 153 Gabions - 1m X 1m X 2m | Pulot Shore, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 20000000 |  | 177 | [8 empty] | For Bidding
1499 | Construction Of Riverbank Protection/Flood Control, Panitian-Abokayan Road | B2 GF SB1 SB1 INFRA 24-03-29 | Transportation Facilities | 873.85 Cu.M - 324 M (L) X 0.30m (T)-162 Gabions -1m X 1m X 2m | Brgy. Panitian, Sofronio Española | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 18000000 | 17799135.86 | 145 | 2024-08-16 |  | 2025-01-08 |  |  | 100% |  | By contract | Completed | St.Timothy Construction Corporation | TIN 008-813-669-000
1500 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) w/ PCCP Approach And Slope Protection, Panitian Seashore Road | B2 GF SB1 INFRA 24-03-040 | Transportation Facilities | Rcbc: 1 Unit - 3.56m(H) - 3.56m(W) - 9.10m(L) - X 0.28m Thk With Slope Protection And Approach | Brgy. Panitian, Sofronio Española | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 3000000 | 2813152.52 | 113 | 2024-07-04 |  | 2024-10-25 |  |  | 100% |  | By contract | Completed | Maximmus Construction
1501 | Construction Of Drainage Structure And Slope Protection, Pulot Interior Road | B2 GF SB1 INFRA 24-03-051 | Transportation Facilities | Slope Protection/Drainage: Net Length: 125 Ln.M - H:3m | Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 4500000 | 3985957.46 | 118 | 2024-06-24 |  | 2024-10-20 |  | 2024-09-02 | 100% |  | By contract | Completed | Hadiyah Construction
1502 | Rehabilitation Of Box Culvert | B2 GF SB1 INFRA 24-03-045 | Transportation Facilities | Rehabilitation Of Wingwall And Construction Of Slope Protection | Bgy.Iraray, Sofrionio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1050000 | 1046240.98 | 59 | 2024-07-04 |  | 2024-09-01 |  | 2024-07-29 | 100% |  | By contract | Completed | Hadiyah Construction
1503 | Construction Of Riverbank Protection/Flood Control | B2 GF SB1 INFRA 24-03-059 | Transportation Facilities | Sp: 761.21 Cu.M - 2 Sides (128m (L) X 0.30 M) - 128 Gabions - 1mx1mx2m | Bgy. Sowangan, Quezon, Palawan | Quezon | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 16000000 | 15569150.17 | 145 | 2024-08-16 |  | 2025-01-08 |  |  |  |  | By contract | Not yet started | Mamsar Construction & Industrial Corporation
1504 | Construction Of Sea Wall Protection | B2 GF SB1 INFRA 24-03-054 | Transportation Facilities | Seawall - Net Length=159 Ln.M - H=1.70m | Bgy. Cocoro, Magsaysay, Palawan | Magsaysay | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 7500000 | 7491074.54 | 128 | 2024-09-05 |  | 2025-01-11 |  |  |  |  | By contract | On going | St. Timothy Construction Corporation | TIN 008-813-669-000
1505 | Construction Of Sea Wall Protection, Sitio Pescadores | B2 GF SB1 INFRA 24-03-042 | Transportation Facilities | Seawall - Net Lenght=38 Ln.M - | Bgy. Osmeña, Culion, Palawan | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 4100000 | 4085777.32 | 118 | 2024-08-30 |  | 2024-12-26 |  |  | 78.21% |  | By contract | On going | Luis YC Builders & Supply
1506 | Construction Of Seawall | B2 GF SB1 INFRA 24-03-053 | Transportation Facilities | Net Length=17 Ln.M - H=1.70m | Bgy. Libis, Culion, Palawan | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 1000000 | 997052.1 | 118 | 2024-08-30 |  | 2024-12-26 |  |  | 15% |  | By contract | On going | Luis YC Builders & Supply
1507 | Construction Of Slope Protection | B2 GF SB1 INFRA 24-03-037 | Transportation Facilities | Slope Protection: Volume (Cu.M): 159.04 - Length:1 Side=20m | Balala, Culion, Palawan | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 3500000 | 3484197.27 | 105 | 2024-08-30 |  | 2024-12-13 |  |  | 15% |  | By contract | On going | Luis YC Builders & Supply
1508 | Construction Of Slope Protection & Lined Canal In Balala - Malaking Patag Road | B2 GF SB1 INFRA 24-03-039 | Transportation Facilities | Slope Protection - Slope Protection Volume: 210.61 Cu.M - Length S.P: 1side: 43.60m - Length Line Canal: 1 Side: 43.6m | Balala, Baldat, Malaking Patag | Culion | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 5000000 | 4976942.63 | 113 | 2024-10-02 |  | 2025-01-23 |  |  | 15% |  | By contract | On going | Luis YC Builders & Supply | TIN 120-420-502-00006
1509 | Construction Of 1-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection | B2 GF SB1 INFRA 24-03-044 | Transportation Facilities | 1 Unit: Rcbc: 3.56m(H) X 3.56(W) X 9.10m(L) X 0.28m Thk | Bgy. San Jose, Coron, Palawan | Coron | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 3000000 | 2995965.57 | 113 | 2024-06-03 |  | 2024-09-24 |  |  | 100% |  | By contract | Completed | Maximmus Construction
1510 | Construction Of Slope Protection In Paglaum-Itangil Road |  | Transportation Facilities | Slope Protection: Sp Volume (Cu.M)=519.75 - Length Sp (Both Sides): 192.50 M - Shoulder (Both Sides): 192.50 M | Brgy. Talog, Taytay | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 11700000 |  | 153 | [8 empty] | For Bidding
1511 | Construction Of Sea Wall Protection | B2 GF SB1 INFRA 24-03-035 | Transportation Facilities | Net Length=101 Ln.M - H=1.70m | Bancal & Cambian, Agutaya | Agutaya | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 5000000 | 4996829.56 | 118 | 2024-05-27 |  | 2024-09-22 | 2024-11-21 |  | 100% |  | By contract | Completed | J.JH Construction Supplies Trading
1512 | Construction Of Spillway, Phase II | B2 GF SB1 INFRA 24-03-034 (Re-bid) | Transportation Facilities | Spillway - (A) Spillway=10m(L) X 9.60m(W) X 3.05m(H) - (B) Approach= 6.50m(L) X 6m(W) X 0.20m(T) © Slope Protection= 13m(L) X 1.50m(Sh) - 4 Sides | Brgy. Tinitian, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 2400000 | 2132585.14 | 115 | 2024-08-22 |  | 2024-12-15 |  |  | 85% |  | By contract | On going | RD Abacial Construction | TIN 327-679-690
1513 | Construction Of Spillway |  | Transportation Facilities | (A) Spillway=30m(L) X 9.74m(W) X 3.05m(H) (B) Appproach=10m(L) X 6.10m(W) X 0.20(T) - © Slope Protection 15(L) X 3.80m(Sh) - 4 Sides | Brgy. Nicanor Zabala, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 9000000 |  | 205 | [8 empty] | For Bidding
1514 | Construction Of Slope Protection, Magara Little Caramay - Magara Road | B2 GF SB1 INFRA 24-03-041 | Transportation Facilities | Slope Protection: Sp: 366.24.32 Cu.M - Length: 1 Side: 70m | Bgy. Magara, Roxas, Palawan | Roxas | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 7000000 | 6993408.68 | 126 | 2024-08-16 |  | 2024-12-20 |  |  | 100% |  | By contract | Completed | Mamsar Construction & Industrial Corporation
1515 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection, Alimanguan - Sto. Niño Road |  | Transportation Facilities | Rcbc: (A) Rcbc - 1 Unit 3.0m(H) X 6.9m(W) X 9.1(L) X 0.30m Thk With Slope Protection And Approch | Sto. Niño, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 6000000 |  | 120 | [8 empty] | For Bidding
1516 | Construction Of 3-Barrel Reinforced Concrete Box Culvert (RCBC) W/ Pccp Approach And Slope Protection, Alimanguan - Sto. Niño Road |  | Transportation Facilities | (A) Rcbc = 1 Unit 3.0m (H) X 10.20m (W) X 9.1 (L) X 0.30m Thk With Slope Protection And Approach | Sto. Niño, San Vicente, Palawan | San Vicente | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 8000000 |  | 131 | [8 empty] | For Bidding
1517 | Construction Of 2-Barrel Reinforced Concrete Box Culvert (RCBC) W/ PCCP Approach And Slope Protection, National Highway - Old Guinlo Road (4 Units) |  | Transportation Facilities | Rcbc: (A) Rcbc; 4 Units In Different Location 3m(H) X 6.9m(W) X 9.10m(L) X 0.30m (Thck) With Slope Protection And Approach | Old Guinlo And Poblacio, Taytay | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 24000000 |  | 208 | [8 empty] | For Bidding
1518 | Upgrading of Barotuan Bailey Bridge to RCDG Bridge | B2 GF SB1 INFRA 24-03-047 | Transportation Facilities | Bridge: Approach: 9.22m X 4m (Both Sides) - Bridge: 9.52m X 32 Ln.M - Rc Slope (Cu.M): 147.60 Cu.M - Pccp:8 Ln.M | Barotuan, El Nido, Palawan | El Nido | PEO | 2024 | 2024 - DBP Loan Projects (Flood Control) | 30500000 | 30458698.76 | 226 | 2024-08-19 |  | 2025-04-02 |  |  | 48% |  | By contract | On going | Seven Digit Construction and Supplies | TIN 008-664-275
1519 | Construction Of Forward Operating Bases/PGP Government Center | B2 GF SB1 INFRA 24-08-103 | Other Facilities | 60M (W) X 90M(L) | Abo-abo, Sofronio Española, Palawan | Sofronio Española | PEO | 2024 | 2024 - DBP Loan Projects (Building) | 150000000 | 146964646.78 | 300 | 2024-11-25 |  | 2025-09-21 |  |  |  |  | By contract | Recently Awarded | Arlustre Construction Corporation
1520 | Construction Of Forward Operating Bases/PGP Government Center | B2 GF SB1 INFRA 24 - 08 - 102 | Other Facilities | Building: 60m (w) x 90m (l) | Poblacion, Taytay, Palawan | Taytay | PEO | 2024 | 2024 - DBP Loan Projects (Building) | 150000000 | 146988960.14 | 300 | 2024-11-25 |  | 2025-09-21 |  |  |  |  | By contract | Recently Awarded | Arlustre Construction Corporation |  | Buildimg Permit on process
1521 | Construction of TB DOTS |  | Medical Facilities | 1.00m x 8.00m TB DOTS Building - Concrete Pathwalk (L=5.00m, W=2.50m) | Coron, Palawan | Coron | PEO | 2020 | Covid-19 Fund SB3 | 1785000 |  | 120 | [5 empty] | 100% |  |  | Completed
1522 | Construction of Balabac Waterworks Offic (Re-bid) | B2 GF BWS 23-01-007 |  |  | Poblacion, Balabac, Palawan | Balabac |  | 2023 | PEEDO Fund | 2600000 | 2598151.01 | 90 | 2023-07-17 |  | 2023-10-15 | [5 empty] | PEEDO Validate | Rabb Construction and Supply
1523 | Installation of Brackish Reverse Osmosis Desalination System, Bancalaan, Balabac | B2 GF BWS 23-01-002 |  |  | Bgy. Bancalaan, Balabac | Balabac |  | 2023 | PEEDO Fund | 5464987.5 | 5460092.98 | 100 | 2023-07-24 |  | 2023-11-01 | [5 empty] | PEEDO Validate | Sparkotech Engineering Solution Inc.
1524 | Installation of Mobile Platform Floating Dock | B2 GF SB4 CSPMP 24-01-003 | Other Infrastructure | Mobile Platform Floating Dock (Specifications: 50cm x 50cm x 40cm) | Bgy. Buluang, Busuanga, Palawan | Busuanga |  | 2024 | PEEDO Fund | 6225000 | 5630000 | 60 | 2024-05-16 |  | 2024-07-15 |  |  | 100% |  | By contract | Completed | Tektwin Marketing Corporation
1525 | Concreting of Provincial Disaster Operation Center of Palawan Road Network with Parking Area | B2 DPF 300-21-10-14114 | Transportation Facilities | 367.24m x 5.00m Road Network - 50.46m x 10.00m Parking - 3-L=4.00M x 2.50m, L=14.00m x 2.50m Concrete Pathwalk | Bgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2021 | Disaster Preparedness Fund (PDRRMO Fund) | 5000000 | 4989988.73 | 60 | 2021-12-20 |  | 2022-02-18 |  |  | 100% |  | By contract | Completed | Smmiley Builders and Trading
1526 | Construction of Magsaysay Water System Pipiline Expansion | B2 GF MWS 23-01-001 |  |  | Magsaysay, Palawan | Magsaysay | PEEDO | 2023 | PEEDO Fund | 1900000 | 1898531.1 | 120 | 2023-05-24 |  | 2023-09-21 |  |  | 100% |  | By contract | Completed | Rabb Construction and Supply
1527 | Construction of Staff Quarter's, Reservoir Tank and Perimeter Fence for Free Standing Covid-19 Testing Laboratory | SB3 HDMP 300-20-07-08061 | Medical Facilities | (a) Staff Qaurter's: 20.00m x 8.00m - (b) Reservoir Tank: 3.50m diameter x 4.05m © Perimeter Fence - CHB Tubular Fence and Gate: 68.20m x 2.00m | Brgy. Irawan, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2020 | HDMP - Supplemental Budget No. 3 | 6226165 | 6225165 | 180 | 2020-07-30 |  | 2021-01-26 |  |  | 100% |  | By contract | Completed | RDF Trading and Construction | CTC 097-331-47
1528 | Repair and Maintenance of Southern Palawan Provincial Hospital, Brooke's Point | B2 GF SPPH 24-05-082 | Medical Facilities | Road And Drainage: Rc Canal With Steel Cover: (L)=133m - Rcpc (L)=18m - Rc Canal With Concrete Cover (L)=36m - Canopy Pathwalk (L)= 83.58m - Pathwalk (Lxwxt) = 83.58m(L) - Varies X 150mm | Brooke's Point | Brooke's Point |  | 2024 | SPPH Fund | 4000000 | 3995944.41 | 155 | 2024-08-15 |  | 2025-01-17 | For approval |  | 90.43% |  | By Contract | On going | FSD Construction
1529 | Airport Development/Expansion of Pag-Asa Island Airport (Extension of Runway Strip), Brgy. Pag-Asa,Kalayaan, Palawan | B2 TF PEO 24-05-088 | Transportation Facilities | Extension of Runway Strip | Kalayaan, Palawan | Kalayaan |  | 2024 | Trust Fund - DOTr | 1454910037.53 | 1453565284.74 | 540 | 2024-07-09 |  | 2025-12-31 |  |  | 30% |  | By Contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1530 | Construction of Retaining Wall, Roxas Medicare Hospital | B2 GF SB3 PDP 24-09-109 | Medical Facilities | Retaining wall: 44.20m (L) x 3.0M (H) - CHD Fence; 64.20m (L) x 2.0M (H) | Roxas Medicare Hospital | Roxas | PEO | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 2630000 | 2140036.43 | 118 | 2024-11-25 |  | 2025-03-23 |  |  | 20% |  | By contract | On going | RL Abia Construction
1531 | Supply and Installation of Fire Protection System, Vice Governor Ponce De Leon Memorial Hospital |  | Medical Facilities | Supply, Installation, Testing and Comissioning of Fire Detection and Alarm System (FDAS) | Vice Governor Ponce De Leon Memorial Hospital | Dumaran |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 3000000 | [10 empty] | For Bidding
1532 | Construction of Elevated Water Tank with Deepwell System, Araceli-Dumaran District Hospital |  | Medical Facilities | 100.00 cu.m Capacity Tank | Araceli-Dumaran District Hospital | Dumaran |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 8000000 | [10 empty] | For Bidding
1533 | Construction of WaterTank and Water Facility, Vice Governor Ponce De Leon Memorial Hospital |  | Medical Facilities | 100.00 cu.m Capacity Tank | Vice Governor Ponce De Leon Memorial Hospital | Dumaran |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 8000000 | [10 empty] | For Bidding
1534 | Construction of Cistern Tank, Northern Palawan Provincial Hospital |  | Medical Facilities | Cistern Tank: 100 cu.m capacity tank | Northern Palawal Provincial Hospital | Taytay |  | 2024 | 20% Development Fund - Re-aligned to SB No. 3 | 1500000 |  | 60 | [8 empty] | For Bidding
1535 | Renovation of Offices (Provincial Employment Service Office and SPS Alay sa Kabataan Office) |  | Other Facilities | Building: 14.95m X 13.12m - Installation Of Partition Wall Fabrication Of Tables And Cabinets | Capitol Building, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City |  | 2024 | Supplemental Budget No. 2 | 1400000 |  | 60 | [8 empty] | For Bidding
1536 | Construction of Visitor's Lounge, Palawan Police Provincial Office |  | Other Infrastructure | 1 Storey Building: 10m X 7.5m (Lounge) | Palawan Police Provincial Office | Puerto Princesa City |  | 2024 | Supplemental Budget No. 2 | 2500000 |  | 90 | [8 empty] | For Bidding
1537 | Improvenment of Provincial Security Group Office (Supply and Installation of Airconditioning Units & Tileworks) | B2 GF SB2 PEO 24 - 09 - 108 | Other Facilities | PSG: Installation Of Airconditioning Unit And Floor Tiles. Ceiling And Interior Walls (For Repainting) | Capitol Building, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City |  | 2024 | Supplemental Budget No. 2 | 370000 | 366718 | 60 | 2024-11-21 |  | 2025-01-20 |  |  |  |  | By contract | Recently Awarded | ZYK Construction
1538 | Supply and Installation of Securing Monitoring Devices (CCTV System), Provincial Engineering Office |  | Other Facilities | Supply, Installation, Testing and Comissioning | Capitol Compound, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | SFVIP | 200000 |  | 30 | [8 empty] | For Bidding
1539 | Construction of PDRRMO Mini Motorpool, Brgy. Irawan, PPC | B2 GP DPF 24-05-090 | Other Infrastructure | Building: 2 storey (24mx6m) | Brgy. Irawan, Puerto Princesa City | Puerto Princesa City | PEO | 2024 | PDRRMO Fund | 5000000 | 4444748.95 | 183 | 2024-08-19 |  | 2025-02-18 |  |  | 60% |  | By contract | On going | RC Gadiano Construction | TIN 342-792-217
1540 | Construction of DRRM Training Center (A) Combatt Battle Quarter (B) Fitness Training Center © Rapelling Tower | B2 TF PDRRMO 24-04-080 | Other Infrastructure | Combat Battle Quarter: Floor area 101.25 sq.m of 5 storey - Physical Fitness Training Range: Floor area 21.00m x 37.50m - Rapelling tower: Floor area 112 sq.m - 4 storey | Brgy. Irawan, Puerto Princesa City | Puerto Princesa City |  | 2024 | PDRRMO Fund | 7000000 | 5745560.71 | [6 empty] | 0% |  | By contract | For Award | Luis YC Builders & Supply |  | NTP on process
1541 | Palawan Forest Restoration Network Program (Construction of Green House and Potting Shed) Brgy. Sagpangan, Aborlan, Palawan | BF GF PFRNP 24-08-101 | Other Infrastructure | 1 Storey Building: Potting Shed 4.0m (l) x 4.0m(w), Greenhouse 10.0m (l) x 8.0m (w) | Brgy. Sagpangan, Aborlan, Palawan | Aborlan |  | 2024 | BF GF PFRNP 24-08-101 | 500000 | 497978.04 | 62 | 2024-11-04 |  | 2025-01-05 |  |  |  |  | By contract | Recently Awarded | RL Abia Construction
1542 | Construction of Shelterd Port at Lawak, Palawan Island, Municipality of Kalayaan | B2 TF PEO 24-07-096 | Other Infrastructure | Port: Concrete Pavement Area: 1,040.03 sq.m and Unpaved Back Up Area: 14,525.26 sq.m | Municipality of Kalayaan | Kalayaan |  | 2024 | Trust Fund - DOTr | 766143904.23 | 765118981.36 | 600 | 2024-10-12 |  | 2026-06-04 |  |  | 4.5% |  | By contract | On going | Mamsar Construction & Industrial Corporation | TIN 273-578-000
1543 | Enhancement Of Provincial Budget Office, Brgy. Tanglaw, PPC | B2 GF SB3 PBO 24-08-104 | Other Facilities | Buildings: GF: 14.80M X 6.05M - 2F:14.80M X 10.55M | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | PBO - SB. No. 3 | 1000000 | 998169.59 | 60 | 2024-09-27 |  | 2024-11-26 |  |  | 100% |  | By contract | Completed | RD Abacial Construction | TIN 327-679-690
1544 | Repair and Maintenance of Narra Municipal Hospital | B2 GF NMH 24-06-094 | Medical Facilities | NMH:60m (W) X 60m(L) - Mental Health Clinic: 42m(W) X 12.5m(L) - Motorpool: 21.2m(W) X 5.8m (L) | Brgy. Antipuluan, Narra | Narra | PEO | 2024 | NMH Fund | 3000000 | 2950000 | 150 | 2024-08-28 |  | 2025-01-25 |  |  | 100% |  | By contract | Completed | Maximmus Construction
1545 | Construction of Embedment Mooring System | B2 GF SB4 TPMB23 24-07-095 | Other Infrastructure | Port | Cagayancillo, Palawan | Cagayancillo |  | 2023 | Supplemental Budget No. 4 - Tubbataha Fund | 1352000 | 1351035 | 30 | 2024-08-29 |  | 2024-09-28 | For approval |  |  |  | By contract | Not yet started | E.C Timbancaya Enterprises
1546 | Repair & Maintenance - Building & Other Structures, PJMD | B2 GF DB3 JMFDP 24-08-097 | Other Facilities | Remove & Replace 585.40 sq.m Roofing, Roof Eaves Ceiling with C-Purlins Fascia Board and Downspout - Cyclone Wire Fence, Door and Window - Tubular Door | Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | PJMD Fund | 1500000 | 1499096.52 | 90 | 2024-10-28 |  | 2025-01-26 |  |  | 75% |  | By contract | On going | E.C Timbancaya Enterprises
1547 | Renovation of Provincial Administrator's Office (Addiitonal Works) | B2 GF SB2 ADM 24-08-100 | Other Facilities | Building: 15.1m x 11.35m (a) Repainting, Replacement of tile and plumbing fixtures | Capitol Building, Brgy. Tanglaw, Puerto Princesa City | Puerto Princesa City |  | 2024 | Admin Fund | 1200000 | 1199997.71 | 60 | 2024-08-31 |  | 2024-10-30 |  |  | 100% |  | By contract | Completed | Gth Builders and Developers
1548 | Medical Waste Sterilization System with Housing Facility |  | Medical Facilities |  | SPPH, Brooke's Point | Brooke's Point | PEO | 2023 | SPPH Fund | 25000000 | 25000000 | 60 | 2023-12-27 |  | 2024-02-25 |  |  | 97.5% |  | By contract | On going | The Clean O2 Eco-Friendly Corporation
1549 | Development of Rural Agricultural Center (Construction of Water Supply System) | B2 GF DRAC 24-09-105 | Other Infrastructure | Water Tank: 2000 L Water Tank - Solar Pumping System | Brgy. Danleg, Dumaran, Palawan | Dumaran |  | 2024 | PAO Fund (Agri) | 600000 | 594681.7 | 60 | 2024-11-22 |  | 2025-01-21 |  |  |  |  | By contract | Recently Awarded | J.JH Construction Supplies Trading
1550 | Supply and Installation of Fiber Reinforced Plasric (FRP) Filters for Linapacan Deepwell System, Brgy. San Miguel, Linapacan | B2 GF LWS 24-11-124 | Other Facilities | 8 Units of Fiber Reinforced Plastic (FRP) Filter - 4 Units Bag Filter | Brgy. San Miguel, Linapacan | Linapacan |  | 2024 | PEEDO Fund | 998563.85 | 991600 | 60 | [7 empty] | By contract | For Award | Sparkotech Engineering Solution Inc.
1551 | Repair and Maintenance of the Intensive Juvenile Intervention Support Center (IJISC) | B2 GF BPYC 24 - 09 -111 | Other Facilities | Outer wall: 254.88 sqm - Ceiling: 294.215 sqm | Brgy. Irawan, Puerto Princesa City | Puerto Princesa City |  | 2024 | PJMD Fund | 500000 | 495057.2 | 60 | 2024-11-21 |  | 2025-01-20 |  |  |  |  | By contract | Recently Awarded | ZYK Construction
1552 | Supply and Installation of 140 KW Grid Tied Solar PV System at Three (3) Storey Building, Capitol Compound, Brgy. Tanglaw, PPC | B2 GF PZC 24 - 09 - 107 | Other Facilities | Solar PV: 268 pcs - Inverter: 8 Units | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 |  | 20000000 | 19877760 | 150 | [7 empty] | By contract | For Award | Macspower Construction Supply and Services Corporation |  | NTP on process
1553 | Repair and Re-varnish of Seven (7) Narra Tables and Re-upholstery of One (1) Long Sofa and Two (2) 1 Seater Sofa of Provincial Auditor's Office, brgy. Tanglaw, Puerto Princesa City | B2 GF COA 24 - 11 - 131 | Other Facilities | Repainting of Office Tables (2 Tables) | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | COA Fund | 50000 | 49568 | [8 empty] | By contract | For Award | RD Abacial Construction |  | NTP on process
1554 | Repair and Maintenance of Two (2) Stocks Rooms and Two (2) Container Vans of Provincial Auditor's Office, Brgy. Tanglaw. PPC | B2 GF COA 24 - 11 - 137 | Other Facilities | 30 sq.m | Brgy. Tanglaw, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | COA Fund | 200000 | 198987.62 | 90 | [7 empty] | By contract | For Award | RD Abacial Construction |  | NTP on process
1555 | Construction of Hazardous Waste Storage Building (AMH) | B2 GF HDMP 24-11-132 | Medical Facilities | Area: 6m x 4m (1 Storey Building) | Aborlan Medicare Hospital | Aborlan |  | 2024 | HDMP Fund | 650000 | 648521.44 | 120 | [7 empty] | By contract | For Award | Maximmus Construction |  | NTP on process
1556 | Construction of El Nido STP Staffhouse for Operations in Brgy. Villa Liibertad, El Nido, Palawan | B2 GF ENSWT 24-11-126 | Other Facilities | Area: 11m x 7m Building | Brgy. Villa Libertad , El Nido, Palawan | El Nido |  | 2024 | PEEDO Fund | 1000000 | 997743.03 | 100 | [7 empty] | By contract | For Award | RD Abacial Construction |  | NTP on process
1557 | Supply and Installation of Solar Power System for Linapacan Reverse Osmosis Desalination Water System, Brgy. Nangalao and Cabunlawan, Linapacan, Palawan | B2 GF LWS 24-11-122 | Other Facilities | 2 sets of 39 pcs Solar Panel (600w) | Brgy. Nangalao and Cabunlawan, Linapacan, Palawan | Linapacan |  | 2024 | PEEDO Fund | 3399511.83 | 3385815.82 | 120 | [7 empty] | By contract | For Award | J.JH Construction Supplies Trading |  | NTP on process
1558 | Construction of Magsaysay Waterworks Office, Magsaysay, Palawan | B2 GF MWS 24-11-123 | Other Facilities | 1 unit 10m x 8m Building |  | Magsaysay |  | 2024 | PEEDO Fund | 5000000 | 4996671.21 | 180 | [7 empty] | By contract | For Award | J.JH Construction Supplies Trading |  | NTP on process
1559 | Repair and Rehabilitaion of Water Supply System (PJMD), PEO Road, Brgy. Bancao-bancao, Puerto Princesa City, Palawan | B2 GF PJMD 24-11-130 | Other Facilities | New waterline connection, 2 vertical water tank (7.70 cu.m each) with water pump and cistern tank | PEO Road, Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | PJMD Fund | 2000000 | 1999520.27 | 60 | [7 empty] | By contract | For Award | E.C Timbancaya Enterprises |  | NTP on process
1560 | Repair and Rehabilitation of Primary Line Including Line Hardwares, Brgy. Bancao-Bancao, Puerto Princesa City | B2 GF SB4 PGSO 24-11-136 | Other Facilities | 3 Phase line: 600 meters - 1 Phase Line: 600 meters | Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | PJMD - PGSO Fund (Supplemental Budget. No. 4) | 4677283.09 | 4634162.36 | 60 | [7 empty] | By contract | For Award | TCC Powerserve Trading and Engineering Services |  | NTP on process
1561 | Repair and Maintenance of Provincial Jail Annex Building (Provincial Jail Management Division SPS Government Center) | B2 GF PJMD 24-11-134 | Other Facilities | (a) Repair of Ceiling and Roofing: Ceiling: 264.82 SQ.M - Roofing: 45MX33M - Trench Drain Cover: 24 sets | Brgy. Bancao-bancao, Puerto Princesa City, Palawan | Puerto Princesa City |  | 2024 | PJMD Fund | 3000000 | 2544446.69 | 135 | [7 empty] | By contract | For Award | RD Abacial Construction |  | NTP on process
1562 | Construction of Warehouse with OpCen Phase I |  | Other Infrastructure | Building: Fo Phase I: Area: 20m(L) x 10m (W) - 200 sq.m | Cuyo, Palawan | Cuyo |  | 2024 | PDRRMO - Special Trust Fund | 5000000 |  | 258 | [8 empty] | For Bidding
1563 | Construction of 2 Barrel Reinforced Concrete Box Culvert (RCBC), Highway Jct. Tagumpay - Maliko Road | B2 TF PDRRMO 24-11-166 | Other Infrastructure | (A) RCBC: 3.30M (h) X 6.0M (w) X 8.30M (l) - (B) Slope Protection: 17.32M ( C) Gabions: 12.66M | Brgy. Tagumpay, Roxas, Palawan | Roxas |  | 2024 | PDRRMO - Special Trust Fund | 3800000 | 3778641.37 | 113 | [7 empty] | By contract | For Award | Maximmus Construction |  | NTP on process
1564 | Construction Of Seawall |  | Other Infrastructure | Seawall Protection: 100 LN.M | Brgy. Teresita, Dumaran, Palawan | Dumaran |  | 2024 | PDRRMO - Special Trust Fund | 6000000 |  | 122 | [8 empty] | For Bidding
1565 | Construction of 2 Barrel Reinforced Concrete Box Culvert (RCBC) with Slope Protection |  | Other Infrastructure | (A) RCBC: 3.30M (h) X 6.0M (w) X 8.30M (l) - (B) Slope Protection: 21.32M ( C) Gabions: 13.56M | So. Banglen, Brgy. Taloto, Dumaran, Palawan | Dumaran |  | 2024 | PDRRMO - Special Trust Fund | 4200000 |  | 113 | [8 empty] | For Bidding
1566 | Completion of Evacuation Center/Covered Court Phase I |  | Other Infrastructure | Court: 30m (l) x 18m (w) | Quezon, Busuanga, Palawan | Busuanga |  | 2024 | PDRRMO - Special Trust Fund | 4000000 |  | 170 | [8 empty] | For Bidding
1567 | Completion of Covered Court/Evacuation Center |  | Other Infrastructure | Court: 30m (l) x 18m (w) | Santo Niño, Araceli, Palawan | Araceli |  | 2024 | PDRRMO - Special Trust Fund | 4000000 |  | 170 | [8 empty] | For Bidding
1568 | Construction of Warehouse for South |  | Other Infrastructure | 20M (l) x 10.00M (w) | Brgy. Punta Baja, Rizal, Palawan | Rizal |  | 2024 | PDRRMO - Special Trust Fund | 5000000 |  | 258 | [8 empty] | For Bidding
1569 | Construction of Warehouse for North |  | Other Infrastructure | 20M (l) x 10.00M (w) | San Vicente, Palawan | San Vicente |  | 2024 | PDRRMO - Special Trust Fund | 5000000 |  | 258 | [8 empty] | For Bidding
1570 | TEST | TEST | Other Infrastructure | TEST | TEST | San Vicente | PEO | 2025 | TEST |  |  | 150 |  |  |  | TEST |  |  |  | TEST | Completed | TEST | TEST | TEST
Formulas:
TARGET COMPLETION DATE = [NTP DATE]+[C.D]